## Final 1.2 Rebaseline Cost Workb
RowID | L2 | WBS | P/C | Institution | Schedule Task Name | Cost Activity | Resource Name | FTE% | Type | Subtype | Resource ID | Shift | M&O | Estimating Technique | Actual Rate | Labor Table Rate | Fringe Rate | Start Date | End Date | Indirect | On/Off Ice | Contingency | PY4 Funding | Change in Effort | CR# | CR Date | Notes | 10-2022 | 11-2022 | 12-2022 | 01-2023 | 02-2023 | 03-2023 | 04-2023 | 05-2023 | 06-2023 | 07-2023 | 08-2023 | 09-2023 | LPY5 | PY5 CMo | S_10_22 | S_11_22 | S_12_22 | S_01_23 | S_02_23 | S_03_23 | S_04_23 | S_05_23 | S_06_23 | S_07_23 | S_08_23 | S_09_23 | 12mo Subtotal PY5 | Indirect Subtotal PY5 | Complete Total PY5 | 10-2023 | 11-2023 | 12-2023 | 01-2024 | 02-2024 | 03-2024 | 04-2024 | 05-2024 | 06-2024 | 07-2024 | 08-2024 | 09-2024 | LPY6 | PY6 CMo | S_10_23 | S_11_23 | S_12_23 | S_01_24 | S_02_24 | S_03_24 | S_04_24 | S_05_24 | S_06_24 | S_07_24 | S_08_24 | S_09_24 | 12mo Subtotal PY6 | Indirect Subtotal PY6 | Complete Total PY6 | 10-2024 | 11-2024 | 12-2024 | 01-2025 | 02-2025 | 03-2025 | 04-2025 | 05-2025 | 06-2025 | 07-2025 | 08-2025 | 09-2025 | LPY7 | PY7 CMo | S_10_24 | S_11_24 | S_12_24 | S_01_25 | S_02_25 | S_03_25 | S_04_25 | S_05_25 | S_06_25 | S_07_25 | S_08_25 | S_09_25 | 12mo Subtotal PY7 | Indirect Subtotal PY7 | Complete Total PY7 | 10-2025 | 11-2025 | 12-2025 | 01-2026 | 02-2026 | 03-2026 | 04-2026 | 05-2026 | 06-2026 | 07-2026 | 08-2026 | 09-2026 | LPY8 | PY8 CMo | S_10_25 | S_11_25 | S_12_25 | S_01_26 | S_02_26 | S_03_26 | S_04_26 | S_05_26 | S_06_26 | S_07_26 | S_08_26 | S_09_26 | 12mo Subtotal PY8 | Indirect Subtotal PY8 | Complete Total PY8 | Complete Total PY5-PY8 | Escalation PY4 | Escalation PY5 | Escalation PY6 | Escalation PY7 | Escalation PY8 | Salary Cost PY4 | Salary Cost PY5 | Salary Cost PY6 | Salary Cost PY7 | Salary Cost PY8 | Fringe Cost PY4 | Fringe Cost PY5 | Fringe Cost PY6 | Fringe Cost PY7 | Fringe Cost PY8 | Tot Labor Hrs | L3
258 | 1.2 | 1.2.1.1 | Started | UW | Implementation Management and Controls | EHWD Project Management and Controls (WIPAC_Implementation_Manager) | McEwen | 100% | Labor Hours | Labor - LoE | SE |  |  | D - Expert Opinion | 60.69 | 55 | 35% | 2018-10-01 | 2026-04-03 | 53% | Off Ice | C1 | TRUE |  |  |  |  | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1800 | 12 | 12553.9541 | 12553.9541 | 12553.9541 | 12553.9541 | 12553.9541 | 12553.9541 | 12553.9541 | 12553.9541 | 12553.9541 | 12553.9541 | 12553.9541 | 12553.9541 | 150647.449 | 79843.148 | 230490.597 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1800 | 12 | 12823.8641 | 12823.8641 | 12823.8641 | 12823.8641 | 12823.8641 | 12823.8641 | 12823.8641 | 12823.8641 | 12823.8641 | 12823.8641 | 12823.8641 | 12823.8641 | 153886.3692 | 81559.7757 | 235446.1449 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1800 | 12 | 13099.5772 | 13099.5772 | 13099.5772 | 13099.5772 | 13099.5772 | 13099.5772 | 13099.5772 | 13099.5772 | 13099.5772 | 13099.5772 | 13099.5772 | 13099.5772 | 157194.9261 | 83313.3109 | 240508.237 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | [5 empty] | 1050 | 7 | 13381.2181 | 13381.2181 | 13381.2181 | 13381.2181 | 13381.2181 | 13381.2181 | 13381.2181 | 0 | 0 | 0 | 0 | 0 | 93668.5266 | 49644.3191 | 143312.8457 | 849757.8246 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 109242 | 111590.703 | 113989.9031 | 116440.686 | 69384.0938 | 38234.7 | 39056.7461 | 39896.4661 | 40754.2401 | 24284.4328 | 6450 | 1.2.1
264 | 1.2 | 1.2.1.2.4.1 | Started | PSL | 2021-22 Systems Engineering | 2021-22 Systems Engineering (Terry Benson) | Benson | 60% | Labor Hours | Labor - LoE | EN-ME |  |  |  | 115 | 115 | 0% | 2021-10-01 | 2022-09-29 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 124200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
264 | 1.2 | 1.2.1.2.4.1 | Started | PSL | 2021-22 Systems Engineering | 2021-22 Systems Engineering Support | Birrittella | 53.61% | Labor Hours | Labor - LoE | EN-ME |  |  |  | 115 | 115 | 0% | 2021-10-01 | 2022-09-29 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 110975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
271 | 1.2 | 1.2.1.2.5.1 | Not Started | PSL | 2022-23 Management & Systems Engineering | 2022-23 Systems Engineering (Terry Benson) | Benson | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-10-01 | 2023-09-29 | 0% | Off Ice | C1 |  |  |  |  | Engineering oversight and systems development - coordination and planning, season planning, ASC interface, SIP, logistics coordination, drill procedures, EVMS, seasonal reports | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 6 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 105725.25 | 0 | 105725.25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105725.25 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 105725.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 1.2.1
271 | 1.2 | 1.2.1.2.5.1 | Not Started | PSL | 2022-23 Management & Systems Engineering | 2022-23 Management | Gibson | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-10-01 | 2023-09-29 | 0% | Off Ice | C1 |  |  |  |  | Drill Manager LOE: 0.8 FTE = 1440 hr/yr | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 1440 | 9.6 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 169160.4 | 0 | 169160.4 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169160.4 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 169160.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 1.2.1
271 | 1.2 | 1.2.1.2.5.1 | Not Started | PSL | 2022-23 Management & Systems Engineering | 2022-23 Systems Engineering Support |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-10-01 | 2023-09-29 | 0% | Off Ice | C1 |  |  |  |  | Team meetings - weekly status, reviews, collaboration mtgs, ASC weekly and annual Weekly status mtgs: 35 wks * 1 hr * 12 people = 420 hr ASC coord: 18 wks * 1 hr * 3 people = 78 hr Total = 558 hr | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 459.6 | 3.064 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 53990.361 | 0 | 53990.361 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53990.361 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 53990.361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459.6 | 1.2.1
271 | 1.2 | 1.2.1.2.5.1 | Not Started | PSL | 2022-23 Management & Systems Engineering | 2022-23 Systems Engineering Tech Meetings |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-10-01 | 2023-09-29 | 0% | Off Ice | C1 |  |  |  |  | Tech meetings - Tech meetings LOE: 2 hr/wk * 40 wks each year, 8 people = 640 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
272 | 1.2 | 1.2.1.2.5.2 | Not Started | PSL | Drill Procedure Review | Drill Procedure Review |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-15 | 2023-09-28 | 0% | Off Ice | C2 |  |  |  |  | 1 hr session/wk * 35 wks each year 8 people = 280 hr/yr | [6 empty] | 46 | 47 | 47 | 47 | 47 | 46 | 280 | 1.8667 | 0 | 0 | 0 | 0 | 0 | 0 | 5403.735 | 5521.2075 | 5521.2075 | 5521.2075 | 5521.2075 | 5403.735 | 32892.3 | 0 | 32892.3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32892.3 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 32892.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 1.2.1
273 | 1.2 | 1.2.1.2.5.3 | Not Started | PSL | Drill Hole Modeling | Drill Hole Modeling |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-06-15 | 2023-07-13 | 0% | Off Ice | C2 |  |  |  |  | Hole modeling = 120 hr/yr | [8 empty] | 40 | 40 |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 4698.9 | 0 | 0 | 9397.8 | 0 | 9397.8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.1
274 | 1.2 | 1.2.1.2.5.4 | Not Started | PSL | Drill Documentation Support | Drill Documentation Support |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-02-15 | 2023-08-01 | 0% | Off Ice | C2 |  |  |  |  | Documentation (team) = 120 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
276 | 1.2 | 1.2.1.2.6.1 | Not Started | PSL | 2023-24 Management & Systems Engineering | 2023-24 Management & Systems Engineering | Benson | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-10-01 | 2024-10-03 | 0% | Off Ice | C1 |  |  |  |  | Engineering oversight and systems development | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6 |  |  |  | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 599.4 | 3.996 | 7991.8774 | 0 | 0 | 0 | 7991.8774 | 7991.8774 | 7991.8774 | 7991.8774 | 7991.8774 | 7991.8774 | 7991.8774 | 7991.8774 | 71926.8964 | 0 | 71926.8964 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71926.8964 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 71926.8964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 599.4 | 1.2.1
276 | 1.2 | 1.2.1.2.6.1 | Not Started | PSL | 2023-24 Management & Systems Engineering | 2023-24 Management | Gibson | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-10-01 | 2024-10-03 | 0% | Off Ice | C1 |  |  |  |  | Drill Manager LOE: 0.8 FTE = 1440 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106.6 |  |  |  | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 959.4 | 6.396 | 12791.8037 | 0 | 0 | 0 | 12791.8037 | 12791.8037 | 12791.8037 | 12791.8037 | 12791.8037 | 12791.8037 | 12791.8037 | 12791.8037 | 115126.2335 | 0 | 115126.2335 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115126.2335 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 115126.2335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.4 | 1.2.1
276 | 1.2 | 1.2.1.2.6.1 | Not Started | PSL | 2023-24 Management & Systems Engineering | 2023-24 Systems Engineering Support |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-10-01 | 2024-10-03 | 0% | Off Ice | C1 |  |  |  |  | Team meetings - weekly status, reviews, collaboration mtgs, ASC weekly and annual Weekly status mtgs: 35 wks * 1 hr * 12 people = 420 hr ASC coord: 18 wks * 1 hr * 3 people = 54 hr Total = 1914 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 368 | 2.4533 | 4799.9263 | 0 | 0 | 0 | 4919.9245 | 4919.9245 | 4919.9245 | 4919.9245 | 4919.9245 | 4919.9245 | 4919.9245 | 4919.9245 | 44159.3224 | 0 | 44159.3224 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44159.3224 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 44159.3224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 1.2.1
276 | 1.2 | 1.2.1.2.6.1 | Not Started | PSL | 2023-24 Management & Systems Engineering | 2023-24 Systems Engineering Tech Meetings |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-10-01 | 2024-10-03 | 0% | Off Ice | C1 |  |  |  |  | Tech meetings - Tech meetings LOE: 2 hr/wk * 40 wks each year, 8 people = 540 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
277 | 1.2 | 1.2.1.2.6.2 | Not Started | PSL | PY6 Season Debrief | PY6 Season Debrief |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-03-15 | 2024-03-15 | 0% | Off Ice | C2 |  |  |  |  | Season Debrief - 30 people, hybrid, 4 hr = 120 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 120 | [6 empty] | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 14399.779 | 0 | 0 | 0 | 0 | 0 | 0 | 14399.779 | 0 | 14399.779 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14399.779 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 14399.779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.1
278 | 1.2 | 1.2.1.2.6.3 | Not Started | PSL | Drill Procedure Review | Drill Procedure Review |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-04-15 | 2024-09-27 | 0% | Off Ice | C2 |  |  |  |  | 1 hr session/wk * 35 wks each year 8 people = 280 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 37 | 37 | 38 | 38 | 37 | 37 | 224 | 1.4933 | 0 | 0 | 0 | 0 | 0 | 0 | 4439.9319 | 4439.9319 | 4559.93 | 4559.93 | 4439.9319 | 4439.9319 | 26879.5876 | 0 | 26879.5876 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26879.5876 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 26879.5876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 1.2.1
279 | 1.2 | 1.2.1.2.6.4 | Not Started | PSL | PY6 Drill Advisory Panel | PY6 Drill Advisory Panel |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0 | 2024-05-01 | 2024-05-02 | 0% | Off Ice | [5 empty] | DAP - 2 days, 12 people = 192 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
280 | 1.2 | 1.2.1.2.6.5 | Not Started | PSL | Drill Hole Modeling | Drill Hole Modeling |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-06-15 | 2024-07-12 | 0% | Off Ice | C2 |  |  |  |  | Hole modeling = 120 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 40 | 40 |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.1
281 | 1.2 | 1.2.1.2.6.6 | Not Started | PSL | Drill Documentation Support | Drill Documentation Support |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-02-15 | 2024-07-31 | 0% | Off Ice | C1 |  |  |  |  | Documentation (team) = 120 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
283 | 1.2 | 1.2.1.2.7.1 | Not Started | PSL | 2024-25 Management & Systems Engineering | 2024-25 Management & Systems Engineering | Benson | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-10-01 | 2025-10-03 | 0% | Off Ice | C1 |  |  |  |  | System engineering oversight and systems development | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6 |  |  |  | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 599.4 | 3.996 | 8163.7027 | 0 | 0 | 0 | 8163.7027 | 8163.7027 | 8163.7027 | 8163.7027 | 8163.7027 | 8163.7027 | 8163.7027 | 8163.7027 | 73473.3246 | 0 | 73473.3246 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73473.3246 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 73473.3246 | 0 | 0 | 0 | 0 | 0 | 0 | 599.4 | 1.2.1
283 | 1.2 | 1.2.1.2.7.1 | Not Started | PSL | 2024-25 Management & Systems Engineering | 2024-25 Management | Gibson | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-10-01 | 2025-10-03 | 0% | Off Ice | C1 |  |  |  |  | Drill Manager LOE: 0.8 FTE = 1440 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106.6 |  |  |  | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 959.4 | 6.396 | 13066.8275 | 0 | 0 | 0 | 13066.8275 | 13066.8275 | 13066.8275 | 13066.8275 | 13066.8275 | 13066.8275 | 13066.8275 | 13066.8275 | 117601.4475 | 0 | 117601.4475 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117601.4475 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 117601.4475 | 0 | 0 | 0 | 0 | 0 | 0 | 959.4 | 1.2.1
283 | 1.2 | 1.2.1.2.7.1 | Not Started | PSL | 2024-25 Management & Systems Engineering | 2024-25 Systems Engineering Support |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-10-01 | 2025-10-03 | 0% | Off Ice | C1 |  |  |  |  | Team meetings - weekly status, reviews, collaboration mtgs, ASC weekly and annual Weekly status mtgs: 35 wks * 1 hr * 12 people = 420 hr ASC coord: 18 wks * 1 hr * 3 people = 54 hr Total = 1914 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 368 | 2.4533 | 4903.1248 | 0 | 0 | 0 | 5025.7029 | 5025.7029 | 5025.7029 | 5025.7029 | 5025.7029 | 5025.7029 | 5025.7029 | 5025.7029 | 45108.7479 | 0 | 45108.7479 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45108.7479 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 45108.7479 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 1.2.1
283 | 1.2 | 1.2.1.2.7.1 | Not Started | PSL | 2024-25 Management & Systems Engineering | 2024-25 Systems Engineering Tech Meeting |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-10-01 | 2025-10-03 | 0% | Off Ice | C1 |  |  |  |  | Tech meetings - Tech meetings LOE: 2 hr/wk * 40 wks each year, 8 people = 540 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
284 | 1.2 | 1.2.1.2.7.2 | Not Started | PSL | PY7 Season Debrief | PY7 Season Debrief |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2025-03-15 | 2025-03-15 | 0% | Off Ice | C2 |  |  |  |  | Season Debrief - 30 people, hybrid, 4 hr = 120 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 120 | [6 empty] | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 0 | 14709.3743 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 14709.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.1
285 | 1.2 | 1.2.1.2.7.3 | Not Started | PSL | Drill Procedure Review | Drill Procedure Review |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2025-03-15 | 2025-07-31 | 0% | Off Ice | C2 |  |  |  |  | 1 hr session/wk * 35 wks each year 8 people = 280 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 37 | 37 | 38 | 38 | 37 | 37 | 224 | 1.4933 | 0 | 0 | 0 | 0 | 0 | 0 | 4535.3904 | 4535.3904 | 4657.9685 | 4657.9685 | 4535.3904 | 4535.3904 | 27457.4987 | 0 | 27457.4987 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27457.4987 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 27457.4987 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 1.2.1
286 | 1.2 | 1.2.1.2.7.4 | Not Started | PSL | PY7 Drill Advisory Panel | PY7 Drill Advisory Panel |  |  | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0 | 2025-05-01 | 2025-05-02 | 0% | [6 empty] | DAP - 2 days, 12 people = 192 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
287 | 1.2 | 1.2.1.2.7.5 | Not Started | PSL | Drill Hole Modeling | Drill Hole Modeling |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2025-06-15 | 2025-07-11 | 0% | Off Ice | C2 |  |  |  |  | Hole modeling = 120 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 40 | 40 |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4903.1248 | 4903.1248 | 0 | 0 | 9806.2495 | 0 | 9806.2495 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.2495 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 9806.2495 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.1
288 | 1.2 | 1.2.1.2.7.6 | Not Started | PSL | Drill Readiness Review (PSL) | Drill Readiness Review (PSL) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2025-07-01 | 2025-07-02 | 0% | Off Ice | C2 |  |  |  |  | 12 Engineers 2 days @ 8 hrs = 192 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 192 |  |  | 192 | 1.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23534.9989 | 0 | 0 | 23534.9989 | 0 | 23534.9989 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23534.9989 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 23534.9989 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 1.2.1
289 | 1.2 | 1.2.1.2.7.7 | Not Started | PSL | Drill Documentation Support | Drill Documentation Support |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2025-02-15 | 2025-07-31 | 0% | Off Ice | C1 |  |  |  |  | Documentation (team) = 120 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
291 | 1.2 | 1.2.1.2.8.1 | Not Started | PSL | 2025-26 Management & Systems Engineering | 2025-26 Systems Engineering | Benson | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2025-09-30 | 2026-05-05 | 0% | Off Ice | C1 |  |  |  |  | System Engineer - Oct (pre-deployment) & March/April for closeout. On-ice hours captured in Field Seasons. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.5 |  |  |  | 67.5 | 67.5 | 67.5 | [5 empty] | 270 | 1.8 | 8451.9145 | 0 | 0 | 0 | 8451.9145 | 8451.9145 | 8451.9145 | 0 | 0 | 0 | 0 | 0 | 33807.6582 | 0 | 33807.6582 | 33807.6582 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 33807.6582 | 0 | 0 | 0 | 0 | 0 | 270 | 1.2.1
291 | 1.2 | 1.2.1.2.8.1 | Not Started | PSL | 2025-26 Management & Systems Engineering | 2025-26 Management | Gibson | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2025-09-30 | 2026-05-05 | 0% | Off Ice | C1 |  |  |  |  | Drill Manager LOE: Oct (pre-deployment) & March/April for closeout. On-ice hours captured in Field Seasons. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 |  |  |  |  | 120 | 120 | [5 empty] | 360 | 2.4 | 15025.6258 | 0 | 0 | 0 | 0 | 15025.6258 | 15025.6258 | 0 | 0 | 0 | 0 | 0 | 45076.8775 | 0 | 45076.8775 | 45076.8775 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 45076.8775 | 0 | 0 | 0 | 0 | 0 | 360 | 1.2.1
291 | 1.2 | 1.2.1.2.8.1 | Not Started | PSL | 2025-26 Management & Systems Engineering | 2025-26 Systems Engineering Support |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2025-09-30 | 2026-05-05 | 0% | Off Ice | C1 |  |  |  |  | Engineering support hours for weekly status meeting & off-ice engineering support | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 100 | 100 | [5 empty] | 240 | 1.6 | 5008.5419 | 0 | 0 | 0 | 0 | 12521.3549 | 12521.3549 | 0 | 0 | 0 | 0 | 0 | 30051.2517 | 0 | 30051.2517 | 30051.2517 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 30051.2517 | 0 | 0 | 0 | 0 | 0 | 240 | 1.2.1
292 | 1.2 | 1.2.1.2.8.2 | Not Started | PSL | PY8 Season Debrief | PY8 Season Debrief |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2026-03-15 | 2026-03-15 | 0% | Off Ice | C2 |  |  |  |  | Season Debrief - 30 people, hybrid, 4 hr = 120 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 120 | [6 empty] | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 15025.6258 | 0 | 0 | 0 | 0 | 0 | 0 | 15025.6258 | 0 | 15025.6258 | 15025.6258 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 15025.6258 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.1
296 | 1.2 | 1.2.1.3.1.1 | Should have Started | UW | String Management and Controls (2021-2022) | String Management and Controls (2021-2022) | Tosi | 15% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2021-10-01 | 2022-09-30 | 53% | Off Ice | [5 empty] | Tosi - 15% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 12752.1 | 0 | 0 | 0 | 0 | 4463.235 | 0 | 0 | 0 | 0 | 0 | 1.2.1
297 | 1.2 | 1.2.1.3.1.2 | Should have Started | UW | Installation Engineering (2021-2022) | Installation Engineering (2021-2022) | Tosi | 25% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2021-10-01 | 2022-09-30 | 53% | Off Ice | [5 empty] | Tosi - 25% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 21253.5 | 0 | 0 | 0 | 0 | 7438.725 | 0 | 0 | 0 | 0 | 0 | 1.2.1
298 | 1.2 | 1.2.1.3.1.3 | Should have Started | PSL | Installation Engineering Support (2021-2022) | Installation Engineering Support (2021-2022) |  | 2.556% | Labor Hours | Labor - LoE | EN |  |  |  | 115 | 115 | 0% | 2021-10-01 | 2022-09-30 | 0% | Off Ice | [5 empty] | Includes PSL tower work | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 5290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
300 | 1.2 | 1.2.1.3.2.1 | Not Started | UW | String Management and Controls (2022-2023) | String Management and Controls (2022-2023) | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  | D - Expert Opinion | 47.23 | 52 | 35% | 2022-10-01 | 2023-09-29 | 53% | Off Ice | C1 |  |  |  |  | Tosi - 15% | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 22 | 22 | 23 | 23 | 270 | 1.8 | 1432.8897 | 1432.8897 | 1432.8897 | 1432.8897 | 1498.0211 | 1498.0211 | 1498.0211 | 1498.0211 | 1432.8897 | 1432.8897 | 1498.0211 | 1498.0211 | 17585.4647 | 9320.2963 | 26905.761 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26905.761 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 13026.2702 | 0 | 0 | 0 | 0 | 4559.1946 | 0 | 0 | 0 | 270 | 1.2.1
301 | 1.2 | 1.2.1.3.2.2 | Not Started | UW | Installation Engineering (2022-2023) | Installation Engineering (2022-2023) | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  | D - Expert Opinion | 47.23 | 52 | 35% | 2022-10-01 | 2023-09-29 | 53% | Off Ice | C1 |  |  |  |  | Tosi - 25% | 38 | 38 | 38 | 38 | 38 | 36 | 36 | 36 | 38 | 38 | 38 | 38 | 450 | 3 | 2474.9913 | 2474.9913 | 2474.9913 | 2474.9913 | 2474.9913 | 2344.7286 | 2344.7286 | 2344.7286 | 2474.9913 | 2474.9913 | 2474.9913 | 2474.9913 | 29309.1078 | 15533.8272 | 44842.935 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44842.935 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 21710.4503 | 0 | 0 | 0 | 0 | 7598.6576 | 0 | 0 | 0 | 450 | 1.2.1
302 | 1.2 | 1.2.1.3.2.3 | Not Started | PSL | Installation Engineering Support (2022-2023) | Installation Engineering Support (2022-2023) |  | 0% | Labor Hours | Labor - LoE | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-10-01 | 2023-09-29 | 0% | Off Ice | C2 | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 48 | 0.32 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 5638.68 | 0 | 5638.68 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5638.68 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 5638.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1.2.1
304 | 1.2 | 1.2.1.3.3.1 | Not Started | UW | String Management and Controls (2023-2024) | String Management and Controls (2023-2024) | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  | D - Expert Opinion | 47.23 | 52 | 35% | 2023-10-01 | 2024-10-03 | 53% | Off Ice | C1 |  |  |  |  | Tosi - 10% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 180 | 1.2 | 997.9751 | 997.9751 | 997.9751 | 997.9751 | 997.9751 | 997.9751 | 997.9751 | 997.9751 | 997.9751 | 997.9751 | 997.9751 | 997.9751 | 11975.7015 | 6347.1218 | 18322.8232 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18322.8232 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 8870.89 | 0 | 0 | 0 | 0 | 3104.8115 | 0 | 0 | 180 | 1.2.1
305 | 1.2 | 1.2.1.3.3.2 | Not Started | UW | Installation Engineering (2023-2024) | Installation Engineering (2023-2024) | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  | D - Expert Opinion | 47.23 | 52 | 35% | 2023-10-01 | 2024-10-03 | 53% | Off Ice | C1 |  |  |  |  | Tosi - 30% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | 3.6 | 2993.9254 | 2993.9254 | 2993.9254 | 2993.9254 | 2993.9254 | 2993.9254 | 2993.9254 | 2993.9254 | 2993.9254 | 2993.9254 | 2993.9254 | 2993.9254 | 35927.1044 | 19041.3653 | 54968.4697 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54968.4697 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 26612.6699 | 0 | 0 | 0 | 0 | 9314.4345 | 0 | 0 | 540 | 1.2.1
306 | 1.2 | 1.2.1.3.3.3 | Not Started | PSL | Installation Engineering Support (2023-2024) | Installation Engineering Support (2023-2024) |  | 0% | Labor Hours | Labor - LoE | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-10-01 | 2024-10-03 | 0% | Off Ice | C2 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 48 | 0.32 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 5759.9116 | 0 | 5759.9116 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5759.9116 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 5759.9116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1.2.1
308 | 1.2 | 1.2.1.3.4.1 | Not Started | UW | String Management and Controls (2024-2025) | String Management and Controls (2024-2025) | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  | D - Expert Opinion | 47.23 | 52 | 35% | 2024-10-01 | 2025-10-03 | 53% | Off Ice | C1 |  |  |  |  | Tosi - 5% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 90 | 0.6 | 543.6968 | 543.6968 | 0 | 0 | 543.6968 | 611.659 | 611.659 | 611.659 | 611.659 | 679.6211 | 679.6211 | 679.6211 | 6116.5895 | 3241.7924 | 9358.382 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9358.382 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 4530.8071 | 0 | 0 | 0 | 0 | 1585.7825 | 0 | 90 | 1.2.1
309 | 1.2 | 1.2.1.3.4.2 | Not Started | UW | Installation Engineering (2024-2025) | Installation Engineering (2024-2025) | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  | D - Expert Opinion | 47.23 | 52 | 35% | 2024-10-01 | 2025-10-03 | 53% | Off Ice | C1 |  |  |  |  | Tosi - 25% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 450 | 3 | 3058.2948 | 3058.2948 | 0 | 0 | 3058.2948 | 3058.2948 | 3058.2948 | 3058.2948 | 3058.2948 | 3058.2948 | 3058.2948 | 3058.2948 | 30582.9476 | 16208.9622 | 46791.9098 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46791.9098 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 22654.0353 | 0 | 0 | 0 | 0 | 7928.9123 | 0 | 450 | 1.2.1
310 | 1.2 | 1.2.1.3.4.3 | Not Started | PSL | Installation Engineering Support (2024-2025) | Installation Engineering Support (2024-2025) |  | 0% | Labor Hours | Labor - LoE | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-10-01 | 2025-10-03 | 0% | Off Ice | C2 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 44 | 0.29333 | 490.3125 | 490.3125 | 490.3125 | 0 | 490.3125 | 490.3125 | 490.3125 | 490.3125 | 490.3125 | 490.3125 | 490.3125 | 490.3125 | 5393.4372 | 0 | 5393.4372 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5393.4372 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 5393.4372 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 1.2.1
312 | 1.2 | 1.2.1.3.5.1 | Not Started | UW | String Management and Controls (2025-2026) | String Management and Controls (2025-2026) | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  | D - Expert Opinion | 47.23 | 52 | 35% | 2025-10-01 | 2026-05-05 | 53% | Off Ice | C1 |  |  |  |  | Tosi - 5% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 |  |  |  | 12 | [7 empty] | 18 | 0.12 | 416.5397 | 0 | 0 | 0 | 833.0795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1249.6192 | 662.2982 | 1911.9174 | 1911.9174 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 925.6439 | 0 | 0 | 0 | 0 | 323.9754 | 18 | 1.2.1
313 | 1.2 | 1.2.1.3.5.2 | Not Started | UW | Installation Engineering (2025-2026) | Installation Engineering (2025-2026) | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  | D - Expert Opinion | 47.23 | 52 | 35% | 2025-10-01 | 2026-05-05 | 53% | Off Ice | C1 |  |  |  |  | Tosi - 20% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 |  |  |  | 30 | 16 | 16 | [5 empty] | 77 | 0.51333 | 1041.3494 | 0 | 0 | 0 | 2082.6987 | 1110.7727 | 1110.7727 | 0 | 0 | 0 | 0 | 0 | 5345.5934 | 2833.1645 | 8178.7579 | 8178.7579 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 3959.6988 | 0 | 0 | 0 | 0 | 1385.8946 | 77 | 1.2.1
314 | 1.2 | 1.2.1.3.5.3 | Not Started | PSL | Installation Engineering Support (2025-2026) | Installation Engineering Support (2025-2026) |  | 0% | Labor Hours | Labor - LoE | EN |  |  |  | 115 | 115 | 0% | 2025-10-01 | 2026-05-05 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
320 | 1.2 | 1.2.1.4.4 | Should have Started | PSL | 2021-22 Quality & Safety | 2021-22 Quality & Safety (PSL_Safety_Mgr) - adjust cost once USAP support known | Zernick | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2021-10-01 | 2022-09-30 | 0% | Off Ice | [5 empty] | Removed all of Safety Manager from 1.2. Moved all to 1.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
321 | 1.2 | 1.2.1.4.5 | Not Started | PSL | 2022-23 Quality & Safety | 2022-23 Quality & Safety PSL_Quality & Safety Oversight |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0 | 2022-10-03 | 2023-10-02 | 0% | Off Ice | [5 empty] | 0.1 FTE = 144 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
321 | 1.2 | 1.2.1.4.5 | Not Started | PSL | 2022-23 Quality & Safety | 2022-23 Quality & Safety HA Review |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-10-03 | 2023-10-02 | 0% | Off Ice | C2 |  |  |  |  | 12 sessions * 2 hr/session each year 6 people = 144 hr/yr | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 144 | 0.96 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 16916.04 | 0 | 16916.04 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16916.04 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 16916.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 1.2.1
322 | 1.2 | 1.2.1.4.6 | Not Started | PSL | 2023-24 Quality & Safety | 2022-23 Quality & Safety PSL_Quality & Safety Oversight |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0 | 2023-10-03 | 2024-10-04 | 0% | Off Ice | [5 empty] | 0.1 FTE = 144 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
322 | 1.2 | 1.2.1.4.6 | Not Started | PSL | 2023-24 Quality & Safety | 2023-24 Quality & Safety HA Review |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-10-03 | 2024-10-04 | 0% | Off Ice | C2 |  |  |  |  | 12 sessions * 2 hr/session each year 6 people = 144 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 144 | 0.96 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 17279.7349 | 0 | 17279.7349 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17279.7349 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 17279.7349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 1.2.1
323 | 1.2 | 1.2.1.4.7 | Not Started | PSL | 2024-25 Quality & Safety | 2024-25 Quality & Safety PSL_Quality & Safety Oversight |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0 | 2024-10-07 | 2025-10-08 | 0% | Off Ice | [5 empty] | 0.1 FTE = 144 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
323 | 1.2 | 1.2.1.4.7 | Not Started | PSL | 2024-25 Quality & Safety | 2025-25 Quality & Safety HA Review |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-10-07 | 2025-10-08 | 0% | Off Ice | C2 |  |  |  |  | 12 sessions * 2 hr/session each year 6 people = 144 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 144 | 0.96 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 17651.2492 | 0 | 17651.2492 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17651.2492 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 17651.2492 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 1.2.1
324 | 1.2 | 1.2.1.4.8 | Not Started | PSL | 2025-26 Quality & Safety | 2025-26 Quality & Safety PSL_Quality & Safety Oversight |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2025-10-07 | 2026-04-09 | 0% | Off Ice | C1 |  |  |  |  | 0.1 FTE October & November = 24 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
324 | 1.2 | 1.2.1.4.8 | Not Started | PSL | 2025-26 Quality & Safety | 2025-26 Quality & Safety HA Review |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2025-10-07 | 2026-04-09 | 0% | Off Ice | C2 |  |  |  |  | 2 sessions * 2 hr/session each year 6 people = 24 hr/yr October & November | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | [10 empty] | 24 | 0.16 | 1502.5626 | 1502.5626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3005.1252 | 0 | 3005.1252 | 3005.1252 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 3005.1252 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.1
329 | 1.2 | 1.2.1.5.4 | Started | PSL | 2021-22 Travel (non-deployment) | 2021-22 Travel (non-deployment) |  |  | Travel | Travel | [5 empty] | 1 | 0% | 2021-10-01 | 2022-09-30 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
330 | 1.2 | 1.2.1.5.5 | Not Started | PSL | 2022-23 Travel (non-deployment) | 2022-23 Travel (non-deployment) | Domestic |  | Travel | Travel |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2022-10-03 | 2023-09-29 | 53% | Off Ice | C1 |  |  |  |  | Collab Mtg (international): 1x $3600 ASC/Denver (domestic): 5x $1800 = $9k Total = 3.6k+9k = 12.6k | [5 empty] | 9000 | 3600 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 9193.5 | 3677.4 | 0 | 0 | 0 | 0 | 0 | 12870.9 | 6821.577 | 19692.477 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19692.477 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
331 | 1.2 | 1.2.1.5.6 | Not Started | PSL | 2023-24 Travel (non-deployment) | 2023-24 Travel (non-deployment) | Domestic |  | Travel | Travel |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2024-01-05 | 2024-10-03 | 53% | Off Ice | C1 |  |  |  |  | Collab Mtg (international): 1x $3600 ASC/Denver (domestic): 5x $1800 = $9k Total = 3.6k+9k = 12.6k | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 9000 | 3600 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 9391.1603 | 3756.4641 | 0 | 0 | 0 | 0 | 0 | 13147.6244 | 6968.2409 | 20115.8653 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20115.8653 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
332 | 1.2 | 1.2.1.5.7 | Not Started | PSL | 2024-25 Travel (non-deployment) | 2024-25 Travel (non-deployment) | Domestic |  | Travel | Travel |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2025-01-09 | 2025-10-08 | 53% | Off Ice | C1 |  |  |  |  | Collab Mtg (international): 1x $3600 ASC/Denver (domestic): 5x $1800 = $9k Total = 3.6k+9k = 12.6k | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 9000 | 3600 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 9593.0702 | 3837.2281 | 0 | 0 | 0 | 0 | 0 | 13430.2983 | 7118.0581 | 20548.3564 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20548.3564 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
349 | 1.2 | 1.2.1.6.2.8 | Started | PSL | Crate MHP/PHS Replacements & Spares (FY23 Shipment) (Container C - Vessel) | Crate MHP & PHS Replacements & Spares (Container C - Vessel) |  | 0.8889% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-05-31 | 2022-06-07 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
349 | 1.2 | 1.2.1.6.2.8 | Started | PSL | Crate MHP/PHS Replacements & Spares (FY23 Shipment) (Container C - Vessel) | Crate MHP Replacements & Spares (Container C - Vessel) |  |  | M & S | M & S |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-05-31 | 2022-06-07 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
350 | 1.2 | 1.2.1.6.2.9 | Not Started | PSL | Crate Fuel Systems & Tower Components (Container C - Vessel) | Crate Fuel Systems & Tower Components (Container C - Vessel) |  | 0.5% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-05-02 | 2022-05-10 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
351 | 1.2 | 1.2.1.6.2.10 | Not Started | PSL | Crate TOS Components & Spares (Container C - Vessel) | Crate TOS Components & Spares (Container C - Vessel) |  | 1% | Labor Hours | Labor - Task | EN |  |  | C - Engineering Buildup | 115 | 115 | 0% | 2022-06-29 | 2022-07-04 | 0 | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
351 | 1.2 | 1.2.1.6.2.10 | Not Started | PSL | Crate TOS Components & Spares (Container C - Vessel) | Crate TOS Components & Spares (Container C - Vessel) |  |  | M & S | M & S |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-06-29 | 2022-07-04 | 53% | Off Ice | [5 empty] | Collapsible Bulk Container, Black, 34 inH x 32 inL x 30 inW, 1EA w/ lid $425.38 W.W. Grainger Item #8CA51 & #9GFT8 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
352 | 1.2 | 1.2.1.6.2.11 | Started | PSL | Crate Control Systems Components Shipment 1 - DNF (Vessel) | Crate Control Systems Components Shipment 1 - DNF (Vessel) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-10-03 | 2022-10-07 | 0% | Off Ice | C2 | [5 empty] | 16 | [11 empty] | 16 | 0.10667 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.1
352 | 1.2 | 1.2.1.6.2.11 | Started | PSL | Crate Control Systems Components Shipment 1 - DNF (Vessel) | Crate Control Systems Components Shipment 1 - DNF (Vessel) |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-10-03 | 2022-10-07 | 53% | Off Ice | C2 |  |  |  |  | Collapsible Bulk Container, Black, 48 inH x 45 inL x 41 inW, 1EA w/ lid $838 W.W. Grainger Item #36XE25 & #1XGG9 | 838 | [13 empty] | 856.017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856.017 | 453.689 | 1309.706 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1309.706 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
353 | 1.2 | 1.2.1.6.2.12 | Started | PSL | Crate ARA Drill Subsystem Parts - Crate 1 (Container C - Vessel) | Crate ARA Drill Subsystem Parts - Crate 1 (Container C - Vessel) |  | 0.8889% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-10-07 | 2022-10-17 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
353 | 1.2 | 1.2.1.6.2.12 | Started | PSL | Crate ARA Drill Subsystem Parts - Crate 1 (Container C - Vessel) | Crate ARA Drill Subsystem Parts - Crate 1 (Container C - Vessel) |  |  | M & S | M & S |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-10-07 | 2022-10-17 | 53% | Off Ice | [5 empty] | Collapsible Bulk Container, Black, 48 inH x 45 inL x 41 inW, 1EA w/ lid $838 W.W. Grainger Item #36XE25 & #1XGG9 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
354 | 1.2 | 1.2.1.6.2.13 | Started | PSL | Crate ARA Drill Subsystem Parts DNF - Crate 2 (Vessel) | Crate ARA Drill Subsystem Parts DNF - Crate 2 (Vessel) |  | 0.8889% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-10-07 | 2022-10-17 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
354 | 1.2 | 1.2.1.6.2.13 | Started | PSL | Crate ARA Drill Subsystem Parts DNF - Crate 2 (Vessel) | Crate ARA Drill Subsystem Parts DNF - Crate 2 (Vessel) |  |  | M & S | M & S |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-10-07 | 2022-10-17 | 53% | Off Ice | [5 empty] | Collapsible Bulk Container, Black, 34 inH x 32 inL x 30 inW, 1EA w/ lid $425.38 W.W. Grainger Item #8CA51 & #9GFT8 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
355 | 1.2 | 1.2.1.6.2.14 | Not Started | PSL | Crate Spare Main Drill & Combo Cables (Container C - Vessel) | Crate (Drill): Spare Main Drill & Combo Cables to PTH (Vessel) |  | 1.5% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-05-01 | 2022-05-06 | 0% | Off Ice | C2 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
355 | 1.2 | 1.2.1.6.2.14 | Not Started | PSL | Crate Spare Main Drill & Combo Cables (Container C - Vessel) | Crate (Drill): Spare Main Drill & Combo Cables to PTH (Vessel) |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-05-01 | 2022-05-06 | 53% | Off Ice | C2 |  |  |  |  | Tie Down Strap, 27 ftL x 2 inW, 1600 lb Load Limit, Ratchet $52.02 x 8 = $416.16, Lumber for spool support $130.88 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
356 | 1.2 | 1.2.1.6.2.15 | Not Started | PSL | Prepare Bull Wheel for Shipment (Container C - Vessel) | Prepare Bull Wheel for Shipment (Container C - Vessel) |  | 0.5556% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0 | 2022-07-01 | 2022-07-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
356 | 1.2 | 1.2.1.6.2.15 | Not Started | PSL | Prepare Bull Wheel for Shipment (Container C - Vessel) | Prepare Bull Wheel for Shipment (Container C - Vessel) |  |  | M & S | M & S |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-07-01 | 2022-07-04 | 53% | Off Ice | [5 empty] | Tie Down Strap, 20 ftL x 2 inW, 1600 lb Load Limit, Ratchet $50.62 x 4 = $202.48, Lumber for bull wheel support $65.44 - Total $268 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
357 | 1.2 | 1.2.1.6.2.16 | Started | PSL | Crate Shop Parts - Consumables & Spares, etc. (Container C - Vessel) | Crate Shop Parts - Consumables & Spares, etc. (Container C - Vessel) |  | 0.4444% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-09-17 | 2022-09-22 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
358 | 1.2 | 1.2.1.6.2.17 | Started | PSL | Crate Condensate Management Components (Container C - Vessel) | Crate Condensate Management Components (Container C - Vessel) |  | 0.5% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-05-30 | 2022-06-02 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
358 | 1.2 | 1.2.1.6.2.17 | Started | PSL | Crate Condensate Management Components (Container C - Vessel) | Crate Condensate Management Components (Container C - Vessel) |  |  | M & S | M & S |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-05-30 | 2022-06-02 | 53% | Off Ice | [5 empty] | Collapsible Bulk Container, Black, 34 inH x 32 inL x 30 inW, 1EA w/ lid $425.38 W.W. Grainger Item #8CA51 & #9GFT8 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
359 | 1.2 | 1.2.1.6.2.18 | Started | PSL | Crate Pump Repair/Replace Components (Container C - Vessel) | Crate Pump Repair/Replace Components (Container C - Vessel) |  | 0.2222% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-04-07 | 2022-04-08 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
360 | 1.2 | 1.2.1.6.2.19 | Not Started | PSL | Crate Hose Reel Heating System (Container C - Vessel) | Crate Hose Reel Heating System (Container C - Vessel) |  | 2% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-09-07 | 2022-09-13 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
361 | 1.2 | 1.2.1.6.2.20 | Not Started | PSL | Load Container C (Main/Combo Cables, Bull Wheel, Hose Heating Components, ARA Drill Components - Crate 2) (Vessel) | Load Container C (Main/Combo Cables, Bull Wheel, Hose Heating Components, ARA Drill Components - Crate 2) (Vessel) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-10-01 | 2022-10-07 | 0% | Off Ice | C2 | TRUE |  |  |  |  | 30 | [11 empty] | 30 | 0.2 | 2359.665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2359.665 | 0 | 2359.665 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2359.665 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2359.665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1.2.1
361 | 1.2 | 1.2.1.6.2.20 | Not Started | PSL | Load Container C (Main/Combo Cables, Bull Wheel, Hose Heating Components, ARA Drill Components - Crate 2) (Vessel) | Load Container C (Main/Combo Cables, Bull Wheel, Hose Heating Components, ARA Drill Components - Crate 2) (Vessel) |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-10-01 | 2022-10-07 | 53% | Off Ice | C2 |  |  |  |  | $6000 estimated for 20' container purchase with delivery. PY3 container procurement was 6k. | 6000 | [13 empty] | 6129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6129 | 3248.37 | 9377.37 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9377.37 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
362 | 1.2 | 1.2.1.6.2.21 | Not Started | PSL | Crate Drill Heads, Spare Parts to PTH (Vessel) Store in ICL - DNF | Crate Drill Heads, Spare Parts to PTH (Vessel) Store in ICL - DNF |  | 0.4444% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-09-23 | 2022-09-30 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
363 | 1.2 | 1.2.1.6.2.22 | Started | PSL | Crate Control Systems Components Shipment 2 - DNF (Comsur) | Crate Control Systems Components Shipment 2 - DNF (Comsur) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2023-06-20 | 2023-06-28 | 0% | Off Ice | C2 | [13 empty] | 24 |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 0 | 0 | 0 | 1887.732 | 0 | 1887.732 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1887.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.1
363 | 1.2 | 1.2.1.6.2.22 | Started | PSL | Crate Control Systems Components Shipment 2 - DNF (Comsur) | Crate Control Systems Components Shipment 2 - DNF (Comsur) |  |  | M & S | M & S |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-06-20 | 2023-06-28 | 53% | Off Ice | C2 |  |  |  |  | Collapsible Bulk Container, Black, 48 inH x 45 inL x 41 inW, 1EA w/ lid $838 W.W. Grainger Item #36XE25 & #1XGG9 | [8 empty] | 1676 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1712.034 | 0 | 0 | 0 | 1712.034 | 907.378 | 2619.412 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2619.412 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
364 | 1.2 | 1.2.1.6.2.23 | Not Started | PSL | Crate Elect. Distribution System Components (ComSur) | Crate Elect. Distribution System Components (ComSur) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-07-28 | 2023-08-01 | 0% | Off Ice | C2 | [14 empty] | 4 | 4 |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469.89 | 469.89 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.1
365 | 1.2 | 1.2.1.6.2.24 | Started | PSL | Crate MDS Internal Hoses & Spares Resupply (FS2 Resupply Container - Comsur) | Crate MDS Internal Hoses & Spares Resupply (FS2 Resupply Container - Comsur) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2024-06-13 | 2024-07-03 | 0% | Off Ice | C2 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 0 | 0 | 0 | 642.7727 | 0 | 642.7727 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.1
365 | 1.2 | 1.2.1.6.2.24 | Started | PSL | Crate MDS Internal Hoses & Spares Resupply (FS2 Resupply Container - Comsur) | Crate MDS Internal Hoses & Spares Resupply (FS2 Resupply Container - Comsur) |  |  | M & S | M & S |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2024-06-13 | 2024-07-03 | 53% | Off Ice | C2 |  |  |  |  | Collapsible Bulk Container, Black, 34 inH x 32 inL x 30 inW, 1EA w/ lid $425.38 W.W. Grainger Item #8CA51 & #9GFT8 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
366 | 1.2 | 1.2.1.6.2.25 | Started | PSL | Crate Drill Filtration Resupply (FS2 Resupply Container - Comsur) | Crate Drill Filtration Resupply (FS2 Resupply Container - Comsur) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2024-06-15 | 2024-06-24 | 0% | Off Ice | C2 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 0 | 0 | 0 | 642.7727 | 0 | 642.7727 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.1
367 | 1.2 | 1.2.1.6.2.26 | Not Started | PSL | Crate FS2 SES Interconnect Resupply (FS2 Resupply Container - Comsur) | Crate FS2 SES Interconnect Resupply (FS2 Resupply Container - Comsur) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2024-06-15 | 2024-06-27 | 0% | Off Ice | C2 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 0 | 0 | 0 | 642.7727 | 0 | 642.7727 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.1
368 | 1.2 | 1.2.1.6.2.27 | Started | PSL | Crate MHP/PHS Replacements & Spares (FS2 Resupply Container - Comsur) | Crate MHP/PHS Replacements & Spares (FY25 Shipment) (Vessel) |  |  | M & S | M & S |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2024-05-13 | 2024-05-22 | 53% | Off Ice | C2 |  |  |  |  | $250 estimated for packaging materials | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
369 | 1.2 | 1.2.1.6.2.28 | Not Started | PSL | Load FS2 Resupply Container (FS2 Comsur) | Load FS2 Resupply Container (Comsur) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2024-07-15 | 2024-07-23 | 0% | Off Ice | C2 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 16 |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 0 | 0 | 1285.5455 | 0 | 1285.5455 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1285.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.1
370 | 1.2 | 1.2.1.6.2.29 | Not Started | PSL | Crate Repair/Replacement Components Resupply (FS2 Resupply Container - Comsur) | Crate Repair/Replacement Components Resupply (FS2 Resupply Container - Comsur) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2024-07-03 | 2024-07-10 | 0% | Off Ice | C2 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 8 |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 0 | 0 | 642.7727 | 0 | 642.7727 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.1
371 | 1.2 | 1.2.1.6.2.30 | Started | PSL | Crate Control Systems Components Shipment 3 - DNF (Comsur) | Crate Control Systems Components Shipment 3 - DNF (Vessel) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2025-07-15 | 2025-07-23 | 0% | Off Ice | C2 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 16 |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1313.1847 | 0 | 0 | 1313.1847 | 0 | 1313.1847 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1313.1847 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 1313.1847 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.1
372 | 1.2 | 1.2.1.6.2.31 | Not Started | PSL | Load FS3 Resupply Container (Comsur) | Load FS3 Resupply Container (Comsur) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2025-07-15 | 2025-07-23 | 0% | Off Ice | C2 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
372 | 1.2 | 1.2.1.6.2.31 | Not Started | PSL | Load FS3 Resupply Container (Comsur) | Load FS3 Resupply Container (Comsur) |  |  | M & S | M & S |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2025-07-15 | 2025-07-23 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
374 | 1.2 | 1.2.1.6.3.1 | Started | PSL | FS0 - Ship Control Systems Components Shipment 1, ARA System DNF, Drill Heads, & Container C (Vessel) | FS0 - Ship Control Systems Components Shipment 1, ARA System Parts, Drill Heads, & Container C (Vessel) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2022-10-17 | 2022-10-17 | 53% | Off Ice | C2 | TRUE |  |  |  | Estimated based on November 2021 trucking invoice (SEKO) - October '22 is a full 53' trailer load | 4000 | [13 empty] | 4086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4086 | 2165.58 | 6251.58 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6251.58 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
374 | 1.2 | 1.2.1.6.3.1 | Started | PSL | FS0 - Ship Control Systems Components Shipment 1, ARA System DNF, Drill Heads, & Container C (Vessel) | FS0 - Ship Control Systems Components Shipment 1, ARA System Parts, Drill Heads, & Container C (Vessel) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2022-10-17 | 2022-10-17 | 53% | Off Ice | C2 | TRUE |  |  |  | Estimated based on 2021 Reynolds & Reynolds loading support invoice | 1000 | [13 empty] | 1021.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 541.395 | 1562.895 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1562.895 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
375 | 1.2 | 1.2.1.6.3.2 | Started | PSL | FS1 - Ship Control Systems Components Shipment 2 - DNF (Comsur) | FS1 - Ship Control Systems Components Shipment 2 - DNF (Comsur) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2023-08-01 | 2023-08-01 | 53% | Off Ice | C2 | TRUE |  |  |  | Estimated based on November 2021 trucking invoice (SEKO) - August '23 is a partial truck load | [10 empty] | 3500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3575.25 | 0 | 3575.25 | 1894.8825 | 5470.1325 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5470.1325 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
376 | 1.2 | 1.2.1.6.3.3 | Not Started | PSL | FS2 - Ship Control Systems Components Shipment 3, Refit Resupply Container (Comsur) | FS2 - Ship Control Systems Components Shipment 3, Resupply Container (Comsur) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2024-08-01 | 2024-08-01 | 53% | Off Ice | C2 | TRUE |  |  |  | Estimated based on November 2021 trucking invoice (SEKO) - August '24 is a quarter truck load | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 2500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2608.6556 | 0 | 2608.6556 | 1382.5875 | 3991.2431 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3991.2431 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
377 | 1.2 | 1.2.1.6.3.4 | Not Started | PSL | FS3 - Ship Resupply Container (Comsur) | FS3 - Ship Resupply Container (Comsur) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2025-08-01 | 2025-08-01 | 53% | Off Ice | C2 |  |  |  |  | Estimated based on November 2021 trucking invoice (SEKO) - August '25 is a quarter truck load | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 2500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2664.7417 | 0 | 2664.7417 | 1412.3131 | 4077.0548 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4077.0548 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
379 | 1.2 | 1.2.1.6.4.1 | Not Started | PSL | Crate Sensor Handling Structure | Crate (Installation): Sensor Handling Structure (Vessel) |  | 1.111% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-09-07 | 2022-09-30 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
379 | 1.2 | 1.2.1.6.4.1 | Not Started | PSL | Crate Sensor Handling Structure | Crate (Installation): Sensor Handling Structure (Vessel) |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-09-07 | 2022-09-30 | 53% | Off Ice | C2 | [5 empty] | 3000 | [13 empty] | 3064.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3064.5 | 1624.185 | 4688.685 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4688.685 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
380 | 1.2 | 1.2.1.6.4.2 | Not Started | PSL | Crate Installation Kits | Crate (Installation): Installation Kits (Vessel) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2023-06-21 | 2023-07-10 | 0% | Off Ice | C2 | [13 empty] | 16 | 16 |  |  | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 1258.488 | 0 | 0 | 2516.976 | 0 | 2516.976 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2516.976 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2516.976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.1
380 | 1.2 | 1.2.1.6.4.2 | Not Started | PSL | Crate Installation Kits | Crate (Installation): Installation Kits (Vessel) |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-06-21 | 2023-07-10 | 53% | Off Ice | C2 |  |  |  |  | 7x 34"H x 48"L x 40"Wx 7crates at $699/each Grainger 1XGG6 | [8 empty] | 2447 | 2447 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2499.6105 | 2499.6105 | 0 | 0 | 4999.221 | 2649.5871 | 7648.8081 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7648.8081 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
381 | 1.2 | 1.2.1.6.4.3 | Not Started | PSL | Crate String Weights | Crate (Installation): String Weights (Vessel) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2023-06-21 | 2023-06-27 | 0% | Off Ice | C2 |  |  |  |  | 2x $517/each Collapsible Bulk Container, Black, 34 inH x 48 inL x 45 inW, 1EA Item # 39H823 |  |  |  | 8 | [8 empty] | 8 | 0.053333 | 0 | 0 | 0 | 629.244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629.244 | 0 | 629.244 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629.244 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 629.244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.1
381 | 1.2 | 1.2.1.6.4.3 | Not Started | PSL | Crate String Weights | Crate (Installation): String Weights (Vessel) |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-06-21 | 2023-06-27 | 53% | Off Ice | C2 |  |  |  |  | $1317 estimated for three 40" x 48" x 25" bulk containers with lids to package hardware for shipping |  |  |  | 1034 | [10 empty] | 0 | 0 | 0 | 1056.231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056.231 | 559.8024 | 1616.0334 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1616.0334 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
382 | 1.2 | 1.2.1.6.4.4 | Not Started | PSL | Crate Science Equipment FS2 (SPAT, IME, Pressure Sensors, Laser Rangers) | Crate (Installation): Science Equipment FS2 (SPAT, IME, Laser Rangers, Pressure Sensors)(Comsur) |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0% | 2024-06-06 | 2024-06-12 | 53% | Off Ice | C2 |  |  |  |  | $371/each estimated for two 45" x 48" x 44" bulk containers with lids to package hardware for shipping | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 742 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 774.249 | 0 | 0 | 0 | 774.249 | 410.352 | 1184.601 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1184.601 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
383 | 1.2 | 1.2.1.6.4.5 | Not Started | PSL | Crate Science Equipment FS3 | Crate (Installation): Science Equipment FS3 (Comsur) |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0% | 2025-07-01 | 2025-07-07 | 53% | Off Ice | C2 |  |  |  |  | $371/each estimated for two 45" x 48" x 44" bulk containers with lids to package hardware for shipping | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 742 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 790.8953 | 0 | 0 | 790.8953 | 419.1745 | 1210.0699 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1210.0699 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
385 | 1.2 | 1.2.1.6.5.1 | Not Started | PSL | Ship Sensor Handling Structure | Ship (Installation): Sensor Handling Structure (Vessel) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2022-10-15 | 2022-10-15 | 53% | Off Ice | C2 |  |  |  |  | DHF ships on truck with Container C | 3000 | [13 empty] | 3064.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3064.5 | 1624.185 | 4688.685 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4688.685 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
386 | 1.2 | 1.2.1.6.5.2 | Not Started | PSL | Ship Installation Kits | Ship (Installation): Installation Kits (Vessel) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2023-10-15 | 2023-10-15 | 53% | Off Ice | C2 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052 | [13 empty] | 2141.1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2141.1845 | 1134.8278 | 3276.0123 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3276.0123 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
387 | 1.2 | 1.2.1.6.5.3 | Not Started | PSL | Ship String Weights | Ship (Installation): String Weights (Vessel) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2023-10-15 | 2023-10-15 | 53% | Off Ice | C2 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | [13 empty] | 542.6004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542.6004 | 287.5782 | 830.1786 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830.1786 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
388 | 1.2 | 1.2.1.6.5.4 | Not Started | PSL | Ship Science Crate FS2 (SPAT, IME, Pressure Sensors, Laser Rangers) | Ship (Installation): Science Equipment FS2 (SPAT, IME, Laser Rangers, Pressure Sensors) (Comsur) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2024-08-01 | 2024-08-01 | 53% | Off Ice | C2 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1043.4623 | 0 | 1043.4623 | 553.035 | 1596.4972 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1596.4972 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
389 | 1.2 | 1.2.1.6.5.5 | Not Started | PSL | Ship Science Crate FS3 | Ship (Installation): Science Equipment FS3 (Comsur) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2025-08-01 | 2025-08-01 | 53% | Off Ice | C2 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1065.8967 | 0 | 1065.8967 | 564.9252 | 1630.8219 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1630.8219 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.1
393 | 1.2 | 1.2.2.1.2 | Started | PSL | Assemble and Test Components (Flowmeters, PRV & Control boxes ) | MHP: Assemble and Test Components (Flowmeters, PRV & Control boxes ) | Gibson | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-04-01 | 2022-05-23 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
393 | 1.2 | 1.2.2.1.2 | Started | PSL | Assemble and Test Components (Flowmeters, PRV & Control boxes ) | MHP: Assemble and Test Components (Flowmeters, PRV & Control boxes ) |  | 0.8889% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2022-04-01 | 2022-05-23 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
394 | 1.2 | 1.2.2.1.3 | Not Started | PSL | Procure MHP Chimney Stacks (PY4) | MHP: Procure MHP Chimney Stacks | Undergrad | 2.222% | Labor Hours | Labor - Task | UG |  |  |  | 115 |  | 0% | 2022-04-12 | 2022-05-23 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
394 | 1.2 | 1.2.2.1.3 | Not Started | PSL | Procure MHP Chimney Stacks (PY4) | MHP: Procure MHP Chimney Stacks |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-04-12 | 2022-05-23 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
395 | 1.2 | 1.2.2.1.4 | Not Started | PSL | Design and Construct MHP Flush & Pressure Test Kit | MHP: Assemble and Test Components (flowmeters. PRV, control boxes) |  | 4.222% | Labor Hours | Labor - Task | EN-ME |  |  | HD | 115 | 115 | 0% | 2022-04-15 | 2022-05-30 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 8740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
395 | 1.2 | 1.2.2.1.4 | Not Started | PSL | Design and Construct MHP Flush & Pressure Test Kit | MHP: Assemble and Test Components (flowmeters. PRV, control boxes) |  | 1.778% | Labor Hours | Labor - Task | TE |  |  | HD | 77 | 77 | 0% | 2022-04-15 | 2022-05-30 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
395 | 1.2 | 1.2.2.1.4 | Not Started | PSL | Design and Construct MHP Flush & Pressure Test Kit | MHP: Assemble and Test Components (flowmeters. PRV, control boxes) |  |  | CapEx | CapEx |  |  |  | HD |  | 1 | 0% | 2022-04-15 | 2022-05-30 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
396 | 1.2 | 1.2.2.1.5 | Not Started | PSL | Build Electronics Kit for MHP1, Heater 7 | MHP: Design and Construct MHP Flush & Pressure Test Kit |  | 0.8889% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-05-18 | 2022-06-15 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
396 | 1.2 | 1.2.2.1.5 | Not Started | PSL | Build Electronics Kit for MHP1, Heater 7 | MHP: Design and Construct MHP Flush & Pressure Test Kit |  | 1.333% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2022-05-18 | 2022-06-15 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
396 | 1.2 | 1.2.2.1.5 | Not Started | PSL | Build Electronics Kit for MHP1, Heater 7 | MHP: Design and Construct MHP Flush & Pressure Test Kit |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-05-18 | 2022-06-15 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
397 | 1.2 | 1.2.2.1.6 | Not Started | PSL | Procure MHP Upgrade, Sub-Components, Spares (PY5) | MHP: Procure MHP Upgrade, Sub-Components, Spares (PY5) | Gibson | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-12 | 2023-05-23 | 0% | Off Ice | C3 | [11 empty] | 12 | 12 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 1409.67 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.2
397 | 1.2 | 1.2.2.1.6 | Not Started | PSL | Procure MHP Upgrade, Sub-Components, Spares (PY5) | MHP: Procure MHP Upgrade, Sub-Components, Spares (PY5) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-04-12 | 2023-05-23 | 53% | Off Ice | C3 | [11 empty] | 2500 | 2500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2553.75 | 2553.75 | 0 | 0 | 0 | 0 | 5107.5 | 0 | 5107.5 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5107.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
398 | 1.2 | 1.2.2.1.7 | Not Started | PSL | Develop HPU2 Integrate Plan | MHP: Develop HPU2 Integrate Plan |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-05-01 | 2024-06-11 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 25 | 25 |  |  |  | 50 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2999.954 | 2999.954 | 0 | 0 | 0 | 5999.9079 | 0 | 5999.9079 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5999.9079 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 5999.9079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 1.2.2
399 | 1.2 | 1.2.2.1.8 | Not Started | PSL | Procure and Assemble HPU2 Integration Components | MHP: Procure and Assemble HPU2 Integration Components |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-06-12 | 2024-07-23 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 20 | 20 |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.2
399 | 1.2 | 1.2.2.1.8 | Not Started | PSL | Procure and Assemble HPU2 Integration Components | MHP: Procure and Assemble HPU2 Integration Components |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0 | 2024-06-12 | 2024-07-23 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 20 | 20 |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1606.9319 | 1606.9319 | 0 | 0 | 3213.8637 | 0 | 3213.8637 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 3213.8637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.2
399 | 1.2 | 1.2.2.1.8 | Not Started | PSL | Procure and Assemble HPU2 Integration Components | MHP: Procure and Assemble HPU2 Integration Components |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2024-06-12 | 2024-07-23 | 53% | Off Ice | C3 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 5000 | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 5217.3112 | 0 | 0 | 10434.6225 | 0 | 10434.6225 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10434.6225 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
400 | 1.2 | 1.2.2.1.9 | Not Started | PSL | Combustion Analyzers, 3x, Spec-Procure-Validate | MHP: Combustion Analyzers, 3x, Spec-Procure-Validate |  | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-05-02 | 2022-05-20 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
400 | 1.2 | 1.2.2.1.9 | Not Started | PSL | Combustion Analyzers, 3x, Spec-Procure-Validate | MHP: Combustion Analyzers, 3x, Spec-Procure-Validate |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2022-05-02 | 2022-05-20 | 53% | Off Ice | C3 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
401 | 1.2 | 1.2.2.1.10 | Not Started | PSL | Procure MHP Upgrade, Sub-Components, Spares (PY6) | MHP: Procure Upgrade, Sub-Components, Spares (PY6) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-04-15 | 2024-04-19 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 12 | 12 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.2
401 | 1.2 | 1.2.2.1.10 | Not Started | PSL | Procure MHP Upgrade, Sub-Components, Spares (PY6) | MHP: Procure Upgrade, Sub-Components, Spares (PY6) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2024-04-15 | 2024-04-19 | 53% | Off Ice | C3 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2500 | 2500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2608.6556 | 2608.6556 | 0 | 0 | 0 | 0 | 5217.3112 | 0 | 5217.3112 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
403 | 1.2 | 1.2.2.2.1 | Started | PSL | Refine PHS Plumbing Upgrade Design | PHS: Refine PHS Plumbing Upgrade Design | Benson | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-06-02 | 2022-06-29 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
403 | 1.2 | 1.2.2.2.1 | Started | PSL | Refine PHS Plumbing Upgrade Design | PHS: Refine PHS Plumbing Upgrade Design |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-06-02 | 2022-06-29 | 53% | Off Ice |  | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
404 | 1.2 | 1.2.2.2.2 | Not Started | PSL | Identify Upgrade, Replacements & Spares Components | PHS: Identify Parts Upgrade & Spares |  | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-06-02 | 2022-07-13 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
405 | 1.2 | 1.2.2.2.3 | Started | PSL | Procure and Upgrade Control Boxes (PY4) | PHS: Procure and Upgrade Control Boxes (PY4) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-03-24 | 2022-05-25 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
405 | 1.2 | 1.2.2.2.3 | Started | PSL | Procure and Upgrade Control Boxes (PY4) | PHS: Procure and Upgrade Control Boxes (PY4) |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2022-03-24 | 2022-05-25 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
405 | 1.2 | 1.2.2.2.3 | Started | PSL | Procure and Upgrade Control Boxes (PY4) | PHS: Procure and Upgrade Control Boxes (PY4) |  |  | CapEx | CapEx |  |  |  | HD |  | 1 | 0% | 2022-03-24 | 2022-05-25 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
406 | 1.2 | 1.2.2.2.4 | Started | PSL | Procure and Upgrade Control Boxes (PY6) | PHS: Procure and Upgrade Control Boxes (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-03-01 | 2024-04-11 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.2
406 | 1.2 | 1.2.2.2.4 | Started | PSL | Procure and Upgrade Control Boxes (PY6) | PHS: Procure and Upgrade Control Boxes (PY6) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2024-03-01 | 2024-04-11 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 3213.8637 | 0 | 0 | 0 | 0 | 0 | 6427.7275 | 0 | 6427.7275 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6427.7275 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 6427.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.2
406 | 1.2 | 1.2.2.2.4 | Started | PSL | Procure and Upgrade Control Boxes (PY6) | PHS: Procure and Upgrade Control Boxes (PY6) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2024-03-01 | 2024-04-11 | 53% | Off Ice | C3 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2000 | 2000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 2086.9245 | 2086.9245 | 0 | 0 | 0 | 0 | 0 | 4173.849 | 0 | 4173.849 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4173.849 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
407 | 1.2 | 1.2.2.2.5 | Started | PSL | Procure Upgrade, Sub-Components, Spares (PY6) | PHS: Procure Upgrade, Sub-Components, Spares (PY6) |  |  | Labor Hours | Labor Hours | EN-ME |  |  | D - Expert Opinion |  | 115 | 0% | 2024-04-01 | 2024-05-10 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 12 | 12 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.2
407 | 1.2 | 1.2.2.2.5 | Started | PSL | Procure Upgrade, Sub-Components, Spares (PY6) | PHS: Procure Upgrade, Sub-Components, Spares (PY6) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2024-04-01 | 2024-05-10 | 53% | Off Ice | C3 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2500 | 2500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2608.6556 | 2608.6556 | 0 | 0 | 0 | 0 | 5217.3112 | 0 | 5217.3112 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
409 | 1.2 | 1.2.2.3.1 | Complete | PSL | Fuel Systems: Review & Redesign (5k Tank-Tower) | Fuel Systems: Review & Redesign (5k Tank-Tower) | Benson | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2020-10-01 | 2021-01-20 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
410 | 1.2 | 1.2.2.3.2 | Started | PSL | Procurement (Hose, Valves, Sensors, Controls Etc.) | Fuel Systems: Procurement (Hose, Valves, Sensors, Controls Etc.) | Benson | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2021-10-04 | 2022-08-18 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
410 | 1.2 | 1.2.2.3.2 | Started | PSL | Procurement (Hose, Valves, Sensors, Controls Etc.) | Fuel Systems: Procurement (Hose, Valves, Sensors, Controls, Etc.) |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2021-10-04 | 2022-08-18 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
411 | 1.2 | 1.2.2.3.3 | Complete | PSL | Fuel Tower: Review Design & Specs, Field Inputs - Develop Plan | Fuel Tower: Review Design & Specs, Field Inputs - Develop Plan | Benson | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2020-11-02 | 2020-12-11 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
412 | 1.2 | 1.2.2.3.4 | Complete | PSL | Fuel Tower: Redesign Components | Fuel Tower: Redesign Components | Benson | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2020-11-02 | 2020-12-11 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
414 | 1.2 | 1.2.2.3.6 | Started | PSL | Fuel Tower: Procure Upgrade-Replacements, Spares | Fuel Tower: Procure Upgrade-Replacements, Spares | Benson | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-02-07 | 2022-04-29 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
414 | 1.2 | 1.2.2.3.6 | Started | PSL | Fuel Tower: Procure Upgrade-Replacements, Spares | Fuel Tower: Procure Upgrade-Replacements, Spares |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-02-07 | 2022-04-29 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
415 | 1.2 | 1.2.2.3.7 | Not Started | PSL | Fuel Sled Panel Updates - Interface Integration | Fuel Tower: Fuel Sled Panel Updates - Interface Integration | Laundrie | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-05-30 | 2022-09-21 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
416 | 1.2 | 1.2.2.3.8 | Not Started | PSL | Procure ARA Fueling Hose & Nozzle (PY5) | Fuel Tower: Procure ARA Fueling Hose & Nozzle (PY5) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-02-28 | 2023-03-13 | 0% | Off Ice | C3 | [10 empty] | 8 | [6 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.2
416 | 1.2 | 1.2.2.3.8 | Not Started | PSL | Procure ARA Fueling Hose & Nozzle (PY5) | Fuel Tower: Procure ARA Fueling Hose & Nozzle (PY5) |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0 | 2023-02-28 | 2023-03-13 | 53% | Off Ice | C3 | [10 empty] | 4442 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 4537.503 | 0 | 0 | 0 | 0 | 0 | 0 | 4537.503 | 0 | 4537.503 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4537.503 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
417 | 1.2 | 1.2.2.3.9 | Not Started | PSL | Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) | Fuel Tower: Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-02-28 | 2023-03-13 | 0% | Off Ice | C3 | [10 empty] | 16 | [6 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.2
417 | 1.2 | 1.2.2.3.9 | Not Started | PSL | Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) | Fuel Tower: Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0 | 2023-02-28 | 2023-03-13 | 0% | Off Ice | C3 | [10 empty] | 16 | [6 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 1258.488 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.2
417 | 1.2 | 1.2.2.3.9 | Not Started | PSL | Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) | Fuel Tower: Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2023-02-28 | 2023-03-13 | 53% | Off Ice | C3 | [10 empty] | 1500 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 1532.25 | 0 | 0 | 0 | 0 | 0 | 0 | 1532.25 | 0 | 1532.25 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1532.25 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
418 | 1.2 | 1.2.2.3.10 | Not Started | PSL | Procure Fuel system Upgrade/Maintenance Subcomponents (PY6) | Fuel Tower: Procure Fuel system Upgrade/Maintenance Subcomponents (PY6) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-03-30 | 2024-04-11 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 12 | 12 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.2
418 | 1.2 | 1.2.2.3.10 | Not Started | PSL | Procure Fuel system Upgrade/Maintenance Subcomponents (PY6) | Fuel Tower: Procure Fuel system Upgrade/Maintenance Subcomponents (PY6) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2024-03-30 | 2024-04-11 | 53% | Off Ice | C3 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1200 | 1200 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 1252.1547 | 1252.1547 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 0 | 2504.3094 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2504.3094 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
419 | 1.2 | 1.2.2.3.11 | Not Started | PSL | Procure MHP Fuel Heat Exchangers Replacements (PY6) | Fuel Tower: Procure MHP Fuel Heat Exchangers Replacements (PY6) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-04-01 | 2024-04-12 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 16 | [5 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.2
419 | 1.2 | 1.2.2.3.11 | Not Started | PSL | Procure MHP Fuel Heat Exchangers Replacements (PY6) | Fuel Tower: Procure MHP Fuel Heat Exchangers Replacements (PY6) |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2024-04-01 | 2024-04-12 | 53% | Off Ice | C3 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 10283 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10729.9223 | 0 | 0 | 0 | 0 | 0 | 10729.9223 | 0 | 10729.9223 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10729.9223 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.2
422 | 1.2 | 1.2.3.1.1 | Complete | PSL | Reassess Down Hole Loads - String/DOM Configurations | Tower Ops: Reassess Down Hole Loads - String/DOM Configurations | Greenler | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2019-03-01 | 2020-05-01 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
423 | 1.2 | 1.2.3.1.2 | Complete | PSL | Perform Structural Review of Tower & Components | Tower Ops: Perform Structural Review of Tower & Components |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2021-05-03 | 2021-06-11 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
423 | 1.2 | 1.2.3.1.2 | Complete | PSL | Perform Structural Review of Tower & Components | Tower Ops: Perform Structural Review of Tower & Components | Benson | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2021-05-03 | 2021-06-11 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
424 | 1.2 | 1.2.3.1.3 | Not Started | PSL | Crescent & Belt Refurbishment (4 ea) | Tower Ops: Crescent & Belt Refurbishment (4 ea) (PSL_Shop) |  | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-06-01 | 2022-06-28 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
424 | 1.2 | 1.2.3.1.3 | Not Started | PSL | Crescent & Belt Refurbishment (4 ea) | Tower Ops: Crescent & Belt Refurbishment (4 ea) (PSL_Shop) |  | 0.4444% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2022-06-01 | 2022-06-28 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
424 | 1.2 | 1.2.3.1.3 | Not Started | PSL | Crescent & Belt Refurbishment (4 ea) | Tower Ops: Crescent & Belt Refurbishment (4 ea) |  | 2.222% | Labor Hours | Labor - Task | UG |  |  |  | 115 |  | 0% | 2022-06-01 | 2022-06-28 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
424 | 1.2 | 1.2.3.1.3 | Not Started | PSL | Crescent & Belt Refurbishment (4 ea) | Tower Ops: Crescent & Belt Refurbishment (4 ea) |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2022-06-01 | 2022-06-28 | 53% | Off Ice |  | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
426 | 1.2 | 1.2.3.1.5 | Not Started | PSL | Crescent Emergency Repair Kit Assembly (PY6) | Tower Ops: Crescent Emergency Repair Kit Assembly | Lemery | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-02-01 | 2024-03-20 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | [7 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.3
426 | 1.2 | 1.2.3.1.5 | Not Started | PSL | Crescent Emergency Repair Kit Assembly (PY6) | Tower Ops: Crescent Emergency Repair Kit Assembly | Lemry |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2024-02-01 | 2024-03-20 | 53% | Off Ice | C3 | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2500 | [9 empty] | 0 | 0 | 0 | 0 | 2608.6556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2608.6556 | 0 | 2608.6556 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2608.6556 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
427 | 1.2 | 1.2.3.1.6 | Not Started | PSL | Examine Interface between Dust Logger and Tower & Address as Needed | Tower Ops: Examine Interface between Dust Logger and Tower & Address as Needed |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-07-01 | 2023-08-10 | 0% | Off Ice | C4 | TRUE | [13 empty] | 20 | 20 |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.3
427 | 1.2 | 1.2.3.1.6 | Not Started | PSL | Examine Interface between Dust Logger and Tower & Address as Needed | Tower Ops: Examine Interface between Dust Logger and Tower & Address as Needed |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-07-01 | 2023-08-10 | 53% | Off Ice | C4 | TRUE | [13 empty] | 1200 | 1200 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1225.8 | 1225.8 | 0 | 2451.6 | 0 | 2451.6 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2451.6 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
430 | 1.2 | 1.2.3.1.7.2 | Not Started | PSL | Calibration Load Cell | Tower Ops: Load Cell Calibration |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-02-01 | 2023-02-28 | 0% | Off Ice | C2 | TRUE | [8 empty] | 8 | [7 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.3
430 | 1.2 | 1.2.3.1.7.2 | Not Started | PSL | Calibration Load Cell | Tower Ops: Load Cell Calibration |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-02-01 | 2023-02-28 | 53% | Off Ice | C2 | TRUE | [8 empty] | 1789 | [9 empty] | 0 | 0 | 0 | 0 | 1827.4635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1827.4635 | 0 | 1827.4635 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1827.4635 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
431 | 1.2 | 1.2.3.1.7.3 | Not Started | PSL | Calibration Load Cell Rigging | Tower Ops: Identify/Procure: Load Cell Rigging Calibration |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-03-01 | 2023-03-14 | 0% | Off Ice | C2 | TRUE | [9 empty] | 8 | [6 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.3
431 | 1.2 | 1.2.3.1.7.3 | Not Started | PSL | Calibration Load Cell Rigging | Tower Ops: Identify/Procure: Load Cell Rigging Calibration |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-03-01 | 2023-03-14 | 53% | Off Ice | C2 | TRUE | [9 empty] | 1220 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 1246.23 | 0 | 0 | 0 | 0 | 0 | 0 | 1246.23 | 0 | 1246.23 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1246.23 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
432 | 1.2 | 1.2.3.1.8 | Started | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-06-14 | 2023-08-01 | 0% | Off Ice | C3 | TRUE | [12 empty] | 16 |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.3
432 | 1.2 | 1.2.3.1.8 | Started | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-06-14 | 2023-08-01 | 0% | Off Ice | C3 | TRUE | [12 empty] | 8 |  | 8 |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.3
432 | 1.2 | 1.2.3.1.8 | Started | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-06-14 | 2023-08-01 | 53% | Off Ice | C3 | TRUE |  |  |  | Driller tape: 4 cases @ 30 rolls/case = 120 rolls $50/roll -> $6k | [8 empty] | 5232 |  | 5000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5344.488 | 0 | 5107.5 | 0 | 10451.988 | 0 | 10451.988 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10451.988 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
433 | 1.2 | 1.2.3.1.9 | Started | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-06-12 | 2024-07-30 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 16 |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 0 | 0 | 1919.9705 | 0 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.3
433 | 1.2 | 1.2.3.1.9 | Started | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) |  |  | Labor Hours | Labor Hours | EN-ME |  |  | D - Expert Opinion |  | 115 | 0% | 2024-06-12 | 2024-07-30 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 16 |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 0 | 1919.9705 | 0 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.3
433 | 1.2 | 1.2.3.1.9 | Started | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2024-06-12 | 2024-07-30 | 53% | Off Ice | C3 | TRUE |  |  |  | Driller tape: 4 cases @ 30 rolls/case = 120 rolls $50/roll -> $6k | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 5232 | 4000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5459.3945 | 4173.849 | 0 | 0 | 9633.2435 | 0 | 9633.2435 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9633.2435 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
434 | 1.2 | 1.2.3.1.10 | Started | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2025-05-14 | 2025-07-01 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 16 |  |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 0 | 0 | 0 | 0 | 1961.2499 | 0 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 1961.2499 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.3
434 | 1.2 | 1.2.3.1.10 | Started | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2025-05-14 | 2025-07-01 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 16 |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 0 | 0 | 0 | 1961.2499 | 0 | 1961.2499 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 1961.2499 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.3
434 | 1.2 | 1.2.3.1.10 | Started | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2025-05-14 | 2025-07-01 | 53% | Off Ice | C3 | TRUE |  |  |  | Driller tape: 50 rolls/hole x 7 holes = 350 rolls Plus 3 cases @ 30 rolls/case = 440 rolls $50/roll -> $22k | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 20492 | 2500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21842.3549 | 2664.7417 | 0 | 0 | 0 | 24507.0967 | 0 | 24507.0967 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24507.0967 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
437 | 1.2 | 1.2.3.2.2 | Complete | PSL | Drillhead and software subsystem testing | Drillhead: Software Subsystem Testing | Xiang | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2021-04-16 | 2021-05-13 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
437 | 1.2 | 1.2.3.2.2 | Complete | PSL | Drillhead and software subsystem testing | Drillhead: Software Subsystem Testing |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2021-04-16 | 2021-05-13 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
437 | 1.2 | 1.2.3.2.2 | Complete | PSL | Drillhead and software subsystem testing | Drillhead: Software Subsystem Testing |  |  | CapEx | CapEx |  |  |  | HD |  | 1 | 0% | 2021-04-16 | 2021-05-13 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
438 | 1.2 | 1.2.3.2.3 | Complete | PSL | Rework/rewrite drillhead software | Drillhead: Rework/rewrite Drillhead Software |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2021-03-12 | 2021-05-13 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
442 | 1.2 | 1.2.3.2.7 | Not Started | PSL | Update Drillheads for Cable | Drillhead: Update Drillheads for Cable |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | HD | 115 | 115 | 0% | 2022-03-16 | 2022-05-17 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
442 | 1.2 | 1.2.3.2.7 | Not Started | PSL | Update Drillheads for Cable | Drillhead: Update Drillheads for Cable |  | 0% | Labor Hours | Labor - Task | TE |  |  | HD | 77 | 77 | 0% | 2022-03-16 | 2022-05-17 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
443 | 1.2 | 1.2.3.2.8 | Not Started | PSL | Pressure Test Drillhead Hanger & Spare Hose | Drillhead: Pressure Test Drillhead Hanger & Spare Hose |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-03-16 | 2022-05-17 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
443 | 1.2 | 1.2.3.2.8 | Not Started | PSL | Pressure Test Drillhead Hanger & Spare Hose | Drillhead: Pressure Test Drillhead Hanger & Spare Hose |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-03-16 | 2022-05-17 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
445 | 1.2 | 1.2.3.2.10 | Not Started | PSL | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-09-15 | 2022-09-22 | 0% | Off Ice | C3 | [5 empty] | 24 | [11 empty] | 24 | 0.16 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.3
445 | 1.2 | 1.2.3.2.10 | Not Started | PSL | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-09-15 | 2022-09-22 | 0% | Off Ice | C3 | [5 empty] | 24 | [11 empty] | 24 | 0.16 | 1887.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 0 | 1887.732 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1887.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.3
447 | 1.2 | 1.2.3.3.1 | Complete | PSL | Main Drill Cable Reel (at PSL): Rebuild, Upgrade, Test | Reels & Winches: MCR - Rebuild & Upgrade |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2020-11-02 | 2021-02-19 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
447 | 1.2 | 1.2.3.3.1 | Complete | PSL | Main Drill Cable Reel (at PSL): Rebuild, Upgrade, Test | Reels & Winches: MCR - Rebuild & Upgrade |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2020-11-02 | 2021-02-19 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
447 | 1.2 | 1.2.3.3.1 | Complete | PSL | Main Drill Cable Reel (at PSL): Rebuild, Upgrade, Test | Reels & Winches: MCR - Test |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2020-11-02 | 2021-02-19 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
447 | 1.2 | 1.2.3.3.1 | Complete | PSL | Main Drill Cable Reel (at PSL): Rebuild, Upgrade, Test | Reels & Winches: MCR - Test |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2020-11-02 | 2021-02-19 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
448 | 1.2 | 1.2.3.3.2 | Complete | PSL | Return Water Cable Reel (at PSL): Rebuild, Upgrade, Test | Reels & Winches: Return Water Cable Reel - Rebuild & Upgrade |  | 0.8889% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2021-10-02 | 2022-01-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
448 | 1.2 | 1.2.3.3.2 | Complete | PSL | Return Water Cable Reel (at PSL): Rebuild, Upgrade, Test | Reels & Winches: Return Water Cable Reel - Rebuild & Upgrade |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2021-10-02 | 2022-01-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
448 | 1.2 | 1.2.3.3.2 | Complete | PSL | Return Water Cable Reel (at PSL): Rebuild, Upgrade, Test | Reels & Winches: Return Water Cable Reel - Test |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0% | 2021-10-02 | 2022-01-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
448 | 1.2 | 1.2.3.3.2 | Complete | PSL | Return Water Cable Reel (at PSL): Rebuild, Upgrade, Test | Reels & Winches: Return Water Cable Reel - Test |  | 0% | Labor Hours | Labor - Task | TE |  |  | EE | 77 | 77 | 0% | 2021-10-02 | 2022-01-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
449 | 1.2 | 1.2.3.3.3 | Started | PSL | Main Supply Hose Reel (Big Red at NPX) - Procure Replacement Parts | Reels & Winches: MSHR - Procure Replacement Parts |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-01-05 | 2024-04-02 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
449 | 1.2 | 1.2.3.3.3 | Started | PSL | Main Supply Hose Reel (Big Red at NPX) - Procure Replacement Parts | Reels & Winches: MSHR - Procure Replacement Parts | Benson |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-01-05 | 2024-04-02 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
449 | 1.2 | 1.2.3.3.3 | Started | PSL | Main Supply Hose Reel (Big Red at NPX) - Procure Replacement Parts | Reels & Winches: MSHR - Procure Replacement Parts |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2022-01-05 | 2024-04-02 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
451 | 1.2 | 1.2.3.3.5 | Complete | PSL | TU-20 Winches (at NPX) - Plan/Procure Replacement Parts. Design/Fabricate New Axles | Reels & Winches: TU-20 Winches (at NPX) - Plan/Procure Replacement Parts |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2021-02-01 | 2021-04-23 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
451 | 1.2 | 1.2.3.3.5 | Complete | PSL | TU-20 Winches (at NPX) - Plan/Procure Replacement Parts. Design/Fabricate New Axles | Reels & Winches: TU-20 Winches - Plan/Procure Replacement Parts |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2021-02-01 | 2021-04-23 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
454 | 1.2 | 1.2.3.3.7.1 | Should have Started | PSL | Load sharing: Coordination, Design, Documentation (PY4) | Reels & Winches: Load sharing: Coordination, design, documentation (PY4) |  | 15.56% | Labor Hours | Labor - Task | EN-ME |  |  | EE | 115 | 115 | 0 | 2021-12-20 | 2022-09-16 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 32200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
455 | 1.2 | 1.2.3.3.7.2 | Should have Started | PSL | Load sharing: Modeling and Software Development, Bench Testing (PY4) | Reels & Winches: Load sharing: Modeling and software development, bench testing (PY4) |  | 15.56% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0 | 2021-12-20 | 2022-06-17 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 32200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
455 | 1.2 | 1.2.3.3.7.2 | Should have Started | PSL | Load sharing: Modeling and Software Development, Bench Testing (PY4) | Reels & Winches: Load sharing: Modeling and software development, bench testing (PY4) |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0 | 2021-12-20 | 2022-06-17 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
456 | 1.2 | 1.2.3.3.7.3 | Not Started | PSL | Load sharing: Full scale Test Setup (PY4) | Reels & Winches: Load sharing: Full scale test setup (PY4) |  | 8.333% | Labor Hours | Labor - Task | TE |  |  | EE | 77 | 77 | 0 | 2022-04-04 | 2022-08-19 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 11550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
456 | 1.2 | 1.2.3.3.7.3 | Not Started | PSL | Load sharing: Full scale Test Setup (PY4) | Reels & Winches: Load sharing: Full scale test setup (PY4) |  | 18.89% | Labor Hours | Labor - Task | EN-ME |  |  | EE | 115 | 115 | 0 | 2022-04-04 | 2022-08-19 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 39100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
456 | 1.2 | 1.2.3.3.7.3 | Not Started | PSL | Load sharing: Full scale Test Setup (PY4) | Reels & Winches: Load sharing: Full scale test setup (PY4) |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0 | 2022-04-04 | 2022-08-19 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
457 | 1.2 | 1.2.3.3.7.4 | Not Started | PSL | Load sharing: Full-scale Testing - Diameter Correction and Prelim Load Share (PY4) | Reels & Winches: Load sharing: Full scale testing - diameter correction and prelim load share (PY4) |  | 16.33% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0 | 2022-03-14 | 2022-09-23 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 33810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
457 | 1.2 | 1.2.3.3.7.4 | Not Started | PSL | Load sharing: Full-scale Testing - Diameter Correction and Prelim Load Share (PY4) | Reels & Winches: Main Drill Cable Reel/Main Hose Reel Load Sharing Testing |  | 8.333% | Labor Hours | Labor - Task | TE |  |  | EE | 77 | 77 | 0 | 2022-03-14 | 2022-09-23 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 11550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
458 | 1.2 | 1.2.3.3.7.5 | Not Started | PSL | Load Sharing: Full-scale Testing - Load Share & Tuning (PY5) | Reels & Winches: Load sharing: Full scale testing - load share and tuning (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0 | 2023-02-13 | 2023-06-16 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
460 | 1.2 | 1.2.3.3.9 | Not Started | PSL | Reels & Winches: Drill Reels Sliprings - Final Testing & Prep | Reels & Winches: Drill Reels Sliprings - final testing and prep |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-06-10 | 2023-06-22 | 0% | Off Ice | C3 | [13 empty] | 16 |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.3
461 | 1.2 | 1.2.3.3.10 | Not Started | PSL | Reels & Winches: TU20 Sliprings - Spec, Procure, Test | Reels & Winches: TU20 Sliprings - spec, procure, test |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-03-30 | 2023-05-24 | 0% | Off Ice | C3 | [10 empty] | 80 | 80 | [5 empty] | 160 | 1.0667 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 18795.6 | 0 | 18795.6 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18795.6 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 18795.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 1.2.3
461 | 1.2 | 1.2.3.3.10 | Not Started | PSL | Reels & Winches: TU20 Sliprings - Spec, Procure, Test | Reels & Winches: TU20 Sliprings - spec, procure, test |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2023-03-30 | 2023-05-24 | 53% | Off Ice | C3 | [10 empty] | 8413 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 8593.8795 | 0 | 0 | 0 | 0 | 0 | 0 | 8593.8795 | 0 | 8593.8795 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8593.8795 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
462 | 1.2 | 1.2.3.3.11 | Not Started | PSL | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-03-01 | 2024-04-25 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 80 | [6 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.3
462 | 1.2 | 1.2.3.3.11 | Not Started | PSL | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0 | 2024-03-01 | 2024-04-25 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | [6 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 0 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 0 | 3213.8637 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 3213.8637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.3
462 | 1.2 | 1.2.3.3.11 | Not Started | PSL | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2024-03-01 | 2024-04-25 | 53% | Off Ice | C3 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 8770 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 9151.1639 | 0 | 0 | 0 | 0 | 0 | 0 | 9151.1639 | 0 | 9151.1639 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9151.1639 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
465 | 1.2 | 1.2.3.4.2 | Complete | PSL | Confirm & Specify Drill Hose | Main Drill Hose: Confirm & Specify Drill Hose |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2019-10-01 | 2019-11-25 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
466 | 1.2 | 1.2.3.4.3 | Complete | PSL | Procure drill hose (Manufacture by IVG) | Main Drill Hose: Procure Hose (Manufacture by IVG) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2019-09-17 | 2020-08-17 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
469 | 1.2 | 1.2.3.4.6 | Complete | PSL | Manufacture Strain Reliefs (at PSL) | Main Drill Hose: Manufacture Strain Reliefs (PSL_Drafter) |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2019-09-13 | 2020-01-02 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
469 | 1.2 | 1.2.3.4.6 | Complete | PSL | Manufacture Strain Reliefs (at PSL) | Main Drill Hose: Manufacture Strain Reliefs (at PSL) (PSL_Shop) |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2019-09-13 | 2020-01-02 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
469 | 1.2 | 1.2.3.4.6 | Complete | PSL | Manufacture Strain Reliefs (at PSL) | Main Drill Hose: Manufacture Strain Reliefs (at PSL) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2019-09-13 | 2020-01-02 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
470 | 1.2 | 1.2.3.4.7 | Complete | PSL | Ship Strain Reliefs to Italy (Mnftr Install on Hose) | Main Drill Hose: Ship Strain Reliefs to Italy (Mnftr Install on Hose) |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2020-01-03 | 2020-07-16 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
471 | 1.2 | 1.2.3.4.8 | Complete | PSL | Prepare Hose at PSL, Crate for Shipment, Hold 1 Year | Main Drill Hose: Prepare Hose at PSL, Crate for Shipment, Hold 1 Year |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2020-11-17 | 2020-11-23 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
474 | 1.2 | 1.2.3.5.1 | Complete | PSL | Main Drill Cable Spec Review & Revisions | Drill Cables: Main Drill Cable Spec Review & Revisions |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2019-10-01 | 2020-03-13 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
475 | 1.2 | 1.2.3.5.2 | Complete | PSL | Combo Cable - Spec Review & Revisions | Drill Cables: Combo Cable - Spec Review & Revisions |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2019-10-01 | 2020-03-13 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
476 | 1.2 | 1.2.3.5.3 | Complete | PSL | Test Combo Cable (2 at PSL) | Drill Cables: Test Combo Cable (2 at PSL) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2020-03-16 | 2020-05-08 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
476 | 1.2 | 1.2.3.5.3 | Complete | PSL | Test Combo Cable (2 at PSL) | Drill Cables: Test Combo Cable (2 at PSL) |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2020-03-16 | 2020-05-08 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
478 | 1.2 | 1.2.3.5.5 | Complete | PSL | Procure Main Drill Cable | Drill Cables: Procure Main Drill Cable |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2020-10-08 | 2021-06-16 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
478 | 1.2 | 1.2.3.5.5 | Complete | PSL | Procure Main Drill Cable | Drill Cables: Procure Main Drill Cable |  |  | CapEx | CapEx |  |  |  | VQ |  | 1 | 0% | 2020-10-08 | 2021-06-16 | 53% | Off Ice |  | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
480 | 1.2 | 1.2.3.5.7 | Complete | PSL | Connectors - Procure & Install, Both Cables (at vendor) | Drill Cables: Drill Cable Connectors |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2021-03-25 | 2021-06-16 | 0% | Off Ice |  | TRUE |  |  |  | Installed by Fibron (manufacturer) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
481 | 1.2 | 1.2.3.5.8 | Complete | PSL | Spool Main Drill Cable onto Winch/Spool | Drill Cables: Spool Main Drill Cable onto Winch/Spool |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2020-08-31 | 2020-09-18 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
481 | 1.2 | 1.2.3.5.8 | Complete | PSL | Spool Main Drill Cable onto Winch/Spool | Drill Cables: Spool Main Drill Cable onto Winch/Spool |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2020-08-31 | 2020-09-18 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
484 | 1.2 | 1.2.3.6.1.1 | Not Started | PSL | Connectorize Heated Blankets | Hose Reel Heating System: Connectorize Heated Blankets | Laundrie | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-10-01 | 2022-10-06 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
485 | 1.2 | 1.2.3.6.1.2 | Not Started | PSL | Attach RTDs to Inner Insulation & Heated Blankets | Hose Reel Heating System: Attach RTDs to Inner Insulation & Heated Blankets | Laundrie | 0.5% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-04-15 | 2022-05-12 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
486 | 1.2 | 1.2.3.6.1.3 | Not Started | PSL | Design and Fab RTD Patch Panel | Hose Reel Heating System: Design and Fab RTD patch panel | Laundrie | 1% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-04-15 | 2022-05-13 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
488 | 1.2 | 1.2.3.6.2.1 | Not Started | PSL | Size and Procure Insulated Tarps for Inner/Outer Layers | Hose Reel Heating System: Size and procure Insulated Tarps for Inner/Outer Layers | Birrittella | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  | EE | 115 | 115 | 0 | 2022-04-02 | 2022-04-28 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
488 | 1.2 | 1.2.3.6.2.1 | Not Started | PSL | Size and Procure Insulated Tarps for Inner/Outer Layers | Hose Reel Heating System: Size and procure Insulated Tarps for Inner/Outer Layers |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0 | 2022-04-02 | 2022-04-28 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
489 | 1.2 | 1.2.3.6.2.2 | Not Started | PSL | Size and Procure Outer Canvas Tarp | Hose Reel Heating System: Size and Procure Outer Canvas Tarp | Birrittella | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  | EE | 115 | 115 | 0% | 2022-04-29 | 2022-05-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
489 | 1.2 | 1.2.3.6.2.2 | Not Started | PSL | Size and Procure Outer Canvas Tarp | Hose Reel Heating System: Size and Procure Outer Canvas Tarp |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2022-04-29 | 2022-05-26 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.3
491 | 1.2 | 1.2.3.6.3.1 | Not Started | PSL | Cold Test Hose Heating Controller System | Hose Reel Heating System: Cold Test Hose Heating Controller System |  | 4.5% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0 | 2022-02-27 | 2022-03-24 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
493 | 1.2 | 1.2.3.6.4.1 | Not Started | PSL | Develop User Interface, Primarily for Blanket Setpoints, Alarm Setpoints | Hose Reel Heating System: Develop User Interface, Primarily for Blanket Setpoints, Alarm Setpoints |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0 | 2022-03-25 | 2022-04-14 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
494 | 1.2 | 1.2.3.6.4.2 | Not Started | PSL | Develop/Test Blanket Temp Control | Hose Reel Heating System: Develop/Test Blanket Temp Control |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0 | 2022-04-15 | 2022-05-12 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
495 | 1.2 | 1.2.3.6.4.3 | Not Started | PSL | Finalize Data Logging | Hose Reel Heating System: Finalize Data Logging |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0 | 2022-05-13 | 2022-05-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
496 | 1.2 | 1.2.3.6.4.4 | Not Started | PSL | Develop/Test Alerting Notifications | Hose Reel Heating System: Develop/Test Alerting Notifications |  | 2.222% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0 | 2022-09-16 | 2022-09-29 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
497 | 1.2 | 1.2.3.6.4.5 | Not Started | PSL | Document Subsystem | Hose Reel Heating System: Document Subsystem |  | 2.222% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0 | 2022-09-16 | 2022-09-29 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
498 | 1.2 | 1.2.3.6.5 | Not Started | PSL | System Tests | Hose Reel Heating System: Document Subsystem |  | 4.444% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0 | 2022-08-19 | 2022-09-29 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
499 | 1.2 | 1.2.3.6.6 | Not Started | PSL | Make Installation Drawing | Hose Reel Heating System: Make Installation Drawing |  | 4.444% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0 | 2022-08-16 | 2022-08-29 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
500 | 1.2 | 1.2.3.6.7 | Not Started | PSL | Prepare for Shipment | Hose Reel Heating System: Prepare for Shipment |  | 1.333% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0 | 2022-09-30 | 2022-10-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
504 | 1.2 | 1.2.4.1.2 | Complete | PSL | ICUD Requirements & Architecture Plan | Architecture: ICUD Requirements & Architecture Plan (PSL_Software Engineer) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2019-04-24 | 2019-08-13 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
504 | 1.2 | 1.2.4.1.2 | Complete | PSL | ICUD Requirements & Architecture Plan | Architecture: ICUD Requirements & Architecture Plan (PSL_Engineer) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2019-04-24 | 2019-08-13 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
506 | 1.2 | 1.2.4.1.4 | Complete | PSL | System Design | Architecture: System Design (PSL_Software Engineer) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2019-08-15 | 2020-01-29 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
506 | 1.2 | 1.2.4.1.4 | Complete | PSL | System Design | Architecture: System Design (PSL_Engineer) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2019-08-15 | 2020-01-29 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
507 | 1.2 | 1.2.4.1.5 | Not Started | PSL | Control Systems - 60% Design Review Complete | Architecture: Final Design Review (PSL_Engineer) |  | 2.222% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-04-15 | 2022-04-15 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
508 | 1.2 | 1.2.4.1.6 | Not Started | PSL | Control Systems - Electrical Schematic Update 1 | Architecture: Control Systems - Electrical Schematic Update |  | 6.667% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0 | 2022-02-15 | 2022-07-18 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
509 | 1.2 | 1.2.4.1.7 | Not Started | PSL | Coordination with USAP IT (PY4) | Architecture: Coordination with USAP IT (PY4) (station connectivity, internet, phone) |  | 1.111% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0 | 2022-05-15 | 2022-05-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
510 | 1.2 | 1.2.4.1.8 | Not Started | PSL | Coordination with USAP IT (PY5) | Architecture: Coordination with USAP IT (PY5) (station connectivity, internet, phone) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-06-01 | 2023-06-28 | 0% | Off Ice | C3 | [13 empty] | 20 |  |  |  | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1.2.4
511 | 1.2 | 1.2.4.1.9 | Not Started | PSL | CS Drawings & Documentation (PY5) | Architecture: CS Drawings & Documentation (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-07-03 | 2023-09-22 | 0% | Off Ice | C3 | [14 empty] | 8 | 16 | 8 | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1879.56 | 939.78 | 3759.12 | 0 | 3759.12 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.4
512 | 1.2 | 1.2.4.1.10 | Not Started | PSL | CS Drawings & Documentation (PY6) | Architecture: CS Drawings & Documentation (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-08-03 | 2024-10-24 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 16 | 16 | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1919.9705 | 3839.9411 | 0 | 3839.9411 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3839.9411 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 3839.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.4
513 | 1.2 | 1.2.4.1.11 | Not Started | PSL | CS Drawings & Documentation (PY7) | Architecture: CS Drawings & Documentation (PY7) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2025-08-03 | 2025-10-23 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 16 | 16 | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 1961.2499 | 3922.4998 | 0 | 3922.4998 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3922.4998 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 3922.4998 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.4
514 | 1.2 | 1.2.4.1.12 | Started | PSL | CS Drawings & Documentation (PY8) | Architecture: CS Drawings & Documentation (PY8) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2026-03-01 | 2026-04-23 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 32 | [6 empty] | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 4006.8336 | 0 | 0 | 0 | 0 | 0 | 0 | 4006.8336 | 0 | 4006.8336 | 4006.8336 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 4006.8336 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.4
516 | 1.2 | 1.2.4.2.1 | Not Started | PSL | PLC Motor Controllers and Readouts | Controls Hardware: PLC Motor Controllers and Readouts |  | 2.5% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-05-10 | 2022-09-29 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 5175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
516 | 1.2 | 1.2.4.2.1 | Not Started | PSL | PLC Motor Controllers and Readouts | Controls Hardware: PLC Motor Controllers and Readouts (Touch Screen) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-05-10 | 2022-09-29 | 53% | Off Ice | C2 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
518 | 1.2 | 1.2.4.2.1.1.1 | Not Started | PSL | PLC and Network Box for HPP Design & Build | Design, Build, & Test - PLC and Network Box for HPP Design & Build |  | 9.056% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2022-05-10 | 2022-07-20 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 18745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
518 | 1.2 | 1.2.4.2.1.1.1 | Not Started | PSL | PLC and Network Box for HPP Design & Build | Design, Build, & Test - PLC and Network Box for HPP Design & Build |  |  | CapEx | CapEx |  |  |  | VQ |  | 1 | 0% | 2022-05-10 | 2022-07-20 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
520 | 1.2 | 1.2.4.2.1.2 | Not Started | PSL | Design, Build & Test RWCR Control Box | Design, build and test RWCR control box |  | 5.833% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-07-01 | 2022-09-29 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 12075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
523 | 1.2 | 1.2.4.2.2.2 | Started | PSL | Specify, Procure and Test Water Tank Depth & Temp Sensor Box Testing | Specify, Procure and Test Water Tank Depth & Temp Sensor Box Testing |  | 5.111% | Labor Hours | Labor - Task | EN-ME |  |  | VQ | 115 | 115 | 0% | 2022-06-26 | 2022-08-19 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 10580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
523 | 1.2 | 1.2.4.2.2.2 | Started | PSL | Specify, Procure and Test Water Tank Depth & Temp Sensor Box Testing | Specify, Procure and Test Water Tank Depth & Temp Sensor Box Testing |  |  | CapEx | CapEx |  |  |  | VQ |  | 1 | 0% | 2022-06-26 | 2022-08-19 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
524 | 1.2 | 1.2.4.2.2.3 | Not Started | PSL | Specify System Sensors | Controls Hardware: Specify System Sensors |  | 2.222% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-05-28 | 2022-09-29 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
524 | 1.2 | 1.2.4.2.2.3 | Not Started | PSL | Specify System Sensors | Controls Hardware: Specify System Sensors |  | 2.222% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-05-28 | 2022-09-29 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
525 | 1.2 | 1.2.4.2.2.4 | Not Started | PSL | Procure System Sensors (PY4) | Controls Hardware: Procure System Sensors (PY4) |  |  | Labor Hours | Labor Hours | EN-EE |  |  | VQ |  | 115 | 0 | 2022-06-13 | 2022-08-05 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
525 | 1.2 | 1.2.4.2.2.4 | Not Started | PSL | Procure System Sensors (PY4) | Controls Hardware: Procure System Sensors (PY4) |  |  | CapEx | CapEx |  |  |  | VQ |  | 1 | 0% | 2022-06-13 | 2022-08-05 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
526 | 1.2 | 1.2.4.2.2.5 | Not Started | PSL | Procure System Sensors (PY5) | Controls Hardware: Procure System Sensors (PY5) |  |  | Labor Hours | Labor Hours | EN-EE |  |  | D - Expert Opinion |  | 115 | 0% | 2022-10-04 | 2022-10-17 | 0% | Off Ice | C3 | [5 empty] | 32 | [11 empty] | 32 | 0.21333 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 3759.12 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.4
526 | 1.2 | 1.2.4.2.2.5 | Not Started | PSL | Procure System Sensors (PY5) | Controls Hardware: Procure System Sensors (PY5) |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-10-04 | 2022-10-17 | 53% | Off Ice | C2 | [5 empty] | 27776 | [13 empty] | 28373.184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28373.184 | 0 | 28373.184 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28373.184 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
522 | 1.2 | 1.2.4.2.2.1 | Started | PSL | HPP Sensor Box Testing | HPP sensor box testing |  | 6.389% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2022-06-22 | 2022-09-13 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 13225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
528 | 1.2 | 1.2.4.2.3.1 | Started | PSL | Plan MHP Network Box Upgrade | Controls Hardware: Network Controllers (PSL_Software Engineer) |  | 2.222% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-04-15 | 2022-07-14 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
528 | 1.2 | 1.2.4.2.3.1 | Started | PSL | Plan MHP Network Box Upgrade | Plan MHP network box upgrade |  | 4.111% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2022-04-15 | 2022-07-14 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 8510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
529 | 1.2 | 1.2.4.2.3.2 | Not Started | PSL | Redesign, Build and Test Network Box for PHS | Redesign, build and test network box for PHS |  | 6.833% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2022-04-18 | 2022-07-18 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 14145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
530 | 1.2 | 1.2.4.2.4 | Started | PSL | Indoor Cables (sensor and network) | Network Controllers: Indoor Cables (sensor and network) (PSL_Software Engineer) |  | 3.333% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-02-09 | 2022-07-12 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
530 | 1.2 | 1.2.4.2.4 | Started | PSL | Indoor Cables (sensor and network) | Network Controllers: Indoor Cables (sensor and network) (PSL_Engineer) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-02-09 | 2022-07-12 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
530 | 1.2 | 1.2.4.2.4 | Started | PSL | Indoor Cables (sensor and network) | Network Controllers: Indoor Cables (sensor and network) |  |  | CapEx | CapEx |  |  |  | VQ |  | 1 | 0% | 2022-02-09 | 2022-07-12 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
531 | 1.2 | 1.2.4.2.5 | Started | PSL | Infrastructure Repair & Upgrade (w/sub-tasks) | Network Controllers: Infrastructure Repair & Upgrade (w/sub-tasks) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | C - Engineering Buildup | 115 | 115 | 0% | 2022-01-26 | 2022-09-30 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
532 | 1.2 | 1.2.4.2.6 | Not Started | PSL | Return Water Pump Noise Mitigation Subsys. Testing | Network Controllers: Return Water Pump Noise Mitigation Subsys testing |  | 8.667% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2022-04-01 | 2023-06-14 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 17940 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
533 | 1.2 | 1.2.4.2.7 | Started | PSL | TOS pendant I/O box Rebuild & Testing - (one finished, 7 remaining) | Network Controllers: TOS pendant I/O box rebuild and testing - (one finished, 7 remaining) |  | 11.11% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2022-04-01 | 2023-06-14 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 23000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
533 | 1.2 | 1.2.4.2.7 | Started | PSL | TOS pendant I/O box Rebuild & Testing - (one finished, 7 remaining) | Network Controllers: TOS pendant I/O box rebuild and testing - (one finished, 7 remaining) |  |  | CapEx | CapEx |  |  |  | VQ |  | 1 | 0% | 2022-04-01 | 2023-06-14 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
534 | 1.2 | 1.2.4.2.8 | Started | PSL | TOS and DCC PLC Box Design, Build, Test (three new boxes) | Network Controllers: TOS and DCC PLC box design, build, test (three new boxes) |  | 33.06% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2022-01-11 | 2022-09-30 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 68425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
534 | 1.2 | 1.2.4.2.8 | Started | PSL | TOS and DCC PLC Box Design, Build, Test (three new boxes) | Network Controllers: TOS and DCC PLC box design, build, test (three new boxes) |  |  | CapEx | CapEx |  |  |  | VQ |  | 1 | 0% | 2022-01-11 | 2022-09-30 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
535 | 1.2 | 1.2.4.2.9 | Started | PSL | Rodwell Control Interface Definition, - (New I/O box for this Unit) | Network Controllers: Rodwell control interface definition (new I/O box for this unit) |  | 10.83% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2021-11-01 | 2022-02-11 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 22425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
537 | 1.2 | 1.2.4.2.10.1 | Not Started | PSL | CS HW TestBed Ignition Server Testing | Network Controllers: CS HW TestBed Ignition Server Testing |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2022-02-28 | 2022-08-12 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
538 | 1.2 | 1.2.4.2.10.2 | Not Started | PSL | CS HW TestBed Database Server Testing | Network Controllers: CS HW TestBed Database Server Testing |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2022-02-28 | 2022-08-12 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
539 | 1.2 | 1.2.4.2.10.3 | Not Started | PSL | CS HW TestBed Peripherals Testing | Network Controllers: CS HW TestBed Peripherals Testing |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2022-02-28 | 2022-08-12 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
541 | 1.2 | 1.2.4.2.11.1 | Not Started | PSL | CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-02-01 | 2023-05-02 | 0% | Off Ice | C3 | [9 empty] | 2 | 4 | 4 | [5 empty] | 10 | 0.066667 | 0 | 0 | 0 | 0 | 234.945 | 469.89 | 469.89 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 0 | 1174.725 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1174.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1.2.4
541 | 1.2 | 1.2.4.2.11.1 | Not Started | PSL | CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-02-01 | 2023-05-02 | 53% | Off Ice | C2 | [9 empty] | 4671 | [9 empty] | 0 | 0 | 0 | 0 | 4771.4265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4771.4265 | 0 | 4771.4265 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4771.4265 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
542 | 1.2 | 1.2.4.2.11.2 | Not Started | PSL | CS HW Production Database Server (1x: DCC) | Network Controllers: CS HW Production Database Server (1x: DCC) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-02-01 | 2023-05-02 | 0% | Off Ice | C3 | [9 empty] | 2 | 4 | 4 | [5 empty] | 10 | 0.066667 | 0 | 0 | 0 | 0 | 234.945 | 469.89 | 469.89 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 0 | 1174.725 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1174.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1.2.4
542 | 1.2 | 1.2.4.2.11.2 | Not Started | PSL | CS HW Production Database Server (1x: DCC) | Network Controllers: CS HW Production Database Server (1x: DCC) |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-02-01 | 2023-05-02 | 53% | Off Ice | C2 | [9 empty] | 2906 | [9 empty] | 0 | 0 | 0 | 0 | 2968.479 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2968.479 | 0 | 2968.479 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2968.479 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
543 | 1.2 | 1.2.4.2.11.3 | Not Started | PSL | CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-03-01 | 2023-04-25 | 0% | Off Ice | C3 | [10 empty] | 16 | [6 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
543 | 1.2 | 1.2.4.2.11.3 | Not Started | PSL | CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-03-01 | 2023-04-25 | 53% | Off Ice | C2 | [10 empty] | 17520 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 17896.68 | 0 | 0 | 0 | 0 | 0 | 0 | 17896.68 | 0 | 17896.68 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17896.68 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
544 | 1.2 | 1.2.4.2.11.4 | Not Started | PSL | CS HW DCC Core Switch & Security Appliance | Network Controllers: CS HW DCC Core Switch & Security Appliance |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-03-15 | 2023-05-09 | 0% | Off Ice | C3 | [10 empty] | 8 | [6 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
544 | 1.2 | 1.2.4.2.11.4 | Not Started | PSL | CS HW DCC Core Switch & Security Appliance | Network Controllers: CS HW DCC Core Switch & Security Appliance |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-03-15 | 2023-05-09 | 53% | Off Ice | C2 | [10 empty] | 19803 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 20228.7645 | 0 | 0 | 0 | 0 | 0 | 0 | 20228.7645 | 0 | 20228.7645 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20228.7645 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
545 | 1.2 | 1.2.4.2.11.5 | Not Started | PSL | CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-04-03 | 2023-06-23 | 0% | Off Ice | C3 | [11 empty] | 16 | 10 | 10 |  |  |  | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1174.725 | 1174.725 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.4
545 | 1.2 | 1.2.4.2.11.5 | Not Started | PSL | CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-04-03 | 2023-06-23 | 53% | Off Ice | C2 | [11 empty] | 29867 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 30509.1405 | 0 | 0 | 0 | 0 | 0 | 30509.1405 | 0 | 30509.1405 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30509.1405 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
546 | 1.2 | 1.2.4.2.12 | Not Started | PSL | CS HW Build Mobile DCC | Network Controllers: CS HW Build Mobile DCC |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2022-04-01 | 2022-04-28 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
547 | 1.2 | 1.2.4.2.13 | Not Started | PSL | CS HW PY6 Resupply | Network Controllers: CS HW PY6 Resupply |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-03-03 | 2024-04-25 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
547 | 1.2 | 1.2.4.2.13 | Not Started | PSL | CS HW PY6 Resupply | Network Controllers: CS HW PY6 Resupply |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2024-03-03 | 2024-04-25 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2000 | 2000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 2086.9245 | 2086.9245 | 0 | 0 | 0 | 0 | 0 | 4173.849 | 0 | 4173.849 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4173.849 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
548 | 1.2 | 1.2.4.2.14 | Not Started | PSL | CS HW PY7 Resupply | Network Controllers: CS HW PY7 Resupply |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2025-03-03 | 2025-04-25 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 4903.1248 | 4903.1248 | 0 | 0 | 0 | 0 | 0 | 9806.2495 | 0 | 9806.2495 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.2495 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 9806.2495 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
548 | 1.2 | 1.2.4.2.14 | Not Started | PSL | CS HW PY7 Resupply | Network Controllers: CS HW PY7 Resupply |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2025-03-03 | 2025-04-25 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2000 | 2000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 2131.7934 | 2131.7934 | 0 | 0 | 0 | 0 | 0 | 4263.5868 | 0 | 4263.5868 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4263.5868 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
550 | 1.2 | 1.2.4.3.1 | Should have Started | PSL | Motor Controllers and Readouts | Controls Software: Motor Controllers and Readouts (PSL_Software Engineer) |  | 6.667% | Labor Hours | Labor - Task | EN-EE |  |  | C - Engineering Buildup | 115 | 115 | 0% | 2020-11-04 | 2022-09-30 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
550 | 1.2 | 1.2.4.3.1 | Should have Started | PSL | Motor Controllers and Readouts | Controls Software: Motor Controllers and Readouts |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2020-11-04 | 2022-09-30 | 53% | Off Ice | C3 | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
551 | 1.2 | 1.2.4.3.2 | Started | PSL | Data Acquisition | Controls Software: Data Acquisition (PSL_Software Engineer) |  | 2.222% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2021-10-01 | 2022-02-24 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
551 | 1.2 | 1.2.4.3.2 | Started | PSL | Data Acquisition | Controls Software: Data Acquisition |  |  | CapEx | CapEx |  |  |  | VQ |  | 1 | 0% | 2021-10-01 | 2022-02-24 | 53% | Off Ice |  | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
552 | 1.2 | 1.2.4.3.2.1 | Should have Started | PSL | DGH Programming, Testing and Cataloging | Controls Software: DGH programming, testing and cataloging |  | 4.5% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2021-12-08 | 2022-02-24 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
553 | 1.2 | 1.2.4.3.2.2 | Started | PSL | Payout Encoder Specify, Procure, and Test | Controls Software: Payout Encoder Specify, Procure, and Test |  | 3.889% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2021-10-01 | 2021-11-30 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 8050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
553 | 1.2 | 1.2.4.3.2.2 | Started | PSL | Payout Encoder Specify, Procure, and Test | Controls Software: Payout Encoder Specify, Procure, and Test |  |  | CapEx | CapEx |  |  |  | VQ |  | 1 | 0% | 2021-10-01 | 2021-11-30 | 53% | Off Ice |  | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
554 | 1.2 | 1.2.4.3.2.3 | Started | PSL | HPP Sensor DGH Box Testing | Controls Software: HPP Sensor DGH Box Testing |  | 6.833% | Labor Hours | Labor - Task | EN-EE |  |  | VQ | 115 | 115 | 0% | 2021-10-13 | 2021-11-23 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 14145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
556 | 1.2 | 1.2.4.3.3.1 | Started | PSL | Control System Software: System Operator Functions - PY4 software/hardware trials completed | Controls Software: System Operator Functions (PSL Software Engineer) |  | 13.33% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-05-01 | 2022-09-01 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
556 | 1.2 | 1.2.4.3.3.1 | Started | PSL | Control System Software: System Operator Functions - PY4 software/hardware trials completed | Controls Software: System Operator Functions |  |  | CapEx | CapEx |  |  |  | VQ |  | 1 | 0% | 2022-05-01 | 2022-09-01 | 53% | Off Ice |  | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
557 | 1.2 | 1.2.4.3.4 | Started | PSL | PLC & Software Development (w/sub-tasks) | Controls Software: PLC & Software Development (w/sub-tasks) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2021-04-22 | 2024-10-02 | 0% | Off Ice | C3 | TRUE |  |  |  |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 60 | 0.4 | 1174.725 | 0 | 1174.725 | 0 | 1174.725 | 0 | 1174.725 | 0 | 1174.725 | 0 | 1174.725 | 0 | 7048.35 | 0 | 7048.35 | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 60 | 0.4 | 1199.9816 | 0 | 1199.9816 | 0 | 1199.9816 | 0 | 1199.9816 | 0 | 1199.9816 | 0 | 1199.9816 | 0 | 7199.8895 | 0 | 7199.8895 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14248.2395 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 7048.35 | 7199.8895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.4
558 | 1.2 | 1.2.4.3.5 | Not Started | PSL | SCADA Monitoring Software and Server Procurement | Controls Software: SCADA Monitoring Software Procurement - Server |  | 1.111% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-04-01 | 2022-10-28 | 0% | Off Ice | C2 | TRUE |  |  |  |  | 20 | [11 empty] | 20 | 0.13333 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2300 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1.2.4
558 | 1.2 | 1.2.4.3.5 | Not Started | PSL | SCADA Monitoring Software and Server Procurement | Controls Software: SCADA Monitoring Software - Server |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-04-01 | 2022-10-28 | 53% | Off Ice | C2 | TRUE |  |  |  |  | 2297 | [13 empty] | 2346.3855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2346.3855 | 0 | 2346.3855 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2346.3855 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
558 | 1.2 | 1.2.4.3.5 | Not Started | PSL | SCADA Monitoring Software and Server Procurement | Controls Software: SCADA Monitoring Software Procurement Ignition 25K - PSL License - Off Project |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-04-01 | 2022-10-28 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
558 | 1.2 | 1.2.4.3.5 | Not Started | PSL | SCADA Monitoring Software and Server Procurement | Controls Software: SCADA Monitoring Software - Ignition 25K - PSL License - Off Project |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-04-01 | 2022-10-28 | 53% | Off Ice |  | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
559 | 1.2 | 1.2.4.3.6 | Not Started | PSL | SCADA Screen Development | Controls Software: SCADA Screen Development |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-10-31 | 2023-03-17 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
570 | 1.2 | 1.2.4.3.9.1.1 | Not Started | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen MHP: Local-Panel MDS-specific HMI (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-03 | 2023-04-14 | 0% | Off Ice | C3 | TRUE | [10 empty] | 20 | [5 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1.2.4
571 | 1.2 | 1.2.4.3.9.1.2 | Not Started | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen MHP: Local-Panel MDS-specific HMI (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-04-01 | 2024-04-12 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 20 | [5 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 0 | 2399.9632 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1.2.4
572 | 1.2 | 1.2.4.3.9.1.3 | Not Started | PSL | DCC-based SCADA UI (PY5) | Operator Screen MHP: DCC-based SCADA UI (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-17 | 2023-04-28 | 0% | Off Ice | C3 | TRUE | [10 empty] | 80 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
573 | 1.2 | 1.2.4.3.9.1.4 | Not Started | PSL | DCC-based SCADA UI (PY6) | Operator Screen MHP: DCC-based SCADA UI (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-04-15 | 2024-04-26 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 80 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
575 | 1.2 | 1.2.4.3.9.2.1 | Not Started | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen Fuel System: Local-Panel MDS-specific HMI (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-05-01 | 2023-05-12 | 0% | Off Ice | C3 | TRUE | [11 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
576 | 1.2 | 1.2.4.3.9.2.2 | Not Started | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen Fuel System: Local-Panel MDS-specific HMI (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-05-01 | 2024-05-14 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
577 | 1.2 | 1.2.4.3.9.2.3 | Not Started | PSL | DCC-based SCADA (PY5) | Operator Screen Fuel System: DCC-based SCADA (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-05-15 | 2023-05-26 | 0% | Off Ice | C3 | TRUE | [11 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
578 | 1.2 | 1.2.4.3.9.2.4 | Not Started | PSL | DCC-based SCADA (PY6) | Operator Screen Fuel System: DCC-based SCADA (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-05-15 | 2024-05-28 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
580 | 1.2 | 1.2.4.3.9.3.1 | Not Started | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen Gensets: Local-Panel MDS-specific HMI (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-06-01 | 2023-06-14 | 0% | Off Ice | C3 | TRUE | [12 empty] | 8 |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
581 | 1.2 | 1.2.4.3.9.3.2 | Not Started | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen Gensets: Local-Panel MDS-specific HMI (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-06-03 | 2024-06-14 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
582 | 1.2 | 1.2.4.3.9.3.3 | Not Started | PSL | DCC-based SCADA (PY5) | Operator Screen Gensets: DCC-based SCADA (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-06-15 | 2023-06-28 | 0% | Off Ice | C3 | TRUE | [12 empty] | 12 |  |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 0 | 0 | 0 | 1409.67 | 0 | 1409.67 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.4
583 | 1.2 | 1.2.4.3.9.3.4 | Not Started | PSL | DCC-based SCADA (PY6) | Operator Screen Gensets: DCC-based SCADA (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-06-17 | 2024-06-28 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 12 |  |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 0 | 0 | 0 | 1439.9779 | 0 | 1439.9779 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.4
585 | 1.2 | 1.2.4.3.9.4.1 | Not Started | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen Rodwell: Local-Panel MDS-specific HMI (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2023-07-03 | 2023-07-14 | 0% | Off Ice |  | TRUE | [13 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
586 | 1.2 | 1.2.4.3.9.4.2 | Not Started | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen Rodwell: Local-Panel MDS-specific HMI (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2024-07-01 | 2024-07-12 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
587 | 1.2 | 1.2.4.3.9.4.3 | Not Started | PSL | DCC-based SCADA (PY5) | Operator Screen Rodwell: DCC-based SCADA (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-07-17 | 2023-07-28 | 0% | Off Ice | C3 | TRUE | [13 empty] | 40 |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
588 | 1.2 | 1.2.4.3.9.4.4 | Not Started | PSL | DCC-based SCADA (PY6) | Operator Screen Rodwell: DCC-based SCADA (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-07-15 | 2024-07-26 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 40 |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
590 | 1.2 | 1.2.4.3.9.5.1 | Not Started | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen HPP: Local-Panel MDS-specific HMI (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-08-01 | 2023-08-14 | 0% | Off Ice | C3 | TRUE | [14 empty] | 18 |  | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2114.505 | 0 | 2114.505 | 0 | 2114.505 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2114.505 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2114.505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.4
591 | 1.2 | 1.2.4.3.9.5.2 | Not Started | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen HPP: Local-Panel MDS-specific HMI (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-08-01 | 2024-08-14 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 18 |  | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159.9669 | 0 | 2159.9669 | 0 | 2159.9669 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159.9669 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2159.9669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.4
592 | 1.2 | 1.2.4.3.9.5.3 | Not Started | PSL | DCC-based SCADA (PY5) | Operator Screen HPP: DCC-based SCADA (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-08-15 | 2023-08-28 | 0% | Off Ice | C3 | TRUE | [14 empty] | 40 |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
593 | 1.2 | 1.2.4.3.9.5.4 | Not Started | PSL | DCC-based SCADA (PY6) | Operator Screen HPP: DCC-based SCADA (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-08-15 | 2024-08-28 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 40 |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
595 | 1.2 | 1.2.4.3.9.6.1 | Not Started | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen PHS: Local-Panel MDS-specific HMI (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-09-01 | 2023-09-14 | 0% | Off Ice | C3 | TRUE | [15 empty] | 16 | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
596 | 1.2 | 1.2.4.3.9.6.2 | Not Started | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen PHS: Local-Panel MDS-specific HMI (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-09-02 | 2024-09-13 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 16 | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1919.9705 | 0 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
597 | 1.2 | 1.2.4.3.9.6.3 | Not Started | PSL | DCC-based SCADA (PY5) | Operator Screen PHS: DCC-based SCADA (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-09-15 | 2023-09-28 | 0% | Off Ice | C3 | TRUE | [15 empty] | 40 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
598 | 1.2 | 1.2.4.3.9.6.4 | Not Started | PSL | DCC-based SCADA (PY6) | Operator Screen PHS: DCC-based SCADA (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-09-16 | 2024-09-27 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 40 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
600 | 1.2 | 1.2.4.3.10.1 | Not Started | PSL | SCADA - DrillHead (PY5) | TOS Operator Screen: SCADA - DrillHead (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-05-01 | 2023-05-19 | 0% | Off Ice | C3 | TRUE | [11 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
601 | 1.2 | 1.2.4.3.10.2 | Not Started | PSL | SCADA - DrillHead (PY6) | TOS Operator Screen: SCADA - DrillHead (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-05-01 | 2024-05-21 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
602 | 1.2 | 1.2.4.3.10.3 | Not Started | PSL | SCADA - Drill_Settings (PY5) | TOS Operator Screen: SCADA - Drill_Settings (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-05-22 | 2023-06-09 | 0% | Off Ice | C3 | TRUE | [11 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
603 | 1.2 | 1.2.4.3.10.4 | Not Started | PSL | SCADA - Drill_Settings (PY6) | TOS Operator Screen: SCADA - Drill_Settings (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-05-22 | 2024-06-11 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
604 | 1.2 | 1.2.4.3.10.5 | Not Started | PSL | SCADA - Drilling_Drill Control (PY5) | TOS Operator Screen: SCADA - SCADA - Drilling_Drill Control (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-06-12 | 2023-06-30 | 0% | Off Ice | C3 | TRUE | [12 empty] | 12 |  |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 0 | 0 | 0 | 1409.67 | 0 | 1409.67 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.4
605 | 1.2 | 1.2.4.3.10.6 | Not Started | PSL | SCADA - Drilling_Drill Control (PY6) | TOS Operator Screen: SCADA - Drilling_Drill Control (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-06-12 | 2024-07-02 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 12 |  |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 0 | 0 | 0 | 1439.9779 | 0 | 1439.9779 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.4
606 | 1.2 | 1.2.4.3.10.7 | Not Started | PSL | SCADA - Drilling_Cable Level Wind (PY5) | TOS Operator Screen: SCADA - SCADA - Drilling_Cable Level Wind (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-07-03 | 2023-07-21 | 0% | Off Ice | C3 | TRUE | [13 empty] | 12 |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 0 | 0 | 1409.67 | 0 | 1409.67 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.4
607 | 1.2 | 1.2.4.3.10.8 | Not Started | PSL | SCADA - Drilling_Cable Level Wind (PY6) | TOS Operator Screen: SCADA - Drilling_Cable Level Wind (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-07-03 | 2024-07-23 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 12 |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 0 | 0 | 1439.9779 | 0 | 1439.9779 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.4
608 | 1.2 | 1.2.4.3.10.9 | Not Started | PSL | SCADA - Drilling_Hose Level Wind (PY5) | TOS Operator Screen: SCADA - Drilling_Hose Level Wind (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-07-24 | 2023-08-11 | 0% | Off Ice | C3 | TRUE | [13 empty] | 12 |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 0 | 0 | 1409.67 | 0 | 1409.67 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.4
609 | 1.2 | 1.2.4.3.10.10 | Not Started | PSL | SCADA - Drilling_Hose Level Wind (PY6) | TOS Operator Screen: SCADA - Drilling_Hose Level Wind (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-07-24 | 2024-08-13 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 12 |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 0 | 0 | 1439.9779 | 0 | 1439.9779 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.4
610 | 1.2 | 1.2.4.3.10.11 | Not Started | PSL | SCADA - Return Water Pump (PY5) | TOS Operator Screen: SCADA - Return Water Pump (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-08-14 | 2023-09-01 | 0% | Off Ice | C3 | TRUE | [14 empty] | 8 |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
611 | 1.2 | 1.2.4.3.10.12 | Not Started | PSL | SCADA - Return Water Pump (PY6) | TOS Operator Screen: SCADA - Return Water Pump (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-08-14 | 2024-09-03 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 8 |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | 0 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
612 | 1.2 | 1.2.4.3.10.13 | Not Started | PSL | SCADA - Deployment - Cable (PY5) | TOS Operator Screen: SCADA - Deployment - Cable (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-09-04 | 2023-09-22 | 0% | Off Ice | C3 | TRUE | [15 empty] | 8 | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
613 | 1.2 | 1.2.4.3.10.14 | Not Started | PSL | SCADA - Deployment - Cable (PY6) | TOS Operator Screen: SCADA - Deployment - Cable (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-09-04 | 2024-09-24 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 8 | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
614 | 1.2 | 1.2.4.3.10.15 | Not Started | PSL | SCADA - Deployment Settings (PY5) | TOS Operator Screen: SCADA - Deployment Settings (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-09-25 | 2023-10-13 | 0% | Off Ice | C3 | TRUE | [15 empty] | 10 | 10 | 0.066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 1174.725 | 0 | 1174.725 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1174.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1.2.4
615 | 1.2 | 1.2.4.3.10.16 | Not Started | PSL | SCADA - Deployment Settings (PY6) | TOS Operator Screen: SCADA - Deployment Settings (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-09-25 | 2024-10-15 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 10 | 10 | 0.066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1199.9816 | 0 | 1199.9816 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1199.9816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1.2.4
617 | 1.2 | 1.2.4.3.11.1 | Not Started | PSL | Build DCC dB schema (PY5) | TOS Operator Screen: Build DCC dB schema (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-04-05 | 2023-05-02 | 0% | Off Ice | C3 | TRUE | [10 empty] | 40 | 40 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 4698.9 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
618 | 1.2 | 1.2.4.3.11.2 | Not Started | PSL | Build DCC dB schema (PY6) | TOS Operator Screen: Build DCC dB schema (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-04-05 | 2024-05-02 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 80 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
619 | 1.2 | 1.2.4.3.11.3 | Not Started | PSL | Build Drill dB schema (PY5) | TOS Operator Screen: Build Drill dB schema (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-05-03 | 2023-05-30 | 0% | Off Ice | C3 | TRUE | [11 empty] | 40 |  |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
620 | 1.2 | 1.2.4.3.11.4 | Not Started | PSL | Build Drill dB schema (PY6) | TOS Operator Screen: Build Drill dB schema (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-05-03 | 2024-05-30 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 40 |  |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
621 | 1.2 | 1.2.4.3.11.5 | Not Started | PSL | Build Deploy dB schema (PY5) | TOS Operator Screen: Build Deploy dB schema (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-05-31 | 2023-06-27 | 0% | Off Ice | C3 | TRUE | [12 empty] | 30 |  |  |  | 30 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 0 | 0 | 0 | 3524.175 | 0 | 3524.175 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3524.175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1.2.4
622 | 1.2 | 1.2.4.3.11.6 | Not Started | PSL | Build Deploy dB schema (PY6) | TOS Operator Screen: Build Deploy dB schema (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-05-31 | 2024-06-27 | 0% | Off Ice | C3 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 30 |  |  |  | 30 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599.9448 | 0 | 0 | 0 | 3599.9448 | 0 | 3599.9448 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599.9448 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 3599.9448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1.2.4
623 | 1.2 | 1.2.4.3.12 | Not Started | PSL | CS SW Standup Production Computing Hardware, Configure, Verify before Shipment (3x systems) (PY6) | Controls Software: CS SW Standup Production Computing Hardware, Configure, Verify before Shipment (3x systems) (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-03-01 | 2024-07-18 | 0% | Off Ice | C4 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20 | 30 | 30 | 30 | 30 |  |  | 140 | 0.93333 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 3599.9448 | 3599.9448 | 3599.9448 | 3599.9448 | 0 | 0 | 16799.7422 | 0 | 16799.7422 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16799.7422 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 16799.7422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 1.2.4
624 | 1.2 | 1.2.4.3.13 | Not Started | PSL | CS SW MDS-specific HMI Refinement (PY7) | Controls Software: CS SW MDS-specific HMI Refinement (PY7) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2025-04-05 | 2025-07-24 | 0% | Off Ice | C4 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 20 | 20 | 20 | 20 |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 2451.5624 | 2451.5624 | 2451.5624 | 2451.5624 | 0 | 0 | 9806.2495 | 0 | 9806.2495 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.2495 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 9806.2495 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
625 | 1.2 | 1.2.4.3.14 | Not Started | PSL | CS SW DCC-based SCADA Refinement (PY7) | Controls Software: CS SW DCC-based SCADA Refinement (PY7) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2025-04-05 | 2025-07-24 | 0% | Off Ice | C4 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 30 | 30 | 30 | 30 |  |  | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3677.3436 | 3677.3436 | 3677.3436 | 3677.3436 | 0 | 0 | 14709.3743 | 0 | 14709.3743 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 14709.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.4
626 | 1.2 | 1.2.4.3.15 | Not Started | PSL | CS SW TOS-based SCADA Refinement (PY7) | Controls Software: CS SW TOS-based SCADA Refinement (PY7) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2025-04-05 | 2025-07-24 | 0% | Off Ice | C4 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 30 | 30 | 30 | 30 |  |  | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3677.3436 | 3677.3436 | 3677.3436 | 3677.3436 | 0 | 0 | 14709.3743 | 0 | 14709.3743 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 14709.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.4
627 | 1.2 | 1.2.4.3.16 | Not Started | PSL | CS SW dB Refinement (PY7) | Controls Software: CS SW dB Refinement (PY7) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2025-04-05 | 2025-07-24 | 0% | Off Ice | C4 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 30 | 30 | 30 | 30 |  |  | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3677.3436 | 3677.3436 | 3677.3436 | 3677.3436 | 0 | 0 | 14709.3743 | 0 | 14709.3743 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 14709.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.4
629 | 1.2 | 1.2.4.4.1 | Not Started | PSL | Requirements, Functional | Motor Drives: Functional Requirements (PSL_Engineer) |  | 13.33% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-04-14 | 2022-09-14 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 27600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
629 | 1.2 | 1.2.4.4.1 | Not Started | PSL | Requirements, Functional | Motor Drives: Functional Requirements (PSL_Software Engineer) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-04-14 | 2022-09-14 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
630 | 1.2 | 1.2.4.4.2 | Complete | PSL | Requirements, Electrical | Motor Drives: Electrical Requirements (PSL_Engineer) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-05-26 | 2022-11-09 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
630 | 1.2 | 1.2.4.4.2 | Complete | PSL | Requirements, Electrical | Motor Drives: Electrical Requirements (PSL_Software Engineer) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-05-26 | 2022-11-09 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
631 | 1.2 | 1.2.4.4.3 | Not Started | PSL | Specify and Procure | Motor Drives: Specify and Procure (PSL_Engineer) |  | 0.8889% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-08-05 | 2022-09-22 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
631 | 1.2 | 1.2.4.4.3 | Not Started | PSL | Specify and Procure | Motor Drives: Specify and Procure (PSL_Software Engineer) |  | 1.333% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-08-05 | 2022-09-22 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
631 | 1.2 | 1.2.4.4.3 | Not Started | PSL | Specify and Procure | Motor Drives: Specify and Procure |  |  | CapEx | CapEx |  |  |  | VQ |  | 1 | 0% | 2022-08-05 | 2022-09-22 | 53% | Off Ice |  | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
632 | 1.2 | 1.2.4.4.4 | Started | PSL | Programming and Testing at PSL | Motor Drives: Programming and Testing at PSL (PSL_Engineer) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-06-07 | 2025-06-04 | 0% | Off Ice | C3 | TRUE | [9 empty] | 35 | 35 |  | 35 |  | 30 |  | 135 | 0.9 | 0 | 0 | 0 | 0 | 0 | 4111.5375 | 4111.5375 | 0 | 4111.5375 | 0 | 3524.175 | 0 | 15858.7875 | 0 | 15858.7875 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15858.7875 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 15858.7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 1.2.4
632 | 1.2 | 1.2.4.4.4 | Started | PSL | Programming and Testing at PSL | Motor Drives: Programming and Testing at PSL (PSL_Software Engineer) |  | 3.611% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-06-07 | 2025-06-04 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 7475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
633 | 1.2 | 1.2.4.4.5 | Not Started | PSL | Plan Installations of New Motor Drives in Former Unico Locations | Motor Drives: Plan Installations of New Motor Drives in Former Unico Locations |  | 4.444% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-03-09 | 2022-05-10 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
635 | 1.2 | 1.2.4.5.1 | Complete | PSL | Evaluate EHWD system | E-Stop: Evaluate EHWD system (PSL_Engineer) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2021-01-29 | 2021-04-22 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
635 | 1.2 | 1.2.4.5.1 | Complete | PSL | Evaluate EHWD system | E-Stop: Evaluate EHWD system (PSL_Software Engineer) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2021-01-29 | 2021-04-22 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
636 | 1.2 | 1.2.4.5.2 | Started | PSL | Define Requirements | E-Stop: Define Requirements (PSL_Engineer) |  | 4.444% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2021-10-01 | 2022-01-19 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
637 | 1.2 | 1.2.4.5.3 | Started | PSL | TOS E-stop Box Analysis, Documentation Updates | E-Stop: TOS E-stop Box Analysis, Documentation Updates |  | 5.667% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2021-12-16 | 2022-03-24 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 11730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
638 | 1.2 | 1.2.4.5.4 | Started | PSL | System E-stop Controller Redesign, Build, Test | E-Stop: System E-stop Controller Redesign, Build, Test |  | 9.778% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2021-12-14 | 2022-04-18 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 20240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
639 | 1.2 | 1.2.4.5.5 | Started | PSL | TOS E-stop Controller Redesign, Build, Test | E-Stop: TOS E-stop Controller Redesign, Build, Test |  | 11.39% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2021-10-01 | 2022-02-21 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 23575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
640 | 1.2 | 1.2.4.5.6 | Not Started | PSL | E-Stop Resupply (PY6) | E-stop: Estop PY6 Resupply |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-05-01 | 2024-06-25 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 24 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
640 | 1.2 | 1.2.4.5.6 | Not Started | PSL | E-Stop Resupply (PY6) | E-stop: Estop PY6 Resupply |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2024-05-01 | 2024-06-25 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 24 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 0 | 0 | 0 | 0 | 1928.3182 | 0 | 1928.3182 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1928.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
640 | 1.2 | 1.2.4.5.6 | Not Started | PSL | E-Stop Resupply (PY6) | E-stop: Estop PY6 Resupply |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2024-05-01 | 2024-06-25 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 5000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 0 | 0 | 0 | 0 | 5217.3112 | 0 | 5217.3112 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
641 | 1.2 | 1.2.4.5.7 | Not Started | PSL | E-Stop Resupply (PY7) | E-stop: Estop PY7 Resupply |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2025-05-01 | 2025-06-25 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 24 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
641 | 1.2 | 1.2.4.5.7 | Not Started | PSL | E-Stop Resupply (PY7) | E-stop: Estop PY7 Resupply |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2025-05-01 | 2025-06-25 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 24 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1969.7771 | 0 | 0 | 0 | 0 | 1969.7771 | 0 | 1969.7771 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1969.7771 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 1969.7771 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
641 | 1.2 | 1.2.4.5.7 | Not Started | PSL | E-Stop Resupply (PY7) | E-stop: Estop PY7 Resupply |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2025-05-01 | 2025-06-25 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 5000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5329.4834 | 0 | 0 | 0 | 0 | 5329.4834 | 0 | 5329.4834 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5329.4834 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
643 | 1.2 | 1.2.4.6.1 | Started | PSL | Computing System | DCC: Computing System (PSL_Engineer) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2021-04-29 | 2023-07-27 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
643 | 1.2 | 1.2.4.6.1 | Started | PSL | Computing System | DCC: Computing System (PSL_Software Engineer) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2021-04-29 | 2023-07-27 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
643 | 1.2 | 1.2.4.6.1 | Started | PSL | Computing System | DCC: Computing System |  |  | CapEx | CapEx | EN-EE |  |  | VQ |  | 1 | 0% | 2021-04-29 | 2023-07-27 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
644 | 1.2 | 1.2.4.6.2 | Started | PSL | Electrical Improvements - Heater Upgrade Design and Procure | DCC: Electrical Improvements - Heater Upgrade Design and Procure |  | 1.111% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-08-15 | 2022-09-02 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
644 | 1.2 | 1.2.4.6.2 | Started | PSL | Electrical Improvements - Heater Upgrade Design and Procure | DCC: Electrical Improvements - Heater Upgrade Design and Procure |  |  | CapEx | CapEx |  |  |  | VQ |  | 1 | 0 | 2022-08-15 | 2022-09-02 | 53% | Off Ice |  | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
645 | 1.2 | 1.2.4.6.3 | Started | PSL | Update Workspace (desk, chairs), Procure Printer & Accessories | DCC: Update Workspace (desk, chairs), Procure Printer & Accessories |  |  | Labor Hours | Labor Hours | EN-EE |  |  | C - Engineering Buildup |  | 115 | 0 | 2023-02-01 | 2023-03-14 | 0% | Off Ice | C3 | TRUE | [8 empty] | 8 | 24 | [6 empty] | 32 | 0.21333 | 0 | 0 | 0 | 0 | 939.78 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 3759.12 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.4
645 | 1.2 | 1.2.4.6.3 | Started | PSL | Update Workspace (desk, chairs), Procure Printer & Accessories | DCC: Update Workspace (desk, chairs), Procure Printer & Accessories |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-02-01 | 2023-03-14 | 53% | Off Ice | C2 | TRUE | [8 empty] | 10770 | [9 empty] | 0 | 0 | 0 | 0 | 11001.555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11001.555 | 0 | 11001.555 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11001.555 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
647 | 1.2 | 1.2.4.7.1 | Should have Started | PSL | Evaluate/Inventory SES & SES to TOS Cables - Signal | Outdoor Cables: Evaluate/inventory SES & SES to TOS Cables - Signal |  | 2.222% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-01-15 | 2022-02-24 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
648 | 1.2 | 1.2.4.7.2 | Not Started | PSL | Design and Procure Replacement Components - Signal | Outdoor Cables: Design and Procure Replacement Components - Signal |  | 3.278% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0% | 2022-02-25 | 2022-03-29 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 6785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
648 | 1.2 | 1.2.4.7.2 | Not Started | PSL | Design and Procure Replacement Components - Signal | Outdoor Cables: Design and Procure Replacement Components - Signal |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2022-02-25 | 2022-03-29 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
649 | 1.2 | 1.2.4.7.3 | Not Started | PSL | Fabricate and Test SES & SES to TOS Cables - Signal | Outdoor Cables: Fabricate and Test SES & SES to TOS Cables - Signal |  | 4.444% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-05-27 | 2023-07-27 | 0% | Off Ice | C3 | TRUE | [10 empty] | 10 | 10 | 10 | 10 |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 1174.725 | 1174.725 | 1174.725 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9200 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
650 | 1.2 | 1.2.4.7.4 | Not Started | PSL | CS Cabling Resupply (PY6) | Outdoor Cables: CS Cabling Resupply (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-03-27 | 2024-04-09 | 0% | Off Ice | C4 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 12 | 12 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
650 | 1.2 | 1.2.4.7.4 | Not Started | PSL | CS Cabling Resupply (PY6) | Outdoor Cables: CS Cabling Resupply (PY6) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2024-03-27 | 2024-04-09 | 53% | Off Ice | C4 | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2500 | 2500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 2608.6556 | 2608.6556 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 0 | 5217.3112 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
651 | 1.2 | 1.2.4.7.5 | Not Started | PSL | CS Cabling Resupply (PY7) | Outdoor Cables: CS Cabling Resupply (PY7) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2025-03-27 | 2025-04-09 | 0% | Off Ice | C4 | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 12 | 12 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 1470.9374 | 1470.9374 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
651 | 1.2 | 1.2.4.7.5 | Not Started | PSL | CS Cabling Resupply (PY7) | Outdoor Cables: CS Cabling Resupply (PY7) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2025-03-27 | 2025-04-09 | 53% | Off Ice | C4 | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2500 | 2500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 2664.7417 | 2664.7417 | 0 | 0 | 0 | 0 | 0 | 5329.4834 | 0 | 5329.4834 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5329.4834 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
655 | 1.2 | 1.2.4.8.1.1.1 | Not Started | PSL | Program and catalog replacement flow and control DGH modules for all MHP heaters | CS: Program and catalog replacement flow and control DGH modules for all MHP heaters |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-05-02 | 2022-05-27 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
656 | 1.2 | 1.2.4.8.1.1.2 | Not Started | PSL | Procure and configure PLC-to-DGH gateways, develop instructions for field installation and test | CS: Procure and configure PLC-to-DGH gateways, develop instructions for field installation and test |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-05-30 | 2022-06-24 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
657 | 1.2 | 1.2.4.8.1.1.3 | Not Started | PSL | Select and procure backup power supplies for MHP network boxes | CS: Select and procure backup power supplies for MHP network boxes |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-06-27 | 2022-07-22 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
659 | 1.2 | 1.2.4.8.1.2.1 | Not Started | PSL | Procure sample temperature display and digital thermostat, install in test bed heater, test | CS: Procure sample temperature display and digital thermostat, install in test bed heater, test |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-10-03 | 2022-11-11 | 0% | Off Ice | C3 | [5 empty] | 8 | [11 empty] | 8 | 0.053333 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
659 | 1.2 | 1.2.4.8.1.2.1 | Not Started | PSL | Procure sample temperature display and digital thermostat, install in test bed heater, test | CS: Procure sample temperature display and digital thermostat, install in test bed heater, test |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-10-03 | 2022-11-11 | 53% | Off Ice | C2 | [5 empty] | 300 | [13 empty] | 306.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306.45 | 0 | 306.45 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
660 | 1.2 | 1.2.4.8.1.2.2 | Not Started | PSL | Select and procure temperature display units for heater controls, conversion hardware | CS: Select and procure temperature display units for heater controls, conversion hardware |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-11-14 | 2022-12-23 | 0% | Off Ice | C3 | [6 empty] | 8 | [10 empty] | 8 | 0.053333 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
660 | 1.2 | 1.2.4.8.1.2.2 | Not Started | PSL | Select and procure temperature display units for heater controls, conversion hardware | CS: Select and procure temperature display units for heater controls, conversion hardware |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-11-14 | 2022-12-23 | 53% | Off Ice | C2 | [6 empty] | 4500 | [12 empty] | 0 | 4596.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4596.75 | 0 | 4596.75 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4596.75 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
661 | 1.2 | 1.2.4.8.1.2.3 | Not Started | PSL | Replace temperature display units, remove RTD DGHs, transfer net connections, test | CS: Replace temperature display units, remove RTD DGHs, transfer net connections, test |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-12-26 | 2023-02-17 | 0% | Off Ice | C3 | [7 empty] | 24 | [9 empty] | 24 | 0.16 | 0 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
661 | 1.2 | 1.2.4.8.1.2.3 | Not Started | PSL | Replace temperature display units, remove RTD DGHs, transfer net connections, test | CS: Replace temperature display units, remove RTD DGHs, transfer net connections, test |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-12-26 | 2023-02-17 | 0% | Off Ice | C3 | [7 empty] | 100 | [9 empty] | 100 | 0.66667 | 0 | 0 | 7865.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7865.55 | 0 | 7865.55 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7865.55 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 7865.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 1.2.4
662 | 1.2 | 1.2.4.8.1.2.4 | Not Started | PSL | Select and procure digital thermostats for heater controls, conversion hardware | CS: Select and procure digital thermostats for heater controls, conversion hardware |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-02-20 | 2023-03-31 | 0% | Off Ice | C3 | [9 empty] | 8 | [7 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
662 | 1.2 | 1.2.4.8.1.2.4 | Not Started | PSL | Select and procure digital thermostats for heater controls, conversion hardware | CS: Select and procure digital thermostats for heater controls, conversion hardware |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-02-20 | 2023-03-31 | 53% | Off Ice | C2 | [9 empty] | 4962 | [9 empty] | 0 | 0 | 0 | 0 | 5068.683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5068.683 | 0 | 5068.683 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5068.683 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
663 | 1.2 | 1.2.4.8.1.2.5 | Not Started | PSL | Write thermostat field replacement procedure | CS: Write thermostat field replacement procedure |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-03 | 2023-04-14 | 0% | Off Ice | C3 | [11 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
665 | 1.2 | 1.2.4.8.1.3.1 | Not Started | PSL | Write rewiring and test instructions for MHP E-stop boxes (fixes switch contact selections made in Gen 1) | CS: Write rewiring and test instructions for MHP E-stop boxes (fixes switch contact selections made in Gen 1) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-11-01 | 2022-11-28 | 0% | Off Ice | C3 | [6 empty] | 24 | [10 empty] | 24 | 0.16 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
666 | 1.2 | 1.2.4.8.1.3.2 | Not Started | PSL | Write test procedures for dry heater tests | CS: Write test procedures for dry heater tests |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-11-29 | 2022-12-26 | 0% | Off Ice | C3 | [6 empty] | 16 | 16 | [9 empty] | 32 | 0.21333 | 0 | 1879.56 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 3759.12 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.4
667 | 1.2 | 1.2.4.8.1.3.3 | Not Started | PSL | Assemble equipment to test flow meters (excitation coil and portable pulse generator) | CS: Assemble equipment to test flow meters (excitation coil and portable pulse generator) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-12-27 | 2023-01-23 | 0% | Off Ice | C3 | [7 empty] | 12 | 12 | [8 empty] | 24 | 0.16 | 0 | 0 | 1409.67 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
667 | 1.2 | 1.2.4.8.1.3.3 | Not Started | PSL | Assemble equipment to test flow meters (excitation coil and portable pulse generator) | CS: Assemble equipment to test flow meters (excitation coil and portable pulse generator) |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-12-27 | 2023-01-23 | 53% | Off Ice | C3 | [7 empty] | 759 | [11 empty] | 0 | 0 | 775.3185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775.3185 | 0 | 775.3185 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775.3185 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
668 | 1.2 | 1.2.4.8.1.3.4 | Not Started | PSL | Write flow meter test procedure and assemble test kit | CS: Write flow meter test procedure and assemble test kit |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-24 | 2023-02-20 | 0% | Off Ice | C3 | [8 empty] | 12 | 12 | [7 empty] | 24 | 0.16 | 0 | 0 | 0 | 1409.67 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
671 | 1.2 | 1.2.4.8.1.5.1 | Not Started | PSL | Develop heater-based sensor readout; (heater temp/flow manifold pressures | CS: Develop heater-based sensor readout; (heater temp/flow manifold pressures |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-02 | 2023-01-20 | 0% | Off Ice | C3 | [8 empty] | 120 | [8 empty] | 120 | 0.8 | 0 | 0 | 0 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 0 | 14096.7 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.4
672 | 1.2 | 1.2.4.8.1.5.2 | Not Started | PSL | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | CS: Develop environmental sensor readout; (bldg temps, smoke, e-stop) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-23 | 2023-02-10 | 0% | Off Ice | C3 | [8 empty] | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.4
673 | 1.2 | 1.2.4.8.1.5.3 | Not Started | PSL | Develop heater control; (ON/OFF, Thermostat setpoint) | CS: Develop heater control; (ON/OFF, Thermostat setpoint) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-02-13 | 2023-03-03 | 0% | Off Ice | C3 | [9 empty] | 20 | 20 | [6 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
674 | 1.2 | 1.2.4.8.1.5.4 | Not Started | PSL | Configure network switch | CS: Configure network switch |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-07-13 | 2022-07-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
675 | 1.2 | 1.2.4.8.1.5.5 | Not Started | PSL | Configure RTA gateway to M-DGH interface | CS: Configure RTA gateway to M-DGH interface |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-07-27 | 2022-08-09 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
676 | 1.2 | 1.2.4.8.1.5.6 | Not Started | PSL | Configure M-DGHs | CS: Configure M-DGHs |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-08-10 | 2022-08-23 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
677 | 1.2 | 1.2.4.8.1.5.7 | Not Started | PSL | Implement interlocks | CS: Implement interlocks |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-03-06 | 2023-03-31 | 0% | Off Ice | C3 | [10 empty] | 20 | [6 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1.2.4
678 | 1.2 | 1.2.4.8.1.5.8 | Not Started | PSL | Document Subsystem | CS: Document Subsystem |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-03 | 2023-04-14 | 0% | Off Ice | C1 | [11 empty] | 20 | [5 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1.2.4
682 | 1.2 | 1.2.4.8.2.1.1 | Not Started | PSL | Procure motor drives (2 transfer pumps) | CS: Procure motor drives (2 transfer pumps) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-07-01 | 2022-08-25 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
683 | 1.2 | 1.2.4.8.2.1.2 | Not Started | PSL | Configure VFDs with accessories, connection pigtails, document | CS: Configure VFDs with accessories, connection pigtails, document |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-08-26 | 2022-10-06 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
684 | 1.2 | 1.2.4.8.2.1.3 | Not Started | PSL | Develop VFD installation strategy & document, procure materials | CS: Develop VFD installation strategy & document, procure materials |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-10-07 | 2022-10-20 | 0% | Off Ice | C3 | [5 empty] | 40 | [11 empty] | 40 | 0.26667 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
684 | 1.2 | 1.2.4.8.2.1.3 | Not Started | PSL | Develop VFD installation strategy & document, procure materials | CS: Develop VFD installation strategy & document, procure materials |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-10-07 | 2022-10-20 | 0% | Off Ice | C3 | [5 empty] | 16 | [11 empty] | 16 | 0.10667 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 1258.488 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
686 | 1.2 | 1.2.4.8.2.2.1 | Not Started | PSL | Select and procure E-stop relays | CS: Select and procure E-stop relays |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-06-01 | 2022-06-28 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
687 | 1.2 | 1.2.4.8.2.2.2 | Not Started | PSL | Develop and document E-stop box rewiring instructions | CS: Develop and document E-stop box rewiring instructions |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-06-29 | 2022-07-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
689 | 1.2 | 1.2.4.8.2.3.1 | Not Started | PSL | Select and procure PHS network switch, mount in protective enclosure | CS: Select and procure PHS network switch, mount in protective enclosure |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-09-01 | 2022-09-28 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
690 | 1.2 | 1.2.4.8.2.3.2 | Not Started | PSL | Select and procure new power supplies for the network box, procure one RS-485 gateway | CS: Select and procure new power supplies for the network box, procure one RS-485 gateway |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-09-29 | 2022-10-26 | 0% | Off Ice | C3 | [5 empty] | 16 | [11 empty] | 16 | 0.10667 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
690 | 1.2 | 1.2.4.8.2.3.2 | Not Started | PSL | Select and procure new power supplies for the network box, procure one RS-485 gateway | CS: Select and procure new power supplies for the network box, procure one RS-485 gateway |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-09-29 | 2022-10-26 | 53% | Off Ice | C2 | [5 empty] | 925 | [13 empty] | 944.8875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 944.8875 | 0 | 944.8875 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 944.8875 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
691 | 1.2 | 1.2.4.8.2.3.3 | Not Started | PSL | Redesign and rebuild PHS network box with new I/O, document as-built configuration | CS: Redesign and rebuild PHS network box with new I/O, document as-built configuration |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-10-27 | 2022-11-23 | 0% | Off Ice | C3 | [5 empty] | 44 | 100 | [10 empty] | 144 | 0.96 | 5168.79 | 11747.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16916.04 | 0 | 16916.04 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16916.04 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 16916.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 1.2.4
691 | 1.2 | 1.2.4.8.2.3.3 | Not Started | PSL | Redesign and rebuild PHS network box with new I/O, document as-built configuration | CS: Redesign and rebuild PHS network box with new I/O, document as-built configuration |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0 | 2022-10-27 | 2022-11-23 | 0% | Off Ice | C3 | [5 empty] | 20 | 20 | [10 empty] | 40 | 0.26667 | 1573.11 | 1573.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 3146.22 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
691 | 1.2 | 1.2.4.8.2.3.3 | Not Started | PSL | Redesign and rebuild PHS network box with new I/O, document as-built configuration | CS: Redesign and rebuild PHS network box with new I/O, document as-built configuration |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-10-27 | 2022-11-23 | 53% | Off Ice | C3 | [5 empty] | 3850 | [13 empty] | 3932.775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3932.775 | 0 | 3932.775 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3932.775 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
692 | 1.2 | 1.2.4.8.2.3.4 | Not Started | PSL | Indicate where approximately 20 sensor and network cables terminate in PHS and document config. plans | CS: Indicate where approximately 20 sensor and network cables terminate in PHS and document config. plans |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-11-24 | 2022-12-21 | 0% | Off Ice | C3 | [6 empty] | 50 | 58 | [9 empty] | 108 | 0.72 | 0 | 5873.625 | 6813.405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12687.03 | 0 | 12687.03 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12687.03 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 12687.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 1.2.4
693 | 1.2 | 1.2.4.8.2.3.5 | Not Started | PSL | Configure heater-mounted DGH modules, develop and document DGH installation and test plans | CS: Configure heater-mounted DGH modules, develop and document DGH installation and test plans |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-12-22 | 2023-01-18 | 0% | Off Ice | C3 | [7 empty] | 12 | 12 | [8 empty] | 24 | 0.16 | 0 | 0 | 1409.67 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
693 | 1.2 | 1.2.4.8.2.3.5 | Not Started | PSL | Configure heater-mounted DGH modules, develop and document DGH installation and test plans | CS: Configure heater-mounted DGH modules, develop and document DGH installation and test plans |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-12-22 | 2023-01-18 | 0% | Off Ice | C3 | [8 empty] | 16 | [8 empty] | 16 | 0.10667 | 0 | 0 | 0 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 1258.488 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
694 | 1.2 | 1.2.4.8.2.4 | Not Started | PSL | CS PHS HW4: New E-stop Slap Switch & Box for Outdoor Location | CS PHS HW4: New estop slap switch and box for outdoor location |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-19 | 2023-02-01 | 0% | Off Ice | C3 | [8 empty] | 8 | [8 empty] | 8 | 0.053333 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
694 | 1.2 | 1.2.4.8.2.4 | Not Started | PSL | CS PHS HW4: New E-stop Slap Switch & Box for Outdoor Location | CS PHS HW4: New estop slap switch and box for outdoor location |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-01-19 | 2023-02-01 | 53% | Off Ice | C3 | [8 empty] | 200 | [10 empty] | 0 | 0 | 0 | 204.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204.3 | 0 | 204.3 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204.3 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
695 | 1.2 | 1.2.4.8.2.5 | Not Started | PSL | CS PHS HW5: Develop heater test procedures, configure test tools, document test plans | CS PHS HW5: Develop heater test procedures, configure test tools, document test plans |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-02-02 | 2023-03-01 | 0% | Off Ice | C3 | [9 empty] | 18 | 18 | [6 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 2114.505 | 2114.505 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.4
697 | 1.2 | 1.2.4.8.2.6.1 | Not Started | PSL | Select and procure new tank level and temperature sensors | CS: Select and procure new tank level and temperature sensors |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-05-01 | 2022-05-12 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
698 | 1.2 | 1.2.4.8.2.6.2 | Not Started | PSL | Install one level sensors in the test bed and operate over some period | CS: Install one level sensors in the test bed and operate over some period |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-05-13 | 2022-07-07 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
699 | 1.2 | 1.2.4.8.2.6.3 | Not Started | PSL | Test level sensor tolerance of environmental conditions and system noise | CS: Test level sensor tolerance of environmental conditions and system noise |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-07-08 | 2022-07-21 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
700 | 1.2 | 1.2.4.8.2.6.4 | Not Started | PSL | Design and build cables for tank sensors | CS: Design and build cables for tank sensors |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-07-22 | 2022-09-01 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
702 | 1.2 | 1.2.4.8.2.7.1 | Not Started | PSL | Develop and document test plans for all PHS system components | CS: Develop and document test plans for all PHS system components |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-01 | 2023-05-25 | 0% | Off Ice | C3 | [11 empty] | 18 | 18 |  |  |  |  | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 2114.505 | 2114.505 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.4
703 | 1.2 | 1.2.4.8.2.7.2 | Not Started | PSL | Review Gen-1 docs, identify where sensor connections terminated, plan for reconnection and test | CS: Develop and document test plans for all PHS system components |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-05-26 | 2023-06-22 | 0% | Off Ice | C3 | [12 empty] | 18 | 18 |  |  |  | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2114.505 | 2114.505 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.4
705 | 1.2 | 1.2.4.8.2.8.1 | Not Started | PSL | Develop heater-based sensor readout; (heater temp/flow manifold pressures) | CS: Develop heater-based sensor readout; (heater temp/flow manifold pressures) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-02 | 2023-01-27 | 0% | Off Ice | C3 | [8 empty] | 24 | [8 empty] | 24 | 0.16 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
706 | 1.2 | 1.2.4.8.2.8.2 | Not Started | PSL | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | CS: Develop environmental sensor readout; (bldg temps, smoke, e-stop) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-30 | 2023-02-10 | 0% | Off Ice | C3 | [8 empty] | 16 | [8 empty] | 16 | 0.10667 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
707 | 1.2 | 1.2.4.8.2.8.3 | Not Started | PSL | Develop water tank sensors readout | CS: Develop water tank sensors readout |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-02-13 | 2023-03-03 | 0% | Off Ice | C3 | [9 empty] | 12 | 12 | [6 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 1409.67 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
708 | 1.2 | 1.2.4.8.2.8.4 | Not Started | PSL | Develop heater control; (ON/OFF, Thermostat setpoint) | CS: Develop heater control; (ON/OFF, Thermostat setpoint) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-03-06 | 2023-03-17 | 0% | Off Ice | C3 | [10 empty] | 16 | [6 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
709 | 1.2 | 1.2.4.8.2.8.5 | Not Started | PSL | Develop AB drive/pump control; (variable speed velocity drives) | CS: Develop AB drive/pump control; (variable speed velocity drives) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-03-20 | 2023-04-14 | 0% | Off Ice | C3 | [10 empty] | 20 | 20 | [5 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
710 | 1.2 | 1.2.4.8.2.8.6 | Not Started | PSL | Configure/document network switch | CS: Configure/document network switch |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-09-29 | 2022-10-12 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
711 | 1.2 | 1.2.4.8.2.8.7 | Not Started | PSL | Configure/document RTA gateway to M-DGH interface | CS: Configure/document RTA gateway to M-DGH interface |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-10-13 | 2022-10-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
712 | 1.2 | 1.2.4.8.2.8.8 | Not Started | PSL | Configure/document Point I/O Block | CS: Configure/document Point I/O Block |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-10-27 | 2022-11-09 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
713 | 1.2 | 1.2.4.8.2.8.9 | Not Started | PSL | Configure/document M-DGHs (Heater-mounted + all others) | CS: Configure/document M-DGHs (Heater-mounted + all others) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-11-10 | 2022-11-23 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
714 | 1.2 | 1.2.4.8.2.8.10 | Not Started | PSL | Implement interlocks | CS: Implement interlocks |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-17 | 2023-05-12 | 0% | Off Ice | C3 | [11 empty] | 20 | [5 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1.2.4
715 | 1.2 | 1.2.4.8.2.8.11 | Not Started | PSL | Document Subsystem | CS: Implement interlocks |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-05-15 | 2023-05-26 | 0% | Off Ice | C3 | [12 empty] | 40 |  |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
716 | 1.2 | 1.2.4.8.2.9 | Not Started | PSL | CS PHS HW ready to pack for shipment | CS PHS HW ready to pack for shipment |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-01-18 | 2023-01-18 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
719 | 1.2 | 1.2.4.8.3.1.1 | Not Started | PSL | Procure TOS motor drives (16 VFDs) and accessories | CS: Procure TOS motor drives (16 VFDs) and accessories |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-08-01 | 2022-08-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
720 | 1.2 | 1.2.4.8.3.1.2 | Not Started | PSL | (PY4) Configure VFDs with accessories, connection pigtails, document | CS: (PY4) Configure VFDs with accessories, connection pigtails, document |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-08-29 | 2022-10-07 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
721 | 1.2 | 1.2.4.8.3.1.3 | Not Started | PSL | Configure VFDs with accessories, connection pigtails, document | CS: Configure VFDs with accessories, connection pigtails, document |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-10-10 | 2022-12-02 | 0% | Off Ice | C3 | [5 empty] | 24 | [11 empty] | 24 | 0.16 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
721 | 1.2 | 1.2.4.8.3.1.3 | Not Started | PSL | Configure VFDs with accessories, connection pigtails, document | CS: Configure VFDs with accessories, connection pigtails, document |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-10-10 | 2022-12-02 | 0% | Off Ice | C3 | [5 empty] | 20 | 20 | [10 empty] | 40 | 0.26667 | 1573.11 | 1573.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 3146.22 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
721 | 1.2 | 1.2.4.8.3.1.3 | Not Started | PSL | Configure VFDs with accessories, connection pigtails, document | CS: Configure VFDs with accessories, connection pigtails, document |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-10-10 | 2022-12-02 | 53% | Off Ice | C3 | [5 empty] | 5000 | [13 empty] | 5107.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5107.5 | 0 | 5107.5 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5107.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
722 | 1.2 | 1.2.4.8.3.1.4 | Not Started | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-12-05 | 2022-12-30 | 0% | Off Ice | C3 | [7 empty] | 40 | [9 empty] | 40 | 0.26667 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
722 | 1.2 | 1.2.4.8.3.1.4 | Not Started | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-12-05 | 2022-12-30 | 0% | Off Ice | C3 | [7 empty] | 80 | [9 empty] | 80 | 0.53333 | 0 | 0 | 6292.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 0 | 6292.44 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 6292.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
722 | 1.2 | 1.2.4.8.3.1.4 | Not Started | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-12-05 | 2022-12-30 | 53% | Off Ice | C3 | [7 empty] | 2000 | [11 empty] | 0 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 2043 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
723 | 1.2 | 1.2.4.8.3.1.5 | Not Started | PSL | SW configuration and autotuning, make plan - MDCR/LW, DSHR/LW, RWHR, RWCR, Tower Hoist | CS: SW configuration and autotuning, make plan - MDCR/LW, DSHR/LW, RWHR, RWCR, Tower Hoist |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-02 | 2023-01-27 | 0% | Off Ice | C3 | [8 empty] | 80 | [8 empty] | 80 | 0.53333 | 0 | 0 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
725 | 1.2 | 1.2.4.8.3.2.1 | Not Started | PSL | Review Gen 1 documentation against as-built units located at PSL; mark up and update drawings | CS: Review Gen 1 documentation against as-built units located at PSL; mark up and update drawings |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-09-01 | 2022-09-14 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
726 | 1.2 | 1.2.4.8.3.2.2 | Not Started | PSL | Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement | CS: Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-09-15 | 2022-10-12 | 0% | Off Ice | C3 | [5 empty] | 120 | [11 empty] | 120 | 0.8 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 0 | 14096.7 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.4
726 | 1.2 | 1.2.4.8.3.2.2 | Not Started | PSL | Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement | CS: Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-09-15 | 2022-10-12 | 0% | Off Ice | C3 | [5 empty] | 40 | [11 empty] | 40 | 0.26667 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 3146.22 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
726 | 1.2 | 1.2.4.8.3.2.2 | Not Started | PSL | Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement | CS: Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-09-15 | 2022-10-12 | 53% | Off Ice | C3 | [5 empty] | 4000 | [13 empty] | 4086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4086 | 0 | 4086 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4086 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
727 | 1.2 | 1.2.4.8.3.2.3 | Not Started | PSL | Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives | CS: Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-10-13 | 2022-11-09 | 0% | Off Ice | C3 | [6 empty] | 200 | [10 empty] | 200 | 1.3333 | 0 | 23494.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23494.5 | 0 | 23494.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23494.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 23494.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 1.2.4
727 | 1.2 | 1.2.4.8.3.2.3 | Not Started | PSL | Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives | CS: Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2022-10-13 | 2022-11-09 | 0% | Off Ice | C3 | [6 empty] | 80 | [10 empty] | 80 | 0.53333 | 0 | 6292.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 0 | 6292.44 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 6292.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
727 | 1.2 | 1.2.4.8.3.2.3 | Not Started | PSL | Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives | CS: Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-10-13 | 2022-11-09 | 53% | Off Ice | C3 | [6 empty] | 250 | [12 empty] | 0 | 255.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.375 | 0 | 255.375 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.375 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
728 | 1.2 | 1.2.4.8.3.2.4 | Not Started | PSL | Develop and document E-stop switch re-wiring plans for TOS, procure spare slap switches | CS: Develop and document E-stop switch re-wiring plans for TOS, procure spare slap switches |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-11-10 | 2023-01-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
729 | 1.2 | 1.2.4.8.3.2.5 | Not Started | PSL | (PY4) Design new E-stop controllers for TOS, build and test boxes | CS: (PY4) Design new E-stop controllers for TOS, build and test boxes |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-01-05 | 2023-03-29 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
730 | 1.2 | 1.2.4.8.3.2.6 | Not Started | PSL | Design new E-stop controllers for TOS, build and test boxes | CS: Design new E-stop controllers for TOS, build and test boxes |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-03-30 | 2023-06-21 | 0% | Off Ice | C3 | [10 empty] | 30 | 30 | 30 | 30 |  |  |  | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 3524.175 | 3524.175 | 3524.175 | 0 | 0 | 0 | 14096.7 | 0 | 14096.7 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.4
730 | 1.2 | 1.2.4.8.3.2.6 | Not Started | PSL | Design new E-stop controllers for TOS, build and test boxes | CS: Design new E-stop controllers for TOS, build and test boxes |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2023-03-30 | 2023-06-21 | 0% | Off Ice | C3 | [10 empty] | 20 | 20 | 20 | 20 |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 1573.11 | 1573.11 | 1573.11 | 1573.11 | 0 | 0 | 0 | 6292.44 | 0 | 6292.44 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 6292.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
730 | 1.2 | 1.2.4.8.3.2.6 | Not Started | PSL | Design new E-stop controllers for TOS, build and test boxes | CS: Design new E-stop controllers for TOS, build and test boxes |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-03-30 | 2023-06-21 | 53% | Off Ice | C3 | [11 empty] | 1500 | 1500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1532.25 | 1532.25 | 0 | 0 | 0 | 0 | 3064.5 | 0 | 3064.5 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3064.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
732 | 1.2 | 1.2.4.8.3.3.1 | Not Started | PSL | Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes | CS: Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-12-01 | 2023-01-11 | 0% | Off Ice | C3 | [7 empty] | 24 | [9 empty] | 24 | 0.16 | 0 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
732 | 1.2 | 1.2.4.8.3.3.1 | Not Started | PSL | Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes | CS: Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-12-01 | 2023-01-11 | 53% | Off Ice | C2 | [7 empty] | 1650 | [11 empty] | 0 | 0 | 1685.475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685.475 | 0 | 1685.475 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1685.475 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
733 | 1.2 | 1.2.4.8.3.3.2 | Not Started | PSL | Document plans for TOS network box upgrades, specify and procure tools and materials | CS: Document plans for TOS network box upgrades, specify and procure tools and materials |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-12 | 2023-02-08 | 0% | Off Ice | C3 | [8 empty] | 12 | 12 | [7 empty] | 24 | 0.16 | 0 | 0 | 0 | 1409.67 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
733 | 1.2 | 1.2.4.8.3.3.2 | Not Started | PSL | Document plans for TOS network box upgrades, specify and procure tools and materials | CS: Document plans for TOS network box upgrades, specify and procure tools and materials |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2023-01-12 | 2023-02-08 | 0% | Off Ice | C3 | [9 empty] | 16 | [7 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 1258.488 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
733 | 1.2 | 1.2.4.8.3.3.2 | Not Started | PSL | Document plans for TOS network box upgrades, specify and procure tools and materials | CS: Document plans for TOS network box upgrades, specify and procure tools and materials |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-01-12 | 2023-02-08 | 53% | Off Ice | C3 | [9 empty] | 400 | [9 empty] | 0 | 0 | 0 | 0 | 408.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408.6 | 0 | 408.6 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408.6 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
734 | 1.2 | 1.2.4.8.3.3.3 | Not Started | PSL | Spec TOS network switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller | CS: Spec TOS nework switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-02-09 | 2023-03-22 | 0% | Off Ice | C3 | [9 empty] | 30 | 30 | [6 empty] | 60 | 0.4 | 0 | 0 | 0 | 0 | 3524.175 | 3524.175 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 0 | 7048.35 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1.2.4
734 | 1.2 | 1.2.4.8.3.3.3 | Not Started | PSL | Spec TOS network switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller | CS: Spec TOS nework switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2023-02-09 | 2023-03-22 | 0% | Off Ice | C3 | [9 empty] | 16 | 16 | [6 empty] | 32 | 0.21333 | 0 | 0 | 0 | 0 | 1258.488 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 2516.976 | 0 | 2516.976 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2516.976 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2516.976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.4
734 | 1.2 | 1.2.4.8.3.3.3 | Not Started | PSL | Spec TOS network switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller | CS: Spec TOS nework switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-02-09 | 2023-03-22 | 53% | Off Ice | C3 | [10 empty] | 1000 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 1021.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 0 | 1021.5 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
735 | 1.2 | 1.2.4.8.3.3.4 | Not Started | PSL | Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts | CS: Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-03-23 | 2023-05-17 | 0% | Off Ice | C3 | [10 empty] | 20 | 30 | 30 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 3524.175 | 3524.175 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
735 | 1.2 | 1.2.4.8.3.3.4 | Not Started | PSL | Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts | CS: Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-03-23 | 2023-05-17 | 53% | Off Ice | C3 | [11 empty] | 2000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 2043 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
736 | 1.2 | 1.2.4.8.3.3.5 | Not Started | PSL | Construct enclosures for TOS PLCs and attached I/O , test | CS: Construct enclosures for TOS PLCs and attached I/O , test |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-05-18 | 2023-07-12 | 0% | Off Ice | C3 | [12 empty] | 20 | 20 | 20 |  |  | 60 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 2349.45 | 0 | 0 | 7048.35 | 0 | 7048.35 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1.2.4
736 | 1.2 | 1.2.4.8.3.3.5 | Not Started | PSL | Construct enclosures for TOS PLCs and attached I/O , test | CS: Construct enclosures for TOS PLCs and attached I/O , test |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0 | 2023-05-18 | 2023-07-12 | 0% | Off Ice | C3 | [12 empty] | 20 | 32 | 20 |  |  | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1573.11 | 2516.976 | 1573.11 | 0 | 0 | 5663.196 | 0 | 5663.196 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5663.196 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 5663.196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.4
736 | 1.2 | 1.2.4.8.3.3.5 | Not Started | PSL | Construct enclosures for TOS PLCs and attached I/O , test | CS: Construct enclosures for TOS PLCs and attached I/O , test |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-05-18 | 2023-07-12 | 53% | Off Ice | C3 | [12 empty] | 200 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204.3 | 0 | 0 | 0 | 0 | 204.3 | 0 | 204.3 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204.3 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
738 | 1.2 | 1.2.4.8.3.4.1 | Not Started | PSL | Design I/O box upgrades using A-B Point I/O modules, install | CS: Design I/O box upgrades using A-B Point I/O modules, install |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-05-02 | 2022-08-19 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
739 | 1.2 | 1.2.4.8.3.4.2 | Not Started | PSL | Test I/O boxes with pendants and motor drives | CS: Test I/O boxes with pendants and motor drives |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-08-22 | 2022-10-14 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
740 | 1.2 | 1.2.4.8.3.4.3 | Not Started | PSL | Design and build cables for I/O box connections to motor drives and E-stop box | CS: Design and build cables for I/O box connections to motor drives and E-stop box |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-10-17 | 2022-12-09 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
741 | 1.2 | 1.2.4.8.3.4.4 | Not Started | PSL | Rebuild two portable I/O boxes, test (used to operate return water cable reel motor drives with pendant) | CS: Rebuild two portable I/O boxes, test (used to operate return water cable reel motor drives with pendant) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-12-12 | 2023-01-20 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
743 | 1.2 | 1.2.4.8.3.5.1 | Not Started | PSL | Develop and document on-ice test plans for E-stop, Reel-Stop, and Fault Detection hardware | CS: Develop and document on-ice test plans for E-stop, Reel-Stop, and Fault Detection hardware |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-02 | 2023-01-27 | 0% | Off Ice | C3 | [8 empty] | 40 | [8 empty] | 40 | 0.26667 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
744 | 1.2 | 1.2.4.8.3.5.2 | Not Started | PSL | Develop and document on-ice test plans for integrated hardware | CS: Develop and document on-ice test plans for integrated hardware |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-30 | 2023-02-24 | 0% | Off Ice | C3 | [8 empty] | 60 | 60 | [7 empty] | 120 | 0.8 | 0 | 0 | 0 | 7048.35 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 0 | 14096.7 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.4
746 | 1.2 | 1.2.4.8.3.6.1 | Should have Started | PSL | Review documentation, specify hose and cable payout encoders, specify load cells, procure | CS: Review documentation, specify hose and cable payout encoders, specify load cells, procure |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-01-03 | 2022-02-25 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
747 | 1.2 | 1.2.4.8.3.6.2 | Not Started | PSL | Test load cells and payout encoders with PLC, verify functionality required for payout control, load sharing | CS: Test load cells and payout encoders with PLC, verify functionality required for payout control, load sharing |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-11-07 | 2022-12-30 | 0% | Off Ice | C3 | [6 empty] | 100 | 100 | [9 empty] | 200 | 1.3333 | 0 | 11747.25 | 11747.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23494.5 | 0 | 23494.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23494.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 23494.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 1.2.4
748 | 1.2 | 1.2.4.8.3.7 | Not Started | PSL | CS TOS HW8: Line Filters for All Drives in TOS2, Identify and Procure | CS TOS HW8: Line filters for all drives in TOS2, identify and procure |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0 | 2023-01-02 | 2023-02-24 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
749 | 1.2 | 1.2.4.8.3.8 | Not Started | PSL | CS TOS HW9: Tower Hoist Reconnect Materials TOS2, Identify and Procure | CS TOS HW9: Tower hoist reconnect materials TOS2, identify and procure |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-02-27 | 2023-03-24 | 0% | Off Ice | C3 | [9 empty] | 20 | 20 | [6 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
749 | 1.2 | 1.2.4.8.3.8 | Not Started | PSL | CS TOS HW9: Tower Hoist Reconnect Materials TOS2, Identify and Procure | CS TOS HW9: Tower hoist reconnect materials TOS2, identify and procure |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2023-02-27 | 2023-03-24 | 53% | Off Ice | C3 | [9 empty] | 1000 | [9 empty] | 0 | 0 | 0 | 0 | 1021.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 0 | 1021.5 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
750 | 1.2 | 1.2.4.8.3.9 | Not Started | PSL | CS TOS HW10: Review deployment plans and HW, integrate with drill | CS TOS HW10: Review deployment plans and HW, integrate with drill |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-03-27 | 2023-06-02 | 0% | Off Ice | C3 | [10 empty] | 30 | 30 | 30 | 30 |  |  |  | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 3524.175 | 3524.175 | 3524.175 | 0 | 0 | 0 | 14096.7 | 0 | 14096.7 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.4
752 | 1.2 | 1.2.4.8.3.10.1 | Not Started | PSL | Develop general control/monitoring software | CS: Develop general control/monitoring software |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-02 | 2023-03-10 | 0% | Off Ice | C3 | [8 empty] | 40 | 40 | 40 | [6 empty] | 120 | 0.8 | 0 | 0 | 0 | 4698.9 | 4698.9 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 0 | 14096.7 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.4
753 | 1.2 | 1.2.4.8.3.10.2 | Not Started | PSL | Develop reel control software(MCR/LW, DSHR/LW, RWHR, RWCR, Tower Winch) | CS: Develop reel control software(MCR/LW, DSHR/LW, RWHR, RWCR, Tower Winch) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-03-13 | 2023-04-21 | 0% | Off Ice | C3 | [10 empty] | 40 | 40 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
754 | 1.2 | 1.2.4.8.3.10.3 | Not Started | PSL | Develop tension-sharing algorithm software (MCR/LW, DSHR/LW) | CS: Develop tension-sharing algorithm software (MCR/LW, DSHR/LW) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-24 | 2023-07-14 | 0% | Off Ice | C3 | [11 empty] | 30 | 30 | 30 | 30 |  |  | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 3524.175 | 3524.175 | 3524.175 | 0 | 0 | 14096.7 | 0 | 14096.7 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 1.2.4
755 | 1.2 | 1.2.4.8.3.10.4 | Not Started | PSL | Develop drillhead data monitoring interface) | CS: Develop drillhead data monitoring interface) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-07-17 | 2023-08-11 | 0% | Off Ice | C3 | [14 empty] | 24 |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
756 | 1.2 | 1.2.4.8.3.10.5 | Not Started | PSL | Configure/document network switch | CS: Configure/document network switch |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-02-09 | 2023-02-22 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
757 | 1.2 | 1.2.4.8.3.10.6 | Not Started | PSL | Configure RTA gateway to M-DGH interface | CS: Configure RTA gateway to M-DGH interface |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-02-23 | 2023-03-08 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
758 | 1.2 | 1.2.4.8.3.10.7 | Not Started | PSL | Configure M-DGHs | CS: Configure M-DGHs |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-03-09 | 2023-03-22 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
759 | 1.2 | 1.2.4.8.3.10.8 | Not Started | PSL | Implement interlocks | CS: Implement interlocks |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-08-14 | 2023-09-08 | 0% | Off Ice | C3 | [15 empty] | 20 | 20 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
760 | 1.2 | 1.2.4.8.3.10.9 | Not Started | PSL | Document Subsystem | CS: Document Subsystem |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-09-11 | 2023-09-22 | 0% | Off Ice | C3 | [16 empty] | 40 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
763 | 1.2 | 1.2.4.8.4.1 | Not Started | PSL | CS HW Drillhead sofware/hardware production version | CS HW Drillhead sofware/hardware production version |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-05-01 | 2023-06-23 | 0% | Off Ice | C3 | [12 empty] | 30 | 30 |  |  |  | 60 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 3524.175 | 0 | 0 | 0 | 7048.35 | 0 | 7048.35 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1.2.4
763 | 1.2 | 1.2.4.8.4.1 | Not Started | PSL | CS HW Drillhead sofware/hardware production version | CS HW Drillhead sofware/hardware production version |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-05-01 | 2023-06-23 | 53% | Off Ice | C2 | [12 empty] | 2510 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2563.965 | 0 | 0 | 0 | 0 | 2563.965 | 0 | 2563.965 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2563.965 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
765 | 1.2 | 1.2.4.8.4.2.1 | Not Started | PSL | Port C-Lang ingest process to rPI platform & test | CS: Port C-Lang ingest process to rPI platform & test |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-06-26 | 2023-08-04 | 0% | Off Ice | C3 | [13 empty] | 16 | 16 |  |  | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1879.56 | 0 | 0 | 3759.12 | 0 | 3759.12 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.4
766 | 1.2 | 1.2.4.8.4.2.2 | Not Started | PSL | Integrate rPI platform into PLC infrastructure | CS: Integrate rPI platform into PLC infrastructure |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-08-07 | 2023-09-15 | 0% | Off Ice | C3 | [15 empty] | 20 | 20 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
767 | 1.2 | 1.2.4.8.4.2.3 | Not Started | PSL | Document Subsystem | CS: Document Subsystem |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-09-18 | 2023-09-29 | 0% | Off Ice | C3 | [16 empty] | 40 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
770 | 1.2 | 1.2.4.8.5.1 | Not Started | PSL | Design, construct and test master E-stop controller, produce documentation and user instructions | CS: Design, construct and test master E-stop controller, produce documentation and user instructions |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-02 | 2023-04-21 | 0% | Off Ice | C3 | [8 empty] | 40 | 40 | 40 | 40 | [5 empty] | 160 | 1.0667 | 0 | 0 | 0 | 4698.9 | 4698.9 | 4698.9 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 18795.6 | 0 | 18795.6 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18795.6 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 18795.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 1.2.4
770 | 1.2 | 1.2.4.8.5.1 | Not Started | PSL | Design, construct and test master E-stop controller, produce documentation and user instructions | CS: Design, construct and test master E-stop controller, produce documentation and user instructions |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2023-01-02 | 2023-04-21 | 0% | Off Ice | C3 | [8 empty] | 10 | 10 | 10 | 10 | [5 empty] | 40 | 0.26667 | 0 | 0 | 0 | 786.555 | 786.555 | 786.555 | 786.555 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 3146.22 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
770 | 1.2 | 1.2.4.8.5.1 | Not Started | PSL | Design, construct and test master E-stop controller, produce documentation and user instructions | CS: Design, construct and test master E-stop controller, produce documentation and user instructions |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-01-02 | 2023-04-21 | 53% | Off Ice | C3 | [9 empty] | 1500 | 1500 | [8 empty] | 0 | 0 | 0 | 0 | 1532.25 | 1532.25 | 0 | 0 | 0 | 0 | 0 | 0 | 3064.5 | 0 | 3064.5 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3064.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
771 | 1.2 | 1.2.4.8.5.2 | Not Started | PSL | Design and construct general-purpose I/O box for fuel sled, gather required component stock to install | CS: Design and construct general-purpose I/O box for fuel sled, gather required component stock to install |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-24 | 2023-06-02 | 0% | Off Ice | C3 | [11 empty] | 20 | 40 | 20 |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 4698.9 | 2349.45 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
771 | 1.2 | 1.2.4.8.5.2 | Not Started | PSL | Design and construct general-purpose I/O box for fuel sled, gather required component stock to install | CS: Design and construct general-purpose I/O box for fuel sled, gather required component stock to install |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-04-24 | 2023-06-02 | 53% | Off Ice | C3 | [12 empty] | 3850 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3932.775 | 0 | 0 | 0 | 0 | 3932.775 | 0 | 3932.775 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3932.775 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
772 | 1.2 | 1.2.4.8.5.3 | Not Started | PSL | Procure 20 kW three-phase heater for DCC and 208V breakers | CS: Procure 20 kW three-phase heater for DCC and 208V breakers |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2023-06-05 | 2023-06-23 | 0% | Off Ice | C3 | [13 empty] | 16 |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 0 | 0 | 1258.488 | 0 | 1258.488 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
772 | 1.2 | 1.2.4.8.5.3 | Not Started | PSL | Procure 20 kW three-phase heater for DCC and 208V breakers | Procure 20 kW three-phase heater for DCC and 208V breakers |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-06-05 | 2023-06-23 | 53% | Off Ice | C2 | [13 empty] | 3152 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3219.768 | 0 | 0 | 0 | 3219.768 | 0 | 3219.768 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3219.768 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
773 | 1.2 | 1.2.4.8.5.4 | Not Started | PSL | WT1 VT pump drives: procure, configure, rewire plan | CS: WT1 VT pump drives: procure, configure, rewire plan |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-06-26 | 2023-08-18 | 0% | Off Ice | C3 | [13 empty] | 16 |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
773 | 1.2 | 1.2.4.8.5.4 | Not Started | PSL | WT1 VT pump drives: procure, configure, rewire plan | CS: WT1 VT pump drives: procure, configure, rewire plan |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-06-26 | 2023-08-18 | 53% | Off Ice | C2 | [13 empty] | 5083 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5192.2845 | 0 | 0 | 0 | 5192.2845 | 0 | 5192.2845 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5192.2845 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
774 | 1.2 | 1.2.4.8.5.5 | Not Started | PSL | WT1 VT pump drives: final configure | CS: WT1 VT pump drives: final configure |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-08-21 | 2023-09-01 | 0% | Off Ice | C3 | [15 empty] | 30 | 30 | 60 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 3524.175 | 7048.35 | 0 | 7048.35 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1.2.4
775 | 1.2 | 1.2.4.8.5.6 | Not Started | PSL | WT1 VT pump drives: install plan and kit | CS: WT1 VT pump drives: install plan and kit |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-09-04 | 2023-09-29 | 0% | Off Ice | C3 | [16 empty] | 60 | 60 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 7048.35 | 0 | 7048.35 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1.2.4
775 | 1.2 | 1.2.4.8.5.6 | Not Started | PSL | WT1 VT pump drives: install plan and kit | CS: WT1 VT pump drives: install plan and kit |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-09-04 | 2023-09-29 | 53% | Off Ice | C3 | [16 empty] | 1500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1532.25 | 1532.25 | 0 | 1532.25 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1532.25 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
777 | 1.2 | 1.2.4.8.5.7.1 | Not Started | PSL | Develop fuel system sensor readout ; (multi-level tank status, control relay status ) | CS: Develop fuel system sensor readout ; (multi-level tank status, control relay status ) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-06-01 | 2023-07-12 | 0% | Off Ice | C3 | [13 empty] | 18 | 18 |  |  | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2114.505 | 2114.505 | 0 | 0 | 4229.01 | 0 | 4229.01 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.4
778 | 1.2 | 1.2.4.8.5.7.2 | Not Started | PSL | Configure/document Point I/O Block | CS: Configure/document Point I/O Block |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-07-13 | 2023-08-09 | 0% | Off Ice | C3 | [14 empty] | 8 | 8 |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 939.78 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
779 | 1.2 | 1.2.4.8.5.7.3 | Not Started | PSL | Document Subsystem | CS: Document Subsystem |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-08-10 | 2023-08-23 | 0% | Off Ice | C3 | [15 empty] | 36 |  | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | 0 | 4229.01 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.4
780 | 1.2 | 1.2.4.8.5.7.4 | Not Started | PSL | Implement interlocks | CS: Implement interlocks |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-08-24 | 2023-09-20 | 0% | Off Ice | C3 | [15 empty] | 20 |  | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | 0 | 2349.45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1.2.4
783 | 1.2 | 1.2.4.8.6.1 | Not Started | PSL | CS Gensets HW - identify, procure, assemble | CS: CS Gensets HW - identify, procure, assemble |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-03-18 | 2024-05-24 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20 | 20 | [5 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
783 | 1.2 | 1.2.4.8.6.1 | Not Started | PSL | CS Gensets HW - identify, procure, assemble | CS: CS Gensets HW - identify, procure, assemble |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0 | 2024-03-18 | 2024-05-24 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20 | 20 | [5 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 1606.9319 | 1606.9319 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 0 | 3213.8637 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 3213.8637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
783 | 1.2 | 1.2.4.8.6.1 | Not Started | PSL | CS Gensets HW - identify, procure, assemble | CS: CS Gensets HW - identify, procure, assemble |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0 | 2024-03-18 | 2024-05-24 | 53% | Off Ice | C3 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 3850 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 4017.3297 | 0 | 0 | 0 | 0 | 0 | 0 | 4017.3297 | 0 | 4017.3297 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4017.3297 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
785 | 1.2 | 1.2.4.8.6.2.1 | Not Started | PSL | Develop sensor readout; (bldg temps, fuel temps, supply/return water temps) | CS: Develop sensor readout; (bldg temps, fuel temps, supply/return water temps) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-04-15 | 2024-05-10 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 20 | 20 |  |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
786 | 1.2 | 1.2.4.8.6.2.2 | Not Started | PSL | Develop sensor readout; (engine jacket temps, exhaust temps, drip pan status) | CS: Develop sensor readout; (engine jacket temps, exhaust temps, drip pan status) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-05-13 | 2024-06-07 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 20 | 20 |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
787 | 1.2 | 1.2.4.8.6.2.3 | Not Started | PSL | Configure/document network switch | CS: Configure/document network switch |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-06-10 | 2024-06-21 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
788 | 1.2 | 1.2.4.8.6.2.4 | Not Started | PSL | Configure/document RTA gateway to M-DGH interface | CS: Configure/document RTA gateway to M-DGH interface |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-06-24 | 2024-07-05 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 10 |  |  |  | 10 | 0.066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 0 | 0 | 0 | 1199.9816 | 0 | 1199.9816 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1199.9816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 1.2.4
789 | 1.2 | 1.2.4.8.6.2.5 | Not Started | PSL | Configure/document M-DGHs | CS: Configure/document M-DGHs |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-07-08 | 2024-07-19 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 20 |  |  | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 0 | 0 | 2399.9632 | 0 | 2399.9632 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1.2.4
790 | 1.2 | 1.2.4.8.6.2.6 | Not Started | PSL | Document Subsystem | CS: Document Subsystem |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-07-22 | 2024-08-02 | 0% | Off Ice | C3 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 20 | 20 |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
794 | 1.2 | 1.2.4.8.7.1.1 | Not Started | PSL | Procure HPP motor drives (four PF-755 50 hp vfds) (8 hours, task is finished) | CS: Procure HPP motor drives (four PF-755 50 hp vfds) (8 hours, task is finished) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-10-03 | 2022-11-25 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
795 | 1.2 | 1.2.4.8.7.1.2 | Not Started | PSL | Configure four HPP VFDs with accessories, connection pigtails, document | CS: Configure four HPP VFDs with accessories, connection pigtails, document |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-11-28 | 2022-12-23 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
796 | 1.2 | 1.2.4.8.7.1.3 | Not Started | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-12-26 | 2023-01-20 | 0% | Off Ice | C3 | [7 empty] | 36 | 36 | [8 empty] | 72 | 0.48 | 0 | 0 | 4229.01 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8458.02 | 0 | 8458.02 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8458.02 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 8458.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.4
796 | 1.2 | 1.2.4.8.7.1.3 | Not Started | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-12-26 | 2023-01-20 | 53% | Off Ice | C3 | [7 empty] | 1000 | [11 empty] | 0 | 0 | 1021.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 0 | 1021.5 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
797 | 1.2 | 1.2.4.8.7.1.4 | Not Started | PSL | SW configuration and autotuning | CS: SW configuration and autotuning |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-01-23 | 2023-02-17 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
799 | 1.2 | 1.2.4.8.7.2.1 | Not Started | PSL | Define requirements and procedures for reading signals applied to HPP motor drives | CS: Define requirements and procedures for reading signals applied to HPP motor drives |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-10-03 | 2022-10-28 | 0% | Off Ice | C3 | [5 empty] | 16 | [11 empty] | 16 | 0.10667 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
800 | 1.2 | 1.2.4.8.7.2.2 | Not Started | PSL | Define method of verifying sensor readout accuracy (reading vs stimulus) | CS: Define method of verifying sensor readout accuracy (reading vs stimulus) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-10-31 | 2022-11-25 | 0% | Off Ice | C3 | [6 empty] | 16 | [10 empty] | 16 | 0.10667 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
801 | 1.2 | 1.2.4.8.7.2.3 | Not Started | PSL | Develop and document test procedures for on-ice personnel | CS: Develop and document test procedures for on-ice personnel |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-11-28 | 2022-12-09 | 0% | Off Ice | C3 | [7 empty] | 16 | [9 empty] | 16 | 0.10667 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
803 | 1.2 | 1.2.4.8.7.3.1 | Not Started | PSL | Define core HPP PLC functions and requirements, define needed I/O connections | CS: Define core HPP PLC functions and requirements, define needed I/O connections |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-11-01 | 2022-12-12 | 0% | Off Ice | C3 | [6 empty] | 20 | 20 | [9 empty] | 40 | 0.26667 | 0 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
804 | 1.2 | 1.2.4.8.7.3.2 | Not Started | PSL | Select PLC, Enclosure, Power supplies, I/O expansion cards, power distribution, connectors and cables | CS: Select PLC, Enclosure, Power supplies, I/O expansion cards, power distribution, connectors and cables |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-12-13 | 2023-01-09 | 0% | Off Ice | C3 | [7 empty] | 20 | 20 | [8 empty] | 40 | 0.26667 | 0 | 0 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
805 | 1.2 | 1.2.4.8.7.3.3 | Not Started | PSL | Design and Construct PLC enclosure | CS: Design and Construct PLC enclosure |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-10 | 2023-03-06 | 0% | Off Ice | C3 | [8 empty] | 32 | [8 empty] | 32 | 0.21333 | 0 | 0 | 0 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 3759.12 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.4
805 | 1.2 | 1.2.4.8.7.3.3 | Not Started | PSL | Design and Construct PLC enclosure | CS: Design and Construct PLC enclosure |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2023-01-10 | 2023-03-06 | 0% | Off Ice | C3 | [8 empty] | 20 | 20 | [7 empty] | 40 | 0.26667 | 0 | 0 | 0 | 1573.11 | 1573.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 3146.22 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
805 | 1.2 | 1.2.4.8.7.3.3 | Not Started | PSL | Design and Construct PLC enclosure | CS: Design and Construct PLC enclosure |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-01-10 | 2023-03-06 | 53% | Off Ice | C3 | [9 empty] | 7050 | [9 empty] | 0 | 0 | 0 | 0 | 7201.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7201.575 | 0 | 7201.575 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7201.575 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
806 | 1.2 | 1.2.4.8.7.3.4 | Not Started | PSL | Test HPP PLC enclosure with HPP Network box | CS: Test HPP PLC enclosure with HPP Network box |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-03-07 | 2023-05-01 | 0% | Off Ice | C3 | [10 empty] | 24 | [6 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
807 | 1.2 | 1.2.4.8.7.4 | Not Started | PSL | CS HPP HW4: Charge Pump Motor Controllers | CS HPP HW4: Charge pump motor controllers |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-12-01 | 2023-05-03 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
808 | 1.2 | 1.2.4.8.7.4.1 | Not Started | PSL | Install PF-70 motor drive in test bed, configure with local control system, test | CS: Install PF-70 motor drive in test bed, configure with local control system, test |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-12-01 | 2023-01-25 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
809 | 1.2 | 1.2.4.8.7.4.2 | Not Started | PSL | Procure additional drives for charge pumps (4), AC and network pigtail materials | CS: Procure additional drives for charge pumps (4), AC and network pigtail materials |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-26 | 2023-04-05 | 0% | Off Ice | C3 | [8 empty] | 16 | [8 empty] | 16 | 0.10667 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
809 | 1.2 | 1.2.4.8.7.4.2 | Not Started | PSL | Procure additional drives for charge pumps (4), AC and network pigtail materials | CS: Procure additional drives for charge pumps (4), AC and network pigtail materials |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-01-26 | 2023-04-05 | 53% | Off Ice | C2 | [8 empty] | 14505 | [10 empty] | 0 | 0 | 0 | 14816.8575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14816.8575 | 0 | 14816.8575 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14816.8575 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
810 | 1.2 | 1.2.4.8.7.4.3 | Not Started | PSL | Connectorize four drives with power and network pigtails, test each in test bed | CS: Connectorize four drives with power and network pigtails, test each in test bed |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-06 | 2023-05-03 | 0% | Off Ice | C3 | [11 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.4
810 | 1.2 | 1.2.4.8.7.4.3 | Not Started | PSL | Connectorize four drives with power and network pigtails, test each in test bed | CS: Connectorize four drives with power and network pigtails, test each in test bed |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2023-04-06 | 2023-05-03 | 0% | Off Ice | C3 | [11 empty] | 20 | 20 |  |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 1573.11 | 1573.11 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 3146.22 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
810 | 1.2 | 1.2.4.8.7.4.3 | Not Started | PSL | Connectorize four drives with power and network pigtails, test each in test bed | CS: Connectorize four drives with power and network pigtails, test each in test bed |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-04-06 | 2023-05-03 | 53% | Off Ice | C3 | [11 empty] | 1000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 0 | 1021.5 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
811 | 1.2 | 1.2.4.8.7.5 | Not Started | PSL | CS HPP HW5: Sensor Box Reconfig & Test | CS HPP HW5: Sensor box reconfig and test |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-01-02 | 2023-04-21 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
812 | 1.2 | 1.2.4.8.7.5.1 | Not Started | PSL | Build and test a portable network box for sensor box testing (Gateway, power supply, connectors) | CS: Build and test a portable network box for sensor box testing (Gateway, power supply, connectors) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-01-02 | 2023-02-24 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
813 | 1.2 | 1.2.4.8.7.5.2 | Not Started | PSL | Procure and configure test equipment needed to calibrate individual sensors, provide user instructions | CS: Procure and configure test equipment needed to calibrate individual sensors, provide user instructions |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-02-27 | 2023-03-24 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
814 | 1.2 | 1.2.4.8.7.5.3 | Not Started | PSL | Connect HPP sensor readout box with sensor box, connect to network box, test all sensors and document | CS: Connect HPP sensor readout box with sensor box, connect to network box, test all sensors and document |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-03-27 | 2023-04-21 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
815 | 1.2 | 1.2.4.8.7.6 | Not Started | PSL | CS HPP HW6: Sensor Box DGH Reconfig & Test | CS HPP HW6: Sensor box DGH reconfig and test |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-02-01 | 2023-03-28 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
816 | 1.2 | 1.2.4.8.7.7 | Not Started | PSL | CS HPP HW7: Estop box Re-outfitting | CS HPP HW7: Estop box re-outfitting |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-04-03 | 2023-06-09 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
817 | 1.2 | 1.2.4.8.7.7.1 | Not Started | PSL | Select and procure E-stop relays for pump VFD Enable signals | CS: Select and procure E-stop relays for pump VFD Enable signals |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-03 | 2023-04-28 | 0% | Off Ice | C3 | [11 empty] | 8 | [5 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
817 | 1.2 | 1.2.4.8.7.7.1 | Not Started | PSL | Select and procure E-stop relays for pump VFD Enable signals | CS: Select and procure E-stop relays for pump VFD Enable signals |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-04-03 | 2023-04-28 | 53% | Off Ice | C3 | [11 empty] | 200 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 204.3 | 0 | 0 | 0 | 0 | 0 | 204.3 | 0 | 204.3 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 204.3 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.4
818 | 1.2 | 1.2.4.8.7.7.2 | Not Started | PSL | Develop and document rewiring instructions for HPP E-stop box | CS: Develop and document rewiring instructions for HPP E-stop box |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-05-01 | 2023-06-09 | 0% | Off Ice | C3 | [12 empty] | 16 |  |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
819 | 1.2 | 1.2.4.8.7.8 | Not Started | PSL | CS HPP HW8: Network Box Refurb & Config | CS HPP HW8: Network box refurb and config |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-12-01 | 2023-05-31 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
820 | 1.2 | 1.2.4.8.7.8.1 | Not Started | PSL | Select and procure a wall-mount managed Ethernet switch for the HPP electrical closet | CS: Select and procure a wall-mount managed Ethernet switch for the HPP electrical closet |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-12-01 | 2022-12-28 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
821 | 1.2 | 1.2.4.8.7.8.2 | Not Started | PSL | Select and procure new power supplies for the network box, procure one RS-485 gateway | CS: Select and procure new power supplies for the network box, procure one RS-485 gateway |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-12-29 | 2023-01-25 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
822 | 1.2 | 1.2.4.8.7.8.3 | Not Started | PSL | Refurbish the HPP network box, document as-built configureation | CS: Refurbish the HPP network box, document as-built configureation |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-01-26 | 2023-04-19 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
823 | 1.2 | 1.2.4.8.7.8.4 | Not Started | PSL | Select and procure HPP network switch enclosure, integrate with switch | CS: Select and procure HPP network switch enclosure, integrate with switch |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-04-20 | 2023-05-31 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
824 | 1.2 | 1.2.4.8.7.9 | Not Started | PSL | CS HPP HW9-10: Maintain Documentation, Prepare Field Plans | CS HPP HW9-10: Maintain documentation, prepare field plans |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-06-01 | 2023-07-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
825 | 1.2 | 1.2.4.8.7.9.1 | Not Started | PSL | Develop and document test plans for all HPP system components | CS: Develop and document test plans for all HPP system components |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-06-01 | 2023-06-28 | 0% | Off Ice | C3 | [13 empty] | 36 |  |  |  | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.4
826 | 1.2 | 1.2.4.8.7.9.2 | Not Started | PSL | Review Gen-1 docs, identify where sensor connections terminated, plan for field integration and test | CS: Review Gen-1 docs, identify where sensor connections terminated, plan for field integration and test |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-06-29 | 2023-07-26 | 0% | Off Ice | C3 | [13 empty] | 32 |  |  |  | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 0 | 0 | 3759.12 | 0 | 3759.12 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.4
828 | 1.2 | 1.2.4.8.7.10.1 | Not Started | PSL | Develop water path sensor readout; (pressure, temp, flow) | CS: Develop water path sensor readout; (pressure, temp, flow) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-02 | 2023-01-27 | 0% | Off Ice | C3 | [8 empty] | 40 | [8 empty] | 40 | 0.26667 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
829 | 1.2 | 1.2.4.8.7.10.2 | Not Started | PSL | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | CS: Develop environmental sensor readout; (bldg temps, smoke, e-stop) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-30 | 2023-02-10 | 0% | Off Ice | C3 | [8 empty] | 40 | [8 empty] | 40 | 0.26667 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
830 | 1.2 | 1.2.4.8.7.10.3 | Not Started | PSL | Build shared data-tagging w/ DCC core controller | CS: Build shared data-tagging w/ DCC core controller |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-02-13 | 2023-03-10 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
831 | 1.2 | 1.2.4.8.7.10.4 | Not Started | PSL | Develop AB drive/pump control; (variable speed velocity drives) | CS: Develop AB drive/pump control; (variable speed velocity drives) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-03-13 | 2023-04-07 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
832 | 1.2 | 1.2.4.8.7.10.5 | Not Started | PSL | Develop charge pump control; (variable speed velocity drives OR Soft Starter) | CS: Develop charge pump control; (variable speed velocity drives OR Soft Starter) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-04-10 | 2023-04-21 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
833 | 1.2 | 1.2.4.8.7.10.6 | Not Started | PSL | Configure/document network switch | CS: Configure/document network switch |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-04-24 | 2023-05-05 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
834 | 1.2 | 1.2.4.8.7.10.7 | Not Started | PSL | Configure/document RTA gateway to M-DGH interface | CS: Configure/document RTA gateway to M-DGH interface |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-05-08 | 2023-05-19 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
835 | 1.2 | 1.2.4.8.7.10.8 | Not Started | PSL | Configure/document M-DGHs | CS: Configure/document M-DGHs |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-05-22 | 2023-06-02 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
836 | 1.2 | 1.2.4.8.7.10.9 | Not Started | PSL | Implement interlocks | CS: Implement interlocks |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-06-05 | 2023-06-16 | 0% | Off Ice | C3 | [13 empty] | 20 |  |  |  | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1.2.4
837 | 1.2 | 1.2.4.8.7.10.10 | Not Started | PSL | Document Subsystem | CS: Document Subsystem |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-06-19 | 2023-06-30 | 0% | Off Ice | C3 | [13 empty] | 40 |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
838 | 1.2 | 1.2.4.8.7.11 | Not Started | PSL | CS HPP HW Ready to Pack for Shipment | CS HPP HW ready to pack for shipment |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2023-07-26 | 2023-07-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
841 | 1.2 | 1.2.4.8.8.1.1 | Not Started | PSL | CS ARA HW: new system controls and tie-in design | CS ARA HW: new system controls and tie-in |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-05-02 | 2022-06-24 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
842 | 1.2 | 1.2.4.8.8.1.2 | Not Started | PSL | Review ARA drill system documentation and develop a new configuration for Rodewell | CS: Review ARA drill system documentation and develop a new configuration for Rodewell |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-06-27 | 2022-07-22 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
843 | 1.2 | 1.2.4.8.8.1.3 | Not Started | PSL | Select and procure new motor drives for Rodwell pump and combo-cable winch | CS: Select and procure new motor drives for rodwell pump and combo-cable winch |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-07-25 | 2022-09-02 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
844 | 1.2 | 1.2.4.8.8.1.4 | Not Started | PSL | Procure gateway for monitoring control pane instruments, plan for installation in the control box | CS: Procure gateway for monitoring control pane intruments, plan for installation in the control box |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-09-05 | 2022-09-16 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
845 | 1.2 | 1.2.4.8.8.1.5 | Not Started | PSL | Select and procure new hardware to capture flow sensor pulse rates (A-B I/O hardware) | CS: Select and procure new hardware to capture flow sensor pulse rates (A-B I/O hardware) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-09-19 | 2022-10-14 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
846 | 1.2 | 1.2.4.8.8.1.6 | Not Started | PSL | Design and Build network cable, E-stop cable, for connecting rodwell system to drill system | CS: Design and Build network cable, E-stop cable, for connecting rodwell system to drill system |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-10-17 | 2022-11-11 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
848 | 1.2 | 1.2.4.8.8.2.1 | Not Started | PSL | Develop ARA-drill sensor readout; (heater flows, head press, tank level) | CS: Develop ARA-drill sensor readout; (heater flows, head press, tank level) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-11-01 | 2022-11-28 | 0% | Off Ice | C3 | [6 empty] | 80 | [10 empty] | 80 | 0.53333 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.4
849 | 1.2 | 1.2.4.8.8.2.2 | Not Started | PSL | Develop AB drive/pump control; (variable speed velocity drives) | CS: Develop AB drive/pump control; (variable speed velocity drives) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-11-29 | 2023-01-09 | 0% | Off Ice | C3 | [7 empty] | 20 | 20 | [8 empty] | 40 | 0.26667 | 0 | 0 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
850 | 1.2 | 1.2.4.8.8.2.3 | Not Started | PSL | Configure/document Point I/O Block | CS: Configure/document Point I/O Block |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-01-10 | 2023-02-06 | 0% | Off Ice | C3 | [8 empty] | 16 | [8 empty] | 16 | 0.10667 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
851 | 1.2 | 1.2.4.8.8.2.4 | Not Started | PSL | Configure/document network switch | CS: Configure/document network switch |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-02-07 | 2023-02-20 | 0% | Off Ice | C3 | [9 empty] | 8 | [7 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.4
852 | 1.2 | 1.2.4.8.8.2.5 | Not Started | PSL | Configure/document RTA gateway to M-DGH interface | CS: Configure/document RTA gateway to M-DGH interface |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-02-21 | 2023-03-06 | 0% | Off Ice | C3 | [9 empty] | 16 | [7 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.4
853 | 1.2 | 1.2.4.8.8.2.6 | Not Started | PSL | Configure/document M-DGHs | CS: Configure/document M-DGHs |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-03-07 | 2023-03-20 | 0% | Off Ice | C3 | [10 empty] | 20 | [6 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1.2.4
854 | 1.2 | 1.2.4.8.8.2.7 | Not Started | PSL | Implement interlocks | CS: Implement interlocks |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-03-21 | 2023-04-03 | 0% | Off Ice | C3 | [10 empty] | 20 | [6 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1.2.4
855 | 1.2 | 1.2.4.8.8.2.8 | Not Started | PSL | Document Subsystem | CS: Document Subsystem |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-04 | 2023-04-17 | 0% | Off Ice | C3 | [11 empty] | 40 | [5 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.4
868 | 1.2 | 1.2.5.2.2 | Not Started | PSL | GEN-2 - Develop SOW for Gen 2 Repairs Subcontract in New Zealand & Communicate with Vendor | GEN-2, 3, PDM - GEN-2 - Develop SOW for Gen 2 Repairs Subcontract in New Zealand & Communicate with Vendor | Birrittella | 2.222% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-03-01 | 2022-04-25 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
872 | 1.2 | 1.2.5.2.6 | Not Started | PSL | GEN-1, 2, 3 - Procure Batteries | GEN-2, 3, PDM - Procure Batteries |  |  | Labor Hours | Labor Hours | EN-ME |  |  | D - Expert Opinion |  | 115 | 0 | 2022-10-01 | 2022-10-06 | 0% | Off Ice | C2 | [5 empty] | 8 | [11 empty] | 8 | 0.053333 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.5
872 | 1.2 | 1.2.5.2.6 | Not Started | PSL | GEN-1, 2, 3 - Procure Batteries | GEN-2, 3, PDM - Procure Batteries |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0 | 2022-10-01 | 2022-10-06 | 53% | Off Ice | C2 | [5 empty] | 2000 | [13 empty] | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 2043 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.5
873 | 1.2 | 1.2.5.2.7 | Not Started | PSL | Generator 2 Subcontract Repairs in New Zealand | GEN-2, 3, PDM - Generator 2 Subcontract Repairs in New Zealand |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-11-15 | 2023-01-13 | 53% | Off Ice | C2 |  |  |  |  | Round trip trucking (Bascik Transport) from USAP site to Terra Cat $345 NZD plus GST- $275 USD estimated. Terra Cat quoted repair of injection pump governor shaft and electronic controller - $5229.03 USD. Estimated $6500.00 USD for diagnosis/repair/testing of alternator output issue and $2800 for structural repair of the 20' ISO shipping container that houses the power plant. Terra Cat was not willing to quote without diagnosis of alternator/structural issues. Total $14,804.03 USD |  | 7402 | 7402 | [11 empty] | 0 | 7561.143 | 7561.143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15122.286 | 0 | 15122.286 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15122.286 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.5
874 | 1.2 | 1.2.5.2.8 | Not Started | PSL | PDM - Procure Batteries | PDM - Procure Batteries |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2023-07-01 | 2023-07-06 | 53% | Off Ice | C2 | [14 empty] | 600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612.9 | 0 | 0 | 612.9 | 0 | 612.9 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.5
875 | 1.2 | 1.2.5.2.9 | Not Started | PSL | Develop SOW for South Pole Power Generation Technical Support Subcontract & Communicate with Vendor (PY6) | GEN-2, 3, PDM - Develop SOW for South Pole Power Generation Technical Support Subcontract & Communicate with Vendor |  |  | Labor Hours | Labor Hours | EN-ME |  |  | D - Expert Opinion |  | 115 | 0% | 2023-10-01 | 2023-11-30 | 0% | Off Ice | C3 |  |  |  |  | South Pole Contractor cost captured in FS2 (2023-24). | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | [10 empty] | 40 | 0.26667 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.5
876 | 1.2 | 1.2.5.2.10 | Not Started | PSL | Predeployment Coordination with Power Generation Technical Support Subcontract Vendor (PY6) | GEN-2, 3, PDM - Predeployment Coordination with Power Generation Technical Support Subcontract Vendor (PY6) |  |  | Labor Hours | Labor Hours | EN-ME |  |  | D - Expert Opinion |  | 115 | 0% | 2023-08-01 | 2023-09-29 | 0% | Off Ice | C4 | [15 empty] | 20 | 20 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 4698.9 | 0 | 4698.9 | 20 | 20 | [10 empty] | 40 | 0.26667 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9498.8263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.5
883 | 1.2 | 1.2.5.4.1 | Complete | PSL | System Elec Dist: Evaluate EHWD system | Elec Dist. System: Evaluate EHWD system |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2020-12-01 | 2021-01-25 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
884 | 1.2 | 1.2.5.4.2 | Complete | PSL | System Elec Dist: Define Requirements | Elec Dist. System: Define Requirements |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2021-01-26 | 2021-04-19 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
885 | 1.2 | 1.2.5.4.3 | Started | PSL | System Elec Dist: Design & Procure | Elec Dist. System: Design & Procure |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-10-20 | 2022-10-31 | 0% | Off Ice | C4 | [5 empty] | 20 | [11 empty] | 20 | 0.13333 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 1.2.5
885 | 1.2 | 1.2.5.4.3 | Started | PSL | System Elec Dist: Design & Procure | Elec Dist. System: Design & Procure |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-10-20 | 2022-10-31 | 53% | Off Ice | C4 | [5 empty] | 5460 | [13 empty] | 5577.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5577.39 | 0 | 5577.39 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5577.39 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.5
887 | 1.2 | 1.2.5.4.5 | Started | PSL | System Elec Dist: Build and Test Subcomponents | Elec Dist. System: Build and Test Subcomponents |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-12-01 | 2023-04-13 | 0% | Off Ice | C4 | [9 empty] | 18 |  | 18 | [5 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 2114.505 | 0 | 2114.505 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.5
888 | 1.2 | 1.2.5.4.6 | Not Started | PSL | System Electrical Drawings & Documentation (PY5) | Elec Dist. System: System Electrical Drawings & Documentation (PY5) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0 | 2023-03-01 | 2023-03-16 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
889 | 1.2 | 1.2.5.4.7 | Not Started | PSL | System Electrical Drawings & Documentation (PY6) | Elec Dist. System: System Electrical Drawings & Documentation (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2024-03-15 | 2024-04-01 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
890 | 1.2 | 1.2.5.4.8 | Not Started | PSL | System Electrical Resupply (PY6) | Elec Dist. System: System Electrical Resupply (PY6) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-04-15 | 2024-04-23 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.5
890 | 1.2 | 1.2.5.4.8 | Not Started | PSL | System Electrical Resupply (PY6) | Elec Dist. System: System Electrical Resupply (PY6) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2024-04-15 | 2024-04-23 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 0 | 1928.3182 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1928.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.5
890 | 1.2 | 1.2.5.4.8 | Not Started | PSL | System Electrical Resupply (PY6) | Elec Dist. System: System Electrical Resupply (PY6) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2024-04-15 | 2024-04-23 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 0 | 5217.3112 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.5
891 | 1.2 | 1.2.5.4.9 | Not Started | PSL | System Electrical Drawings & Documentation (PY7) | Elec Dist. System: System Electrical Drawings & Documentation (PY7) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2025-03-15 | 2025-03-31 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
892 | 1.2 | 1.2.5.4.10 | Not Started | PSL | System Electrical Resupply (PY7) | Elec Dist. System: System Electrical Resupply (PY7) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2025-04-15 | 2025-04-23 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.5
892 | 1.2 | 1.2.5.4.10 | Not Started | PSL | System Electrical Resupply (PY7) | Elec Dist. System: System Electrical Resupply (PY7) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0 | 2025-04-15 | 2025-04-23 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1969.7771 | 0 | 0 | 0 | 0 | 0 | 1969.7771 | 0 | 1969.7771 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1969.7771 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 1969.7771 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.5
892 | 1.2 | 1.2.5.4.10 | Not Started | PSL | System Electrical Resupply (PY7) | Elec Dist. System: System Electrical Resupply (PY7) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2025-04-15 | 2025-04-23 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 5329.4834 | 0 | 0 | 0 | 0 | 0 | 5329.4834 | 0 | 5329.4834 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5329.4834 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.5
893 | 1.2 | 1.2.5.4.11 | Not Started | PSL | System Electrical Drawings & Documentation (PY8) | Elec Dist. System: System Electrical Drawings & Documentation (PY8) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0 | 2026-03-15 | 2026-03-30 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
896 | 1.2 | 1.2.6.1.1 | Complete | PSL | Identify Upgrades-Replacements and Spares | Water Tanks: Identify Upgrades, Replacements & Spares |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2021-01-04 | 2021-03-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
897 | 1.2 | 1.2.6.1.2 | Started | PSL | Procure Repair Parts, Replacements (PY4) | Water Tanks: Procure Repair Parts, Replacements (PY4) |  | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-05-20 | 2022-05-31 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
897 | 1.2 | 1.2.6.1.2 | Started | PSL | Procure Repair Parts, Replacements (PY4) | Water Tanks: Procure Repair Parts, Replacements (PY4) |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2022-05-20 | 2022-05-31 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
898 | 1.2 | 1.2.6.1.3 | Not Started | PSL | Procure Repair Parts, Replacements (PY6) | Water Tanks: Procure Repair Parts, Replacements (PY6) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-04-15 | 2024-04-19 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.6
898 | 1.2 | 1.2.6.1.3 | Not Started | PSL | Procure Repair Parts, Replacements (PY6) | Water Tanks: Procure Repair Parts, Replacements (PY6) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2024-04-15 | 2024-04-19 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 0 | 5217.3112 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
900 | 1.2 | 1.2.6.2.1 | Complete | PSL | Identify Upgrades-Replacements and Spares | Pumps: Identify Upgrades, Replacements & Spares |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2020-12-04 | 2021-03-25 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
901 | 1.2 | 1.2.6.2.2 | Complete | PSL | Procure Repair/Replacement Components (2020-21) | Pumps: Procure Upgrades, Replacements & Spares (2020-21) |  | 2.222% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2021-10-01 | 2022-02-17 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
901 | 1.2 | 1.2.6.2.2 | Complete | PSL | Procure Repair/Replacement Components (2020-21) | Pumps: Procure Upgrades, Replacements & Spares (2020-21) |  | 1.111% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2021-10-01 | 2022-02-17 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
901 | 1.2 | 1.2.6.2.2 | Complete | PSL | Procure Repair/Replacement Components (2020-21) | Pumps: Procure Repair/Replacement Components (2020-21) |  |  | CapEx | CapEx |  |  |  | HD |  | 1 | 0% | 2021-10-01 | 2022-02-17 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
901 | 1.2 | 1.2.6.2.2 | Complete | PSL | Procure Repair/Replacement Components (2020-21) | Pumps: Procure Replacement Charge and Transfer Pumps |  |  | CapEx | CapEx |  |  |  | HD |  | 1 | 0% | 2021-10-01 | 2022-02-17 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
902 | 1.2 | 1.2.6.2.3 | Started | PSL | Configure Pumps/Plumbing | Pumps: Configure Pumps/Plumbing |  | 0.8889% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-03-18 | 2022-04-06 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
903 | 1.2 | 1.2.6.2.4 | Not Started | PSL | Charge Pump Soft-starter Box Rebuild (four units) | Pumps: Charge pump soft-starter box rebuild (four units) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-04-07 | 2022-08-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
903 | 1.2 | 1.2.6.2.4 | Not Started | PSL | Charge Pump Soft-starter Box Rebuild (four units) | Pumps: Charge pump soft-starter box rebuild (four units) |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-04-07 | 2022-08-04 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
904 | 1.2 | 1.2.6.2.5 | Not Started | PSL | Procure Repair/Replacement Components (PY5) | Pumps: Procure Repair/Replacement Components (PY5) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-04-01 | 2023-04-19 | 0% | Off Ice | C4 | [11 empty] | 40 | [5 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.6
904 | 1.2 | 1.2.6.2.5 | Not Started | PSL | Procure Repair/Replacement Components (PY5) | Pumps: Procure Repair/Replacement Components (PY5)) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-04-01 | 2023-04-19 | 53% | Off Ice | C4 | [11 empty] | 6600 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 6741.9 | 0 | 0 | 0 | 0 | 0 | 6741.9 | 0 | 6741.9 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6741.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
905 | 1.2 | 1.2.6.2.6 | Not Started | PSL | Procure Repair/Replacement Components (PY6) | Pumps: Procure Repair/Replacement Components (PY6) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-04-01 | 2024-04-18 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.6
905 | 1.2 | 1.2.6.2.6 | Not Started | PSL | Procure Repair/Replacement Components (PY6) | Pumps: Procure Repair/Replacement Components (PY6) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2024-04-01 | 2024-04-18 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 0 | 5217.3112 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5217.3112 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
907 | 1.2 | 1.2.6.3.1 | Complete | PSL | Define Requirements & Research Methodologies | Filtration: Define Requirements/Research Methodologies |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2020-11-01 | 2020-12-31 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
908 | 1.2 | 1.2.6.3.2 | Not Started | PSL | Confirm w/ASC & NSF - Disposal of Condensate | Filtration: Confirm w/ASC & NSF - Disposal of Condensate (14,000 gals) |  | 0.6667% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-03-01 | 2022-03-28 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
909 | 1.2 | 1.2.6.3.3 | Complete | PSL | Develop Drilling Algorithms | Filtration: Develop Drilling Algorithms |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-03-01 | 2022-06-13 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
910 | 1.2 | 1.2.6.3.4 | Complete | PSL | Review & Identify Filtration Sub-System Upgrades | FIltration: Review & Identify Filtration Sub-System Upgrades |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-06-14 | 2022-09-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
911 | 1.2 | 1.2.6.3.5 | Started | PSL | Procure Filtration Upgrade-Replacement Components | Filtration: Procure Upgrade/Replacement Components |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-09-27 | 2022-12-19 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
911 | 1.2 | 1.2.6.3.5 | Started | PSL | Procure Filtration Upgrade-Replacement Components | Filtration: Procure Upgrade-Replacement Components |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2022-09-27 | 2022-12-19 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
912 | 1.2 | 1.2.6.3.6 | Started | PSL | Build & Test Filtration System | Filtration: Build & Test Filtration System |  | 1.333% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-04-28 | 2022-05-27 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
912 | 1.2 | 1.2.6.3.6 | Started | PSL | Build & Test Filtration System | Filtration: Build & Test Filtration System |  | 0.8889% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-04-28 | 2022-05-27 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
912 | 1.2 | 1.2.6.3.6 | Started | PSL | Build & Test Filtration System | Filtration: Build & Test Filtration System |  | 2.222% | Labor Hours | Labor - Task | UG | [5 empty] | 0% | 2022-04-28 | 2022-05-27 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
913 | 1.2 | 1.2.6.3.7 | Started | PSL | Design Condensate Collection, Treatment, and Disposal System | Filtration: Design Condensate Collection, Treatment, and Disposal System |  | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-02-19 | 2022-05-12 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
913 | 1.2 | 1.2.6.3.7 | Started | PSL | Design Condensate Collection, Treatment, and Disposal System | Filtration: Design Condensate Collection, Treatment, and Disposal System |  | 3.333% | Labor Hours | Labor - Task | UG | [5 empty] | 0% | 2022-02-19 | 2022-05-12 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
914 | 1.2 | 1.2.6.3.8 | Not Started | PSL | Procure Condensate Disposal System Components | Filtration: Procure Condensate System Components |  | 0.8889% | Labor Hours | Labor - Task | UG | [5 empty] | 0% | 2022-06-15 | 2022-07-15 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
914 | 1.2 | 1.2.6.3.8 | Not Started | PSL | Procure Condensate Disposal System Components | Filtration: Procure Condensate Disposal System Components |  | 1.111% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-06-15 | 2022-07-15 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
914 | 1.2 | 1.2.6.3.8 | Not Started | PSL | Procure Condensate Disposal System Components | Filtration: Procure Condensate Disposal System Components |  | 0.8889% | Labor Hours | Labor - Task | UG | [5 empty] | 0% | 2022-06-15 | 2022-07-15 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
914 | 1.2 | 1.2.6.3.8 | Not Started | PSL | Procure Condensate Disposal System Components | Filtration: Procure Condensate Disposal System Components |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-06-15 | 2022-07-15 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
918 | 1.2 | 1.2.6.4.2 | Not Started | PSL | Identify/Spec Replacements and Spare Heated Hose | Interconnect: Identify/Spec Replacements & Spare Heated Hose 2020-2021 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-05-01 | 2022-05-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
918 | 1.2 | 1.2.6.4.2 | Not Started | PSL | Identify/Spec Replacements and Spare Heated Hose | Interconnect: Identify/Spec Replacements 2022-2023 |  | 2.222% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-05-01 | 2022-05-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
919 | 1.2 | 1.2.6.4.3 | Not Started | PSL | Procure Replacements and Spares | Interconnect: Procure Replacements/Spares |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-05-01 | 2022-05-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
919 | 1.2 | 1.2.6.4.3 | Not Started | PSL | Procure Replacements and Spares | Interconnect: Procure Replacements/Spares |  | 2.222% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-05-01 | 2022-05-26 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
919 | 1.2 | 1.2.6.4.3 | Not Started | PSL | Procure Replacements and Spares | Interconnect: Procure Replacements and Spares/Heated |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2022-05-01 | 2022-05-26 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
920 | 1.2 | 1.2.6.4.4 | Not Started | PSL | Procure Remaining Materials & Fabricate Heated Hose | Interconnect: Procure Remaining Materials & Fabricate Heated Hose |  | 4.444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-05-10 | 2022-07-11 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
920 | 1.2 | 1.2.6.4.4 | Not Started | PSL | Procure Remaining Materials & Fabricate Heated Hose | Interconnect: Procure Remaining Materials & Fabricate Heated Hose |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-05-10 | 2022-07-11 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
921 | 1.2 | 1.2.6.4.5 | Complete | PSL | Assemble Hose End Ball Valves | Interconnect: Procure Parts & Assemble Hose End Ball Valves |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | EE | 115 | 115 | 0% | 2022-05-27 | 2022-07-07 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
921 | 1.2 | 1.2.6.4.5 | Complete | PSL | Assemble Hose End Ball Valves | Interconnect: Procure Parts & Assemble Hose End Ball Valves |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2022-05-27 | 2022-07-07 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
922 | 1.2 | 1.2.6.4.6 | Not Started | PSL | Finalize Design Gen Water Loop | Interconnect: Finalize Design Gen Water Loop |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-07-08 | 2022-08-18 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
923 | 1.2 | 1.2.6.4.7 | Not Started | PSL | Procure Gen Water Loop Materials & Assemble | Interconnect: Procure Gen Water Loop Materials & Assemble |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | EE | 115 | 115 | 0% | 2024-05-23 | 2024-07-05 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
923 | 1.2 | 1.2.6.4.7 | Not Started | PSL | Procure Gen Water Loop Materials & Assemble | Interconnect: Procure Gen Water Loop Materials & Assemble |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2024-05-23 | 2024-07-05 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
924 | 1.2 | 1.2.6.4.8 | Not Started | PSL | Procure Camp and Surface Hose Insulation (PY4) | Interconnect: Procure Camp and Surface Hose Insulation |  | 0.2222% | Labor Hours | Labor - Task | EN-ME |  |  | EE | 115 | 115 | 0% | 2022-07-02 | 2022-07-21 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
924 | 1.2 | 1.2.6.4.8 | Not Started | PSL | Procure Camp and Surface Hose Insulation (PY4) | Interconnect: Procure Camp and Surface Hose Insulation |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2022-07-02 | 2022-07-21 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
925 | 1.2 | 1.2.6.4.9 | Not Started | PSL | Procure External Interconnect Materials (PY6) | Interconnect: Procure External Interconnect materials (PY6) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-05-02 | 2024-05-22 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 40 |  |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.6
925 | 1.2 | 1.2.6.4.9 | Not Started | PSL | Procure External Interconnect Materials (PY6) | Interconnect: Procure External Interconnect materials (PY6) |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0 | 2024-05-02 | 2024-05-22 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 10551 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11009.5702 | 0 | 0 | 0 | 0 | 11009.5702 | 0 | 11009.5702 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11009.5702 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
927 | 1.2 | 1.2.6.5.1 | Started | PSL | Identify Replacement Water Hoses (1-1/2", 3/4", and 1/2" Hose) | MDS: Evaluate Water Hoses (1-1/2", 3/4", and 1/2" Hose) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-04-01 | 2024-04-26 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 8 | [5 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.6
928 | 1.2 | 1.2.6.5.2 | Started | PSL | Identify Replacement Fuel Hoses | MDS: Evaluate Fuel Hoses |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-04-01 | 2024-04-26 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 8 | [5 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.6
929 | 1.2 | 1.2.6.5.3 | Not Started | PSL | Procure Replacements and Spares | MDS: Procure Replacements Internal Hoses and Spares |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-04-29 | 2024-05-24 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 8 | 8 |  |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 1919.9705 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.6
929 | 1.2 | 1.2.6.5.3 | Not Started | PSL | Procure Replacements and Spares | MDS: Procure Replacements Internal Hoses and Spares |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2024-04-29 | 2024-05-24 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 11365 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 11858.9485 | 0 | 0 | 0 | 0 | 0 | 11858.9485 | 0 | 11858.9485 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11858.9485 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
932 | 1.2 | 1.2.6.6.1.1 | Started | PSL | Overall System Redesign and Integration Plan | ARA Drill: Overall System Redesign and Integration Plan |  | 0.8889% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-02-03 | 2022-04-27 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
932 | 1.2 | 1.2.6.6.1.1 | Started | PSL | Overall System Redesign and Integration Plan | ARA Drill: Overall System Redesign and Integration Plan |  |  | CapEx | CapEx | EN-ME |  |  |  |  | 1 | 0% | 2022-02-03 | 2022-04-27 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
933 | 1.2 | 1.2.6.6.1.2 | Started | PSL | Design and Spec Pump and Downhole Assembly | ARA Drill: Design and Spec Pump and Downhole Assembly |  | 1.333% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-04-28 | 2022-05-18 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
933 | 1.2 | 1.2.6.6.1.2 | Started | PSL | Design and Spec Pump and Downhole Assembly | ARA Drill: Design and Spec Pump and Downhole Assembly |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2022-04-28 | 2022-05-18 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
934 | 1.2 | 1.2.6.6.1.3 | Started | PSL | Design and Spec Pump Motor Controller Box | ARA Drill: Design and Spec Pump Motor Controller Box |  | 1.333% | Labor Hours | Labor - Task | EN-EE |  |  | EE | 115 | 115 | 0% | 2022-04-28 | 2022-05-18 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
934 | 1.2 | 1.2.6.6.1.3 | Started | PSL | Design and Spec Pump Motor Controller Box | ARA Drill: Design and Spec Pump Motor Controller Box |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2022-04-28 | 2022-05-18 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
935 | 1.2 | 1.2.6.6.1.4 | Started | PSL | Specify Sensors | ARA Drill: Specify Sensors |  | 0.8889% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-04-28 | 2022-05-18 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
935 | 1.2 | 1.2.6.6.1.4 | Started | PSL | Specify Sensors | ARA Drill: Specify Sensors |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-04-28 | 2022-05-18 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
936 | 1.2 | 1.2.6.6.1.5 | Started | PSL | Design Network/e-stop Interface Box | ARA Drill: Design Network/e-stop Interface Box |  | 1.778% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0 | 2022-04-28 | 2022-07-27 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
937 | 1.2 | 1.2.6.6.1.6 | Started | PSL | Design HotBox Plumbing Manifold II | ARA Drill: Design Network/e-stop Interface Box |  | 1.778% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-04-28 | 2022-06-01 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
939 | 1.2 | 1.2.6.6.2.1 | Started | PSL | Pumps & Motors | ARA Drill: Pumps & Motors |  | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-03-15 | 2022-04-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
939 | 1.2 | 1.2.6.6.2.1 | Started | PSL | Pumps & Motors | ARA Drill: Pumps & Motors |  |  | CapEx | CapEx | [5 empty] | 1 | 0 | 2022-03-15 | 2022-04-04 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
940 | 1.2 | 1.2.6.6.2.2 | Started | PSL | Downhole Assembly Hardware (Mat'l, Fab, & Nozzles) | ARA Drill: Downhole Assembly Hardware (Mat'l, Fab, & Nozzles) |  | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-03-15 | 2022-04-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
941 | 1.2 | 1.2.6.6.2.3 | Started | PSL | Pump Motor Control Box | ARA Drill: Pump Motor Control Box |  | 0.8889% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-03-15 | 2022-04-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
942 | 1.2 | 1.2.6.6.2.4 | Started | PSL | Sensors | ARA Drill: Sensors |  | 0.6667% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-03-15 | 2022-04-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
943 | 1.2 | 1.2.6.6.2.5 | Started | PSL | Network/e-stop Interface Box Components | ARA Drill: Pumps & Motors |  | 1.333% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-03-15 | 2022-04-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
943 | 1.2 | 1.2.6.6.2.5 | Started | PSL | Network/e-stop Interface Box Components | ARA Drill: Pumps & Motors |  |  | CapEx | CapEx | [5 empty] | 1 | 0 | 2022-03-15 | 2022-04-04 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
944 | 1.2 | 1.2.6.6.2.6 | Started | PSL | HotBox II Plumbing | ARA Drill: HotBox II Plumbing |  | 0.6667% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-03-15 | 2022-04-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
944 | 1.2 | 1.2.6.6.2.6 | Started | PSL | HotBox II Plumbing | ARA Drill: HotBox II Plumbing |  |  | CapEx | CapEx | [5 empty] | 1 | 0 | 2022-03-15 | 2022-04-04 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.6
945 | 1.2 | 1.2.6.6.2.7 | Started | PSL | Control Center Instrument tie-in | ARA Drill: Control Center Instrument tie-in |  | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-03-15 | 2022-04-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
946 | 1.2 | 1.2.6.6.2.8 | Started | PSL | Additional Hose, Cabling, Plumbing, & Hardware | ARA Drill: Additional Hose, Cabling, Plumbing, & Hardware |  | 0.2222% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-03-15 | 2022-04-04 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
948 | 1.2 | 1.2.6.6.3.1 | Started | PSL | Legacy Pump Module Assessment | ARA Drill: Legacy Pump Module Assessment |  | 0.8889% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-07-03 | 2022-07-21 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
949 | 1.2 | 1.2.6.6.3.2 | Started | PSL | Fab Downhole Assembly Parts and Assemblies | ARA Drill: Fab Downhole Assembly Parts and Assemblies |  | 2.222% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-07-22 | 2022-08-11 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
950 | 1.2 | 1.2.6.6.3.3 | Started | PSL | Assemble Downhole Assemblies | ARA Drill: Assemble Downhole Assemblies |  | 1.778% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-08-12 | 2022-09-01 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
951 | 1.2 | 1.2.6.6.3.4 | Started | PSL | Configure Pump Motor Controller | ARA Drill: Configure Pump Motor Controller |  | 1.333% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-09-02 | 2022-09-22 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
952 | 1.2 | 1.2.6.6.3.5 | Started | PSL | Test New Downhole Assemblies with Controller | ARA Drill: Test New Downhole Assemblies with Controller |  | 1.333% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-09-23 | 2022-10-06 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
953 | 1.2 | 1.2.6.6.3.6 | Started | PSL | Build and Test Network/e-stop Interface Box | ARA Drill: Build and Test Network/e-stop Interface Box |  | 2.778% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-07-03 | 2022-07-21 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 5750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
954 | 1.2 | 1.2.6.6.3.7 | Started | PSL | Test SplashCam Camera System | ARA Drill: Test SplashCam Camera System |  | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0 | 2022-07-03 | 2022-07-21 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
963 | 1.2 | 1.2.7.1.6 | Complete | PSL | Procure Brake Solenoid | ARA Drill: Procure Brake Solenoid |  | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2021-10-21 | 2021-10-27 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
963 | 1.2 | 1.2.7.1.6 | Complete | PSL | Procure Brake Solenoid | ARA Drill: Procure Brake Solenoid |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2021-10-21 | 2021-10-27 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
964 | 1.2 | 1.2.7.1.7 | Started | PSL | IFD Follow-up Tasks (PY5) | Support Equipment: IFD Follow-up Tasks (PY5) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-10-10 | 2022-10-28 | 0% | Off Ice | C3 | [5 empty] | 40 | [11 empty] | 40 | 0.26667 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.7
964 | 1.2 | 1.2.7.1.7 | Started | PSL | IFD Follow-up Tasks (PY5) | Support Equipment: IFD Follow-up Tasks (PY5) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0 | 2022-10-10 | 2022-10-28 | 0% | Off Ice | C3 | [5 empty] | 24 | [11 empty] | 24 | 0.16 | 1887.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 0 | 1887.732 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1887.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.7
964 | 1.2 | 1.2.7.1.7 | Started | PSL | IFD Follow-up Tasks (PY5) | Support Equipment: IFD Follow-up Tasks (PY5) |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0 | 2022-10-10 | 2022-10-28 | 53% | Off Ice | C3 | [5 empty] | 2000 | [13 empty] | 2043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 0 | 2043 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2043 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
966 | 1.2 | 1.2.7.2.1 | Started | PSL | Identify Spares and Replacements | Support Equipment: Identify Spares and Replacements |  | 1.333% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-01-01 | 2023-02-23 | 0% | Off Ice | C4 | [5 empty] | 8 |  | 8 | 8 | [8 empty] | 24 | 0.16 | 939.78 | 0 | 939.78 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2760 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.7
967 | 1.2 | 1.2.7.2.2 | Started | PSL | Procure Spares and Replacements | Support Equipment: Procure Spares and Replacements |  | 1.333% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-03-01 | 2025-06-11 | 0% | Off Ice | C4 | [13 empty] | 8 | 12 |  |  | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1409.67 | 0 | 0 | 2349.45 | 0 | 2349.45 | 8 | [6 empty] | 6 | 6 |  |  |  | 20 | 0.13333 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 719.989 | 719.989 | 0 | 0 | 0 | 2399.9632 | 0 | 2399.9632 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4749.4132 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2760 | 2349.45 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.7
967 | 1.2 | 1.2.7.2.2 | Started | PSL | Procure Spares and Replacements | Support Equipment: Procure Spares and Replacements |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-03-01 | 2025-06-11 | 53% | Off Ice | C4 | [14 empty] | 4000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4086 | 0 | 0 | 4086 | 0 | 4086 | 1000 | [6 empty] | 1000 | 2000 | [5 empty] | 1043.4623 | 0 | 0 | 0 | 0 | 0 | 0 | 1043.4623 | 2086.9245 | 0 | 0 | 0 | 4173.849 | 0 | 4173.849 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8259.849 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
968 | 1.2 | 1.2.7.2.3 | Started | PSL | Procure Hose Stock and Fittings (PY4) | Support Equipment: Procure Hose Stock and Fittings |  | 1.111% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-02-01 | 2022-03-14 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
968 | 1.2 | 1.2.7.2.3 | Started | PSL | Procure Hose Stock and Fittings (PY4) | Support Equipment: Procure Hose Stock and Fittings |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-02-01 | 2022-03-14 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
969 | 1.2 | 1.2.7.2.4 | Started | PSL | Procure Hose Stock and Fittings (FY5) | Support Equipment: Procure Hose Stock and Fittings |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-05-01 | 2023-06-09 | 0% | Off Ice | C4 | [12 empty] | 8 | 16 |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1879.56 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.7
969 | 1.2 | 1.2.7.2.4 | Started | PSL | Procure Hose Stock and Fittings (FY5) | Support Equipment: Procure Hose Stock and Fittings |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-05-01 | 2023-06-09 | 53% | Off Ice | C4 | [13 empty] | 5000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5107.5 | 0 | 0 | 0 | 5107.5 | 0 | 5107.5 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5107.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
970 | 1.2 | 1.2.7.2.5 | Started | PSL | Spare Parts Inventory and Catalog - Electrical/Controls | Support Equipment: Spare Parts Inventory and Catalog - Electrical/Controls |  | 2.222% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-05-01 | 2023-12-26 | 0% | Off Ice | C4 | [13 empty] | 8 | 8 |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 939.78 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4600 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.7
972 | 1.2 | 1.2.7.3.1 | Not Started | PSL | Identify Upgrade-Replacements, Spares | Shops: Identify Upgrade-Replacements, Spares |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-06-01 | 2023-06-28 | 0% | Off Ice | C4 | [11 empty] | 8 | 8 |  |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 939.78 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.7
973 | 1.2 | 1.2.7.3.2 | Not Started | PSL | Procure Upgrade-Replacements, Spares | Shops: Procure Upgrade-Replacements, Spares |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 115 | 115 | 0% | 2022-11-01 | 2023-08-11 | 0% | Off Ice | C4 | [12 empty] | 16 | 8 | 8 |  |  | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 939.78 | 939.78 | 0 | 0 | 3759.12 | 0 | 3759.12 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.7
973 | 1.2 | 1.2.7.3.2 | Not Started | PSL | Procure Upgrade-Replacements, Spares | Shops: Procure Upgrade-Replacements, Spares |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-11-01 | 2023-08-11 | 53% | Off Ice | C4 | [12 empty] | 1500 | 1000 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1532.25 | 1021.5 | 1021.5 | 0 | 0 | 3575.25 | 0 | 3575.25 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3575.25 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
976 | 1.2 | 1.2.7.4.2 | Complete | PSL | Identify & Procure Upgrade & Replacement Parts | Testbed: Identify & Procure Upgrade & Replacement Parts |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2019-03-18 | 2019-10-25 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
976 | 1.2 | 1.2.7.4.2 | Complete | PSL | Identify & Procure Upgrade & Replacement Parts | Testbed: Identify & Procure Upgrade & Replacement Parts (PSL_Engineer) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2019-03-18 | 2019-10-25 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
976 | 1.2 | 1.2.7.4.2 | Complete | PSL | Identify & Procure Upgrade & Replacement Parts | Testbed: Identify & Procure Upgrade & Replacement Parts |  |  | CapEx | CapEx |  |  |  | EE |  | 1 | 0% | 2019-03-18 | 2019-10-25 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
978 | 1.2 | 1.2.7.4.4 | Complete | PSL | Commission/Maintainence/Decommission (2020) | Testbed: Commission/Maintenance/Decommission (2020) |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2020-04-13 | 2020-11-20 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
978 | 1.2 | 1.2.7.4.4 | Complete | PSL | Commission/Maintainence/Decommission (2020) | Testbed: Commission/Maintenance/Decommission (2020) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2020-04-13 | 2020-11-20 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
978 | 1.2 | 1.2.7.4.4 | Complete | PSL | Commission/Maintainence/Decommission (2020) | Testbed: Commission/Maintenance/Decommission (2020) |  |  | CapEx | CapEx |  |  |  | HD |  | 1 | 0% | 2020-04-13 | 2020-11-20 | 53% | Off Ice |  | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
979 | 1.2 | 1.2.7.4.5 | Complete | PSL | Commission/Maintenance/Decommission (PY3) | Testbed: Commission/Maintenance/Decommission (PY3) |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2021-02-12 | 2021-09-23 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
979 | 1.2 | 1.2.7.4.5 | Complete | PSL | Commission/Maintenance/Decommission (PY3) | Testbed: Commission/Maintenance/Decommission (PY3) |  | 0% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2021-02-12 | 2021-09-23 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
979 | 1.2 | 1.2.7.4.5 | Complete | PSL | Commission/Maintenance/Decommission (PY3) | Testbed: Commission/Maintenance/Decommission (PY3) |  |  | CapEx | CapEx |  |  |  | HD |  | 1 | 0% | 2021-02-12 | 2021-09-23 | 53% | Off Ice |  | TRUE | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
980 | 1.2 | 1.2.7.4.6 | Not Started | PSL | Commission/Maintenance/Decommission (PY4) | Testbed: Commission/Maintenance/Decommission (PY4) |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2022-02-11 | 2022-09-21 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
980 | 1.2 | 1.2.7.4.6 | Not Started | PSL | Commission/Maintenance/Decommission (PY4) | Testbed: Commission/Maintenance/Decommission (PY4) |  | 2.667% | Labor Hours | Labor - Task | EN |  |  |  | 115 | 115 | 0% | 2022-02-11 | 2022-09-21 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 5520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
980 | 1.2 | 1.2.7.4.6 | Not Started | PSL | Commission/Maintenance/Decommission (PY4) | Testbed: Commission/Maintenance/Decommission (PY4) |  |  | CapEx | CapEx |  |  |  | HD |  | 1 | 0% | 2022-02-11 | 2022-09-21 | 53% | Off Ice | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
981 | 1.2 | 1.2.7.4.7 | Not Started | PSL | Commission/Maintenance/Decommission (PY5) | Testbed: Commission/Maintenance/Decommission (PY5) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0 | 2022-10-03 | 2023-09-29 | 0% | Off Ice | C4 | [9 empty] | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 1573.11 | 1573.11 | 1573.11 | 1573.11 | 0 | 0 | 0 | 0 | 6292.44 | 0 | 6292.44 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 6292.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.7
981 | 1.2 | 1.2.7.4.7 | Not Started | PSL | Commission/Maintenance/Decommission (PY5) | Testbed: Commission/Maintenance/Decommission (PY5) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-10-03 | 2023-09-29 | 0% | Off Ice | C4 | [9 empty] | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.7
981 | 1.2 | 1.2.7.4.7 | Not Started | PSL | Commission/Maintenance/Decommission (PY5) | Testbed: Commission/Maintenance/Decommission (PY5) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2022-10-03 | 2023-09-29 | 53% | Off Ice | C4 | [9 empty] | 2500 | 2500 | 2500 | 2500 | [6 empty] | 0 | 0 | 0 | 0 | 2553.75 | 2553.75 | 2553.75 | 2553.75 | 0 | 0 | 0 | 0 | 10215 | 0 | 10215 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10215 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
982 | 1.2 | 1.2.7.4.8 | Not Started | PSL | Commission/Maintenance/Decommission (PY6) | Testbed: Commission/Maintenance/Decommission (PY6) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0 | 2023-10-02 | 2024-09-30 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 1606.9319 | 1606.9319 | 1606.9319 | 1606.9319 | 0 | 0 | 0 | 0 | 6427.7275 | 0 | 6427.7275 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6427.7275 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 6427.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.7
982 | 1.2 | 1.2.7.4.8 | Not Started | PSL | Commission/Maintenance/Decommission (PY6) | Testbed: Commission/Maintenance/Decommission (PY6) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2023-10-02 | 2024-09-30 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.7
982 | 1.2 | 1.2.7.4.8 | Not Started | PSL | Commission/Maintenance/Decommission (PY6) | Testbed: Commission/Maintenance/Decommission (PY6) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2023-10-02 | 2024-09-30 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2500 | 2500 | 2500 | 2500 | [6 empty] | 0 | 0 | 0 | 0 | 2608.6556 | 2608.6556 | 2608.6556 | 2608.6556 | 0 | 0 | 0 | 0 | 10434.6225 | 0 | 10434.6225 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10434.6225 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
983 | 1.2 | 1.2.7.4.9 | Not Started | PSL | Commission/Maintenance/Decommission (PY7) | Testbed: Commission/Maintenance/Decommission (PY7) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0 | 2024-10-01 | 2025-09-30 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 1641.4809 | 1641.4809 | 1641.4809 | 1641.4809 | 0 | 0 | 0 | 0 | 6565.9236 | 0 | 6565.9236 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6565.9236 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 6565.9236 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.7
983 | 1.2 | 1.2.7.4.9 | Not Started | PSL | Commission/Maintenance/Decommission (PY7) | Testbed: Commission/Maintenance/Decommission (PY7) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2024-10-01 | 2025-09-30 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 2451.5624 | 2451.5624 | 2451.5624 | 2451.5624 | 0 | 0 | 0 | 0 | 9806.2495 | 0 | 9806.2495 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.2495 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 9806.2495 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.7
983 | 1.2 | 1.2.7.4.9 | Not Started | PSL | Commission/Maintenance/Decommission (PY7) | Testbed: Commission/Maintenance/Decommission (PY7) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2024-10-01 | 2025-09-30 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2500 | 2500 | 2500 | 2500 | [6 empty] | 0 | 0 | 0 | 0 | 2664.7417 | 2664.7417 | 2664.7417 | 2664.7417 | 0 | 0 | 0 | 0 | 10658.9669 | 0 | 10658.9669 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10658.9669 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
984 | 1.2 | 1.2.7.4.10 | Not Started | PSL | Commission/Maintenance/Decommission (PY8) | Testbed: Commission/Maintenance/Decommission (PY8) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0 | 2025-10-01 | 2026-03-31 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | [10 empty] | 40 | 0.26667 | 1676.7727 | 1676.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3353.5455 | 0 | 3353.5455 | 3353.5455 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 3353.5455 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.7
984 | 1.2 | 1.2.7.4.10 | Not Started | PSL | Commission/Maintenance/Decommission (PY8) | Testbed: Commission/Maintenance/Decommission (PY8) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0 | 2025-10-01 | 2026-03-31 | 0% | Off Ice | C4 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | [10 empty] | 40 | 0.26667 | 2504.271 | 2504.271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5008.5419 | 0 | 5008.5419 | 5008.5419 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 5008.5419 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.7
984 | 1.2 | 1.2.7.4.10 | Not Started | PSL | Commission/Maintenance/Decommission (PY8) | Testbed: Commission/Maintenance/Decommission (PY8) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2025-10-01 | 2026-03-31 | 53% | Off Ice | C4 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | [12 empty] | 1088.8135 | 1088.8135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2177.6269 | 0 | 2177.6269 | 2177.6269 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
989 | 1.2 | 1.2.7.5.4 | Should have Started | PSL | Identify Tools & Equipment, & Consumables | Tools & Equipment: Identify Tools & Consumables |  | 3.111% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2019-03-01 | 2022-09-30 | 0% | Off Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 6440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
990 | 1.2 | 1.2.7.5.5 | Started | PSL | Procure Tools & Equipment, & Consumables | Tools & Equipment: Procure Tools & Consumables |  | 0.4444% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2019-03-01 | 2025-07-31 | 0% | Off Ice | C4 | TRUE | [12 empty] | 8 | 8 | 8 |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 939.78 | 939.78 | 0 | 2819.34 | 0 | 2819.34 | [8 empty] | 8 | 8 | 8 |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 959.9853 | 0 | 2879.9558 | 0 | 2879.9558 | [7 empty] | 8 | 8 | 8 |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 980.625 | 980.625 | 0 | 0 | 2941.8749 | 0 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8641.1707 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 2819.34 | 2879.9558 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.7
990 | 1.2 | 1.2.7.5.5 | Started | PSL | Procure Tools & Equipment, & Consumables | Tools & Equipment: Procure Tools & Consumables |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0% | 2019-03-01 | 2025-07-31 | 53% | Off Ice | C4 | TRUE | [13 empty] | 2500 | 2500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2553.75 | 2553.75 | 0 | 5107.5 | 2706.975 | 7814.475 | [9 empty] | 2500 | 2500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2608.6556 | 2608.6556 | 0 | 5217.3112 | 2765.175 | 7982.4862 | [8 empty] | 2500 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2664.7417 | 2664.7417 | 0 | 0 | 5329.4834 | 2824.6262 | 8154.1097 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23951.0709 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.7
991 | 1.2 | 1.2.7.5.6 | Complete | PSL | Complete Hose Crimper Calibration | Tools & Equipment: Calibrate Crimper |  | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2021-10-10 | 2021-10-18 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
991 | 1.2 | 1.2.7.5.6 | Complete | PSL | Complete Hose Crimper Calibration | Tools & Equipment: Calibrate Crimper |  | 0.4444% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2021-10-10 | 2021-10-18 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
995 | 1.2 | 1.2.8.1.2 | Not Started | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - 5 Drillers (w/ 2 alternates) (Driller_PSL_DirectHire) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2023-05-31 | 2023-08-22 | 0% | Off Ice | C1 | TRUE |  |  |  | Contract staff training/travel labor - 3 Direct Hire + 2 alternates - assuming 7 days @ 8 hours per | [10 empty] | 280 |  | 280 | 1.8667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22023.54 | 0 | 22023.54 | 0 | 22023.54 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22023.54 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 22023.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 1.2.8
995 | 1.2 | 1.2.8.1.2 | Not Started | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - 10 PSL (Driller Lead/Engineers) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-05-31 | 2023-08-22 | 0% | Off Ice | C1 | TRUE |  |  |  | PSL staff training labor - Assuming 30 hours per PSL team member for training x 10 PSL Engineers | [10 empty] | 300 |  | 300 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35241.75 | 0 | 35241.75 | 0 | 35241.75 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35241.75 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 35241.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 1.2.8
995 | 1.2 | 1.2.8.1.2 | Not Started | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - Safety Training Materials/Vendors |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0 | 2023-05-31 | 2023-08-22 | 53% | Off Ice | C1 | TRUE |  |  |  | SafeStart, rigging, and Red Cross training - additional training materials added in coordination with USAP contractor | [10 empty] | 5000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5107.5 | 0 | 5107.5 | 2706.975 | 7814.475 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7814.475 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
995 | 1.2 | 1.2.8.1.2 | Not Started | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - Safety Equipment/Consumables |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0 | 2023-05-31 | 2023-08-22 | 53% | Off Ice | C1 | TRUE |  |  |  | Procurement of replacement smoke detector batteries, smoke detectors, toe warmers, hand warmers, oxygen, CO, H2S, monitors, first aid kit, work gloves, knee pads, goggles, and N95 masks | [7 empty] | 1000 | 1000 | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1021.5 | 1021.5 | 204.3 | 0 | 0 | 2247.3 | 1191.069 | 3438.369 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3438.369 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
995 | 1.2 | 1.2.8.1.2 | Not Started | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - 5 DH Drillers (w/ 2 alternates) - (Direct Hire Travel -1 Domestic, 2 International, 2 Local) | Foreign |  | Travel | Travel |  |  |  | D - Expert Opinion |  | 1 | 0 | 2023-05-31 | 2023-08-22 | 53% | Off Ice | C1 | TRUE |  |  |  | Contract staff training Foreign Travel - 3 Direct Hire w/ 2 alternates - 5 Total (estimating 2 local, 1 domestic, 2 intl). Duration 7 days. $8200 total travel cost 2 Local - No travel costs 1 Domestic - $1800 2 International - $6400 | [10 empty] | 6400 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6537.6 | 0 | 6537.6 | 3464.928 | 10002.528 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10002.528 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
995 | 1.2 | 1.2.8.1.2 | Not Started | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - 5 DH Drillers (w/ 2 alternates) - (Direct Hire Travel -1 Domestic, 2 International, 2 Local) | Domestic |  | Travel | Travel |  |  |  | D - Expert Opinion |  | 1 | 0% | 2023-05-31 | 2023-08-22 | 53% | Off Ice | C1 | TRUE |  |  |  | Contract staff training Domestic Travel - 3 Direct Hire w/ 2 alternates - 5 Total (estimating 2 local, 1 domestic, 2 intl). Duration 7 days. $8200 total travel cost 2 Local - No travel costs 1 Domestic - $1800 2 International - $6400 | [10 empty] | 1800 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1838.7 | 0 | 1838.7 | 974.511 | 2813.211 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2813.211 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
996 | 1.2 | 1.2.8.1.3 | Not Started | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - 8 Drillers (2 alternates) (Driller_PSL_DirectHire) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2024-05-31 | 2024-08-22 | 0% | Off Ice | C1 |  |  |  |  | Contract staff training/travel labor - 8 Direct Hire (w/ 2 alternates) - assuming 7 days @ 8 hours per (448 hours total) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 224 | 224 |  | 448 | 2.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17997.6369 | 17997.6369 | 0 | 35995.2738 | 0 | 35995.2738 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35995.2738 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 35995.2738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448 | 1.2.8
996 | 1.2 | 1.2.8.1.3 | Not Started | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - 10 PSL (Driller_Lead/Engineer) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2024-05-31 | 2024-08-22 | 0% | Off Ice | C1 |  |  |  |  | PSL staff training labor - Assuming 30 hours per PSL team member for training x 10 PSL Engineers | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 150 | 150 |  | 300 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17999.7238 | 17999.7238 | 0 | 35999.4476 | 0 | 35999.4476 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35999.4476 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 35999.4476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 1.2.8
996 | 1.2 | 1.2.8.1.3 | Not Started | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - Safety Training Materials/Vendors |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0 | 2024-05-31 | 2024-08-22 | 53% | Off Ice | C1 | TRUE |  |  |  | Red Cross and job specific training TBD - additional training materials added in coordination with USAP contractor | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2608.6556 | 0 | 0 | 0 | 0 | 2608.6556 | 1382.5875 | 3991.2431 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3991.2431 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
996 | 1.2 | 1.2.8.1.3 | Not Started | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - Safety Equipment/Consumables |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0 | 2024-05-31 | 2024-08-22 | 53% | Off Ice | C1 | TRUE |  |  |  | Procurement of replacement smoke detector batteries, smoke detectors, toe warmers, hand warmers, absorbent pads, N95 masks, smoke and CO monitors | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1000 | 1000 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1043.4623 | 1043.4623 | 521.7311 | 0 | 0 | 2608.6556 | 1382.5875 | 3991.2431 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3991.2431 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
996 | 1.2 | 1.2.8.1.3 | Not Started | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - 8 DH Drillers w/ 2 alternates - (Direct Hire Travel -1 Domestic 2 International) | Foreign |  | Travel | Travel |  |  |  | D - Expert Opinion |  | 1 | 0 | 2024-05-31 | 2024-08-22 | 53% | Off Ice | C1 |  |  |  |  | Contract staff training International Travel - 8 Direct Hire w/ 2 alternates Duration 7 days. 2 Local - No travel costs 3 Domestic - $5400 3 International - $9600 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 4800 | 4800 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5008.6188 | 5008.6188 | 0 | 10017.2376 | 5309.1359 | 15326.3735 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15326.3735 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
996 | 1.2 | 1.2.8.1.3 | Not Started | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - 6 DH Drillers w/ 2 alternates - (Direct Hire Travel -1 Domestic 2 International) | Domestic |  | Travel | Travel |  |  |  | D - Expert Opinion |  | 1 | 0% | 2024-05-31 | 2024-08-22 | 53% | Off Ice | C1 |  |  |  |  | Contract staff training Domestic Travel - 8 Direct Hire w/ 2 alternates Duration 7 days. 2 Local - No travel costs 3 Domestic - $5400 3 International - $9600 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2700 | 2700 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2817.3481 | 2817.3481 | 0 | 5634.6961 | 2986.389 | 8621.0851 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8621.0851 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
997 | 1.2 | 1.2.8.1.4 | Not Started | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - 22 Drillers (w/ 4 alternates) (Driller_PSL_DirectHire) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2025-05-28 | 2025-08-19 | 0% | Off Ice | C1 |  |  |  |  | Contract staff training/travel labor - 24 Direct Hire - 20 deploy w/ 4 alternates. Duration 14 - 8 hour days with travel. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1344 | 1344 |  | 2688 | 17.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110307.5165 | 110307.5165 | 0 | 220615.033 | 0 | 220615.033 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220615.033 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 220615.033 | 0 | 0 | 0 | 0 | 0 | 0 | 2688 | 1.2.8
997 | 1.2 | 1.2.8.1.4 | Not Started | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - 10 PSL Staff - 2 Rotators (Engineer/Driller PSL_Lead) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2025-05-28 | 2025-08-19 | 0% | Off Ice | C1 |  |  |  |  | PSL staff training labor - Assuming 60 hours per PSL team member for training x 10 PSL Engineers | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 300 | 300 |  | 600 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36773.4357 | 36773.4357 | 0 | 73546.8715 | 0 | 73546.8715 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73546.8715 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 73546.8715 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 1.2.8
997 | 1.2 | 1.2.8.1.4 | Not Started | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - Safety Training Materials/Vendors |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0 | 2025-05-28 | 2025-08-19 | 53% | Off Ice | C1 | TRUE |  |  |  | SafeStart, rigging, job specific training (TBD) and Red Cross training - additional training materials added in coordination with USAP contractor | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2000 | 3000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2131.7934 | 3197.6901 | 0 | 0 | 0 | 5329.4834 | 2824.6262 | 8154.1097 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8154.1097 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
997 | 1.2 | 1.2.8.1.4 | Not Started | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - Safety Equipment/Consumables |  |  | M & S | M & S |  |  |  | D - Expert Opinion |  | 1 | 0 | 2025-05-28 | 2025-08-19 | 53% | Off Ice | C1 | TRUE |  |  |  | Procurement of replacement smoke detector batteries, smoke detectors, toe warmers, hand warmers, absorbent pads, N95 masks, smoke and CO monitors | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2000 | 2000 | 500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2131.7934 | 2131.7934 | 532.9483 | 0 | 0 | 4796.5351 | 2542.1636 | 7338.6987 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7338.6987 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
997 | 1.2 | 1.2.8.1.4 | Not Started | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - 24 Drillers (Direct Hire Travel) | Foreign |  | Travel | Travel |  |  |  | D - Expert Opinion |  | 1 | 0 | 2025-05-28 | 2025-08-19 | 53% | Off Ice | C1 |  |  |  |  | Contract staff - Training Foreign Travel - 24 Direct Hire - 20 deploy w/ 4 alternates Duration 14 days with travel. 6 Local - No travel costs 12 Domestic - $21600 6 International - $19200 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 9600 | 9600 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10232.6082 | 10232.6082 | 0 | 20465.2164 | 10846.5647 | 31311.7811 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31311.7811 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
997 | 1.2 | 1.2.8.1.4 | Not Started | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - 24 Drillers (Direct Hire Travel) | Domestic |  | Travel | Travel |  |  |  | D - Expert Opinion |  | 1 | 0% | 2025-05-28 | 2025-08-19 | 53% | Off Ice | C1 |  |  |  |  | Contract staff -Training Domestic Travel - 24 Direct Hire - 20 deploy w/ 4 alternates Duration 14 days with travel. 6 Local - No travel costs 12 Domestic - $21600 6 International - $19200 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 10800 | 10800 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11511.6842 | 11511.6842 | 0 | 23023.3685 | 12202.3853 | 35225.7538 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35225.7538 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
998 | 1.2 | 1.2.8.1.5 | Not Started | PSL | FS3 Off-Ice Logging Winch Training with IDP (3 Drillers 1 day) | FS3 - Off-Ice Logging Winch Training - 3 Drillers 1 day |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 115 | 115 | 0% | 2025-08-19 | 2025-08-19 | 0% | Off Ice | C1 |  |  |  |  | Logging Winch Training - 3 Drillers 1 day training with IDP support (IDP cost in Calibration WBS) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 24 |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 2941.8749 | 0 | 2941.8749 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.8
1103 | 1.2 | 1.2.8.5.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Driller_PSL_Manager) |  | 0% | Labor Hours | Labor - Task | EN |  |  | E - Extrapolation from Actuals | 115 | 115 | 0 | 2023-06-02 | 2024-02-29 | 0% | Off Ice | C1 |  |  |  |  | 1 Drill Manager, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0.42667 | 0 | 4799.9263 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7679.8822 | 0 | 7679.8822 |  | 40 |  |  | 24 | [7 empty] | 64 | 0.42667 | 0 | 4903.1248 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7844.9996 | 0 | 7844.9996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15524.8818 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 7679.8822 | 7844.9996 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 1.2.8
1103 | 1.2 | 1.2.8.5.2 | Not Started | UW | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Safety Engineer) | Zernick | 0% | Labor Hours | Labor - Task | EN-S |  |  | E - Extrapolation from Actuals | 60.69 | 46 | 35% | 2023-06-02 | 2024-02-29 | 53% | Off Ice | C1 |  |  |  |  | 1 Safety Engineer, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0.42667 | 0 | 3419.6971 | 0 | 0 | 2051.8183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5471.5153 | 2899.9031 | 8371.4185 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8371.4185 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4052.9743 | 0 | 0 | 0 | 0 | 1418.541 | 0 | 0 | 64 | 1.2.8
1103 | 1.2 | 1.2.8.5.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Driller_PSL_DirectHire) x 3 |  | 0% | Labor Hours | Labor - Task | TE |  |  | E - Extrapolation from Actuals | 77 | 77 | 0% | 2023-06-02 | 2024-02-29 | 0% | Off Ice | C1 |  |  |  |  | 3 Seasonal drillers, 5 days deployment travel 3 days redeployment (No Contributed drillers) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 |  |  | 72 | [7 empty] | 192 | 1.28 | 0 | 9641.5912 | 0 | 0 | 5784.9547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15426.5459 | 0 | 15426.5459 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15426.5459 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 15426.5459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192 | 1.2.8
1103 | 1.2 | 1.2.8.5.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (PSL_Engineer) x 9 |  | 0% | Labor Hours | Labor - Task | EN |  |  | E - Extrapolation from Actuals | 115 | 115 | 0% | 2023-06-02 | 2024-02-29 | 0% | Off Ice | C1 |  |  |  |  | 9 PSL Engineers (2 Rotators), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 280 | 128 |  | 168 | [7 empty] | 576 | 3.84 | 0 | 33599.4845 | 15359.7643 | 0 | 20159.6907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69118.9394 | 0 | 69118.9394 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69118.9394 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 69118.9394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 576 | 1.2.8
1103 | 1.2 | 1.2.8.5.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Drill Team) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2023-06-02 | 2024-02-29 | 53% | Off Ice | C1 |  |  |  |  | 16 - PQ's 1 Drill Lead, 1 Safety Engineer, 5 Direct Hire (2 alternate) & 9 PSL Engineers @ $950/each (anticipated cost) | [8 empty] | 7600 |  | 7600 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7763.4 | 0 | 7763.4 | 0 | 15526.8 | 8229.204 | 23756.004 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23756.004 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
1103 | 1.2 | 1.2.8.5.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Drill Team) | Foreign |  | Travel | Travel |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2023-06-02 | 2024-02-29 | 53% | Off Ice | C1 |  |  |  |  | 14 - Deployment Travel @ $1800 each | [9 empty] | 12600 | 12600 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12870.9 | 12870.9 | 0 | 25741.8 | 13643.154 | 39384.954 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39384.954 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
1130 | 1.2 | 1.2.8.5.4.4 | Not Started | PSL | Set-up MECC & Shop for Season Activities (Driller) | Kick-off Tasking: Set-up MECC (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-14 | 2023-11-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | [10 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.8
1130 | 1.2 | 1.2.8.5.4.4 | Not Started | PSL | Set-up MECC & Shop for Season Activities (Driller) | Kick-off Tasking: Set-up SHOP (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-14 | 2023-11-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | [10 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.8
1136 | 1.2 | 1.2.8.5.4.9.1 | Not Started | PSL | Stock Shelves/Cabinets w/ Needed Hardware and Tools | Kick-off Tasking: Stock Shelves/Cabinets w/ Needed Hardware and Tools (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-13 | 2023-11-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1137 | 1.2 | 1.2.8.5.4.9.2 | Not Started | PSL | Install new DGH Gateway/Ethernet box, Connect to Gen-1 Network Box, M-DGHs & Test | Kick-off Tasking: Install new DGH Gateway/Ethernet box, connect to Gen-1 Network Box, M-DGHs & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-13 | 2023-11-14 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1143 | 1.2 | 1.2.8.5.5.5 | Not Started | PSL | Generators 1,3 & PDM - Repairs & Pre-operational Checks | Power Gen: Generators/PDM: Generators & PDM - Repairs & Pre-operational Checks (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-24 | 2023-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10 | 53 | [9 empty] | 63 | 0.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 1.2.8
1143 | 1.2 | 1.2.8.5.5.5 | Not Started | PSL | Generators 1,3 & PDM - Repairs & Pre-operational Checks | Power Gen: Generators/PDM: Generators & PDM - Repairs & Pre-operational Checks (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-24 | 2023-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10 | 53 | [9 empty] | 63 | 0.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 1.2.8
1147 | 1.2 | 1.2.8.5.5.11 | Not Started | PSL | Ready, Start-up & Exercise Gen1, Gen 2, & Gen3 (Driller & USAP) | Power Gen: Ready, Start-up & Exercise Gen1, Gen 2, & Gen3 (Driller & USAP) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-05 | 2023-12-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1147 | 1.2 | 1.2.8.5.5.11 | Not Started | PSL | Ready, Start-up & Exercise Gen1, Gen 2, & Gen3 (Driller & USAP) | Power Gen: Ready, Start-up & Exercise Gen1, Gen 2, & Gen3 (Driller & USAP) (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-05 | 2023-12-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.8
1148 | 1.2 | 1.2.8.5.5.12 | Not Started | PSL | Install Intake & Exhaust Hoods | Power Gen: Install Intake & Exhaust Hoods (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-07 | 2023-12-12 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1151 | 1.2 | 1.2.8.5.5.15 | Not Started | PSL | Winterize Gen Modules and PDM (Driller & USAP) | Power Gen: Winterize Gen Modules and PDM (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-21 | 2023-12-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1151 | 1.2 | 1.2.8.5.5.15 | Not Started | PSL | Winterize Gen Modules and PDM (Driller & USAP) | Power Gen: Winterize Gen Modules and PDM (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-21 | 2023-12-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1154 | 1.2 | 1.2.8.5.6.1.1 | Not Started | PSL | Assess SES/TOS Interconnect Inventory | Global Computing/Controls: Assess SES/TOS Interconnect Inventory (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-10 | 2024-01-12 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16 | [8 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.8
1155 | 1.2 | 1.2.8.5.6.1.2 | Not Started | PSL | Install and Test Modbus DGH Modules | Global Computing/Controls: Install and Test Modbus DGH Modules (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-05 | 2024-01-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1158 | 1.2 | 1.2.8.5.6.2.2 | Not Started | PSL | Replace Electric Heater in Electrical Closet | DCC: Heater Replacement (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-14 | 2023-11-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | [10 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.8
1158 | 1.2 | 1.2.8.5.6.2.2 | Not Started | PSL | Replace Electric Heater in Electrical Closet | DCC: Heater Replacement (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-14 | 2023-11-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 14 | [10 empty] | 14 | 0.093333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1.2.8
1159 | 1.2 | 1.2.8.5.6.2.3 | Not Started | PSL | Clean-up Workspace & Configure | DCC: Clean-up Workspace & Configure (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2023-11-14 | 2023-11-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | [10 empty] | 6 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1.2.8
1165 | 1.2 | 1.2.8.5.6.3.3.1.1 | Not Started | PSL | Heater Flush and Pressure Test | MHP1: Heater Flush and Pressure Test (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-14 | 2023-11-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | [10 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1165 | 1.2 | 1.2.8.5.6.3.3.1.1 | Not Started | PSL | Heater Flush and Pressure Test | MHP1: Heater Flush and Pressure Test (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-14 | 2023-11-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | [10 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1166 | 1.2 | 1.2.8.5.6.3.3.1.2 | Not Started | PSL | Plumbing Upgrades & Repairs | MHP1: Plumbing Upgrades & Repairs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-27 | 2023-11-30 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1166 | 1.2 | 1.2.8.5.6.3.3.1.2 | Not Started | PSL | Plumbing Upgrades & Repairs | MHP1: Plumbing Upgrades & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-27 | 2023-11-30 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1167 | 1.2 | 1.2.8.5.6.3.3.1.3 | Not Started | PSL | Fuel System Upgrades and Repairs | MHP1: Fuel System Upgrades & Repairs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-14 | 2023-11-15 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1167 | 1.2 | 1.2.8.5.6.3.3.1.3 | Not Started | PSL | Fuel System Upgrades and Repairs | MHP1: Fuel System Upgrades & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-14 | 2023-11-15 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1168 | 1.2 | 1.2.8.5.6.3.3.1.4 | Not Started | PSL | Exhaust System Upgrades and Repairs | MHP1: Exhaust System Upgrades & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-15 | 2023-11-16 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1169 | 1.2 | 1.2.8.5.6.3.3.1.5 | Not Started | PSL | MHP Subsystem Evaluation | MHP1: Subsystem Evaluation (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-30 | 2023-12-01 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1172 | 1.2 | 1.2.8.5.6.3.3.2.1 | Not Started | PSL | Install PLC-to-DGH Gateway in Network Box, Install M-DGHs, & Test | MHP1: Install PLC-to-DGH Gateway in Network Box, Install M-DGHs, & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-17 | 2023-11-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1173 | 1.2 | 1.2.8.5.6.3.3.2.2 | Not Started | PSL | Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) | MHP1: Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-14 | 2023-11-17 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1173 | 1.2 | 1.2.8.5.6.3.3.2.2 | Not Started | PSL | Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) | MHP1: Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-14 | 2023-11-17 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1174 | 1.2 | 1.2.8.5.6.3.3.2.3 | Not Started | PSL | Replace Thermostats in Heaters & Test | MHP1: Replace Thermostats in Heaters & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-02 | 2023-12-04 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1175 | 1.2 | 1.2.8.5.6.3.3.2.4 | Not Started | PSL | Reconfigure MHP E-stop Panel to Function with N.C. Slap Switch Contacts | MHP1: Reconfigure MHP E-stop Panel to Function with N.C. Slap Switch Contacts (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-18 | 2023-11-19 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1176 | 1.2 | 1.2.8.5.6.3.3.2.5 | Not Started | PSL | Test E-stop and Heater Controls with No Water | MHP1: Test E-stop and Heater Controls with No Water (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-19 | 2023-11-21 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1177 | 1.2 | 1.2.8.5.6.3.3.2.6 | Not Started | PSL | Test Flow Sensor Operation with No Water | MHP1: Test Flow Sensor Operation with No Water (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-04 | 2023-12-05 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1178 | 1.2 | 1.2.8.5.6.3.3.2.7 | Not Started | PSL | Install Ethernet Switch, Connect to Network Box, Route Cable to DCC & Test | MHP1: Install Ethernet Switch, Connect to Network Box, Route Cable to DCC & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-30 | 2023-12-01 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1182 | 1.2 | 1.2.8.5.6.3.4.1.1 | Not Started | PSL | Heater Flush and Pressure Test | MHP2: Heater Flush and Pressure Test (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-18 | 2023-11-21 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | [10 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1182 | 1.2 | 1.2.8.5.6.3.4.1.1 | Not Started | PSL | Heater Flush and Pressure Test | MHP2: Heater Flush and Pressure Test (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-18 | 2023-11-21 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1183 | 1.2 | 1.2.8.5.6.3.4.1.2 | Not Started | PSL | Plumbing Upgrades & Repairs | MHP2: Plumbing Upgrades & Repairs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-24 | 2023-11-27 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1183 | 1.2 | 1.2.8.5.6.3.4.1.2 | Not Started | PSL | Plumbing Upgrades & Repairs | MHP2: Plumbing Upgrades & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-24 | 2023-11-27 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1184 | 1.2 | 1.2.8.5.6.3.4.1.3 | Not Started | PSL | Fuel System Upgrades and Repairs | MHP2: Fuel System Upgrades & Repairs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-15 | 2023-11-16 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1184 | 1.2 | 1.2.8.5.6.3.4.1.3 | Not Started | PSL | Fuel System Upgrades and Repairs | MHP2: Fuel System Upgrades & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-15 | 2023-11-16 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1185 | 1.2 | 1.2.8.5.6.3.4.1.4 | Not Started | PSL | Exhaust System Upgrades and Repairs | MHP2: Exhaust System Upgrades & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-16 | 2023-11-17 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1186 | 1.2 | 1.2.8.5.6.3.4.1.5 | Not Started | PSL | MHP2 Subsystem Evaluation | MHP2: Subsystem Evaluation (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-27 | 2023-11-28 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1189 | 1.2 | 1.2.8.5.6.3.4.2.1 | Not Started | PSL | Install PLC-to-DGH Gateway in Network Box, Install M-DGHs, & Test | MHP2: Install PLC-to-DGH Gateway in Network Box, Install M-DGHs, & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-16 | 2023-11-17 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1190 | 1.2 | 1.2.8.5.6.3.4.2.2 | Not Started | PSL | Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) | MHP2: Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-17 | 2023-11-20 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1190 | 1.2 | 1.2.8.5.6.3.4.2.2 | Not Started | PSL | Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) | MHP2: Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-17 | 2023-11-20 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1191 | 1.2 | 1.2.8.5.6.3.4.2.3 | Not Started | PSL | Replace Thermostats in Heaters & Test | MHP2: Replace Thermostats in Heaters & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-30 | 2023-12-02 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1192 | 1.2 | 1.2.8.5.6.3.4.2.4 | Not Started | PSL | Test E-stop and Heater Controls with No Water | MHP2: Test E-stop and Heater Controls with No Water (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-21 | 2023-11-23 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1193 | 1.2 | 1.2.8.5.6.3.4.2.5 | Not Started | PSL | Test Flow Sensor Operation with No Water | MHP2: Test Flow Sensor Operation with No Water (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-05 | 2023-12-06 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1194 | 1.2 | 1.2.8.5.6.3.4.2.6 | Not Started | PSL | Install Ethernet Switch, Connect to Network Box, Route Cable to DCC & Test | MHP2: Install Ethernet Switch, Connect to Network Box, Route Cable to DCC & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-29 | 2023-11-30 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1198 | 1.2 | 1.2.8.5.6.3.5.1.1 | Not Started | PSL | Heater Flush and Pressure Test | MHP3: Heater Flush and Pressure Test (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-21 | 2023-11-24 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | [10 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1198 | 1.2 | 1.2.8.5.6.3.5.1.1 | Not Started | PSL | Heater Flush and Pressure Test | MHP3: Heater Flush and Pressure Test (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-21 | 2023-11-24 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1199 | 1.2 | 1.2.8.5.6.3.5.1.2 | Not Started | PSL | Plumbing Upgrades & Repairs | MHP3: Plumbing Upgrades & Repairs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-21 | 2023-11-24 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1199 | 1.2 | 1.2.8.5.6.3.5.1.2 | Not Started | PSL | Plumbing Upgrades & Repairs | MHP3: Plumbing Upgrades & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-21 | 2023-11-24 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1200 | 1.2 | 1.2.8.5.6.3.5.1.3 | Not Started | PSL | Fuel System Upgrades and Repairs | MHP3: Fuel System Upgrades & Repairs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-16 | 2023-11-17 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1200 | 1.2 | 1.2.8.5.6.3.5.1.3 | Not Started | PSL | Fuel System Upgrades and Repairs | MHP3: Fuel System Upgrades & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-16 | 2023-11-17 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1201 | 1.2 | 1.2.8.5.6.3.5.1.4 | Not Started | PSL | Exhaust System Upgrades and Repairs | MHP3: Exhaust System Upgrades & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-17 | 2023-11-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1202 | 1.2 | 1.2.8.5.6.3.5.1.5 | Not Started | PSL | MHP3 Subsystem Evaluation | MHP3: Subsystem Evaluation (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-24 | 2023-11-25 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1205 | 1.2 | 1.2.8.5.6.3.5.2.1 | Not Started | PSL | Install PLC-to-DGH Gateway in Network Box, Install M-DGHs, & Test | MHP3: Install PLC-to-DGH Gateway in Network Box, Install M-DGHs, & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-15 | 2023-11-16 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1206 | 1.2 | 1.2.8.5.6.3.5.2.2 | Not Started | PSL | Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) | MHP3: Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-20 | 2023-11-23 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1206 | 1.2 | 1.2.8.5.6.3.5.2.2 | Not Started | PSL | Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) | MHP3: Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-20 | 2023-11-23 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1207 | 1.2 | 1.2.8.5.6.3.5.2.3 | Not Started | PSL | Replace Thermostats in Heaters & Test | MHP3: Replace Thermostats in Heaters & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-28 | 2023-11-30 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1208 | 1.2 | 1.2.8.5.6.3.5.2.4 | Not Started | PSL | Test E-stop and Heater Controls with No Water | MHP3: Test E-stop and Heater Controls with No Water (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-23 | 2023-11-25 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1209 | 1.2 | 1.2.8.5.6.3.5.2.5 | Not Started | PSL | Test Flow Sensor Operation with No Water | MHP3: Test Flow Sensor Operation with No Water (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-06 | 2023-12-07 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1210 | 1.2 | 1.2.8.5.6.3.5.2.6 | Not Started | PSL | Install Ethernet Switch, Connect to Network Box, Route Cable to DCC & Test | MHP3: Install Ethernet Switch, Connect to Network Box, Route Cable to DCC & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-28 | 2023-11-29 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1214 | 1.2 | 1.2.8.5.6.3.6.1.1 | Not Started | PSL | Heater Flush and Pressure Test | MHP4: Heater Flush and Pressure Test (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-24 | 2023-11-26 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | [10 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1214 | 1.2 | 1.2.8.5.6.3.6.1.1 | Not Started | PSL | Heater Flush and Pressure Test | MHP4: Heater Flush and Pressure Test (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-24 | 2023-11-26 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1215 | 1.2 | 1.2.8.5.6.3.6.1.2 | Not Started | PSL | Plumbing Upgrades & Repairs | MHP4: Plumbing Upgrades & Repairs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-18 | 2023-11-21 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1215 | 1.2 | 1.2.8.5.6.3.6.1.2 | Not Started | PSL | Plumbing Upgrades & Repairs | MHP4: Plumbing Upgrades & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-18 | 2023-11-21 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1216 | 1.2 | 1.2.8.5.6.3.6.1.3 | Not Started | PSL | Fuel System Upgrades and Repairs | MHP4: Fuel System Upgrades & Repairs - (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-17 | 2023-11-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1216 | 1.2 | 1.2.8.5.6.3.6.1.3 | Not Started | PSL | Fuel System Upgrades and Repairs | MHP4: Fuel System Upgrades & Repairs - (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-17 | 2023-11-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1217 | 1.2 | 1.2.8.5.6.3.6.1.4 | Not Started | PSL | Exhaust System Upgrades and Repairs | MHP4: Exhaust System Upgrades & Repairs - (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-18 | 2023-11-19 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1218 | 1.2 | 1.2.8.5.6.3.6.1.5 | Not Started | PSL | MHP4 Subsystem Evaluation | MHP4: Subsystem Evaluation (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-26 | 2023-11-27 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1221 | 1.2 | 1.2.8.5.6.3.6.2.1 | Not Started | PSL | Install PLC-to-DGH Gateway in Network Box, Install M-DGHs, & Test | MHP4: Install PLC-to-DGH Gateway in Network Box, Install M-DGHs, & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-14 | 2023-11-15 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1222 | 1.2 | 1.2.8.5.6.3.6.2.2 | Not Started | PSL | Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) | MHP4: Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-23 | 2023-11-26 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1222 | 1.2 | 1.2.8.5.6.3.6.2.2 | Not Started | PSL | Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) | MHP4: Install Refurbished Heater Control Assemblies on All Heaters (M-DGHs pre-installed) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-23 | 2023-11-26 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1223 | 1.2 | 1.2.8.5.6.3.6.2.3 | Not Started | PSL | Replace Thermostats in Heaters & Test | MHP4: Replace Thermostats in Heaters & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-26 | 2023-11-28 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1224 | 1.2 | 1.2.8.5.6.3.6.2.4 | Not Started | PSL | Test E-stop and Heater Controls with No Water | MHP4: Test E-stop and Heater Controls with No Water (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-25 | 2023-11-27 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1225 | 1.2 | 1.2.8.5.6.3.6.2.5 | Not Started | PSL | Test Flow Sensor Operation with No Water | MHP4: Test Flow Sensor Operation with No Water (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-07 | 2023-12-08 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1226 | 1.2 | 1.2.8.5.6.3.6.2.6 | Not Started | PSL | Install Ethernet Switch, Connect to Network Box, Route Cable to DCC & Test | MHP4: Install Ethernet Switch, Connect to Network Box, Route Cable to DCC & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-27 | 2023-11-28 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1232 | 1.2 | 1.2.8.5.6.4.3.1 | Not Started | PSL | Heater Flush and Pressure Test | PHS: Heater Flush and Pressure Test (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-28 | 2023-11-29 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1232 | 1.2 | 1.2.8.5.6.4.3.1 | Not Started | PSL | Heater Flush and Pressure Test | PHS: Heater Flush and Pressure Test (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-28 | 2023-11-29 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | [10 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1233 | 1.2 | 1.2.8.5.6.4.3.2 | Not Started | PSL | Plumbing Upgrades & Repairs | PHS: Plumbing Upgrades & Repairs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-30 | 2023-11-30 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1233 | 1.2 | 1.2.8.5.6.4.3.2 | Not Started | PSL | Plumbing Upgrades & Repairs | PHS: Plumbing Upgrades & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-30 | 2023-11-30 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1234 | 1.2 | 1.2.8.5.6.4.3.3 | Not Started | PSL | Fuel System Upgrades & Repairs | PHS: Fuel System Upgrades and Repairs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-01 | 2023-12-01 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1234 | 1.2 | 1.2.8.5.6.4.3.3 | Not Started | PSL | Fuel System Upgrades & Repairs | PHS: Fuel System Upgrades and Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-01 | 2023-12-01 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1235 | 1.2 | 1.2.8.5.6.4.3.4 | Not Started | PSL | Exhaust System Upgrades & Repairs | PHS: Exhaust System Upgrades and Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-11-29 | 2023-11-29 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1236 | 1.2 | 1.2.8.5.6.4.3.5 | Not Started | PSL | Install Condensate System | PHS: Install Condensate System (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-01 | 2023-12-08 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1236 | 1.2 | 1.2.8.5.6.4.3.5 | Not Started | PSL | Install Condensate System | PHS: Install Condensate System (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-01 | 2023-12-08 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1237 | 1.2 | 1.2.8.5.6.4.3.6 | Not Started | PSL | Install Filtration System | PHS: Install Filtration System (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-01 | 2023-12-08 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1237 | 1.2 | 1.2.8.5.6.4.3.6 | Not Started | PSL | Install Filtration System | PHS: Install Filtration System (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-01 | 2023-12-08 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1238 | 1.2 | 1.2.8.5.6.4.3.7 | Not Started | PSL | PHS Subsystem Evaluation | PHS: Subsystem Evaluation (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-12 | 2023-12-12 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1241 | 1.2 | 1.2.8.5.6.4.4.1 | Not Started | PSL | Mount 4 Motor Drives, Connect AC Input and Output Leads | PHS: Mount 4 Motor Drives, Connect AC Input and Output Leads (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-28 | 2023-12-01 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | 20 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1241 | 1.2 | 1.2.8.5.6.4.4.1 | Not Started | PSL | Mount 4 Motor Drives, Connect AC Input and Output Leads | PHS: Mount 4 Motor Drives, Connect AC Input and Output Leads (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-11-28 | 2023-12-01 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | 9 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1242 | 1.2 | 1.2.8.5.6.4.4.2 | Not Started | PSL | Install New Motor-enable Relays in E-stop Box, Test with Motor Drives | PHS: Install New Motor-enable Relays in E-stop Box, Test with Motor Drives (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-04 | 2023-12-05 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1243 | 1.2 | 1.2.8.5.6.4.4.3 | Not Started | PSL | Install Refurbished Network Box and Heater M-DGHs, Connect Sensor Cables, & Test | PHS: Install Refurbished Network Box and Heater M-DGHs, Connect Sensor Cables, & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-04 | 2023-12-06 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1244 | 1.2 | 1.2.8.5.6.4.4.4 | Not Started | PSL | Replace Outdoor E-stop Slap Switch | PHS: Replace Outdoor E-stop Slap Switch (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-07 | 2023-12-07 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5 | [9 empty] | 5 | 0.033333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1.2.8
1245 | 1.2 | 1.2.8.5.6.4.4.5 | Not Started | PSL | Test Heater Controls | PHS: Test Heater Controls (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-06 | 2023-12-07 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1246 | 1.2 | 1.2.8.5.6.4.4.6 | Not Started | PSL | Connect and Test Tank Temperature and Level Sensors | PHS: Connect and Test Tank Temperature and Level Sensors (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-07 | 2023-12-11 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1247 | 1.2 | 1.2.8.5.6.4.4.7 | Not Started | PSL | Test Integrated Subsystem with Mobile HMI: Controls, Feedback, Operational Logic | PHS: Test Integrated Subsystem with Mobile HMI: Controls, Feedback, Operational Logic (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-08 | 2023-12-12 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1247 | 1.2 | 1.2.8.5.6.4.4.7 | Not Started | PSL | Test Integrated Subsystem with Mobile HMI: Controls, Feedback, Operational Logic | PHS: Test Integrated Subsystem with Mobile HMI: Controls, Feedback, Operational Logic (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-08 | 2023-12-12 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1248 | 1.2 | 1.2.8.5.6.4.4.8 | Not Started | PSL | Connect and Test Environmental Sensors (temperature, fire/smoke, flooding) | PHS: Connect and Test Environmental Sensors (temperature, fire/smoke, flooding) (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-08 | 2023-12-11 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1249 | 1.2 | 1.2.8.5.6.4.4.9 | Not Started | PSL | PHS Subsystem Evaluation | PHS Subsystem Evaluation (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-12 | 2023-12-12 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1255 | 1.2 | 1.2.8.5.6.5.3.1 | Not Started | PSL | Plumbing Upgrades & Repairs | HPP: Plumbing Upgrades & Repairs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2023-12-11 | 2023-12-12 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1255 | 1.2 | 1.2.8.5.6.5.3.1 | Not Started | PSL | Plumbing Upgrades & Repairs | HPP: Plumbing Upgrades & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-11 | 2023-12-12 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1256 | 1.2 | 1.2.8.5.6.5.3.2 | Not Started | PSL | Fuel System Upgrades and Repairs | HPP: Fuel System Upgrades and Repairs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-11 | 2023-12-11 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1257 | 1.2 | 1.2.8.5.6.5.3.3 | Not Started | PSL | Exhaust System Upgrades and Repairs | HPP: Exhaust System Upgrades and Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-12 | 2023-12-12 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1258 | 1.2 | 1.2.8.5.6.5.3.4 | Not Started | PSL | High Pressure Pump Upgrade & Repairs | HPP: High Pressure Pump Upgrade & Repairs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2023-12-13 | 2023-12-15 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1258 | 1.2 | 1.2.8.5.6.5.3.4 | Not Started | PSL | High Pressure Pump Upgrade & Repairs | HPP: High Pressure Pump Upgrade & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-13 | 2023-12-15 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1259 | 1.2 | 1.2.8.5.6.5.3.5 | Not Started | PSL | HPP Subsystem Evaluation | HPP: Subsystem Evaluation (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-18 | 2023-12-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1262 | 1.2 | 1.2.8.5.6.5.4.1 | Not Started | PSL | Mount 4 Motor Drives, Connect AC Input & Output Leads | HPP: Mount 4 motor drives, Connect AC Input & Output Leads (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-13 | 2023-12-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1262 | 1.2 | 1.2.8.5.6.5.4.1 | Not Started | PSL | Mount 4 Motor Drives, Connect AC Input & Output Leads | HPP: Mount 4 motor drives, Connect AC Input & Output Leads (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-13 | 2023-12-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1263 | 1.2 | 1.2.8.5.6.5.4.2 | Not Started | PSL | Test Motor Drive Connections to E-stop, Sensors, Air Dampers, Inlet Pressure Switches | HPP: Test Motor Drive Connections to E-stop, Sensors, Air Dampers, Inlet Pressure Switches (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-19 | 2023-12-20 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 16 | [9 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.8
1264 | 1.2 | 1.2.8.5.6.5.4.3 | Not Started | PSL | Install New PLC box in HPP, Connect to Network Box, Test with Mobile HMI | HPP: Install New PLC box in HPP, Connect to Network Box, Test with Mobile HMI (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-13 | 2023-12-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1265 | 1.2 | 1.2.8.5.6.5.4.4 | Not Started | PSL | Install 4 Refurbished Soft-Start Boxes in HPP, Connect to AC & New PLC Box | HPP: Install 4 Refurbished Soft-Start Boxes in HPP, Connect to AC & New PLC Box (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-19 | 2023-12-20 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1265 | 1.2 | 1.2.8.5.6.5.4.4 | Not Started | PSL | Install 4 Refurbished Soft-Start Boxes in HPP, Connect to AC & New PLC Box | HPP: Install 4 Refurbished Soft-Start Boxes in HPP, Connect to AC & New PLC Box (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-19 | 2023-12-20 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1266 | 1.2 | 1.2.8.5.6.5.4.5 | Not Started | PSL | Install Re-built Pressure and Flow Sensor Box in HPP & Test | HPP: Install Re-built Pressure and Flow Sensor Box in HPP & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-21 | 2023-12-22 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1266 | 1.2 | 1.2.8.5.6.5.4.5 | Not Started | PSL | Install Re-built Pressure and Flow Sensor Box in HPP & Test | HPP: Install Re-built Pressure and Flow Sensor Box in HPP & Test (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-21 | 2023-12-22 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1267 | 1.2 | 1.2.8.5.6.5.4.6 | Not Started | PSL | Install Rebuilt DGH box for Reading Pressure and Flow Sensors & Test | HPP: Install Rebuilt DGH box for Reading Pressure and Flow Sensors & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-21 | 2023-12-22 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1267 | 1.2 | 1.2.8.5.6.5.4.6 | Not Started | PSL | Install Rebuilt DGH box for Reading Pressure and Flow Sensors & Test | HPP: Install Rebuilt DGH box for Reading Pressure and Flow Sensors & Test (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-21 | 2023-12-22 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1268 | 1.2 | 1.2.8.5.6.5.4.7 | Not Started | PSL | Install New Motor-enable Relays in E-stop box, Test with Motor Drives | HPP: Install New Motor-enable Relays in E-stop box, Test with Motor Drives (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-26 | 2023-12-27 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1269 | 1.2 | 1.2.8.5.6.5.4.8 | Not Started | PSL | Install Refurbished Network box with M-DGHs, Connect Sensor Cables, & Test | HPP: Install Refurbished Network box with M-DGHs, Connect Sensor Cables, & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-26 | 2023-12-28 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1270 | 1.2 | 1.2.8.5.6.5.4.9 | Not Started | PSL | Test Integrated Subsystem with Mobile HMI: Controls, Feedback, & Operational Logic | HPP: Test Integrated Subsystem with Mobile HMI: Controls, Feedback, & Operational Logic (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-28 | 2024-01-04 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 20 | 25 | [8 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.8
1271 | 1.2 | 1.2.8.5.6.5.4.10 | Not Started | PSL | Connect and Test Environmental Sensors (temperature, fire/smoke, flooding) | HPP: Connect and Test Environmental Sensors (temperature, fire/smoke, flooding) (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-05 | 2024-01-08 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1272 | 1.2 | 1.2.8.5.6.5.4.11 | Not Started | PSL | Test Air-handling System in HPP | HPP: Test Air Handling System in HPP (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-26 | 2023-12-27 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1273 | 1.2 | 1.2.8.5.6.5.4.12 | Not Started | PSL | HPP Subsystem Evaluation | HPP: HPP Subsystem Evaluation (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-09 | 2024-01-09 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1278 | 1.2 | 1.2.8.5.6.6.2.1 | Not Started | PSL | Water Tank Modifications (Railings & Ladders) | Water Tanks: Water Tank Modifications (Railings, Ladders) (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-14 | 2023-12-19 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1279 | 1.2 | 1.2.8.5.6.6.2.2 | Not Started | PSL | Water Tanks Plumbing (Vert pumps, Sub. Pumps, Manifolds) | Water Tanks: Water Tanks Plumbing (Vert pumps, Sub. Pumps, Manifolds) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2023-12-18 | 2023-12-21 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1279 | 1.2 | 1.2.8.5.6.6.2.2 | Not Started | PSL | Water Tanks Plumbing (Vert pumps, Sub. Pumps, Manifolds) | Water Tanks: Water Tanks Plumbing (Vert pumps, Sub. Pumps, Manifolds) (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-18 | 2023-12-21 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1282 | 1.2 | 1.2.8.5.6.6.2.5 | Not Started | PSL | Water Tank Subsystem Evaluation | Water Tank: Subsystem Evaluation (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-21 | 2023-12-21 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1285 | 1.2 | 1.2.8.5.6.6.3.1 | Not Started | PSL | Sensor Updates and Wiring Evaluation | Water Tank: Sensor Updates and Wiring Evaluation (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-21 | 2023-12-21 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1290 | 1.2 | 1.2.8.5.6.7.2.1 | Not Started | PSL | Mate TOS1/Tower1 | Mate TOS1/Tower1: (ME) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-01 | 2023-12-02 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.8
1290 | 1.2 | 1.2.8.5.6.7.2.1 | Not Started | PSL | Mate TOS1/Tower1 | Mate TOS1/Tower1: (TE) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-01 | 2023-12-02 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5 | [9 empty] | 5 | 0.033333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1.2.8
1291 | 1.2 | 1.2.8.5.6.7.2.2 | Not Started | PSL | Mate TOS2/Tower2 | Mate TOS2/Tower2: (ME) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-01 | 2023-12-02 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.8
1291 | 1.2 | 1.2.8.5.6.7.2.2 | Not Started | PSL | Mate TOS2/Tower2 | Mate TOS2/Tower2:(TE) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-01 | 2023-12-02 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5 | [9 empty] | 5 | 0.033333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1.2.8
1292 | 1.2 | 1.2.8.5.6.7.2.3 | Not Started | PSL | Evaluate Structures & Inventory TOS2/Tower2 | TOS2/Tower2: Evaluate Structures & Inventory (ME) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-02 | 2023-12-04 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.8
1292 | 1.2 | 1.2.8.5.6.7.2.3 | Not Started | PSL | Evaluate Structures & Inventory TOS2/Tower2 | TOS2/Tower2: Evaluate Structures & Inventory (TE) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-02 | 2023-12-04 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1293 | 1.2 | 1.2.8.5.6.7.2.4 | Not Started | PSL | Evaluate Structures & Inventory TOS1/Tower1 | TOS1/Tower1: Evaluate Structures & Inventory (ME) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-04 | 2023-12-06 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.8
1293 | 1.2 | 1.2.8.5.6.7.2.4 | Not Started | PSL | Evaluate Structures & Inventory TOS1/Tower1 | TOS1/Tower1: Evaluate Structures & Inventory (TE) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-04 | 2023-12-06 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1294 | 1.2 | 1.2.8.5.6.7.2.5 | Not Started | PSL | Fuel and Exhaust System Upgrades and Repairs TOS1/Tower1 | TOS1/Tower1: Fuel and Exhaust System Repairs/Upgrades (ME) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-06 | 2023-12-07 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1294 | 1.2 | 1.2.8.5.6.7.2.5 | Not Started | PSL | Fuel and Exhaust System Upgrades and Repairs TOS1/Tower1 | TOS1/Tower1: Fuel and Exhaust System Repairs/Upgrades (TE) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-06 | 2023-12-07 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1295 | 1.2 | 1.2.8.5.6.7.2.6 | Not Started | PSL | Fuel and Exhaust System Upgrades and Repairs TOS2/Tower2 | TOS2/Tower2: Fuel and Exhaust System Repairs/Upgrades (ME) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-07 | 2023-12-08 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1295 | 1.2 | 1.2.8.5.6.7.2.6 | Not Started | PSL | Fuel and Exhaust System Upgrades and Repairs TOS2/Tower2 | TOS2/Tower2: Fuel and Exhaust System Repairs/Upgrades (TE) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-07 | 2023-12-08 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1296 | 1.2 | 1.2.8.5.6.7.2.7 | Not Started | PSL | Evaluate TOS/Tower Interconnects TOS2/Tower2 | TOS2/Tower2: Evaluate TOS/Tower Interconnects (ME) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-08 | 2023-12-09 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1296 | 1.2 | 1.2.8.5.6.7.2.7 | Not Started | PSL | Evaluate TOS/Tower Interconnects TOS2/Tower2 | TOS2/Tower2: Evaluate TOS/Tower Interconnects (TE) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-08 | 2023-12-09 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1297 | 1.2 | 1.2.8.5.6.7.2.8 | Not Started | PSL | Evaluate TOS/Tower Interconnects TOS1/Tower1 | TOS1/Tower1: Evaluate TOS/Tower Interconnects (ME) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-09 | 2023-12-10 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1297 | 1.2 | 1.2.8.5.6.7.2.8 | Not Started | PSL | Evaluate TOS/Tower Interconnects TOS1/Tower1 | TOS1/Tower1: Evaluate TOS/Tower Interconnects (TE) - TOS Team 1 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-09 | 2023-12-10 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1300 | 1.2 | 1.2.8.5.6.7.3.1 | Not Started | PSL | TOS1 - Install 8 Motor Drives, Connect AC Input & Output Leads, Connect to Network & I/O Boxes | TOS1/Tower1: Install 8 Motor Drives, Connect AC Input & Output Leads, Connect to Network & I/O Boxes (EE) - TOS Team 2 (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-02 | 2023-12-10 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | [9 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1300 | 1.2 | 1.2.8.5.6.7.3.1 | Not Started | PSL | TOS1 - Install 8 Motor Drives, Connect AC Input & Output Leads, Connect to Network & I/O Boxes | TOS1/Tower1: Install 8 Motor Drives, Connect AC Input & Output Leads, Connect to Network & I/O Boxes (ME) - TOS Team 2 (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-02 | 2023-12-10 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1301 | 1.2 | 1.2.8.5.6.7.3.2 | Not Started | PSL | TOS2 - Install 8 Motor Drives, Connect AC Input & Output Leads, Connect to Network & I/O Boxes | TOS2/Tower2: Install 8 Motor Drives, Connect AC Input & Output Leads, Connect to Network & I/O Boxes (EE) - TOS Team 2 (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-10 | 2023-12-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | [9 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1301 | 1.2 | 1.2.8.5.6.7.3.2 | Not Started | PSL | TOS2 - Install 8 Motor Drives, Connect AC Input & Output Leads, Connect to Network & I/O Boxes | TOS2/Tower2: Install 8 Motor Drives, Connect AC Input & Output Leads, Connect to Network & I/O Boxes (ME) - TOS Team 2 (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-10 | 2023-12-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1301 | 1.2 | 1.2.8.5.6.7.3.2 | Not Started | PSL | TOS2 - Install 8 Motor Drives, Connect AC Input & Output Leads, Connect to Network & I/O Boxes | TOS2/Tower2: Install 8 Motor Drives, Connect AC Input & Output Leads, Connect to Network & I/O Boxes (ME) - TOS Team 2 (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-10 | 2023-12-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1302 | 1.2 | 1.2.8.5.6.7.3.3 | Not Started | PSL | TOS2 - Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box | TOS2/Tower2: Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box (EE) - TOS Team 2 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-18 | 2023-12-22 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1302 | 1.2 | 1.2.8.5.6.7.3.3 | Not Started | PSL | TOS2 - Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box | TOS2/Tower2: Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box (ME) - TOS Team 2 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-18 | 2023-12-22 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1302 | 1.2 | 1.2.8.5.6.7.3.3 | Not Started | PSL | TOS2 - Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box | TOS2/Tower2: Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box (TE) - TOS Team 2 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-18 | 2023-12-22 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1303 | 1.2 | 1.2.8.5.6.7.3.4 | Not Started | PSL | TOS1 - Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box | TOS1/Tower1: Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box (EE) - TOS Team 2 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-22 | 2023-12-26 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1303 | 1.2 | 1.2.8.5.6.7.3.4 | Not Started | PSL | TOS1 - Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box | TOS1/Tower1: Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box (ME) - TOS Team 2 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-22 | 2023-12-26 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1303 | 1.2 | 1.2.8.5.6.7.3.4 | Not Started | PSL | TOS1 - Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box | TOS1/Tower1: Install and Test New Payout Encoders, Load Cells, and Connections to new PLC Box (TE) - TOS Team 2 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-22 | 2023-12-26 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1304 | 1.2 | 1.2.8.5.6.7.3.5 | Not Started | PSL | TOS2 - Install Missing TOS2 Line Filters for all Motor Drives (removed in 2010 by G.T.) | TOS2/Tower2: Install Missing TOS2 Line Filters for all Motor Drives (removed in 2010 by G.T.) (EE) TOS Team 2 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-27 | 2023-12-29 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1305 | 1.2 | 1.2.8.5.6.7.3.6 | Not Started | PSL | TOS2 - Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors | TOS2/Tower2: Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors (EE) TOS Team 2 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-29 | 2024-01-02 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | 18 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1305 | 1.2 | 1.2.8.5.6.7.3.6 | Not Started | PSL | TOS2 - Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors | TOS2/Tower2: Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors (ME) TOS Team 2 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-29 | 2024-01-02 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | 5 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1305 | 1.2 | 1.2.8.5.6.7.3.6 | Not Started | PSL | TOS2 - Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors | TOS2/Tower2: Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors (TE) TOS Team 2 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-29 | 2024-01-02 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 8 | 10 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1306 | 1.2 | 1.2.8.5.6.7.3.7 | Not Started | PSL | TOS1 - Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors | TOS1/Tower1: Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors (EE) TOS Team 2 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-02 | 2024-01-06 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1306 | 1.2 | 1.2.8.5.6.7.3.7 | Not Started | PSL | TOS1 - Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors | TOS1/Tower1: Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors (ME) TOS Team 2 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-02 | 2024-01-06 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1306 | 1.2 | 1.2.8.5.6.7.3.7 | Not Started | PSL | TOS1 - Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors | TOS1/Tower1: Test MCR Drives w/ SHR motors, Limit Switches, E/R-stops, Pendant and Sensors (TE) TOS Team 2 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-02 | 2024-01-06 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1307 | 1.2 | 1.2.8.5.6.7.3.8 | Not Started | PSL | TOS1 - Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors | TOS1/Tower1: Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors (EE) TOS Team 2 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-06 | 2024-01-10 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1307 | 1.2 | 1.2.8.5.6.7.3.8 | Not Started | PSL | TOS1 - Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors | TOS1/Tower1: Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors (ME) TOS Team 2 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-06 | 2024-01-10 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1307 | 1.2 | 1.2.8.5.6.7.3.8 | Not Started | PSL | TOS1 - Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors | TOS1/Tower1: Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors (TE) TOS Team 2 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-06 | 2024-01-10 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1308 | 1.2 | 1.2.8.5.6.7.3.9 | Not Started | PSL | TOS2 - Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors | TOS2/Tower2: Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors (EE) TOS Team 2 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-10 | 2024-01-14 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1308 | 1.2 | 1.2.8.5.6.7.3.9 | Not Started | PSL | TOS2 - Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors | TOS2/Tower2: Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors (ME) TOS Team 2 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-10 | 2024-01-14 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1308 | 1.2 | 1.2.8.5.6.7.3.9 | Not Started | PSL | TOS2 - Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors | TOS2/Tower2: Test MSHR Drives with SHR Motors, Limit Switches, E/R-stops, Pendant and Sensors (TE) TOS Team 2 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-10 | 2024-01-14 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1309 | 1.2 | 1.2.8.5.6.7.3.10 | Not Started | PSL | TOS2 - Test Return Water Pump Motor Drive | TOS2/Tower2: Test Return Water Pump Motor Drive TOS (EE) Team 2 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-14 | 2024-01-17 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1309 | 1.2 | 1.2.8.5.6.7.3.10 | Not Started | PSL | TOS2 - Test Return Water Pump Motor Drive | TOS2/Tower2: Test Return Water Pump Motor Drive TOS (ME) Team 2 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-14 | 2024-01-17 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1310 | 1.2 | 1.2.8.5.6.7.3.11 | Not Started | PSL | TOS1 - Test Return Water Pump Motor Drive | TOS1/Tower1: Test Return Water Pump Motor Drive TOS (EE) Team 2 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-17 | 2024-01-20 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1310 | 1.2 | 1.2.8.5.6.7.3.11 | Not Started | PSL | TOS1 - Test Return Water Pump Motor Drive | TOS1/Tower1: Test Return Water Pump Motor Drive TOS (ME) Team 2 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-17 | 2024-01-20 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1313 | 1.2 | 1.2.8.5.6.7.4.1 | Not Started | PSL | TOS2 - Install and Test Refurbished E-stop Box | TOS2/Tower2: Install and Test Refurbished E-stop Box (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-02 | 2023-12-05 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1314 | 1.2 | 1.2.8.5.6.7.4.2 | Not Started | PSL | TOS1 - Install and Test Refurbished E-stop Box | TOS1/Tower1: Install and Test Refurbished E-stop Box (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-05 | 2023-12-08 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1315 | 1.2 | 1.2.8.5.6.7.4.3 | Not Started | PSL | TOS1 - Install 4 Rebuilt I/O Boxes for Cable Reel, Hose Reel, & RW Hose Reel | TOS1/Tower1: Install 4 Rebuilt I/O Boxes for Cable Reel, Hose Reel, & RW Hose Reel (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-08 | 2023-12-12 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1316 | 1.2 | 1.2.8.5.6.7.4.4 | Not Started | PSL | TOS2 - Install 4 Rebuilt I/O Boxes for Cable Reel, Hose Reel, RW Hose Reel, & Tower Hoist Wiring | TOS2/Tower2: Install 4 Rebuilt I/O Boxes for Cable Reel, Hose Reel, RW Hose Reel, & Tower Hoist Wiring (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-12 | 2023-12-16 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1318 | 1.2 | 1.2.8.5.6.7.4.6 | Not Started | PSL | TOS1 - Install all Local Ethernet, E-stop, Fault Connections & Test | TOS2/Tower2: Install all Local Ethernet, E-stop, Fault Connections & Test (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-16 | 2023-12-20 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1319 | 1.2 | 1.2.8.5.6.7.4.7 | Not Started | PSL | TOS2 - Install all Local Ethernet, E-stop, Fault Connections & Test | TOS1/Tower1: Install all Local Ethernet, E-stop, Fault Connections & Test (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-20 | 2023-12-24 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1320 | 1.2 | 1.2.8.5.6.7.4.8 | Not Started | PSL | TOS1 - Install New DGH Gateway/Ethernet Switch/PLC box, Connect to Gen-1 Network Box | TOS1/Tower1: Install New DGH Gateway/Ethernet Switch/PLC box, Connect to Gen-1 Network Box (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-24 | 2023-12-26 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1321 | 1.2 | 1.2.8.5.6.7.4.9 | Not Started | PSL | TOS2 - Install New DGH Gateway/Ethernet Switch/PLC box, Connect to Gen-1 Network Box | TOS2/Tower2: Install New DGH Gateway/Ethernet Switch/PLC box, Connect to Gen-1 Network Box (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-26 | 2023-12-28 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1322 | 1.2 | 1.2.8.5.6.7.4.10 | Not Started | PSL | TOS2 - Test RWCR Motor, E & Reel Stops, Pendant and Sensors | TOS2/Tower2: Test RWCR Motor, E & Reel Stops, Pendant and Sensors (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-28 | 2023-12-30 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1322 | 1.2 | 1.2.8.5.6.7.4.10 | Not Started | PSL | TOS2 - Test RWCR Motor, E & Reel Stops, Pendant and Sensors | TOS2/Tower2: Test RWCR Motor, E & Reel Stops, Pendant and Sensors (ME) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-28 | 2023-12-30 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1323 | 1.2 | 1.2.8.5.6.7.4.11 | Not Started | PSL | TOS1 - Test RWCR Motor, E & Reel Stops, Pendant and Sensors | TOS1/Tower1: Test RWCR Motor, E & Reel Stops, Pendant and Sensors (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-30 | 2024-01-01 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | 9 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1323 | 1.2 | 1.2.8.5.6.7.4.11 | Not Started | PSL | TOS1 - Test RWCR Motor, E & Reel Stops, Pendant and Sensors | TOS1/Tower1: Test RWCR Motor, E & Reel Stops, Pendant and Sensors (ME) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-30 | 2024-01-01 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12 | 15 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1324 | 1.2 | 1.2.8.5.6.7.4.12 | Not Started | PSL | TOS1 - Test RWHR Motor, E & Reel Stops, Pendant and Sensors | TOS1/Tower1: Test RWHR Motor, E & Reel Stops, Pendant and Sensors (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-01 | 2024-01-03 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1324 | 1.2 | 1.2.8.5.6.7.4.12 | Not Started | PSL | TOS1 - Test RWHR Motor, E & Reel Stops, Pendant and Sensors | TOS1/Tower1: Test RWHR Motor, E & Reel Stops, Pendant and Sensors (ME) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-01 | 2024-01-03 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1325 | 1.2 | 1.2.8.5.6.7.4.13 | Not Started | PSL | TOS2 - Test RWHR Motor, E & Reel Stops, Pendant and Sensors | TOS2/Tower2: Test RWHR Motor, E & Reel Stops, Pendant and Sensors (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-03 | 2024-01-05 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1325 | 1.2 | 1.2.8.5.6.7.4.13 | Not Started | PSL | TOS2 - Test RWHR Motor, E & Reel Stops, Pendant and Sensors | TOS2/Tower2: Test RWHR Motor, E & Reel Stops, Pendant and Sensors (ME) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-03 | 2024-01-05 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1326 | 1.2 | 1.2.8.5.6.7.4.14 | Not Started | PSL | TOS2 - Install and Test Tower Hoist AC and Encoder Wiring (cut when hoist was removed for WISSARD) | TOS2/Tower2: Install and Test Tower Hoist AC and Encoder Wiring (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-05 | 2024-01-07 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1326 | 1.2 | 1.2.8.5.6.7.4.14 | Not Started | PSL | TOS2 - Install and Test Tower Hoist AC and Encoder Wiring (cut when hoist was removed for WISSARD) | TOS2/Tower2: Install and Test Tower Hoist AC and Encoder Wiring (TE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-05 | 2024-01-07 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1327 | 1.2 | 1.2.8.5.6.7.4.15 | Not Started | PSL | TOS2 - Test Tower Winch, E-stop, Reel Stop, Pendant, & Limit Switches | TOS1/Tower1: Test Tower Winch, E-stop, Reel Stop, Pendant, & Limit Switches (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-07 | 2024-01-09 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1327 | 1.2 | 1.2.8.5.6.7.4.15 | Not Started | PSL | TOS2 - Test Tower Winch, E-stop, Reel Stop, Pendant, & Limit Switches | TOS1/Tower1: Test Tower Winch, E-stop, Reel Stop, Pendant, & Limit Switches (TE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-07 | 2024-01-09 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1328 | 1.2 | 1.2.8.5.6.7.4.16 | Not Started | PSL | TOS1 - Test Tower Winch, E-stop, Reel Stop, Pendant, & Limit Switches | TOS2/Tower2: Test Tower Winch, E-stop, Reel Stop, Pendant, & Limit Switches (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-09 | 2024-01-11 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1328 | 1.2 | 1.2.8.5.6.7.4.16 | Not Started | PSL | TOS1 - Test Tower Winch, E-stop, Reel Stop, Pendant, & Limit Switches | TOS2/Tower2: Test Tower Winch, E-stop, Reel Stop, Pendant, & Limit Switches (TE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-09 | 2024-01-11 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1329 | 1.2 | 1.2.8.5.6.7.4.17 | Not Started | PSL | TOS2 - Test Integrated Subsystem with Mobile HMI: Controls, Feedback, Operational Logic | TOS2/Tower2: Test Integrated Subsystem with Mobile HMI: Controls, Feedback, Operational Logic (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-11 | 2024-01-15 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1330 | 1.2 | 1.2.8.5.6.7.4.18 | Not Started | PSL | TOS1 - Test Integrated Subsystem with Mobile HMI: Controls, Feedback, Operational Logic | TOS1/Tower1: Test Integrated Subsystem with Mobile HMI: Controls, Feedback, Operational Logic (EE) TOS Team 3 |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-15 | 2024-01-19 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1336 | 1.2 | 1.2.8.5.6.8.1.1 | Not Started | PSL | MSHR Relocation Support (USAP) | MSHR: Install Manifold, Heat Trace & Insulation (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-22 | 2023-12-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1336 | 1.2 | 1.2.8.5.6.8.1.1 | Not Started | PSL | MSHR Relocation Support (USAP) | MSHR: Install Manifold, Heat Trace & Insulation (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-22 | 2023-12-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1337 | 1.2 | 1.2.8.5.6.8.1.2 | Not Started | PSL | Install Manifold, Heat Trace & Insulation | MSHR: Inspect Drive and Control Components, Energize & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-11 | 2024-01-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1337 | 1.2 | 1.2.8.5.6.8.1.2 | Not Started | PSL | Install Manifold, Heat Trace & Insulation | MSHR: Inspect Drive and Control Components, Energize & Test (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-11 | 2024-01-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1342 | 1.2 | 1.2.8.5.6.8.2.2 | Not Started | PSL | Install Microbrake & Service Drum Brake and Gear Box | RWHR: Install Microbrake & Service Drum Brake and Gear Box (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-02 | 2024-01-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1343 | 1.2 | 1.2.8.5.6.8.2.3 | Not Started | PSL | Install Heat Trace & Insulation on Water Plumbing | RWHR: Install Heat Trace & Insulation on Water Plumbing (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-04 | 2024-01-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1344 | 1.2 | 1.2.8.5.6.8.2.4 | Not Started | PSL | Install Motor | RWHR: Install Motor & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-05 | 2024-01-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1345 | 1.2 | 1.2.8.5.6.8.2.5 | Not Started | PSL | Inspect Drive and Control Components, Energize & Test | RWHR: Inspect Drive and Control Components, Energize & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-09 | 2024-01-10 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1345 | 1.2 | 1.2.8.5.6.8.2.5 | Not Started | PSL | Inspect Drive and Control Components, Energize & Test | RWHR: Inspect Drive and Control Components, Energize & Test (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-09 | 2024-01-10 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1349 | 1.2 | 1.2.8.5.6.8.4.2 | Not Started | PSL | Install Slip Rings | RWCR: Install Slip Rings (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-02 | 2024-01-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1349 | 1.2 | 1.2.8.5.6.8.4.2 | Not Started | PSL | Install Slip Rings | RWCR: Install Slip Rings (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-02 | 2024-01-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1350 | 1.2 | 1.2.8.5.6.8.4.3 | Not Started | PSL | Inspect Drive and Control Components, Energize & Test | RWCR: Inspect Drive and Control Components, Energize & Test (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-05 | 2024-01-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1350 | 1.2 | 1.2.8.5.6.8.4.3 | Not Started | PSL | Inspect Drive and Control Components, Energize & Test | RWCR: Inspect Drive and Control Components, Energize & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-05 | 2024-01-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1354 | 1.2 | 1.2.8.5.6.8.5.2 | Not Started | PSL | Install Slip Ring | MCR: Install Slip Ring (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2023-12-26 | 2023-12-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 8 | [9 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.8
1354 | 1.2 | 1.2.8.5.6.8.5.2 | Not Started | PSL | Install Slip Ring | MCR: Install Slip Ring (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2023-12-26 | 2023-12-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.8
1355 | 1.2 | 1.2.8.5.6.8.5.3 | Not Started | PSL | Inspect Drive and Control Components, Energize & Test | MCR: Inspect Drive and Control Components, Energize & Test (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-08 | 2024-01-10 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1355 | 1.2 | 1.2.8.5.6.8.5.3 | Not Started | PSL | Inspect Drive and Control Components, Energize & Test | MCR: Inspect Drive and Control Components, Energize & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-08 | 2024-01-10 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1359 | 1.2 | 1.2.8.5.6.9.2 | Not Started | PSL | TU20 x 2 - Replace Hydraulic Pump & Upgrade Hydraulic Plumbing | Winches, Mechanical, TU20: Replace Hydraulic Pump & Upgrade Hydraulic Plumbing (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-09 | 2024-01-12 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1360 | 1.2 | 1.2.8.5.6.9.3 | Not Started | PSL | TU15 - Replace Hydraulic Pump & Upgrade Hydraulic Plumbing | Winches, Mechanical, TU15: Replace Hydraulic Pump & Upgrade Hydraulic Plumbing (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-15 | 2024-01-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1361 | 1.2 | 1.2.8.5.6.9.4 | Not Started | PSL | TU20 Test Brake/Control Interface Boxes w/ Brakes (FW rectifier and fuse) | Winches, Controls, TU20: Test Brake/Control Interface Boxes w/ Brakes (FW rectifier and fuse) (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-12 | 2024-01-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5 | [8 empty] | 5 | 0.033333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1.2.8
1362 | 1.2 | 1.2.8.5.6.9.5 | Not Started | PSL | TU20 - Install Slip Rings & Test | Winches, Controls, TU20: Install Slip Rings & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-12 | 2024-01-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1362 | 1.2 | 1.2.8.5.6.9.5 | Not Started | PSL | TU20 - Install Slip Rings & Test | Winches, Controls, TU20: Install Slip Rings & Test (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-12 | 2024-01-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1363 | 1.2 | 1.2.8.5.6.9.6 | Not Started | PSL | Inspect Drive and Control Components, Energize & Test | Winches - Controls: Inspect Drive and Control Components, Energize & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-12 | 2024-01-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8 | [8 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.8
1371 | 1.2 | 1.2.8.5.6.10.1.3 | Not Started | PSL | Install Sheave - Crane or Station Hoist | IFD: Install Sheave - Crane or Station Hoist (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-10 | 2024-01-11 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1371 | 1.2 | 1.2.8.5.6.10.1.3 | Not Started | PSL | Install Sheave - Crane or Station Hoist | IFD: Install Sheave - Crane or Station Hoist (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-10 | 2024-01-11 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1373 | 1.2 | 1.2.8.5.6.10.1.5 | Not Started | PSL | Install Brake Pump & Solenoid | IFD: Install Brake Pump & Solenoid (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-08 | 2024-01-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5 | [8 empty] | 5 | 0.033333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1.2.8
1374 | 1.2 | 1.2.8.5.6.10.1.6 | Not Started | PSL | Install DNF - Black box, Thermostats, Power Meter, & Inst. Readout | IFD: Install DNF - Black box, Thermostats, Power Meter, & Inst. Readout (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-08 | 2024-01-09 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1374 | 1.2 | 1.2.8.5.6.10.1.6 | Not Started | PSL | Install DNF - Black box, Thermostats, Power Meter, & Inst. Readout | IFD: Install DNF - Black box, Thermostats, Power Meter, & Inst. Readout (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-08 | 2024-01-09 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5 | [8 empty] | 5 | 0.033333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1.2.8
1375 | 1.2 | 1.2.8.5.6.10.1.7 | Not Started | PSL | Load Cell Calibration/Verification | IFD: Load Cell Integration (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-12 | 2024-01-12 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1375 | 1.2 | 1.2.8.5.6.10.1.7 | Not Started | PSL | Load Cell Calibration/Verification | IFD: Load Cell Integration (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-12 | 2024-01-12 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1377 | 1.2 | 1.2.8.5.6.10.1.9 | Not Started | PSL | Fill System w/ Glycol | IFD: Fill System w/ Glycol (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-08 | 2024-01-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1378 | 1.2 | 1.2.8.5.6.10.1.11 | Not Started | PSL | Test Firn Drill | IFD: Test Firn Drill (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-15 | 2024-01-17 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1378 | 1.2 | 1.2.8.5.6.10.1.11 | Not Started | PSL | Test Firn Drill | IFD: Test Firn Drill (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-15 | 2024-01-17 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1382 | 1.2 | 1.2.8.5.6.11.1 | Not Started | PSL | Deliver ARA Drill To Cryo Worksite - Precommission | ARA Drill: Deliver ARA Drill To Cryo Worksite - Precommission (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-01 | 2024-01-01 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1382 | 1.2 | 1.2.8.5.6.11.1 | Not Started | PSL | Deliver ARA Drill To Cryo Worksite - Precommission | ARA Drill: Deliver ARA Drill To Cryo Worksite - Precommission (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-01 | 2024-01-01 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1384 | 1.2 | 1.2.8.5.6.11.2.1 | Not Started | PSL | Warm-up, Inspect Gen, Fill fluids, Install Fire Extinguisher, & Test-run John Deere with External Load | ARA Drill: Warm-up, Inspect Gen, Fill fluids, Install Fire Extinguisher, & Test-run with External Load (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-02 | 2024-01-02 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1384 | 1.2 | 1.2.8.5.6.11.2.1 | Not Started | PSL | Warm-up, Inspect Gen, Fill fluids, Install Fire Extinguisher, & Test-run John Deere with External Load | ARA Drill: Warm-up, Inspect Gen, Fill fluids, Install Fire Extinguisher, & Test-run with External Load (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-02 | 2024-01-02 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1385 | 1.2 | 1.2.8.5.6.11.2.2 | Not Started | PSL | White Gen Electrical Rework | ARA Drill: White Gen Electrical Rework (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-02 | 2024-01-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1385 | 1.2 | 1.2.8.5.6.11.2.2 | Not Started | PSL | White Gen Electrical Rework | ARA Drill: White Gen Electrical Rework (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-02 | 2024-01-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1387 | 1.2 | 1.2.8.5.6.11.2.4 | Not Started | PSL | Install Control Interface Panel, Downhole Pump Controller, Ext. E-stop Slap, & Power up from Cryo | ARA Drill: Install Control Interface Panel, Downhole Pump Controller, Ext. E-stop Slap, & Power up from Cryo (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-04 | 2024-01-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1387 | 1.2 | 1.2.8.5.6.11.2.4 | Not Started | PSL | Install Control Interface Panel, Downhole Pump Controller, Ext. E-stop Slap, & Power up from Cryo | ARA Drill: Install Control Interface Panel, Downhole Pump Controller, Ext. E-stop Slap, & Power up from Cryo (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-04 | 2024-01-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1389 | 1.2 | 1.2.8.5.6.11.3.1 | Not Started | PSL | Warm-up & Inspect, Check HMW Sheets, & Tie-offs, Glycol Tank, Glycol Heater, Hoses & Connections | ARA Drill: Warm-up & Inspect, Check HMW Sheets, & Tie-offs, Glycol Tank, Glycol Heater, Hoses & Connections (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-03 | 2024-01-03 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1389 | 1.2 | 1.2.8.5.6.11.3.1 | Not Started | PSL | Warm-up & Inspect, Check HMW Sheets, & Tie-offs, Glycol Tank, Glycol Heater, Hoses & Connections | ARA Drill: Warm-up & Inspect, Check HMW Sheets, & Tie-offs, Glycol Tank, Glycol Heater, Hoses & Connections (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-03 | 2024-01-03 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1390 | 1.2 | 1.2.8.5.6.11.3.2 | Not Started | PSL | Install ePump, Accessories, & ePump Controller (DNF-requires power) | ARA Drill: Install ePump, Accessories, & ePump Controller (DNF-requires power) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-04 | 2024-01-04 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1390 | 1.2 | 1.2.8.5.6.11.3.2 | Not Started | PSL | Install ePump, Accessories, & ePump Controller (DNF-requires power) | ARA Drill: Install ePump, Accessories, & ePump Controller (DNF-requires power) (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-04 | 2024-01-04 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1391 | 1.2 | 1.2.8.5.6.11.3.3 | Not Started | PSL | Checkout & Testing Sled 2 | ARA Drill: Checkout & Testing Sled 2 (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-05 | 2024-01-05 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1391 | 1.2 | 1.2.8.5.6.11.3.3 | Not Started | PSL | Checkout & Testing Sled 2 | ARA Drill: Checkout & Testing Sled 2 (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-05 | 2024-01-05 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1393 | 1.2 | 1.2.8.5.6.11.4.1 | Not Started | PSL | Warm-up & Inspect Components, Install Stacks, Install Hoist, Top-off Fuel Tank, Reel Brake, Heat Trace | ARA Drill: Warm-up & Inspect Components, Install Stacks, Install Hoist, Top-off Fuel Tank, Reel Brake, Heat Trace (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-08 | 2024-01-09 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1393 | 1.2 | 1.2.8.5.6.11.4.1 | Not Started | PSL | Warm-up & Inspect Components, Install Stacks, Install Hoist, Top-off Fuel Tank, Reel Brake, Heat Trace | ARA Drill: Warm-up & Inspect Components, Install Stacks, Install Hoist, Top-off Fuel Tank, Reel Brake, Heat Trace (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-08 | 2024-01-09 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1394 | 1.2 | 1.2.8.5.6.11.4.2 | Not Started | PSL | Plumbing Upgrades & Repairs | ARA Drill: Plumbing Upgrades & Repairs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-10 | 2024-01-11 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1394 | 1.2 | 1.2.8.5.6.11.4.2 | Not Started | PSL | Plumbing Upgrades & Repairs | ARA Drill: Plumbing Upgrades & Repairs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-10 | 2024-01-11 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1395 | 1.2 | 1.2.8.5.6.11.4.3 | Not Started | PSL | ARA DCC Upgrades & Install | ARA Drill: ARA DCC Upgrades & Install (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-05 | 2024-01-08 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1395 | 1.2 | 1.2.8.5.6.11.4.3 | Not Started | PSL | ARA DCC Upgrades & Install | ARA Drill: ARA DCC Upgrades & Install (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-05 | 2024-01-08 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1396 | 1.2 | 1.2.8.5.6.11.4.4 | Not Started | PSL | Hose Cable Bundle Replace | ARA Drill: Hose Cable Bundle Replace (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-12 | 2024-01-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1396 | 1.2 | 1.2.8.5.6.11.4.4 | Not Started | PSL | Hose Cable Bundle Replace | ARA Drill: Hose Cable Bundle Replace (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-12 | 2024-01-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1396 | 1.2 | 1.2.8.5.6.11.4.4 | Not Started | PSL | Hose Cable Bundle Replace | ARA Drill: Hose Cable Bundle Replace (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-12 | 2024-01-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1398 | 1.2 | 1.2.8.5.6.11.5.1 | Not Started | PSL | Locate Components, Set-up Drillheads on Bench, Inspect, Sensor tests | ARA Drill: Locate Components, Set-up Drillheads on Bench, Inspect, Sensor tests (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-19 | 2024-01-19 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1398 | 1.2 | 1.2.8.5.6.11.5.1 | Not Started | PSL | Locate Components, Set-up Drillheads on Bench, Inspect, Sensor tests | ARA Drill: Locate Components, Set-up Drillheads on Bench, Inspect, Sensor tests (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-19 | 2024-01-19 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1399 | 1.2 | 1.2.8.5.6.11.5.2 | Not Started | PSL | Drillhead Chain Testing & Verification | ARA Drill: Drillhead Chain Testing & Verification (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-22 | 2024-01-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1399 | 1.2 | 1.2.8.5.6.11.5.2 | Not Started | PSL | Drillhead Chain Testing & Verification | ARA Drill: Drillhead Chain Testing & Verification (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-22 | 2024-01-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1401 | 1.2 | 1.2.8.5.6.11.6.1 | Not Started | PSL | System Commissioning Set-up Tasks & Global Tests | ARA Drill: System Commissioning Set-up Tasks & Global Tests (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-23 | 2024-01-23 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1401 | 1.2 | 1.2.8.5.6.11.6.1 | Not Started | PSL | System Commissioning Set-up Tasks & Global Tests | ARA Drill: System Commissioning Set-up Tasks & Global Tests (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-23 | 2024-01-23 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1402 | 1.2 | 1.2.8.5.6.11.6.2 | Not Started | PSL | Hose Reel Commissioning | ARA Drill: Hose Reel Commissioning (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-09 | 2024-01-10 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1402 | 1.2 | 1.2.8.5.6.11.6.2 | Not Started | PSL | Hose Reel Commissioning | ARA Drill: Hose Reel Commissioning (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-09 | 2024-01-10 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1403 | 1.2 | 1.2.8.5.6.11.6.3 | Not Started | PSL | Circulation Testing, w/ Glycol - Staged Approach | ARA Drill: Circulation Testing, w/ Glycol - Staged Approach (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-11 | 2024-01-11 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1403 | 1.2 | 1.2.8.5.6.11.6.3 | Not Started | PSL | Circulation Testing, w/ Glycol - Staged Approach | ARA Drill: Circulation Testing, w/ Glycol - Staged Approach (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-11 | 2024-01-11 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1404 | 1.2 | 1.2.8.5.6.11.6.4 | Not Started | PSL | Heater Commissioning | ARA Drill: Heater Commissioning (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-12 | 2024-01-12 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1404 | 1.2 | 1.2.8.5.6.11.6.4 | Not Started | PSL | Heater Commissioning | ARA Drill: Heater Commissioning (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-01-12 | 2024-01-12 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1405 | 1.2 | 1.2.8.5.6.11.6.5 | Not Started | PSL | Global Controls & E-stop Testing | ARA Drill: Global Controls & E-stop Testing (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-11 | 2024-01-11 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1405 | 1.2 | 1.2.8.5.6.11.6.5 | Not Started | PSL | Global Controls & E-stop Testing | ARA Drill: Global Controls & E-stop Testing (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-11 | 2024-01-11 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1406 | 1.2 | 1.2.8.5.6.11.6.6 | Not Started | PSL | System Testing in Test Well | ARA Drill: System Testing in Test Well (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-15 | 2024-01-15 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1406 | 1.2 | 1.2.8.5.6.11.6.6 | Not Started | PSL | System Testing in Test Well | ARA Drill: System Testing in Test Well (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-15 | 2024-01-15 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1408 | 1.2 | 1.2.8.5.6.11.7.1 | Not Started | PSL | Drain & Blow-out System | ARA Drill: Drain & Blow-out System (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-16 | 2024-01-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1408 | 1.2 | 1.2.8.5.6.11.7.1 | Not Started | PSL | Drain & Blow-out System | ARA Drill: Drain & Blow-out System (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-16 | 2024-01-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1409 | 1.2 | 1.2.8.5.6.11.7.2 | Not Started | PSL | Remove and Store DNF Hardware | ARA Drill: Remove and Store DNF Hardware (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-17 | 2024-01-17 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1409 | 1.2 | 1.2.8.5.6.11.7.2 | Not Started | PSL | Remove and Store DNF Hardware | ARA Drill: Remove and Store DNF Hardware (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-17 | 2024-01-17 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1410 | 1.2 | 1.2.8.5.6.11.7.3 | Not Started | PSL | Tarp, Cover, & Plug | ARA Drill: Tarp, Cover, & Plug (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-01-18 | 2024-01-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1410 | 1.2 | 1.2.8.5.6.11.7.3 | Not Started | PSL | Tarp, Cover, & Plug | ARA Drill: Tarp, Cover, & Plug (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-18 | 2024-01-18 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1413 | 1.2 | 1.2.8.5.6.12.2 | Not Started | PSL | Mechanical Repairs & Upgrades | Fuel Tower: Mechanical Repairs & Upgrades (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-01 | 2023-12-04 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1414 | 1.2 | 1.2.8.5.6.12.3 | Not Started | PSL | Test Existing Local Hardware, Control Functionality, Document | Fuel Tower: Test Existing Local Hardware, Control Functionality, document (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2023-12-07 | 2023-12-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1414 | 1.2 | 1.2.8.5.6.12.3 | Not Started | PSL | Test Existing Local Hardware, Control Functionality, Document | Fuel Tower: Test Existing Local Hardware, Control Functionality, document (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-07 | 2023-12-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1419 | 1.2 | 1.2.8.5.6.13.2 | Not Started | PSL | Initial Evaluation & Refit (HPU2) | HPU2: Initial Evaluation & Refit (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-18 | 2024-01-31 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1419 | 1.2 | 1.2.8.5.6.13.2 | Not Started | PSL | Initial Evaluation & Refit (HPU2) | HPU2: Initial Evaluation & Refit (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-18 | 2024-01-31 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1423 | 1.2 | 1.2.8.5.7.1.2 | Not Started | PSL | Driller Support for MHP Relocation (Driller) | SES: Drillers Support for SES Layout (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-19 | 2023-12-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1436 | 1.2 | 1.2.8.5.7.2 | Not Started | PSL | Provide Temp Small Temp Generator for SES and Establish (USAP) | SES: Establish Temp Power for SES (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2023-12-12 | 2023-12-12 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1438 | 1.2 | 1.2.8.5.7.3.1 | Not Started | PSL | Cable Trays - Mount/Install | Interconnects: Cable Trays - Mount/Install (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-12 | 2024-01-17 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1438 | 1.2 | 1.2.8.5.7.3.1 | Not Started | PSL | Cable Trays - Mount/Install | Interconnects: Cable Trays - Mount/Install (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-12 | 2024-01-17 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1439 | 1.2 | 1.2.8.5.7.3.2 | Not Started | PSL | Hoses - Layout, Inventory, Repair & Test | Interconnects: Hoses - Layout, Inventory, Repair & Test (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-12 | 2024-01-17 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1439 | 1.2 | 1.2.8.5.7.3.2 | Not Started | PSL | Hoses - Layout, Inventory, Repair & Test | Interconnects: Hoses - Layout, Inventory, Repair & Test (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-12 | 2024-01-17 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1439 | 1.2 | 1.2.8.5.7.3.2 | Not Started | PSL | Hoses - Layout, Inventory, Repair & Test | Interconnects: Cables - Layout, Inventory, Repair & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-12 | 2024-01-17 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1439 | 1.2 | 1.2.8.5.7.3.2 | Not Started | PSL | Hoses - Layout, Inventory, Repair & Test | Interconnects: Cables - Layout, Inventory, Repair & Test (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-12 | 2024-01-17 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1441 | 1.2 | 1.2.8.5.7.4 | Not Started | PSL | Establish Fuel Tower at SES | SES: Establish Fuel Tower at SES (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-12 | 2024-01-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1444 | 1.2 | 1.2.8.5.8.1 | Not Started | PSL | Document, Photograph Equip & Upgrade Work, Further Req's | Close-out: Document, Photograph Equip & Upgrade Work, Further Req's (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-23 | 2024-01-26 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 60 | [8 empty] | 60 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1.2.8
1444 | 1.2 | 1.2.8.5.8.1 | Not Started | PSL | Document, Photograph Equip & Upgrade Work, Further Req's | Close-out: Document, Photograph Equip & Upgrade Work, Further Req's (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-23 | 2024-01-26 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 60 | [8 empty] | 60 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1.2.8
1445 | 1.2 | 1.2.8.5.8.2 | Not Started | PSL | Remove DNF (Computer Equip, Drives, & Capacitors) & Store | Close-out: Remove DNF (Computer Equip, Drives, Capacitors) & Store (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-22 | 2024-01-25 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16 | [8 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.8
1445 | 1.2 | 1.2.8.5.8.2 | Not Started | PSL | Remove DNF (Computer Equip, Drives, & Capacitors) & Store | Close-out: Remove DNF (Computer Equip, Drives, Capacitors) & Store (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-22 | 2024-01-25 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16 | [8 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.8
1446 | 1.2 | 1.2.8.5.8.3 | Not Started | PSL | Winterize/Close/Store all EHWD Equipment | Close-out: Winterize/Close/Store all EHWD Equipment (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-24 | 2024-01-28 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 84 | [8 empty] | 84 | 0.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 1.2.8
1447 | 1.2 | 1.2.8.5.8.4 | Not Started | PSL | Setup & Connect Hose Heating Controller, test over FS1-FS2 winter | Close-out: Setup and Connect Hose Heating Controller, Test over FS1-FS2 Winter (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-01-24 | 2024-01-25 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1447 | 1.2 | 1.2.8.5.8.4 | Not Started | PSL | Setup & Connect Hose Heating Controller, test over FS1-FS2 winter | Close-out: Setup and Connect Hose Heating Controller, Test over FS1-FS2 Winter (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-24 | 2024-01-25 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1448 | 1.2 | 1.2.8.5.8.5 | Not Started | PSL | Crate, Pack and Deliver Retro to Cargo | Close-out: Retro all Components, Crate, Pack and Deliver to Cargo (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-01-17 | 2024-01-25 | 0% | On Ice |  | TRUE | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.8
1459 | 1.2 | 1.2.8.5.11 | Not Started | PSL | On-Ice Labor (FS1) | On-Ice Labor (FS1) (PSL Engineers) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 85.1852 | 115 | 0% | 2023-06-02 | 2024-02-29 | 0% | On Ice | C2 |  |  |  |  | EE/ME Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 0 days northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1044 | 1818 | 1728 | [8 empty] | 4590 | 30.6 | 0 | 92798.5761 | 161597.5205 | 153597.6432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407993.7398 | 0 | 407993.7398 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407993.7398 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 407993.7398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4590 | 1.2.8
1459 | 1.2 | 1.2.8.5.11 | Not Started | PSL | On-Ice Labor (FS1) | On-Ice Labor (FS1) (PSL Contract Drillers) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 57.037 | 77 | 0% | 2023-06-02 | 2024-02-29 | 0% | On Ice | C2 |  |  |  |  | Technician Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 0 days northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 279 | 549 | 648 | [8 empty] | 1476 | 9.84 | 0 | 16604.9626 | 32674.2813 | 38566.3648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87845.6086 | 0 | 87845.6086 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87845.6086 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 87845.6086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1476 | 1.2.8
1459 | 1.2 | 1.2.8.5.11 | Not Started | UW | On-Ice Labor (FS1) | On-Ice Labor (FS1) (Safety Engineer) | Zernick | 0% | Labor Hours | Labor - Task | EN-S |  |  | D - Expert Opinion | 44.96 | 46 | 35% | 2023-06-02 | 2024-02-29 | 53% | On Ice | C1 |  |  |  |  | Safety Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 0 days northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 162 | 135 | [9 empty] | 297 | 1.98 | 0 | 10260.1055 | 8550.0879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18810.1935 | 9969.4025 | 28779.596 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28779.596 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 13933.4766 | 0 | 0 | 0 | 0 | 4876.7168 | 0 | 0 | 297 | 1.2.8
1468 | 1.2 | 1.2.8.6.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (Driller_PSL_Manager) |  | 0% | Labor Hours | Labor - Task | EN |  |  | E - Extrapolation from Actuals | 115 | 115 | 0 | 2024-07-01 | 2025-02-07 | 0% | Off Ice | C1 |  |  |  |  | 1 Drill Manager, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0.42667 | 0 | 4903.1248 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7844.9996 | 0 | 7844.9996 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7844.9996 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 7844.9996 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 1.2.8
1468 | 1.2 | 1.2.8.6.2 | Not Started | UW | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (Safety_Engineer) | Zernick | 0% | Labor Hours | Labor - Task | EN-S |  |  | E - Extrapolation from Actuals | 60.69 | 46 | 35% | 2024-07-01 | 2025-02-07 | 53% | Off Ice | C1 |  |  |  |  | 1 Safety Engineer, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0.42667 | 0 | 3493.2206 | 0 | 0 | 2095.9323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5589.1529 | 2962.2511 | 8551.404 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8551.404 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 4140.1133 | 0 | 0 | 0 | 0 | 1449.0396 | 0 | 64 | 1.2.8
1468 | 1.2 | 1.2.8.6.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (PSL_Direct_Hire) |  | 0% | Labor Hours | Labor - Task | TE |  |  | E - Extrapolation from Actuals | 77 | 77 | 0% | 2024-07-01 | 2025-02-07 | 0% | Off Ice | C1 |  |  |  |  | 6 PSL Direct Hire, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 240 |  |  | 144 | [7 empty] | 384 | 2.56 | 0 | 19697.7708 | 0 | 0 | 11818.6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31516.4333 | 0 | 31516.4333 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31516.4333 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 31516.4333 | 0 | 0 | 0 | 0 | 0 | 0 | 384 | 1.2.8
1468 | 1.2 | 1.2.8.6.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (PSL_Engineer) |  | 0% | Labor Hours | Labor - Task | EN |  |  | E - Extrapolation from Actuals | 115 | 115 | 0% | 2024-07-01 | 2025-02-07 | 0% | Off Ice | C1 |  |  |  |  | 9 PSL Engineers w/ 2 Rotators, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 280 | 128 |  | 168 | [7 empty] | 576 | 3.84 | 0 | 34321.8734 | 15689.9993 | 0 | 20593.124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70604.9966 | 0 | 70604.9966 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70604.9966 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 70604.9966 | 0 | 0 | 0 | 0 | 0 | 0 | 576 | 1.2.8
1468 | 1.2 | 1.2.8.6.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (Drill Team) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2024-07-01 | 2025-02-07 | 53% | Off Ice | C1 |  |  |  |  | 19 - PQ's @ $950/each (anticipated cost) - 2 Alternates and 17 Primaries | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 9025 | 9025 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9417.2468 | 9417.2468 | 0 | 18834.4936 | 9982.2816 | 28816.7752 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28816.7752 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
1468 | 1.2 | 1.2.8.6.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (Drill Team) | Foreign |  | Travel | Travel |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2024-07-01 | 2025-02-07 | 53% | Off Ice | C1 |  |  |  |  | 17 - Deploy travel costs w/ 2 PSL rotator @ $1800 each | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 15300 | 15300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15964.9724 | 15964.9724 | 31929.9448 | 16922.8708 | 48852.8156 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48852.8156 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
1498 | 1.2 | 1.2.8.6.4.6 | Not Started | PSL | Excavate ICL Storage Site & Deliver TOS1/2, DCC, & MSHR to SES (USAP) | SES: Site Snow Removal SES Digout (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-14 | 2024-11-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | [10 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1498 | 1.2 | 1.2.8.6.4.6 | Not Started | PSL | Excavate ICL Storage Site & Deliver TOS1/2, DCC, & MSHR to SES (USAP) | SES: Site Snow Removal SES Digout (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-14 | 2024-11-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 45 | [10 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.8
1510 | 1.2 | 1.2.8.6.4.18 | Not Started | PSL | Supply local fuel tanks for both TOSes (2x) and keep filled throughout (USAP) --> Change duration | SES: Fuel Tower: Connect, Test and Make Ready (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-15 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1510 | 1.2 | 1.2.8.6.4.18 | Not Started | PSL | Supply local fuel tanks for both TOSes (2x) and keep filled throughout (USAP) --> Change duration | SES: Fuel Tower: Connect, Test and Make Ready (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-15 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1499 | 1.2 | 1.2.8.6.4.7 | Not Started | PSL | Driller Support for SES Digout | SES: Make Ready all SES Modules (DCC, PHS, MHPs, MECC, WTs, All) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-15 | 2024-11-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1499 | 1.2 | 1.2.8.6.4.7 | Not Started | PSL | Driller Support for SES Digout | SES: Make Ready all SES Modules (DCC, PHS, MHPs, MECC, WTs, All) (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-15 | 2024-11-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1500 | 1.2 | 1.2.8.6.4.8 | Not Started | PSL | Built Ramp to Water Tank 1 (USAP) | SES: Complete Interconnects (DCC, PHS, MHPs, MECC, WTs, Gens, & PDMs) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-16 | 2024-11-19 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1500 | 1.2 | 1.2.8.6.4.8 | Not Started | PSL | Built Ramp to Water Tank 1 (USAP) | SES: Complete Interconnects (DCC, PHS, MHPs, MECC, WTs, Gens, & PDMs) (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-16 | 2024-11-19 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1510 | 1.2 | 1.2.8.6.4.18 | Not Started | PSL | Supply local fuel tanks for both TOSes (2x) and keep filled throughout (USAP) --> Change duration | SES: Furnace Checkout & Fire Up (All modules) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-15 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1510 | 1.2 | 1.2.8.6.4.18 | Not Started | PSL | Supply local fuel tanks for both TOSes (2x) and keep filled throughout (USAP) --> Change duration | SES: Furnace Checkout & Fire Up (All modules) (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-15 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1511 | 1.2 | 1.2.8.6.4.19 | Not Started | PSL | Fuel Tanks Connection Support (USAP) | SES: Perform Emergency Incident Drill & Safety Training (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-15 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | [9 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1511 | 1.2 | 1.2.8.6.4.19 | Not Started | PSL | Fuel Tanks Connection Support (USAP) | SES: Perform Emergency Incident Drill & Safety Training (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-15 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | [9 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1511 | 1.2 | 1.2.8.6.4.19 | Not Started | PSL | Fuel Tanks Connection Support (USAP) | SES: Perform Emergency Incident Drill & Safety Training (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-15 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 108 | [9 empty] | 108 | 0.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 1.2.8
1514 | 1.2 | 1.2.8.6.5.1 | Not Started | PSL | SES Maintenance Activities - Season-long Driller Support | SES: Maintenance Activities (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-15 | 2025-01-31 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 27 | [9 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.8
1514 | 1.2 | 1.2.8.6.5.1 | Not Started | PSL | SES Maintenance Activities - Season-long Driller Support | SES: Maintenance Activities (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-15 | 2025-01-31 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 54 | 54 | [8 empty] | 126 | 0.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 1.2.8
1528 | 1.2 | 1.2.8.6.6.5 | Not Started | PSL | Connect Fuel Hoses & Prime Gens 1-3 (Driller & USAP) | Generators/PDM: Connect Fuel Hoses & Prime Gens 1-3 (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-21 | 2024-11-23 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1528 | 1.2 | 1.2.8.6.6.5 | Not Started | PSL | Connect Fuel Hoses & Prime Gens 1-3 (Driller & USAP) | Generators/PDM: Connect Fuel Hoses & Prime Gens 1-3 (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-21 | 2024-11-23 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1529 | 1.2 | 1.2.8.6.6.6 | Not Started | PSL | Generators & PDM - Pre-operational Checks | Generators/PDM: Generators & PDM - Pre-operational Checks (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-21 | 2024-11-23 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1529 | 1.2 | 1.2.8.6.6.6 | Not Started | PSL | Generators & PDM - Pre-operational Checks | Generators/PDM: Generators & PDM - Pre-operational Checks (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-21 | 2024-11-23 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1531 | 1.2 | 1.2.8.6.6.8 | Not Started | PSL | Ready & Start-up Gen1, Gen 2, & Gen3 (Driller & USAP) | Ready & Start-up Gen1, Gen 2, & Gen3 (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-23 | 2024-11-25 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1531 | 1.2 | 1.2.8.6.6.8 | Not Started | PSL | Ready & Start-up Gen1, Gen 2, & Gen3 (Driller & USAP) | Ready & Start-up Gen1, Gen 2, & Gen3 (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-23 | 2024-11-25 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1532 | 1.2 | 1.2.8.6.6.9 | Not Started | PSL | Parallel Gens through PDM Bays (Driller & Contract Gen Tech) | Generators/PDM: Parallel Gens through PDM Bays (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-25 | 2024-11-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1532 | 1.2 | 1.2.8.6.6.9 | Not Started | PSL | Parallel Gens through PDM Bays (Driller & Contract Gen Tech) | Generators/PDM: Parallel Gens through PDM Bays (Contract Gen Tech) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2024-11-25 | 2024-11-28 | 53% | On Ice | C3 |  |  |  |  | Estimated 18 days of contractor cost @ $250 per hour 9 hour days plus travel & PQ allowance of $1200 for a total of $41,700 or $5957 for each of the 7 days of work at the Pole. | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13900 | [12 empty] | 0 | 14815.964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14815.964 | 0 | 14815.964 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14815.964 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
1533 | 1.2 | 1.2.8.6.6.10 | Not Started | PSL | Load Test using Resistance Heaters (Driller & Contract Gen Tech) | Generators/PDM: Load Test using Resistance Heaters (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-29 | 2024-12-01 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1533 | 1.2 | 1.2.8.6.6.10 | Not Started | PSL | Load Test using Resistance Heaters (Driller & Contract Gen Tech) | Generators/PDM: Load Test using Resistance Heaters (Contract Gen Tech) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2024-11-29 | 2024-12-01 | 53% | On Ice | C3 |  |  |  |  | Estimated 18 days of contractor cost @ $250 per hour 9 hour days plus travel & PQ allowance of $1200 for a total of $41,700 or $5957 for each of the 7 days of work at the Pole. | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13900 | [12 empty] | 0 | 14815.964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14815.964 | 0 | 14815.964 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14815.964 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
1534 | 1.2 | 1.2.8.6.6.11 | Not Started | PSL | Test Safety Shut-downs (Driller & Contract Gen Tech) | Generators/PDM: Test Safety Shut-downs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-01 | 2024-12-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1534 | 1.2 | 1.2.8.6.6.11 | Not Started | PSL | Test Safety Shut-downs (Driller & Contract Gen Tech) | Generators/PDM: Test Safety Shut-downs (Contract Gen Tech) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2024-12-01 | 2024-12-03 | 53% | On Ice | C3 |  |  |  |  | Estimated 18 days of contractor cost @ $250 per hour 9 hour days plus travel & PQ allowance of $1200 for a total of $41,700 or $5957 for each of the 7 days of work at the Pole. | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 13900 | [11 empty] | 0 | 0 | 14815.964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14815.964 | 0 | 14815.964 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14815.964 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
1536 | 1.2 | 1.2.8.6.6.13 | Not Started | PSL | Integrate and test new generator and PDM controls/point I/O | Generator/PDM: Integrate and Test New Generator and PDM controls/point I/O) (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-03 | 2024-12-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1536 | 1.2 | 1.2.8.6.6.13 | Not Started | PSL | Integrate and test new generator and PDM controls/point I/O | Generator/PDM: Integrate and Test New Generator and PDM controls/point I/O) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-03 | 2024-12-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1536 | 1.2 | 1.2.8.6.6.13 | Not Started | PSL | Integrate and test new generator and PDM controls/point I/O | Generator/PDM: Integrate and Test New Generator and PDM controls/point I/O) (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-12-03 | 2024-12-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1537 | 1.2 | 1.2.8.6.6.14 | Not Started | PSL | Scheduled Preventive Maintenance (Driller & USAP) | Generator/PDM: Scheduled Preventive Maintenance (Driller & USAP) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-12 | 2025-01-01 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | 18 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1538 | 1.2 | 1.2.8.6.6.15 | Not Started | PSL | Winterize Gen Modules and PDM (Driller & USAP) | Generator/PDM: Winterize (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-01-26 | 2025-01-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1538 | 1.2 | 1.2.8.6.6.15 | Not Started | PSL | Winterize Gen Modules and PDM (Driller & USAP) | Generator/PDM: Winterize (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-01-26 | 2025-01-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1541 | 1.2 | 1.2.8.6.7.1.1 | Not Started | PSL | Relocate DCC to Cryo & Power-up (USAP) | DCC: Relocate DCC to SES, Position & Power Up (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-11-12 | 2024-11-12 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1542 | 1.2 | 1.2.8.6.7.1.2 | Not Started | PSL | Electrical Closet Rework (USAP) | DCC: Electrical Closet Rework (Electrician) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-13 | 2024-11-14 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1543 | 1.2 | 1.2.8.6.7.1.3 | Not Started | PSL | Install New Fuel Day Tank System Controls | DCC: Install New Fuel Day Tank System Controls (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-15 | 2024-11-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1543 | 1.2 | 1.2.8.6.7.1.3 | Not Started | PSL | Install New Fuel Day Tank System Controls | DCC: Install New Fuel Day Tank System Controls (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-11-15 | 2024-11-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1544 | 1.2 | 1.2.8.6.7.1.4 | Not Started | PSL | Install and Wire 2x Motor Drives for WT1 VT Pumps | DCC: Install and Wire 2x Motor Drives for WT1 VT Pumps (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-18 | 2024-11-18 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1544 | 1.2 | 1.2.8.6.7.1.4 | Not Started | PSL | Install and Wire 2x Motor Drives for WT1 VT Pumps | DCC: Install and Wire 2x Motor Drives for WT1 VT Pumps (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-11-18 | 2024-11-18 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1545 | 1.2 | 1.2.8.6.7.1.5 | Not Started | PSL | Install New E-Stop Controller Equipment | DCC: Install New E-Stop Controller Equipment (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-19 | 2024-11-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1545 | 1.2 | 1.2.8.6.7.1.5 | Not Started | PSL | Install New E-Stop Controller Equipment | DCC: Install New E-Stop Controller Equipment (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-19 | 2024-11-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1546 | 1.2 | 1.2.8.6.7.1.6 | Not Started | PSL | Install Racks & Computing Equipment | DCC: Install Racks & Computing Equipment (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-21 | 2024-11-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1546 | 1.2 | 1.2.8.6.7.1.6 | Not Started | PSL | Install Racks & Computing Equipment | DCC: Install Racks & Computing Equipment (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-21 | 2024-11-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1546 | 1.2 | 1.2.8.6.7.1.6 | Not Started | PSL | Install Racks & Computing Equipment | DCC: Install Racks & Computing Equipment (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-11-21 | 2024-11-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1547 | 1.2 | 1.2.8.6.7.1.7 | Not Started | PSL | Install Core PLC System in DCC | DCC: Install Core PLC System in DCC (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-25 | 2024-11-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | [10 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1547 | 1.2 | 1.2.8.6.7.1.7 | Not Started | PSL | Install Core PLC System in DCC | DCC: Install Core PLC System in DCC (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-25 | 2024-11-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1547 | 1.2 | 1.2.8.6.7.1.7 | Not Started | PSL | Install Core PLC System in DCC | DCC: Install Core PLC System in DCC (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-11-25 | 2024-11-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1548 | 1.2 | 1.2.8.6.7.1.8 | Not Started | PSL | Connect and Configure Hub and Spoke Elements, including Motor Drives | DCC: Connect & Configure Hub & Spoke Elements, including Motor Drives (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-27 | 2024-11-29 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | [10 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1548 | 1.2 | 1.2.8.6.7.1.8 | Not Started | PSL | Connect and Configure Hub and Spoke Elements, including Motor Drives | DCC: Connect & Configure Hub & Spoke Elements, including Motor Drives (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-27 | 2024-11-29 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1548 | 1.2 | 1.2.8.6.7.1.8 | Not Started | PSL | Connect and Configure Hub and Spoke Elements, including Motor Drives | DCC: Connect & Configure Hub & Spoke Elements, including Motor Drives (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-11-27 | 2024-11-29 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1550 | 1.2 | 1.2.8.6.7.1.10 | Not Started | PSL | Install and Commission Latest Software, SCADA, and Database | DCC: Install & Commission Latest Software, SCADA, and Database (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-02 | 2024-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1551 | 1.2 | 1.2.8.6.7.1.11 | Not Started | PSL | QA on Controls By SES Subsystem - Wet System | DCC: QA on Controls by Subsystem (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-19 | 2025-01-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | 9 | [8 empty] | 81 | 0.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 1.2.8
1551 | 1.2 | 1.2.8.6.7.1.11 | Not Started | PSL | QA on Controls By SES Subsystem - Wet System | DCC: QA on Controls by Subsystem (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-19 | 2025-01-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | 9 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1551 | 1.2 | 1.2.8.6.7.1.11 | Not Started | PSL | QA on Controls By SES Subsystem - Wet System | DCC: QA on Controls by Subsystem (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-12-19 | 2025-01-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | 18 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1555 | 1.2 | 1.2.8.6.7.2.1.1 | Not Started | PSL | Final Upgrade & Replacement Activities | MHP (Mechanical Refit): Final Upgrade & Replacement Activities (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1555 | 1.2 | 1.2.8.6.7.2.1.1 | Not Started | PSL | Final Upgrade & Replacement Activities | MHP (Mechanical Refit): Final Upgrade & Replacement Activities (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1556 | 1.2 | 1.2.8.6.7.2.1.2 | Not Started | PSL | System Evaluation | MHP (Mechanical Refit): System Evaluation (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-27 | 2024-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | 9 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1556 | 1.2 | 1.2.8.6.7.2.1.2 | Not Started | PSL | System Evaluation | MHP (Mechanical Refit): System Evaluation (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-27 | 2024-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | 9 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1558 | 1.2 | 1.2.8.6.7.2.2.1 | Not Started | PSL | Final Upgrade & Replacement Activities | MHP (Electrical/Controls Refit): Final Upgrade & Replacement Activities (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | [10 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1558 | 1.2 | 1.2.8.6.7.2.2.1 | Not Started | PSL | Final Upgrade & Replacement Activities | MHP (Electrical/Controls Refit): Final Upgrade & Replacement Activities (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1558 | 1.2 | 1.2.8.6.7.2.2.1 | Not Started | PSL | Final Upgrade & Replacement Activities | MHP (Electrical/Controls Refit): Final Upgrade & Replacement Activities (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1559 | 1.2 | 1.2.8.6.7.2.2.2 | Not Started | PSL | System Evaluation and Final Testing | MHP (Electrical/Controls Refit): System Evaluation (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-27 | 2024-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | 36 | [9 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.8
1562 | 1.2 | 1.2.8.6.7.3.1.1 | Not Started | PSL | Install Filters in H2O System | PHS (Mechanical Refit): Install Filters in H2O System (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-21 | 2024-11-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1562 | 1.2 | 1.2.8.6.7.3.1.1 | Not Started | PSL | Install Filters in H2O System | PHS (Mechanical Refit): Install Filters in H2O System (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-21 | 2024-11-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1563 | 1.2 | 1.2.8.6.7.3.1.2 | Not Started | PSL | Final Upgrade & Replacement Activities | PHS (Mechanical Refit): Final Upgrade & Replacement Activities (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1563 | 1.2 | 1.2.8.6.7.3.1.2 | Not Started | PSL | Final Upgrade & Replacement Activities | PHS (Mechanical Refit): Final Upgrade & Replacement Activities (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1564 | 1.2 | 1.2.8.6.7.3.1.3 | Not Started | PSL | System Evaluation | PHS (Mechanical Refit): System Evaluation (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-27 | 2024-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | 9 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1566 | 1.2 | 1.2.8.6.7.3.2.1 | Not Started | PSL | Final Upgrade & Replacement Activities | PHS (Electrical/Controls Refit): Final Upgrade & Replacement Activities (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1566 | 1.2 | 1.2.8.6.7.3.2.1 | Not Started | PSL | Final Upgrade & Replacement Activities | PHS (Electrical/Controls Refit): Final Upgrade & Replacement Activities (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1566 | 1.2 | 1.2.8.6.7.3.2.1 | Not Started | PSL | Final Upgrade & Replacement Activities | PHS (Electrical/Controls Refit): Final Upgrade & Replacement Activities (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1567 | 1.2 | 1.2.8.6.7.3.2.2 | Not Started | PSL | System Evaluation and Final Testing | PHS (Electrical/Controls Refit): System Evaluation & Testing (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-27 | 2024-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 18 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1569 | 1.2 | 1.2.8.6.7.4.1 | Not Started | PSL | Final Upgrade & Replacement Activities | Water Tanks: Final Upgrade & Replacement Activities (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1569 | 1.2 | 1.2.8.6.7.4.1 | Not Started | PSL | Final Upgrade & Replacement Activities | Water Tanks: Final Upgrade & Replacement Activities (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1570 | 1.2 | 1.2.8.6.7.4.2 | Not Started | PSL | System Evaluation and Final Testing | Water Tanks: System Evaluation and Final Testing (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-27 | 2024-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 18 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1570 | 1.2 | 1.2.8.6.7.4.2 | Not Started | PSL | System Evaluation and Final Testing | Water Tanks: System Evaluation and Final Testing (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-27 | 2024-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | 18 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1573 | 1.2 | 1.2.8.6.7.5.1.1 | Not Started | PSL | Final Upgrade & Replacement Activities | HPP (Mechanical Refit): Final Upgrade & Replacement Activities (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1573 | 1.2 | 1.2.8.6.7.5.1.1 | Not Started | PSL | Final Upgrade & Replacement Activities | HPP (Mechanical Refit): Final Upgrade & Replacement Activities (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1574 | 1.2 | 1.2.8.6.7.5.1.2 | Not Started | PSL | Pump Testing & System Evaluation | HPP (Mechanical Refit): Pump Testing & System Evaluation (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-27 | 2024-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 18 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1576 | 1.2 | 1.2.8.6.7.5.2.1 | Not Started | PSL | Final Upgrade & Replacement Activities | HPP (Electrical/Controls Refit): Final Upgrade & Replacement Activities (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1576 | 1.2 | 1.2.8.6.7.5.2.1 | Not Started | PSL | Final Upgrade & Replacement Activities | HPP (Electrical/Controls Refit): Final Upgrade & Replacement Activities (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1576 | 1.2 | 1.2.8.6.7.5.2.1 | Not Started | PSL | Final Upgrade & Replacement Activities | HPP (Electrical/Controls Refit): Final Upgrade & Replacement Activities (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-11-21 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1577 | 1.2 | 1.2.8.6.7.5.2.2 | Not Started | PSL | System Evaluation and Final Testing | HPP (Electrical/Controls Refit): System Evaluation and Final Testing (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-27 | 2024-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 36 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1579 | 1.2 | 1.2.8.6.7.6.1 | Not Started | PSL | Relocate HPU2 to SES, Position | HPU2: Relocate to SES, Position (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-21 | 2024-11-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | [10 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.8
1580 | 1.2 | 1.2.8.6.7.6.2 | Not Started | PSL | Supply Power to HPU2, Warm Up | HPU2: Supply Power to HPU2, Warm Up (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-22 | 2024-11-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5 | [10 empty] | 5 | 0.033333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1.2.8
1581 | 1.2 | 1.2.8.6.7.6.3 | Not Started | PSL | Initiate final Refit/Integration (HPU2) | HPU2: Initiate Final Refit/Integration (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-25 | 2024-12-09 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | 27 | [9 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.8
1581 | 1.2 | 1.2.8.6.7.6.3 | Not Started | PSL | Initiate final Refit/Integration (HPU2) | HPU2: Initiate Final Refit/Integration (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-25 | 2024-12-09 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 36 | 54 | [9 empty] | 90 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 1.2.8
1583 | 1.2 | 1.2.8.6.7.7.1 | Not Started | PSL | Install New Point I/O, connect to DCC, and configure/troubleshoot | Fuel Tower: Install a New Point I/O Box on the Day Tank Sled & Test over the Network (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-02 | 2024-12-02 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1583 | 1.2 | 1.2.8.6.7.7.1 | Not Started | PSL | Install New Point I/O, connect to DCC, and configure/troubleshoot | Fuel Tower: Install a New Point I/O Box on the Day Tank Sled & Test over the Network (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-02 | 2024-12-02 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1584 | 1.2 | 1.2.8.6.7.7.2 | Not Started | PSL | Fuel Tower: Commission - NPX | Fuel Storage/Delivery: Commission Fuel Tower (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-03 | 2024-12-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1584 | 1.2 | 1.2.8.6.7.7.2 | Not Started | PSL | Fuel Tower: Commission - NPX | Fuel Storage/Delivery: Commission Fuel Tower (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-03 | 2024-12-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1584 | 1.2 | 1.2.8.6.7.7.2 | Not Started | PSL | Fuel Tower: Commission - NPX | Fuel Storage/Delivery: Commission Fuel Tower (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-03 | 2024-12-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1586 | 1.2 | 1.2.8.6.7.8.1 | Not Started | PSL | Final Upgrade/Retrofit Shops, MECC | Shops: Final Upgrade/Retrofit Shops, MECC (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-14 | 2024-11-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1589 | 1.2 | 1.2.8.6.7.9.1.1 | Not Started | PSL | Install Inner Insulation Layer & RTDs | MSHR: Install Inner Insulation Layer & RTDs (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-12 | 2024-12-13 | 0% | On Ice | [5 empty] | 2 Contract Drillers 2 days | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1589 | 1.2 | 1.2.8.6.7.9.1.1 | Not Started | PSL | Install Inner Insulation Layer & RTDs | MSHR: Install Inner Insulation Layer & RTDs (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-12 | 2024-12-13 | 0% | On Ice | [5 empty] | 2 Contract Drillers 2 days | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1590 | 1.2 | 1.2.8.6.7.9.1.2 | Not Started | PSL | Install Drill Hose on Reel | MSHR: Install Drill Hose on Reel (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-16 | 2024-12-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 45 | [9 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.8
1590 | 1.2 | 1.2.8.6.7.9.1.2 | Not Started | PSL | Install Drill Hose on Reel | MSHR: Install Drill Hose on Reel (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-16 | 2024-12-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 135 | [9 empty] | 135 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 1.2.8
1591 | 1.2 | 1.2.8.6.7.9.1.3 | Not Started | PSL | Final Upgrades & Testing (MSHR) | MSHR: Final Upgrades & Testing (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-23 | 2024-12-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1591 | 1.2 | 1.2.8.6.7.9.1.3 | Not Started | PSL | Final Upgrades & Testing (MSHR) | MSHR: Final Upgrades & Testing (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-23 | 2024-12-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1591 | 1.2 | 1.2.8.6.7.9.1.3 | Not Started | PSL | Final Upgrades & Testing (MSHR) | MSHR: Final Upgrades & Testing (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-23 | 2024-12-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1592 | 1.2 | 1.2.8.6.7.9.1.4 | Not Started | PSL | Install Hose Heating Blankets & RTDs & Install Outer Cover | MSHR: Install Hose Heating Blankets & RTDs & Install Outer Cover (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-01-21 | 2025-01-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1592 | 1.2 | 1.2.8.6.7.9.1.4 | Not Started | PSL | Install Hose Heating Blankets & RTDs & Install Outer Cover | MSHR: Install Hose Heating Blankets & RTDs & Install Outer Cover (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-01-21 | 2025-01-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1593 | 1.2 | 1.2.8.6.7.9.1.5 | Not Started | PSL | Install Hose Heating Controller, Connect to Power, & Test | MSHR: Install Hose Heating Controller, Connect to Power, & Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-01-23 | 2025-01-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1595 | 1.2 | 1.2.8.6.7.9.2.1 | Not Started | PSL | Install Return Hose on Reel | RWHR: Install Return Hose on Reel (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-09 | 2024-12-13 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1595 | 1.2 | 1.2.8.6.7.9.2.1 | Not Started | PSL | Install Return Hose on Reel | RWHR: Install Return Hose on Reel (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-09 | 2024-12-13 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1595 | 1.2 | 1.2.8.6.7.9.2.1 | Not Started | PSL | Install Return Hose on Reel | RWHR: Install Return Hose on Reel (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-09 | 2024-12-13 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1596 | 1.2 | 1.2.8.6.7.9.2.2 | Not Started | PSL | Final Upgrades & Testing | RWHR: Final Upgrades & Testing (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-10 | 2024-12-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1596 | 1.2 | 1.2.8.6.7.9.2.2 | Not Started | PSL | Final Upgrades & Testing | RWHR: Final Upgrades & Testing (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-10 | 2024-12-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1598 | 1.2 | 1.2.8.6.7.9.3.1 | Not Started | PSL | Final Upgrades & Testing | RWCR: Final Upgrades & Testing (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-10 | 2024-12-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1600 | 1.2 | 1.2.8.6.7.9.4.1 | Not Started | PSL | Final Upgrades & Testing | MCR: Final Upgrades & Testing (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-10 | 2024-12-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1600 | 1.2 | 1.2.8.6.7.9.4.1 | Not Started | PSL | Final Upgrades & Testing | MCR: Final Upgrades & Testing (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-10 | 2024-12-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1600 | 1.2 | 1.2.8.6.7.9.4.1 | Not Started | PSL | Final Upgrades & Testing | MCR: Final Upgrades & Testing (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-10 | 2024-12-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1602 | 1.2 | 1.2.8.6.7.10.1 | Not Started | PSL | Winches Final Integration & Testing (TU-20, TU-15) | Winches/Reels: Winches Final Integration & Testing (TU-20, TU-15) (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-15 | 2024-12-31 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 45 | [9 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.8
1602 | 1.2 | 1.2.8.6.7.10.1 | Not Started | PSL | Winches Final Integration & Testing (TU-20, TU-15) | Winches/Reels: Winches Final Integration & Testing (TU-20, TU-15) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-15 | 2024-12-31 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1602 | 1.2 | 1.2.8.6.7.10.1 | Not Started | PSL | Winches Final Integration & Testing (TU-20, TU-15) | Winches/Reels: Winches Final Integration & Testing (TU-20, TU-15) (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-15 | 2024-12-31 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1605 | 1.2 | 1.2.8.6.7.11.1.1 | Not Started | PSL | TOS1 - Install Racks & Computing Equipment | TOS1 - Install Racks & Computing Equipment (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-22 | 2024-11-25 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1605 | 1.2 | 1.2.8.6.7.11.1.1 | Not Started | PSL | TOS1 - Install Racks & Computing Equipment | TOS1 - Install Racks & Computing Equipment (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-22 | 2024-11-25 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1605 | 1.2 | 1.2.8.6.7.11.1.1 | Not Started | PSL | TOS1 - Install Racks & Computing Equipment | TOS1 - Install Racks & Computing Equipment (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-22 | 2024-11-25 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1606 | 1.2 | 1.2.8.6.7.11.1.2 | Not Started | PSL | TOS1 - Install Core PLC System | TOS1 - Install Core PLC System (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-26 | 2024-11-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1606 | 1.2 | 1.2.8.6.7.11.1.2 | Not Started | PSL | TOS1 - Install Core PLC System | TOS1 - Install Core PLC System (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-26 | 2024-11-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1606 | 1.2 | 1.2.8.6.7.11.1.2 | Not Started | PSL | TOS1 - Install Core PLC System | TOS1 - Install Core PLC System (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-26 | 2024-11-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1607 | 1.2 | 1.2.8.6.7.11.1.3 | Not Started | PSL | TOS1 - Connect & Configure I/O & Motor Drives | TOS1 - Connect & Configure I/O & Motor Drives (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-27 | 2024-11-29 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1607 | 1.2 | 1.2.8.6.7.11.1.3 | Not Started | PSL | TOS1 - Connect & Configure I/O & Motor Drives | TOS1 - Connect & Configure I/O & Motor Drives (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-11-27 | 2024-11-29 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1607 | 1.2 | 1.2.8.6.7.11.1.3 | Not Started | PSL | TOS1 - Connect & Configure I/O & Motor Drives | TOS1 - Connect & Configure I/O & Motor Drives (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-27 | 2024-11-29 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1608 | 1.2 | 1.2.8.6.7.11.1.4 | Not Started | PSL | TOS1 - Install & Commission Latest Software, SCADA | TOS1 - Install & Commission Latest Software, SCADA (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-02 | 2024-12-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1609 | 1.2 | 1.2.8.6.7.11.1.5 | Not Started | PSL | TOS1 - Connect Reels & Perform QA on Controls | TOS1 - Connect Reels & Perform QA on Controls (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-04 | 2024-12-05 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1609 | 1.2 | 1.2.8.6.7.11.1.5 | Not Started | PSL | TOS1 - Connect Reels & Perform QA on Controls | TOS1 - Connect Reels & Perform QA on Controls (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-04 | 2024-12-05 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1609 | 1.2 | 1.2.8.6.7.11.1.5 | Not Started | PSL | TOS1 - Connect Reels & Perform QA on Controls | TOS1: Connect Reels & Perform QA on Controls (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-04 | 2024-12-05 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1610 | 1.2 | 1.2.8.6.7.11.1.6 | Not Started | PSL | TOS1 - Install Drill Head Power Supply | TOS1: Install Drill Head Power Supply (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-06 | 2024-12-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1611 | 1.2 | 1.2.8.6.7.11.1.7 | Not Started | PSL | TOS1 - Test Drill Head Data Chain With Actual Drill Head | TOS1: Test Drill Head Data Chain With Actual Drill Head (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-09 | 2024-12-09 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1611 | 1.2 | 1.2.8.6.7.11.1.7 | Not Started | PSL | TOS1 - Test Drill Head Data Chain With Actual Drill Head | TOS1: Test Drill Head Data Chain With Actual Drill Head (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-09 | 2024-12-09 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1611 | 1.2 | 1.2.8.6.7.11.1.7 | Not Started | PSL | TOS1 - Test Drill Head Data Chain With Actual Drill Head | TOS1: Test Drill Head Data Chain With Actual Drill Head (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-09 | 2024-12-09 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1614 | 1.2 | 1.2.8.6.7.11.2.1 | Not Started | PSL | TOS2 - Install Racks & Computing Equipment | TOS2 - Install Racks & Computing Equipment (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-10 | 2024-12-11 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1614 | 1.2 | 1.2.8.6.7.11.2.1 | Not Started | PSL | TOS2 - Install Racks & Computing Equipment | TOS2 - Install Racks & Computing Equipment (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-10 | 2024-12-11 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1614 | 1.2 | 1.2.8.6.7.11.2.1 | Not Started | PSL | TOS2 - Install Racks & Computing Equipment | TOS2 - Install Racks & Computing Equipment (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-10 | 2024-12-11 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1615 | 1.2 | 1.2.8.6.7.11.2.2 | Not Started | PSL | TOS2 - Install Core PLC System | TOS2 - Install Core PLC System (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-12 | 2024-12-12 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1615 | 1.2 | 1.2.8.6.7.11.2.2 | Not Started | PSL | TOS2 - Install Core PLC System | TOS2 - Install Core PLC System (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-12 | 2024-12-12 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1615 | 1.2 | 1.2.8.6.7.11.2.2 | Not Started | PSL | TOS2 - Install Core PLC System | TOS2 - Install Core PLC System (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-12 | 2024-12-12 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1616 | 1.2 | 1.2.8.6.7.11.2.3 | Not Started | PSL | TOS2 - Connect & Configure I/O & Motor Drives | TOS2 - Connect & Configure I/O & Motor Drives (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-13 | 2024-12-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1616 | 1.2 | 1.2.8.6.7.11.2.3 | Not Started | PSL | TOS2 - Connect & Configure I/O & Motor Drives | TOS2 - Connect & Configure I/O & Motor Drives (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-13 | 2024-12-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1616 | 1.2 | 1.2.8.6.7.11.2.3 | Not Started | PSL | TOS2 - Connect & Configure I/O & Motor Drives | TOS2 - Connect & Configure I/O & Motor Drives (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-13 | 2024-12-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1617 | 1.2 | 1.2.8.6.7.11.2.4 | Not Started | PSL | TOS2 - Install & Commission Latest Software, SCADA | TOS2 - Install & Commission Latest Software, SCADA (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-17 | 2024-12-18 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1618 | 1.2 | 1.2.8.6.7.11.2.5 | Not Started | PSL | TOS2 - Connect Reels & Perform QA on Controls | TOS2 - Connect Reels & Perform QA on Controls (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-19 | 2024-12-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1618 | 1.2 | 1.2.8.6.7.11.2.5 | Not Started | PSL | TOS2 - Connect Reels & Perform QA on Controls | TOS2 - Connect Reels & Perform QA on Controls (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-19 | 2024-12-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1618 | 1.2 | 1.2.8.6.7.11.2.5 | Not Started | PSL | TOS2 - Connect Reels & Perform QA on Controls | TOS2: Connect Reels & Perform QA on Controls (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-19 | 2024-12-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1619 | 1.2 | 1.2.8.6.7.11.2.6 | Not Started | PSL | TOS2 - Install Drill Head Power Supply | TOS2: Install Drill Head Power Supply (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-23 | 2024-12-23 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1620 | 1.2 | 1.2.8.6.7.11.2.7 | Not Started | PSL | TOS2 - Test Drill Head Data Chain With Actual Drill Head | TOS2: Test Drill Head Data Chain With Actual Drill Head (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-24 | 2024-12-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1620 | 1.2 | 1.2.8.6.7.11.2.7 | Not Started | PSL | TOS2 - Test Drill Head Data Chain With Actual Drill Head | TOS2: Test Drill Head Data Chain With Actual Drill Head (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-24 | 2024-12-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1620 | 1.2 | 1.2.8.6.7.11.2.7 | Not Started | PSL | TOS2 - Test Drill Head Data Chain With Actual Drill Head | TOS2: Test Drill Head Data Chain With Actual Drill Head (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-24 | 2024-12-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1623 | 1.2 | 1.2.8.6.7.12.1 | Not Started | PSL | Commission Sled 1 - Generator Sled | Rodwell System: Commission Sled 1 - Generator Sled (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-22 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1623 | 1.2 | 1.2.8.6.7.12.1 | Not Started | PSL | Commission Sled 1 - Generator Sled | Rodwell System: Commission Sled 1 - Generator Sled (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-22 | 2024-11-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 54 | [10 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1624 | 1.2 | 1.2.8.6.7.12.2 | Not Started | PSL | Commission Sled 2 - Water Tank Sled | Rodwell System: Commission Sled 2 - Water Tank Sled (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-29 | 2024-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | 18 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1624 | 1.2 | 1.2.8.6.7.12.2 | Not Started | PSL | Commission Sled 2 - Water Tank Sled | Rodwell System: Commission Sled 2 - Water Tank Sled (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-29 | 2024-12-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | 18 | [9 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.8
1625 | 1.2 | 1.2.8.6.7.12.3 | Not Started | PSL | Commission Sled 3 - Heater/reel Sled | Rodwell System: Commission Sled 3 - Heater/reel Sled (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-05 | 2024-12-10 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1625 | 1.2 | 1.2.8.6.7.12.3 | Not Started | PSL | Commission Sled 3 - Heater/reel Sled | Rodwell System: Commission Sled 3 - Heater/reel Sled (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-05 | 2024-12-10 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1626 | 1.2 | 1.2.8.6.7.12.4 | Not Started | PSL | System Commissioning and Checkout | Rodwell System: System Commissioning and Checkout (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-11 | 2024-12-13 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1626 | 1.2 | 1.2.8.6.7.12.4 | Not Started | PSL | System Commissioning and Checkout | Rodwell System: System Commissioning and Checkout (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-11 | 2024-12-13 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1626 | 1.2 | 1.2.8.6.7.12.4 | Not Started | PSL | System Commissioning and Checkout | Rodwell System: System Commissioning and Checkout (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-11 | 2024-12-13 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1627 | 1.2 | 1.2.8.6.7.12.5 | Not Started | PSL | Fill System with Seed Water | Rodwell System: Fill System with Seed Water (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-11 | 2024-12-11 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1627 | 1.2 | 1.2.8.6.7.12.5 | Not Started | PSL | Fill System with Seed Water | Rodwell System: Fill System with Seed Water (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-11 | 2024-12-11 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1628 | 1.2 | 1.2.8.6.7.12.6 | Not Started | PSL | Decommission & Store ARA | Rodwell System: Decommission & Store ARA (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-01-20 | 2025-01-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1628 | 1.2 | 1.2.8.6.7.12.6 | Not Started | PSL | Decommission & Store ARA | Rodwell System: Decommission & Store ARA (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-01-20 | 2025-01-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1630 | 1.2 | 1.2.8.6.8.1 | Not Started | PSL | Setup ARA System over mini FS2 Condensate Bulb Firn Hole Location | Setup ARA System over mini FS2 Condensate Bulb Firn Hole Location (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-16 | 2024-12-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1630 | 1.2 | 1.2.8.6.8.1 | Not Started | PSL | Setup ARA System over mini FS2 Condensate Bulb Firn Hole Location | Setup ARA System over mini FS2 Condensate Bulb Firn Hole Location (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-16 | 2024-12-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1631 | 1.2 | 1.2.8.6.8.2 | Not Started | PSL | Drill Dry Pilot Hole, Develop, Pump Out (mini cond) | Drill Dry Pilot Hole, Develop, Pump Out (mini condensate) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-17 | 2024-12-18 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1631 | 1.2 | 1.2.8.6.8.2 | Not Started | PSL | Drill Dry Pilot Hole, Develop, Pump Out (mini cond) | Drill Dry Pilot Hole, Develop, Pump Out (mini condensate) (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-17 | 2024-12-18 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1632 | 1.2 | 1.2.8.6.8.3 | Not Started | PSL | Setup ARA System over main FS3 Condensate Bulb Hole Location | Setup ARA System over main FS3 Condensate Bulb Hole Location (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-20 | 2024-12-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1632 | 1.2 | 1.2.8.6.8.3 | Not Started | PSL | Setup ARA System over main FS3 Condensate Bulb Hole Location | Setup ARA System over main FS3 Condensate Bulb Hole Location (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-20 | 2024-12-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1633 | 1.2 | 1.2.8.6.8.4 | Not Started | PSL | Drill Dry Pilot Hole (main cond) | Condensate Bulb: Drill Dry Pilot Hole (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-23 | 2024-12-23 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1633 | 1.2 | 1.2.8.6.8.4 | Not Started | PSL | Drill Dry Pilot Hole (main cond) | Condensate Bulb: Drill Dry Pilot Hole (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-23 | 2024-12-23 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1634 | 1.2 | 1.2.8.6.8.5 | Not Started | PSL | Develop Bulb (main cond) | Condensate Bulb: Develop Bulb (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-24 | 2024-12-30 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1634 | 1.2 | 1.2.8.6.8.5 | Not Started | PSL | Develop Bulb (main cond) | Condensate Bulb: Develop Bulb (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-24 | 2024-12-30 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1635 | 1.2 | 1.2.8.6.8.6 | Not Started | PSL | Maintain Bulb for Test, then Pump out Water (main cond) | Condensate Bulb: Maintain Bulb for Systems Test, then Pump out Water (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-31 | 2025-01-14 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1635 | 1.2 | 1.2.8.6.8.6 | Not Started | PSL | Maintain Bulb for Test, then Pump out Water (main cond) | Condensate Bulb: Maintain Bulb for Systems Test, then Pump out Water (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-31 | 2025-01-14 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1638 | 1.2 | 1.2.8.6.9.2 | Not Started | PSL | Drill and CRREL Integration and Commissioning | IFD: Integration and Commissioning (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-18 | 2024-11-25 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1638 | 1.2 | 1.2.8.6.9.2 | Not Started | PSL | Drill and CRREL Integration and Commissioning | IFD: Integration and Commissioning (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-18 | 2024-11-25 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1639 | 1.2 | 1.2.8.6.9.3 | Not Started | PSL | Excavation of 7 x Firn Hole Pits 4' x 4' x 2' (Set String Anchor in Each Hole) | IFD: Excavate 7x Firn Hole Pits 4'x4'x2' & set string anchors (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-18 | 2024-11-19 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1639 | 1.2 | 1.2.8.6.9.3 | Not Started | PSL | Excavation of 7 x Firn Hole Pits 4' x 4' x 2' (Set String Anchor in Each Hole) | IFD: Excavate 7x Firn Hole Pits 4'x4'x2' & set string anchors (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2024-11-18 | 2024-11-19 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1641 | 1.2 | 1.2.8.6.9.5 | Not Started | PSL | Drill 9 Firn Holes w/ Independent Firn Drill (IFD) | IFD: Drill 9 Firn Holes (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-11-29 | 2025-01-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | 36 | 9 | [8 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1641 | 1.2 | 1.2.8.6.9.5 | Not Started | PSL | Drill 9 Firn Holes w/ Independent Firn Drill (IFD) | IFD: Drill 9 Firn Holes (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-11-29 | 2025-01-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | 72 | 9 | [8 empty] | 90 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 1.2.8
1644 | 1.2 | 1.2.8.6.9.8 | Not Started | PSL | Winterize & Store IFD | IFD: Winterize & Store (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-01-07 | 2025-01-14 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1644 | 1.2 | 1.2.8.6.9.8 | Not Started | PSL | Winterize & Store IFD | IFD: Winterize & Store (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-01-07 | 2025-01-14 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1646 | 1.2 | 1.2.8.6.10.1 | Not Started | PSL | Setup TOS, Tower, Reels over Rodwell Hole Location | Wet Test: Setup TOS, Tower, Reels over Rodwell Hole Location (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-06 | 2024-12-10 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1646 | 1.2 | 1.2.8.6.10.1 | Not Started | PSL | Setup TOS, Tower, Reels over Rodwell Hole Location | Wet Test: Setup TOS, Tower, Reels over Rodwell Hole Location (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-06 | 2024-12-10 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1647 | 1.2 | 1.2.8.6.10.2 | Not Started | PSL | Phase 1: TOS Motion control testing and Tuning | Wet Test Phase 1: TOS Motion Control Testing and Tuning (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-26 | 2025-01-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | 180 | [8 empty] | 252 | 1.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 1.2.8
1647 | 1.2 | 1.2.8.6.10.2 | Not Started | PSL | Phase 1: TOS Motion control testing and Tuning | Wet Test Phase 1: TOS Motion Control Testing and Tuning (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-26 | 2025-01-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | 144 | [8 empty] | 216 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216 | 1.2.8
1647 | 1.2 | 1.2.8.6.10.2 | Not Started | PSL | Phase 1: TOS Motion control testing and Tuning | Wet Test Phase 1: TOS Motion Control Testing and Tuning (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-26 | 2025-01-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | 216 | [8 empty] | 288 | 1.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 1.2.8
1648 | 1.2 | 1.2.8.6.10.3 | Not Started | PSL | Readiness Review, Safety Refresher, Emergency & Safety Systems Tested | Wet Test: Readiness Review, Safety Refresher, Emergency & Safety Systems Tested (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-01-07 | 2025-01-07 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1648 | 1.2 | 1.2.8.6.10.3 | Not Started | PSL | Readiness Review, Safety Refresher, Emergency & Safety Systems Tested | Wet Test: Readiness Review, Safety Refresher, Emergency & Safety Systems Tested (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-01-07 | 2025-01-07 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1648 | 1.2 | 1.2.8.6.10.3 | Not Started | PSL | Readiness Review, Safety Refresher, Emergency & Safety Systems Tested | Wet Test: Readiness Review, Safety Refresher, Emergency & Safety Systems Tested (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-01-07 | 2025-01-07 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 54 | [8 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1649 | 1.2 | 1.2.8.6.10.4 | Not Started | PSL | Phase 2: Full System Wet-Test | Wet Test Phase 2: Full System Wet Test (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-01-08 | 2025-01-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 270 | [8 empty] | 270 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 1.2.8
1649 | 1.2 | 1.2.8.6.10.4 | Not Started | PSL | Phase 2: Full System Wet-Test | Wet Test Phase 2: Full System Wet Test (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-01-08 | 2025-01-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 252 | [8 empty] | 252 | 1.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 1.2.8
1649 | 1.2 | 1.2.8.6.10.4 | Not Started | PSL | Phase 2: Full System Wet-Test | Wet Test Phase 2: Full System Wet Test (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-01-08 | 2025-01-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 378 | [8 empty] | 378 | 2.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 378 | 1.2.8
1650 | 1.2 | 1.2.8.6.10.5 | Not Started | PSL | Blow Out Systems | Wet Test: Blow Out Systems (need ASC compressor) (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-01-17 | 2025-01-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 54 | [8 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1650 | 1.2 | 1.2.8.6.10.5 | Not Started | PSL | Blow Out Systems | Wet Test: Blow Out Systems (need ASC compressor) (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-01-17 | 2025-01-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 108 | [8 empty] | 108 | 0.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 1.2.8
1653 | 1.2 | 1.2.8.6.11.1 | Not Started | PSL | Sensor Handling Facility Construction Oversight | Sensor Handling Facility: Construction Oversight (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2024-12-04 | 2024-12-16 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1655 | 1.2 | 1.2.8.6.12.1 | Not Started | PSL | Document, Photograph Equip & Upgrade Work, Further Req's | Close-out: Document, Photograph Equip & Upgrade Work, Further Req's (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-24 | 2024-12-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1655 | 1.2 | 1.2.8.6.12.1 | Not Started | PSL | Document, Photograph Equip & Upgrade Work, Further Req's | Close-out: Document, Photograph Equip & Upgrade Work, Further Req's (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-24 | 2024-12-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1656 | 1.2 | 1.2.8.6.12.2 | Not Started | PSL | Collect Video Record of Condensate Bulb and Rodwell | Close-out: Collect Video Record of Condensate Bulb and Rodwell (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-01-23 | 2025-01-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1656 | 1.2 | 1.2.8.6.12.2 | Not Started | PSL | Collect Video Record of Condensate Bulb and Rodwell | Close-out: Collect Video Record of Condensate Bulb and Rodwell (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-01-23 | 2025-01-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1657 | 1.2 | 1.2.8.6.12.3 | Not Started | PSL | Prepare Retrograde for Shipment | Close-out: Prepare Retrograde for Shipment (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-24 | 2025-01-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | 54 | [8 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1657 | 1.2 | 1.2.8.6.12.3 | Not Started | PSL | Prepare Retrograde for Shipment | Close-out: Prepare Retrograde for Shipment (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2024-12-24 | 2025-01-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | 54 | [8 empty] | 63 | 0.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 1.2.8
1657 | 1.2 | 1.2.8.6.12.3 | Not Started | PSL | Prepare Retrograde for Shipment | Close-out: Prepare Retrograde for Shipment (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2024-12-24 | 2025-01-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | 72 | [8 empty] | 108 | 0.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 1.2.8
1660 | 1.2 | 1.2.8.6.12.5.1 | Not Started | PSL | Remove DNF, Computer Equip, Drives, Capacitors, Etc | Close-out: Remove DNF, Computer Equip, Drives, Capacitors, Etc. (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-01-23 | 2025-01-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1660 | 1.2 | 1.2.8.6.12.5.1 | Not Started | PSL | Remove DNF, Computer Equip, Drives, Capacitors, Etc | Close-out: Remove DNF, Computer Equip, Drives, Capacitors, Etc. (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-01-23 | 2025-01-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1660 | 1.2 | 1.2.8.6.12.5.1 | Not Started | PSL | Remove DNF, Computer Equip, Drives, Capacitors, Etc | Close-out: Remove DNF, Computer Equip, Drives, Capacitors, Etc. (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-01-23 | 2025-01-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1661 | 1.2 | 1.2.8.6.12.5.2 | Not Started | PSL | Winterize SES & TOS, Disconnect All Cables Hoses, Connections | Close-out: Winterize/Close/Store all EHWD Equipment (EE) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-01-22 | 2025-01-29 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 54 | [8 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1661 | 1.2 | 1.2.8.6.12.5.2 | Not Started | PSL | Winterize SES & TOS, Disconnect All Cables Hoses, Connections | Close-out: Winterize/Close/Store all EHWD Equipment (ME) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-01-22 | 2025-01-29 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 45 | [8 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.8
1661 | 1.2 | 1.2.8.6.12.5.2 | Not Started | PSL | Winterize SES & TOS, Disconnect All Cables Hoses, Connections | Close-out: Winterize/Close/Store all EHWD Equipment (TE) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-01-22 | 2025-01-29 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 54 | [8 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1668 | 1.2 | 1.2.8.6.15 | Not Started | PSL | On-ice Labor FS2 | On-Ice Labor (FS2) (PSL Engineers) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 85.1852 | 115 | 0% | 2024-11-08 | 2025-02-04 | 0% | On Ice | C2 |  |  |  |  | EE/ME Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 990 | 1818 | 1647 | [8 empty] | 4455 | 29.7 | 0 | 89890.6207 | 165071.8671 | 149545.3054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404507.7932 | 0 | 404507.7932 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404507.7932 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 404507.7932 | 0 | 0 | 0 | 0 | 0 | 0 | 4455 | 1.2.8
1668 | 1.2 | 1.2.8.6.15 | Not Started | PSL | On-ice Labor FS2 | On-Ice Labor (FS2) (PSL Drillers) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 57.037 | 77 | 0% | 2024-11-08 | 2025-02-04 | 0% | On Ice | C2 |  |  |  |  | Technician Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 819 | 1197 | 1359 | [8 empty] | 3375 | 22.5 | 0 | 49791.5873 | 72772.3199 | 82621.2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205185.1125 | 0 | 205185.1125 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205185.1125 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 205185.1125 | 0 | 0 | 0 | 0 | 0 | 0 | 3375 | 1.2.8
1668 | 1.2 | 1.2.8.6.15 | Not Started | UW | On-ice Labor FS2 | On-Ice Labor (FS2) (Safety Engineer) | Zernick | 0% | Labor Hours | Labor - Task | EN-S |  |  | D - Expert Opinion | 44.96 | 46 | 35% | 2024-11-08 | 2025-02-04 | 53% | On Ice | C2 |  |  |  |  | Safety Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 225 | 108 | [8 empty] | 381 | 2.54 | 0 | 3105.3919 | 14556.5247 | 6987.1319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24649.0485 | 13063.9957 | 37713.0442 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37713.0442 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 18258.5545 | 0 | 0 | 0 | 0 | 6390.4941 | 0 | 381 | 1.2.8
1671 | 1.2 | 1.2.8.7.1 | Not Started | PSL | FS3 Milestones | START NPX FS3 Season - Team Arrives 28 [Drilling/Installation] {DELETE?} |  | 0% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2025-02-15 | 2025-11-25 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1680 | 1.2 | 1.2.8.7.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS3) | Deployment Travel & PQ Costs (FS3) (Driller_Manager) |  | 0% | Labor Hours | Labor - Task | EN |  |  | E - Extrapolation from Actuals | 115 | 115 | 0 | 2025-06-01 | 2026-03-03 | 0% | Off Ice | C1 |  |  |  |  | 1 (Drill Manager), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0.42667 | 0 | 5008.5419 | 0 | 0 | 3005.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8013.6671 | 0 | 8013.6671 | 8013.6671 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 8013.6671 | 0 | 0 | 0 | 0 | 0 | 64 | 1.2.8
1680 | 1.2 | 1.2.8.7.2 | Not Started | UW | PQ, ECW & Deployment Travel Costs (FS3) | Deployment Travel & PQ Costs (FS3) (Safety_Engineer) | Zernick | 0% | Labor Hours | Labor - Task | EN-S |  |  | E - Extrapolation from Actuals | 60.69 | 46 | 35% | 2025-06-01 | 2026-03-03 | 53% | Off Ice | C1 |  |  |  |  | 1 (Safety Engineer), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 24 | [8 empty] | 64 | 0.42667 | 0 | 3568.3248 | 0 | 2140.9949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5709.3197 | 3025.9395 | 8735.2592 | 8735.2592 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 4229.1257 | 0 | 0 | 0 | 0 | 1480.194 | 64 | 1.2.8
1680 | 1.2 | 1.2.8.7.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS3) | Deployment Travel & PQ Costs (FS3) (Driller_PSL_Direct_Hire) |  | 0% | Labor Hours | Labor - Task | EN |  |  | E - Extrapolation from Actuals | 115 | 115 | 0% | 2025-06-01 | 2026-03-03 | 0% | Off Ice | C1 |  |  |  |  | 20 (PSL Direct Hire), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 800 |  | 480 | [8 empty] | 1280 | 8.5333 | 0 | 100170.839 | 0 | 60102.5034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160273.3424 | 0 | 160273.3424 | 160273.3424 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 160273.3424 | 0 | 0 | 0 | 0 | 0 | 1280 | 1.2.8
1680 | 1.2 | 1.2.8.7.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS3) | Deployment Travel & PQ Costs (FS3) (Engineer_PSL) |  | 0% | Labor Hours | Labor - Task | EN |  |  | E - Extrapolation from Actuals | 115 | 115 | 0% | 2025-06-01 | 2026-03-03 | 0% | Off Ice | C1 |  |  |  |  | 8 (PSL Engineers), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 320 |  | 192 | [8 empty] | 512 | 3.4133 | 0 | 40068.3356 | 0 | 24041.0014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64109.3369 | 0 | 64109.3369 | 64109.3369 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 64109.3369 | 0 | 0 | 0 | 0 | 0 | 512 | 1.2.8
1680 | 1.2 | 1.2.8.7.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS3) | PQ Costs (FS3) (Drill Team) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2025-06-01 | 2026-03-03 | 53% | Off Ice | C1 |  |  |  |  | 33 - PQ's @ $950/each (anticipated cost) 28 Drillers, Safety Engineer & 4 Alternates | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 15675 | 15675 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16707.9306 | 16707.9306 | 0 | 0 | 33415.8612 | 17710.4064 | 51126.2676 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51126.2676 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
1680 | 1.2 | 1.2.8.7.2 | Not Started | PSL | PQ, ECW & Deployment Travel Costs (FS3) | Travel (FS3) (Drill Team) | Foreign |  | Travel | Travel |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2025-06-01 | 2026-03-03 | 53% | Off Ice | C1 |  |  |  |  | 29 - Deploy travel costs 29 (28 Drillers & 1 Safety Engineer) @ $1800 each | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 26100 | 26100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27819.9036 | 27819.9036 | 55639.8071 | 29489.0978 | 85128.9049 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85128.9049 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.8
1700 | 1.2 | 1.2.8.7.4.3 | Not Started | PSL | SES Dig-out (Driller) | SES: Dig-out |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-11-14 | 2025-11-18 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 54 | [10 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1700 | 1.2 | 1.2.8.7.4.3 | Not Started | PSL | SES Dig-out (Driller) | SES: Dig-out |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-14 | 2025-11-18 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 96 | [10 empty] | 96 | 0.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 1.2.8
1710 | 1.2 | 1.2.8.7.4.13 | Not Started | PSL | Make Ready all SES Modules (DCC, PHS, MHPs, MECC, WTs, All) | SES: Make Ready all Drill Modules (DCC, PHS, MHPs, TOS 1&2, WTs, Handling Facility) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-11-17 | 2025-11-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 108 | [10 empty] | 108 | 0.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 1.2.8
1710 | 1.2 | 1.2.8.7.4.13 | Not Started | PSL | Make Ready all SES Modules (DCC, PHS, MHPs, MECC, WTs, All) | SES: Make Ready all Drill Modules (DCC, PHS, MHPs, TOS 1&2, WTs, Handling Facility) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-17 | 2025-11-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 185 | [10 empty] | 185 | 1.2333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 1.2.8
1711 | 1.2 | 1.2.8.7.4.14 | Not Started | PSL | Furnace Checkout & Fire Up (All modules) | SES: Furnace Checkout & Fire Up (All modules) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-17 | 2025-11-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | [10 empty] | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.8
1712 | 1.2 | 1.2.8.7.4.15 | Not Started | PSL | SES and Equipment Maintenance Activities | SES: SES and Equipment Maintenance |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2025-11-17 | 2026-01-29 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 60 | 96 | 96 | [8 empty] | 252 | 1.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252 | 1.2.8
1714 | 1.2 | 1.2.8.7.4.17 | Not Started | PSL | Drill Control Center Set-up, Integration, & Commissioning | SES: Drill Control Center Set-up, Integration, & Commissioning |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-11-18 | 2025-11-25 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 324 | [10 empty] | 324 | 2.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 324 | 1.2.8
1719 | 1.2 | 1.2.8.7.4.22 | Not Started | PSL | Ready Antarctic Rodwell Apparatus (ARA) for Service | SES: Make ARA Ready for Service |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-01 | 2025-12-05 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1719 | 1.2 | 1.2.8.7.4.22 | Not Started | PSL | Ready Antarctic Rodwell Apparatus (ARA) for Service | SES: Make ARA Ready for Service |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-01 | 2025-12-05 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | [9 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1721 | 1.2 | 1.2.8.7.4.24 | Not Started | PSL | Perform Emergency Incident Drill & Safety Training | SES: Perform Emergency Incident Drill & Safety Training |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-11-26 | 2025-12-01 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 96 | 18 | [9 empty] | 114 | 0.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 1.2.8
1721 | 1.2 | 1.2.8.7.4.24 | Not Started | PSL | Perform Emergency Incident Drill & Safety Training | SES: Perform Emergency Incident Drill & Safety Training |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-11-26 | 2025-12-01 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 96 | 18 | [9 empty] | 114 | 0.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 1.2.8
1721 | 1.2 | 1.2.8.7.4.24 | Not Started | PSL | Perform Emergency Incident Drill & Safety Training | SES: Perform Emergency Incident Drill & Safety Training |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-26 | 2025-12-01 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 240 | 240 | [9 empty] | 480 | 3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 1.2.8
1723 | 1.2 | 1.2.8.7.4.26 | Not Started | PSL | Final SES Readiness Assessment | SES: Final SES Readiness Assessment |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-08 | 2025-12-09 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 34 | [9 empty] | 34 | 0.22667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1.2.8
1723 | 1.2 | 1.2.8.7.4.26 | Not Started | PSL | Final SES Readiness Assessment | SES: Final SES Readiness Assessment |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-08 | 2025-12-09 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 34 | [9 empty] | 34 | 0.22667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 1.2.8
1726 | 1.2 | 1.2.8.7.5.1 | Not Started | PSL | Generator & PDM: Commission - NPX | Generator/PDM: Generator & PDM: Commission - NPX |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-11-18 | 2025-11-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 45 | [10 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.8
1726 | 1.2 | 1.2.8.7.5.1 | Not Started | PSL | Generator & PDM: Commission - NPX | Generator/PDM: Generator & PDM: Commission - NPX |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-18 | 2025-11-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 45 | [10 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.8
1729 | 1.2 | 1.2.8.7.5.4 | Not Started | PSL | Change from Temp Power to Generators (USAP) | Generator/PDM: Change from Temp Power to Generators (Stand Alone) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-11-24 | 2025-11-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1731 | 1.2 | 1.2.8.7.6.1 | Not Started | PSL | Uncover Hole 1 / String 87 | TOS1/Tower1: Uncover Hole 1 / String 87 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-11-19 | 2025-11-19 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | [10 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.8
1731 | 1.2 | 1.2.8.7.6.1 | Not Started | PSL | Uncover Hole 1 / String 87 | TOS1/Tower1: Uncover Hole 1 / String 87 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-19 | 2025-11-19 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | [10 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.8
1732 | 1.2 | 1.2.8.7.6.2 | Not Started | PSL | Relocate TOS1 and Main Hose Reel to Hole 1 / String 87 | TOS1/Tower1: Relocate Tower, TOS1 and Main Hose Reel to Hole 1 / String 87 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-11-19 | 2025-11-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32 | [10 empty] | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.8
1732 | 1.2 | 1.2.8.7.6.2 | Not Started | PSL | Relocate TOS1 and Main Hose Reel to Hole 1 / String 87 | TOS1/Tower1: Relocate Tower, TOS1 and Main Hose Reel to Hole 1 / String 87 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-19 | 2025-11-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | [10 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.8
1734 | 1.2 | 1.2.8.7.6.4 | Not Started | PSL | Position Sensor Handling Structure | TOS1/Tower1: Position Sensor Handling Structure |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-20 | 2025-11-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1735 | 1.2 | 1.2.8.7.6.5 | Not Started | PSL | Trench & Install Reel Anchors (Hole 1 & 2) | TOS1/Tower1: Trench & Install Reel Anchors (Hole 1 & 2) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-20 | 2025-11-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1736 | 1.2 | 1.2.8.7.6.6 | Not Started | PSL | Position Hose & Cable Reels (Hole 1) | TOS1/Tower1: Position Hose & Cable Reels (Hole 1) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-20 | 2025-11-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1737 | 1.2 | 1.2.8.7.6.7 | Not Started | PSL | Hose & Cable Delivery & Layout SES-TOS | TOS1/Tower1: Hose & Cable Delivery/Layout SES-TOS |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-11-24 | 2025-11-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1737 | 1.2 | 1.2.8.7.6.7 | Not Started | PSL | Hose & Cable Delivery & Layout SES-TOS | TOS1/Tower1: Hose & Cable Delivery/Layout SES-TOS |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-24 | 2025-11-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 69 | [10 empty] | 69 | 0.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 1.2.8
1738 | 1.2 | 1.2.8.7.6.8 | Not Started | PSL | TOS1 Network/Comms Set-up | TOS1/Tower1: TOS1 Network/Comms Set-up |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-11-24 | 2025-11-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1739 | 1.2 | 1.2.8.7.6.9 | Not Started | PSL | Make TOS1 Operational, Deliver Fuel, Fire Furnace | TOS1/Tower1: Make TOS1 Operational, Deliver Fuel, Fire Furnace |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-11-28 | 2025-12-02 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 32 | [9 empty] | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.8
1739 | 1.2 | 1.2.8.7.6.9 | Not Started | PSL | Make TOS1 Operational, Deliver Fuel, Fire Furnace | TOS1/Tower1: Make TOS1 Operational, Deliver Fuel, Fire Furnace |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-28 | 2025-12-02 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 32 | [9 empty] | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.8
1740 | 1.2 | 1.2.8.7.6.10 | Not Started | PSL | Prepare MCA (Mount on TU20, test slip ring), Setup both TU20 (Hole 1 & 2) | TOS1/Tower1: Prepare MCA (Mount on TU20, test slip ring) - both TU20s |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-04 | 2025-12-05 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 16 | [9 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.8
1741 | 1.2 | 1.2.8.7.6.11 | Not Started | PSL | Connect Hose Loop & Circulate Water | TOS1/Tower1: Connect Hose Loop, Circulate Water |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-12-01 | 2025-12-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1741 | 1.2 | 1.2.8.7.6.11 | Not Started | PSL | Connect Hose Loop & Circulate Water | TOS1/Tower1: Connect Hose Loop, Circulate Water |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-01 | 2025-12-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 30 | [9 empty] | 30 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1.2.8
1742 | 1.2 | 1.2.8.7.6.12 | Not Started | PSL | Pull Drill Heads from ICL & Final Testing in TOS | TOS1/Tower1: Pull Drill Heads from ICL, Final Testing in TOS |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-12-08 | 2025-12-11 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1742 | 1.2 | 1.2.8.7.6.12 | Not Started | PSL | Pull Drill Heads from ICL & Final Testing in TOS | TOS1/Tower1: Pull Drill Heads from ICL, Final Testing in TOS |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-12-08 | 2025-12-11 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1742 | 1.2 | 1.2.8.7.6.12 | Not Started | PSL | Pull Drill Heads from ICL & Final Testing in TOS | TOS1/Tower1: Pull Drill Heads from ICL, Final Testing in TOS |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-08 | 2025-12-11 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1745 | 1.2 | 1.2.8.7.7.1 | Not Started | PSL | Uncover Hole 2 / String 88 | TOS2/Tower2: Uncover Hole 2 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2025-11-19 | 2025-11-19 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5 | [10 empty] | 5 | 0.033333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1.2.8
1746 | 1.2 | 1.2.8.7.7.2 | Not Started | PSL | Relocate TOS2 to Hole 2 / String 88 | TOS2/Tower2: Relocate TOS2/Tower2 to Hole 2 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-11-19 | 2025-11-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1746 | 1.2 | 1.2.8.7.7.2 | Not Started | PSL | Relocate TOS2 to Hole 2 / String 88 | TOS2/Tower2: Relocate TOS2/Tower2 to Hole 2 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0 | 2025-11-19 | 2025-11-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1748 | 1.2 | 1.2.8.7.7.4 | Not Started | PSL | Cable Layout SES to TOS2 | TOS2/Tower2: Cable Layout SES to TOS2 |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-11-20 | 2025-11-25 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1748 | 1.2 | 1.2.8.7.7.4 | Not Started | PSL | Cable Layout SES to TOS2 | TOS2/Tower2: Cable Layout SES to TOS2 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-20 | 2025-11-25 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1749 | 1.2 | 1.2.8.7.7.5 | Not Started | PSL | TOS2 Network/Comms Install | TOS2/Tower2: TOS2 Network/Comms Install |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-11-20 | 2025-11-25 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1750 | 1.2 | 1.2.8.7.7.6 | Not Started | PSL | Make TOS2 Operational, Deliver Fuel, Fire Furnace | TOS2/Tower2:Make TOS2 Operational, Deliver Fuel, Fire Furnace |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-11-25 | 2025-11-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | [10 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.8
1750 | 1.2 | 1.2.8.7.7.6 | Not Started | PSL | Make TOS2 Operational, Deliver Fuel, Fire Furnace | TOS2/Tower2:Make TOS2 Operational, Deliver Fuel, Fire Furnace |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-11-25 | 2025-11-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | [10 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.8
1750 | 1.2 | 1.2.8.7.7.6 | Not Started | PSL | Make TOS2 Operational, Deliver Fuel, Fire Furnace | TOS2/Tower2:Make TOS2 Operational, Deliver Fuel, Fire Furnace |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-25 | 2025-11-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 16 | [10 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.8
1753 | 1.2 | 1.2.8.7.8.1 | Not Started | PSL | Begin Circulation of Water & Fire Boilers | Wet Test: Begin Circulation of Water & Fire Boilers |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-11-25 | 2025-12-02 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | [10 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.8
1753 | 1.2 | 1.2.8.7.8.1 | Not Started | PSL | Begin Circulation of Water & Fire Boilers | Wet Test: Begin Circulation of Water & Fire Boilers |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-11-25 | 2025-12-02 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80 | [10 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.8
1754 | 1.2 | 1.2.8.7.8.2 | Not Started | PSL | Develop & Establish Rodwell | Wet Test: Develop & Establish Rodwell |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-01 | 2025-12-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 165 | [9 empty] | 165 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 1.2.8
1754 | 1.2 | 1.2.8.7.8.2 | Not Started | PSL | Develop & Establish Rodwell | Wet Test: Develop & Establish Rodwell |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-01 | 2025-12-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 448 | [9 empty] | 448 | 2.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448 | 1.2.8
1755 | 1.2 | 1.2.8.7.8.3 | Not Started | PSL | New Driller Training | Wet Test: New Driller Training (Engineer/Drillers - 3) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-03 | 2025-12-09 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 96 | [9 empty] | 96 | 0.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 1.2.8
1755 | 1.2 | 1.2.8.7.8.3 | Not Started | PSL | New Driller Training | Wet Test: New Driller Training (Direct Hire Drillers -15) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-03 | 2025-12-09 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 650 | [9 empty] | 650 | 4.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 1.2.8
1756 | 1.2 | 1.2.8.7.8.4 | Not Started | PSL | Emergency & Safety Systems Tests | Wet Test: Emergency & Safety Systems Tests |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-03 | 2025-12-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | [9 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1756 | 1.2 | 1.2.8.7.8.4 | Not Started | PSL | Emergency & Safety Systems Tests | Wet Test: Emergency & Safety Systems Tests |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-03 | 2025-12-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | [9 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1756 | 1.2 | 1.2.8.7.8.4 | Not Started | PSL | Emergency & Safety Systems Tests | Wet Test: Emergency & Safety Systems Tests |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-03 | 2025-12-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1757 | 1.2 | 1.2.8.7.8.5 | Not Started | PSL | Perform Complete Systems Testing (Wet-test & Comm) | Wet Test: Perform Complete Systems Testing (Wet Test & Comm.) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-08 | 2025-12-12 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 144 | [9 empty] | 144 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 1.2.8
1757 | 1.2 | 1.2.8.7.8.5 | Not Started | PSL | Perform Complete Systems Testing (Wet-test & Comm) | Wet Test: Perform Complete Systems Testing (Wet Test & Comm.) |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-08 | 2025-12-12 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 144 | [9 empty] | 144 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 1.2.8
1757 | 1.2 | 1.2.8.7.8.5 | Not Started | PSL | Perform Complete Systems Testing (Wet-test & Comm) | Wet Test: Perform Complete Systems Testing (Wet Test & Comm.) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-08 | 2025-12-12 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 500 | [9 empty] | 500 | 3.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1.2.8
1758 | 1.2 | 1.2.8.7.8.6 | Not Started | PSL | Readiness Review/Safety Refresher | Wet Test: Readiness Review/Safety Refresher |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-12 | 2025-12-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 45 | [9 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.8
1758 | 1.2 | 1.2.8.7.8.6 | Not Started | PSL | Readiness Review/Safety Refresher | Wet Test: Readiness Review/Safety Refresher |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-12 | 2025-12-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1758 | 1.2 | 1.2.8.7.8.6 | Not Started | PSL | Readiness Review/Safety Refresher | Wet Test: Readiness Review/Safety Refresher |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-12 | 2025-12-15 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 108 | [9 empty] | 108 | 0.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 1.2.8
1762 | 1.2 | 1.2.8.7.9.1.1 | Not Started | PSL | Drill Hole 1 / String 87 | Deep Drilling: DRILL HOLE 1 / String 87 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-15 | 2025-12-17 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 148 | [9 empty] | 148 | 0.98667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 1.2.8
1762 | 1.2 | 1.2.8.7.9.1.1 | Not Started | PSL | Drill Hole 1 / String 87 | Deep Drilling: DRILL HOLE 1 / String 87 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-15 | 2025-12-17 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 374 | [9 empty] | 374 | 2.4933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374 | 1.2.8
1764 | 1.2 | 1.2.8.7.9.1.3 | Not Started | PSL | Installation - Hole 1 / String 87 - Driller Supported | Deep Drilling: Installation - Hole 1 / String 87 - Driller Support |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-17 | 2025-12-19 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | [9 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1765 | 1.2 | 1.2.8.7.9.1.4 | Not Started | PSL | Relocate Hose, Cable Reels to Hole 2 / String 88 | Deep Drilling: Relocate Hose, Cable Reels (Hole 2 / String 88) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-17 | 2025-12-18 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1765 | 1.2 | 1.2.8.7.9.1.4 | Not Started | PSL | Relocate Hose, Cable Reels to Hole 2 / String 88 | Deep Drilling: Relocate Hose, Cable Reels (Hole 2 / String 88) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-17 | 2025-12-18 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 15 | [9 empty] | 15 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1.2.8
1767 | 1.2 | 1.2.8.7.9.1.6 | Not Started | PSL | Relocate Sensor Handling Structure to Hole 2 / String 88 | Deep Drilling: Relocate Sensor Handling Structure to Hole 2 / String 88 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-19 | 2025-12-19 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1768 | 1.2 | 1.2.8.7.9.1.7 | Not Started | PSL | Uncover Hole 3 / String 89 | Deep Drilling: Uncover Hole 3/ String 89 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-20 | 2025-12-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1769 | 1.2 | 1.2.8.7.9.1.8 | Not Started | PSL | Closeout & Relocate Tower & TOS-1 to Hole 3 / String 89 | Deep Drilling: Closeout & Relocate Tower & TOS1 to Hole 3/ String 89 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-20 | 2025-12-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1769 | 1.2 | 1.2.8.7.9.1.8 | Not Started | PSL | Closeout & Relocate Tower & TOS-1 to Hole 3 / String 89 | Deep Drilling: Closeout & Relocate Tower & TOS1 to Hole 3/ String 89 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-20 | 2025-12-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 23 | [9 empty] | 23 | 0.15333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1.2.8
1771 | 1.2 | 1.2.8.7.9.1.10 | Not Started | PSL | Trench & Install Reel Anchors at Hole 3 / String 89 | Deep Drilling: Trench & Install Reel Anchors (Hole 3 / String 89) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-20 | 2025-12-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1773 | 1.2 | 1.2.8.7.9.1.12 | Not Started | PSL | Prepare MCA Cable (Mount on TU20, test slip ring) for Hole 3 / String 89 | Deep Drilling: Prepare MCA Cable (Mount on TU20, test slip ring) for Hole 3/String 89 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-20 | 2025-12-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1773 | 1.2 | 1.2.8.7.9.1.12 | Not Started | PSL | Prepare MCA Cable (Mount on TU20, test slip ring) for Hole 3 / String 89 | Deep Drilling: Prepare MCA Cable (Mount on TU20, test slip ring) for Hole 3/String 89 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-20 | 2025-12-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1775 | 1.2 | 1.2.8.7.9.2 | Not Started | PSL | Operational Debrief/Drill Maintenance | Deep Drilling: Operational Debrief |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0% | 2025-12-20 | 2025-12-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | [9 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1775 | 1.2 | 1.2.8.7.9.2 | Not Started | PSL | Operational Debrief/Drill Maintenance | Deep Drilling: Operational Debrief |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-20 | 2025-12-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 180 | [9 empty] | 180 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 1.2.8
1777 | 1.2 | 1.2.8.7.9.3.1 | Not Started | PSL | Drill Hole 2 / String 88 | Deep Drilling: DRILL HOLE 2 / String 88 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-12-21 | 2025-12-23 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 148 | [9 empty] | 148 | 0.98667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 1.2.8
1777 | 1.2 | 1.2.8.7.9.3.1 | Not Started | PSL | Drill Hole 2 / String 88 | Deep Drilling: DRILL HOLE 2 / String 88 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-21 | 2025-12-23 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 374 | [9 empty] | 374 | 2.4933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374 | 1.2.8
1779 | 1.2 | 1.2.8.7.9.3.3 | Not Started | PSL | Installation - Hole 2 / String 88 - Driller Supported | Deep Drilling: Installation - Hole 2 / String 88 - Driller Support |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-23 | 2025-12-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | [9 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1780 | 1.2 | 1.2.8.7.9.3.4 | Not Started | PSL | Relocate Hose, Cable Reels to Hole 3 / String 89 | Deep Drilling: Relocate Hose, Cable Reels to Hole 3 / String 89 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-12-23 | 2025-12-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1780 | 1.2 | 1.2.8.7.9.3.4 | Not Started | PSL | Relocate Hose, Cable Reels to Hole 3 / String 89 | Deep Drilling: Relocate Hose, Cable Reels to Hole 3 / String 89 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-23 | 2025-12-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1782 | 1.2 | 1.2.8.7.9.3.6 | Not Started | PSL | Relocate Sensor Handling Structure to Hole 3 / String 89 | Deep Drilling: Relocate Sensor Handling Structure to Hole 3 / String 89 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-24 | 2025-12-24 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1783 | 1.2 | 1.2.8.7.9.3.7 | Not Started | PSL | Uncover Hole 4 / String 90 | Deep Drilling: Uncover Hole 4/String 90 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-25 | 2025-12-25 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1786 | 1.2 | 1.2.8.7.9.3.8 | Not Started | PSL | Closeout & Relocate Tower & TOS2 to Hole 4 / String 90 | Deep Drilling: Closeout & Relocate Tower & TOS to Hole 4 / String 90 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-12-25 | 2025-12-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1786 | 1.2 | 1.2.8.7.9.3.8 | Not Started | PSL | Closeout & Relocate Tower & TOS2 to Hole 4 / String 90 | Deep Drilling: Closeout & Relocate Tower & TOS to Hole 4 / String 90 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-25 | 2025-12-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 23 | [9 empty] | 23 | 0.15333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1.2.8
1788 | 1.2 | 1.2.8.7.9.3.10 | Not Started | PSL | Trench & Install Reel Anchors at Hole 4 / String 90 | Deep Drilling: Trench & Install Reel Anchors (Hole 4 / String 90) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-26 | 2025-12-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1784 | 1.2 | 1.2.8.7.9.3.12 | Not Started | PSL | Prepare MCA (Mount on TU20, test slip ring) - Prep for Hole 4 / String 90 | Deep Drilling: Prepare MCA (Mount on TU20, test slip ring) - Prep for Hole 4 / String 90 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-12-26 | 2025-12-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1784 | 1.2 | 1.2.8.7.9.3.12 | Not Started | PSL | Prepare MCA (Mount on TU20, test slip ring) - Prep for Hole 4 / String 90 | Deep Drilling: Prepare MCA (Mount on TU20, test slip ring) - Prep for Hole 4 / String 90 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-26 | 2025-12-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1791 | 1.2 | 1.2.8.7.9.4.1 | Not Started | PSL | Drill Hole 3 / String 89 | Deep Drilling: DRILL HOLE 3 / String 90 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-12-24 | 2025-12-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 148 | [9 empty] | 148 | 0.98667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 1.2.8
1791 | 1.2 | 1.2.8.7.9.4.1 | Not Started | PSL | Drill Hole 3 / String 89 | Deep Drilling: DRILL HOLE 3 / String 90 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-24 | 2025-12-26 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 374 | [9 empty] | 374 | 2.4933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374 | 1.2.8
1793 | 1.2 | 1.2.8.7.9.4.3 | Not Started | PSL | Installation - Hole 3 / String 89 - Driller Supported | Deep Drilling: Installation - Hole 3 / String 89 - Driller Support |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-26 | 2025-12-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | [9 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1794 | 1.2 | 1.2.8.7.9.4.4 | Not Started | PSL | Relocate Hose, Cable Reels to Hole 4 / String 90 | Deep Drilling: Relocate Hose, Cable Reels to Hole 4 / String 90 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-12-26 | 2025-12-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1794 | 1.2 | 1.2.8.7.9.4.4 | Not Started | PSL | Relocate Hose, Cable Reels to Hole 4 / String 90 | Deep Drilling: Relocate Hose, Cable Reels to Hole 4 / String 90 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-26 | 2025-12-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1796 | 1.2 | 1.2.8.7.9.4.6 | Not Started | PSL | Relocate Sensor Handling Structure to Hole 4 / String 90 | Deep Drilling: Relocate Sensor Handling Structure to Hole 4 / String 90 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-27 | 2025-12-27 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1799 | 1.2 | 1.2.8.7.9.4.7 | Not Started | PSL | Uncover Hole 5 / String 91 | Deep Drilling: Uncover Hole 5 / String 91 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-28 | 2025-12-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1800 | 1.2 | 1.2.8.7.9.4.8 | Not Started | PSL | Closeout & Relocate Tower & TOS1 to Hole 5 / String 91 | Deep Drilling: Closeout & Relocate Tower & TOS for Hole 5 / String 91 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-12-28 | 2025-12-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1800 | 1.2 | 1.2.8.7.9.4.8 | Not Started | PSL | Closeout & Relocate Tower & TOS1 to Hole 5 / String 91 | Deep Drilling: Closeout & Relocate Tower & TOS for Hole 5 / String 91 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-28 | 2025-12-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 23 | [9 empty] | 23 | 0.15333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1.2.8
1802 | 1.2 | 1.2.8.7.9.4.10 | Not Started | PSL | Trench & Install Reel Anchors at Hole 5 / String 91 | Deep Drilling: Trench & Install Reel Anchors (Hole 5 / String 91) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-28 | 2025-12-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1797 | 1.2 | 1.2.8.7.9.4.12 | Not Started | PSL | Prepare MCA (Mount on TU20, test slip ring) - Prep for Hole 5 / String 91 | Deep Drilling: Prepare MCA (Mount on TU20, test slip ring) - Prep for String 5 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-12-28 | 2025-12-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1797 | 1.2 | 1.2.8.7.9.4.12 | Not Started | PSL | Prepare MCA (Mount on TU20, test slip ring) - Prep for Hole 5 / String 91 | Deep Drilling: Prepare MCA (Mount on TU20, test slip ring) - Prep for String 5 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-28 | 2025-12-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1806 | 1.2 | 1.2.8.7.9.6.1 | Not Started | PSL | Drill Hole 4 / String 90 | Deep Drilling: DRILL HOLE 4 / String 90 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-12-29 | 2025-12-31 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 148 | [9 empty] | 148 | 0.98667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 1.2.8
1806 | 1.2 | 1.2.8.7.9.6.1 | Not Started | PSL | Drill Hole 4 / String 90 | Deep Drilling: DRILL HOLE 4 / String 90 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-29 | 2025-12-31 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 374 | [9 empty] | 374 | 2.4933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374 | 1.2.8
1808 | 1.2 | 1.2.8.7.9.6.3 | Not Started | PSL | Installation - Hole 4 / String 90 - Driller Supported | Deep Drilling: Installation - Hole 4 / String 90 - Driller Support |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-31 | 2026-01-01 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1809 | 1.2 | 1.2.8.7.9.6.4 | Not Started | PSL | Relocate Hose, Cable Reels to Hole 5 / String 91 | Deep Drilling: Relocate Hose, Cable Reels to Hole 5 / String 91 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2025-12-31 | 2026-01-01 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1809 | 1.2 | 1.2.8.7.9.6.4 | Not Started | PSL | Relocate Hose, Cable Reels to Hole 5 / String 91 | Deep Drilling: Relocate Hose, Cable Reels to Hole 5 / String 91 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2025-12-31 | 2026-01-01 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1811 | 1.2 | 1.2.8.7.9.6.6 | Not Started | PSL | Relocate Sensor Handling Structure to Hole 5 / String 91 | Deep Drilling: Relocate Sensor Handling Structure to Hole 5 / String 91 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-01 | 2026-01-01 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1814 | 1.2 | 1.2.8.7.9.6.7 | Not Started | PSL | Uncover Hole 6 / String 92 | Deep Drilling: Uncover Hole 5 / String 91 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-02 | 2026-01-02 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 6 | [8 empty] | 6 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1.2.8
1815 | 1.2 | 1.2.8.7.9.6.8 | Not Started | PSL | Closeout & Relocate Tower & TOS2 for Hole 6 / String 92 | Deep Drilling: Closeout & Relocate Tower & TOS for Hole 6 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-02 | 2026-01-02 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1815 | 1.2 | 1.2.8.7.9.6.8 | Not Started | PSL | Closeout & Relocate Tower & TOS2 for Hole 6 / String 92 | Deep Drilling: Closeout & Relocate Tower & TOS for Hole 6 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-02 | 2026-01-02 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 23 | [8 empty] | 23 | 0.15333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1.2.8
1817 | 1.2 | 1.2.8.7.9.6.10 | Not Started | PSL | Trench & Install Reel Anchors at Hole 6 / String 92 | Deep Drilling: Trench & Install Reel Anchors (Hole 6 / String 92) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-02 | 2026-01-02 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 16 | [8 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1.2.8
1812 | 1.2 | 1.2.8.7.9.6.12 | Not Started | PSL | Prepare MCA Cable (Mount on TU20, test slip ring) - Prep for Hole 6 / String 92 | Deep Drilling: Prepare MCA (Mount on TU20, test slip ring) - Prep for String 6 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-02 | 2026-01-02 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1812 | 1.2 | 1.2.8.7.9.6.12 | Not Started | PSL | Prepare MCA Cable (Mount on TU20, test slip ring) - Prep for Hole 6 / String 92 | Deep Drilling: Prepare MCA (Mount on TU20, test slip ring) - Prep for String 6 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-02 | 2026-01-02 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1820 | 1.2 | 1.2.8.7.9.7.1 | Not Started | PSL | Drill Hole 5 / String 91 | Deep Drilling: DRILL HOLE 5 / String 91 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-01 | 2026-01-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 148 | [8 empty] | 148 | 0.98667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 1.2.8
1820 | 1.2 | 1.2.8.7.9.7.1 | Not Started | PSL | Drill Hole 5 / String 91 | Deep Drilling: DRILL HOLE 5 / String 91 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-01 | 2026-01-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 374 | [8 empty] | 374 | 2.4933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374 | 1.2.8
1822 | 1.2 | 1.2.8.7.9.7.3 | Not Started | PSL | Installation - Hole 5 / String 91 - Driller Supported | Deep Drilling: Installation - Hole 5 / String 91 - Driller Support |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-03 | 2026-01-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1823 | 1.2 | 1.2.8.7.9.7.4 | Not Started | PSL | Relocate Hose, Cable Reels to Hole 6 / String 92 | Deep Drilling: Relocate Hose, Cable Reels to Hole 6 / String 92 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-03 | 2026-01-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1823 | 1.2 | 1.2.8.7.9.7.4 | Not Started | PSL | Relocate Hose, Cable Reels to Hole 6 / String 92 | Deep Drilling: Relocate Hose, Cable Reels to Hole 6 / String 92 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-03 | 2026-01-03 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1825 | 1.2 | 1.2.8.7.9.7.6 | Not Started | PSL | Relocate Sensor Handling Structure to Hole 6 / String 92 | Deep Drilling: Relocate Sensor Handling Structure to Hole 6 / String 92 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-04 | 2026-01-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1826 | 1.2 | 1.2.8.7.9.7.7 | Not Started | PSL | Uncover Hole 7 / String 93 | Deep Drilling: Uncover Hole 7 / String 93 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-04 | 2026-01-04 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 6 | [8 empty] | 6 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1.2.8
1830 | 1.2 | 1.2.8.7.9.7.8 | Not Started | PSL | Closeout & Relocate Tower & TOS1 to Hole 7 / String 93 | Deep Drilling: Closeout & Relocate Tower & TOS1 for Hole 7 / String 93 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-04 | 2026-01-05 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1830 | 1.2 | 1.2.8.7.9.7.8 | Not Started | PSL | Closeout & Relocate Tower & TOS1 to Hole 7 / String 93 | Deep Drilling: Closeout & Relocate Tower & TOS1 for Hole 7 / String 93 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-04 | 2026-01-05 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1832 | 1.2 | 1.2.8.7.9.7.10 | Not Started | PSL | Trench & Install Reel Anchors at Hole 7 / String 93 | Deep Drilling: Trench & Install Reel Anchors (Hole 7 / String 93) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-04 | 2026-01-05 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1828 | 1.2 | 1.2.8.7.9.7.12 | Not Started | PSL | Prepare MCA Cable (Mount on TU20, test slip ring) - Prep for Hole 7 / String 93 | Deep Drilling: Prepare MCA (Mount on TU20, test slip ring) - Prep for Hole 7 / String 93 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-05 | 2026-01-05 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1828 | 1.2 | 1.2.8.7.9.7.12 | Not Started | PSL | Prepare MCA Cable (Mount on TU20, test slip ring) - Prep for Hole 7 / String 93 | Deep Drilling: Prepare MCA (Mount on TU20, test slip ring) - Prep for Hole 7 / String 93 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-05 | 2026-01-05 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1833 | 1.2 | 1.2.8.7.9.8 | Not Started | PSL | Operational Debrief | Deep Drilling: Operational Debrief |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-05 | 2026-01-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1833 | 1.2 | 1.2.8.7.9.8 | Not Started | PSL | Operational Debrief | Deep Drilling: Operational Debrief |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-05 | 2026-01-06 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 180 | [8 empty] | 180 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 1.2.8
1835 | 1.2 | 1.2.8.7.9.9.1 | Not Started | PSL | Drill Hole 6 / String 92 | Deep Drilling: DRILL HOLE 6 / String 92 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-06 | 2026-01-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 148 | [8 empty] | 148 | 0.98667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 1.2.8
1835 | 1.2 | 1.2.8.7.9.9.1 | Not Started | PSL | Drill Hole 6 / String 92 | Deep Drilling: DRILL HOLE 6 / String 92 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-06 | 2026-01-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 374 | [8 empty] | 374 | 2.4933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374 | 1.2.8
1837 | 1.2 | 1.2.8.7.9.9.3 | Not Started | PSL | Driller Support for Dust Logging Activities | Deep Drilling: Driller Support for Dust Logging Activities |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-08 | 2026-01-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 48 | [8 empty] | 48 | 0.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 1.2.8
1838 | 1.2 | 1.2.8.7.9.9.4 | Not Started | PSL | Installation - Hole 6 / String 92 - Driller Supported | Deep Drilling: Installation - Hole 6 / String 92 - Driller Support |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-08 | 2026-01-09 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1839 | 1.2 | 1.2.8.7.9.9.5 | Not Started | PSL | Relocate Hose & Cable Reels to Hole 7/ String 93 | Deep Drilling: Relocate Hose, Cable Reels to Hole 7 / String 93 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-08 | 2026-01-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1839 | 1.2 | 1.2.8.7.9.9.5 | Not Started | PSL | Relocate Hose & Cable Reels to Hole 7/ String 93 | Deep Drilling: Relocate Hose, Cable Reels to Hole 7 / String 93 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-08 | 2026-01-08 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1841 | 1.2 | 1.2.8.7.9.9.7 | Not Started | PSL | Relocate Sensor Handling Structure to Hole 7 / String 93 | Deep Drilling: Relocate Sensor Handling Structure to Hole 7 / String 93 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-09 | 2026-01-09 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1842 | 1.2 | 1.2.8.7.9.9.8 | Not Started | PSL | Closeout & Relocate Tower & TOS2 to Storage | Deep Drilling: Closeout & Relocate Tower & TOS2 to Storage |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-10 | 2026-01-10 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.8
1842 | 1.2 | 1.2.8.7.9.9.8 | Not Started | PSL | Closeout & Relocate Tower & TOS2 to Storage | Deep Drilling: Closeout & Relocate Tower & TOS2 to Storage |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-10 | 2026-01-10 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1845 | 1.2 | 1.2.8.7.9.10.1 | Not Started | PSL | Drill Hole 7 / String 93 | Deep Drilling: DRILL HOLE 7 / String 93 |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-08 | 2026-01-11 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 148 | [8 empty] | 148 | 0.98667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 1.2.8
1845 | 1.2 | 1.2.8.7.9.10.1 | Not Started | PSL | Drill Hole 7 / String 93 | Deep Drilling: DRILL HOLE 7 / String 93 |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-08 | 2026-01-11 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 374 | [8 empty] | 374 | 2.4933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374 | 1.2.8
1847 | 1.2 | 1.2.8.7.9.10.3 | Not Started | PSL | Installation - Hole 7 / String 93 - Driller Supported | Deep Drilling: Installation - Hole 7 / String 93 - Driller Support |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-11 | 2026-01-12 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1848 | 1.2 | 1.2.8.7.9.10.4 | Not Started | PSL | Closeout & Relocate Tower & TOS1 to Storage | Deep Drilling: Closeout & Relocate Tower & TOS1 to Storage |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-12 | 2026-01-13 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.8
1848 | 1.2 | 1.2.8.7.9.10.4 | Not Started | PSL | Closeout & Relocate Tower & TOS1 to Storage | Deep Drilling: Closeout & Relocate Tower & TOS1 to Storage |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-12 | 2026-01-13 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1851 | 1.2 | 1.2.8.7.9.12 | Not Started | PSL | Operational Debrief | Deep Drilling: Operational Debrief |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-13 | 2026-01-13 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 1.2.8
1851 | 1.2 | 1.2.8.7.9.12 | Not Started | PSL | Operational Debrief | Deep Drilling: Operational Debrief |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-13 | 2026-01-13 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 180 | [8 empty] | 180 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 1.2.8
1855 | 1.2 | 1.2.8.7.10.2 | Not Started | PSL | Drain and Decommission EHWD Components | Decommission and Store: Remove & Retro/Store All DNF |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-14 | 2026-01-19 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 165 | [8 empty] | 165 | 1.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165 | 1.2.8
1855 | 1.2 | 1.2.8.7.10.2 | Not Started | PSL | Drain and Decommission EHWD Components | Decommission and Store: Remove & Retro/Store All DNF |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-14 | 2026-01-19 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 195 | [8 empty] | 195 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 1.2.8
1856 | 1.2 | 1.2.8.7.10.3 | Not Started | PSL | Remove & Retro/Store All DNF | Decommission and Store: Disconnect All Interconnects |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-14 | 2026-01-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 137 | [8 empty] | 137 | 0.91333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137 | 1.2.8
1856 | 1.2 | 1.2.8.7.10.3 | Not Started | PSL | Remove & Retro/Store All DNF | Decommission and Store: Disconnect All Interconnects |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-14 | 2026-01-20 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 54 | [8 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1857 | 1.2 | 1.2.8.7.10.4 | Not Started | PSL | Disconnect all Interconnect Cables & Hoses (All including SES to TOS) | Decommission and Store: Disconnect all Interconnect Cables & Hoses (All including SES to TOS) |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-14 | 2026-01-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 54 | [8 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.8
1857 | 1.2 | 1.2.8.7.10.4 | Not Started | PSL | Disconnect all Interconnect Cables & Hoses (All including SES to TOS) | Decommission and Store: Disconnect all Interconnect Cables & Hoses (All including SES to TOS) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-14 | 2026-01-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 157 | [8 empty] | 157 | 1.0467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 1.2.8
1858 | 1.2 | 1.2.8.7.10.5 | Not Started | PSL | Decommission SES | Decommission and Store: Decommission SES |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-14 | 2026-01-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 195 | [8 empty] | 195 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 1.2.8
1858 | 1.2 | 1.2.8.7.10.5 | Not Started | PSL | Decommission SES | Decommission and Store: Decommission SES |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-14 | 2026-01-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.8
1858 | 1.2 | 1.2.8.7.10.5 | Not Started | PSL | Decommission SES | Decommission and Store: Decommission SES |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-14 | 2026-01-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 270 | [8 empty] | 270 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 1.2.8
1859 | 1.2 | 1.2.8.7.10.6 | Not Started | PSL | Decommission TOS | Decommission and Store: Decommission TOS |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-15 | 2026-01-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1859 | 1.2 | 1.2.8.7.10.6 | Not Started | PSL | Decommission TOS | Decommission and Store: Decommission TOS |  | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-15 | 2026-01-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1859 | 1.2 | 1.2.8.7.10.6 | Not Started | PSL | Decommission TOS | Decommission and Store: Decommission TOS |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-15 | 2026-01-22 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 144 | [8 empty] | 144 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 1.2.8
1860 | 1.2 | 1.2.8.7.10.7 | Not Started | PSL | Winterize all EHWD Equipment | Decommission and Store: Drain and Winterize EHWD components |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-23 | 2026-01-29 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 175 | [8 empty] | 175 | 1.1667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 1.2.8
1860 | 1.2 | 1.2.8.7.10.7 | Not Started | PSL | Winterize all EHWD Equipment | Decommission and Store: Drain and Winterize EHWD components |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-23 | 2026-01-29 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 305 | [8 empty] | 305 | 2.0333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 305 | 1.2.8
1864 | 1.2 | 1.2.8.7.10.10.1 | Not Started | PSL | Remove Drill Hose from MSHR and Respool Individually | Decommission and Store: Remove Drill Hose from MSHR, Respool Individually |  | 0% | Labor Hours | Labor - Task | EN-ME |  |  | D - Expert Opinion | 0 | 115 | 0 | 2026-01-16 | 2026-01-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.8
1864 | 1.2 | 1.2.8.7.10.10.1 | Not Started | PSL | Remove Drill Hose from MSHR and Respool Individually | Decommission and Store: Remove Drill Hose from MSHR, Respool Individually |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-16 | 2026-01-21 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 180 | [8 empty] | 180 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 1.2.8
1866 | 1.2 | 1.2.8.7.10.10.3 | Not Started | PSL | Deliver to Cargo Yard and Prepare for Shipping (Driller & USAP) | Decommission and Store: UNL Equipment - Deliver to Cargo for Retro or Redistribution |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 0 | 77 | 0% | 2026-01-22 | 2026-01-28 | 0% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 80 | [8 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 1.2.8
1883 | 1.2 | 1.2.8.7.13 | Not Started | PSL | On-Ice Labor (FS3) | On-Ice Labor (FS3) (PSL Engineers) |  | 0% | Labor Hours | Labor - Task | EN |  |  | D - Expert Opinion | 85.1852 | 115 | 0% | 2025-10-31 | 2026-02-02 | 0% | On Ice | C2 |  |  |  |  | EE/ME Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 702 | 1872 | 1467 | [8 empty] | 4041 | 26.94 | 0 | 65111.0453 | 173629.4542 | 136065.3896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374805.8892 | 0 | 374805.8892 | 374805.8892 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 374805.8892 | 0 | 0 | 0 | 0 | 0 | 4041 | 1.2.8
1883 | 1.2 | 1.2.8.7.13 | Not Started | PSL | On-Ice Labor (FS3) | On-Ice Labor (FS3) (PSL Contract Drillers) |  | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 57.037 | 77 | 0% | 2025-10-31 | 2026-02-02 | 0% | On Ice | C2 |  |  |  |  | Technician Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1890 | 4680 | 3825 | [8 empty] | 10395 | 69.3 | 0 | 117374.0918 | 290640.6082 | 237542.8048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 645557.5047 | 0 | 645557.5047 | 645557.5047 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 645557.5047 | 0 | 0 | 0 | 0 | 0 | 10395 | 1.2.8
1883 | 1.2 | 1.2.8.7.13 | Not Started | UW | On-Ice Labor (FS3) | On-Ice Labor (FS3) (Safety Engineer) | Zernick | 0% | Labor Hours | Labor - Task | EN-S |  |  | D - Expert Opinion | 44.96 | 46 | 35% | 2025-10-31 | 2026-02-02 | 53% | On Ice | C2 |  |  |  |  | Safety Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 144 | 234 | 234 | [8 empty] | 612 | 4.08 | 0 | 9516.4736 | 15464.2696 | 15464.2696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40445.0128 | 21435.8568 | 61880.8696 | 61880.8696 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 29959.2687 | 0 | 0 | 0 | 0 | 10485.7441 | 612 | 1.2.8
1887 | 1.2 | 1.2.9.1.1 | Should have Started | UW | Finalize Sensor Handling Process | Off-Ice Install: Finalize Sensor Handling Process | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 52 | 52 | 35% | 2022-01-02 | 2022-02-10 | 53% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1887 | 1.2 | 1.2.9.1.1 | Should have Started | PSL | Finalize Sensor Handling Process | Off-Ice Install: Finalize Sensor Handling Process | Nesbitt | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-01-02 | 2022-02-10 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1890 | 1.2 | 1.2.9.1.3.1 | Not Started | PSL | Spec Sensor Handling Equipment | Off-Ice Install: Spec Sensor Handling Equipment | Nesbitt | 0.4444% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-08-15 | 2022-09-15 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1891 | 1.2 | 1.2.9.1.3.2 | Not Started | UW | Procure Sensor Handling Equipment | Off-Ice Install: Procure Sensor Handling Equipment |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-09-16 | 2022-10-13 | 53% | Off Ice | C3 | [5 empty] | 8453 | [13 empty] | 8634.7395 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8634.7395 | 0 | 8634.7395 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8634.7395 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1892 | 1.2 | 1.2.9.1.3.3 | Not Started | UW | Procure ESD Mitigation Equipment | Off-Ice Install: Procure ESD Sensor Handling Equipment |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-09-20 | 2022-10-17 | 53% | Off Ice | C4 |  |  |  |  | Lab coats, ESDgloves, ESD runners | 5549 | [13 empty] | 5668.3035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5668.3035 | 0 | 5668.3035 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5668.3035 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1894 | 1.2 | 1.2.9.1.4.1 | Should have Started | PSL | Finalize Sensor Handling Facility Design | Off-Ice Install: Finalize Sensor Handling Facility Design | Nesbitt | 0.3333% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-01-15 | 2022-02-10 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1894 | 1.2 | 1.2.9.1.4.1 | Should have Started | PSL | Finalize Sensor Handling Facility Design | Off-Ice Install: Finalize Sensor Handling Facility Design | Drafting | 2.167% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2022-01-15 | 2022-02-10 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1895 | 1.2 | 1.2.9.1.4.2 | Not Started | PSL | Sensor Handling Facility Design Review | Off-Ice Install: Sensor Handling Facility Design Review | PSL Eng | 0.1111% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-02-15 | 2022-02-15 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1897 | 1.2 | 1.2.9.1.4.4 | Not Started | PSL | Procure Sensor Handling Facility Materials (or Administer Subcontract) | Off-Ice Install: Procure Sensor Handling Facility Materials (or Administer Subcontract) | Nesbitt | 0.8889% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-02-16 | 2022-05-10 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1897 | 1.2 | 1.2.9.1.4.4 | Not Started | PSL | Procure Sensor Handling Facility Materials (or Administer Subcontract) | Off-Ice Install: Procure Sensor Handling Facility Materials (or Administer Subcontract) |  |  | M & S | M & S | [5 empty] | 1 | 0% | 2022-02-16 | 2022-05-10 | 53% | Off Ice | [5 empty] | Cost includes building materials, crane and crane fork. Truck crane estimated 25k. Dolly, conveyor and lifting table procurement pushed to PY5. | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1898 | 1.2 | 1.2.9.1.4.5 | Not Started | PSL | Fabricate and Assemble Sensor Handling Structure at PSL and Verify Function | Off-Ice Install: Fabricate and Assemble Sensor Handling Facility and Verify Function | Nesbitt | 1.778% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-05-11 | 2022-08-23 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3680 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1898 | 1.2 | 1.2.9.1.4.5 | Not Started | PSL | Fabricate and Assemble Sensor Handling Structure at PSL and Verify Function | Off-Ice Install: Fabricate and Assemble Sensor Handling Facility and Verify Function |  | 8.944% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2022-05-11 | 2022-08-23 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 12397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1899 | 1.2 | 1.2.9.1.4.6 | Not Started | UW | Disassemble Sensor Handling Structure Marking for Reassembly | Off-Ice Install: Disassemble Sensor Handling Structure Marking for Reassembly | Tosi | 0% | Labor Hours | Labor - LoE | EN |  |  |  | 52 | 49 | 35% | 2022-08-29 | 2022-09-06 | 53% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1899 | 1.2 | 1.2.9.1.4.6 | Not Started | PSL | Disassemble Sensor Handling Structure Marking for Reassembly | Off-Ice Install: Disassemble Sensor Handling Structure Marking for Reassembly | PSL Tech | 0.4444% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2022-08-29 | 2022-09-06 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1901 | 1.2 | 1.2.9.1.5.1 | Not Started | UW | Finalize Sensor Sled Design in Collaboration with USAP Contractor | Off-Ice Install: Finalize Sensor Sled Design in Collaboration with USAP Contractor | Tosi | 0% | Labor Hours | Labor - LoE | EN |  |  |  | 52 | 49 | 35% | 2022-02-11 | 2022-06-01 | 53% | Off Ice | [5 empty] | Pending usage request of existing sleds | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1904 | 1.2 | 1.2.9.1.6.1 | Not Started | UW | Coordinate with USAP Contractor on Requirements, Tent Availability, and Sensor Staging Site | Off-Ice Install: Coordinate with USAP Contractor on Requirements, Tent Availability, and Sensor Staging Site | McEwen | 0% | Labor Hours | Labor - LoE | EN |  |  |  | 61 | 49 | 35% | 2022-02-11 | 2022-06-01 | 53% | Off Ice | [5 empty] | Pending usage request of existing tent | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1906 | 1.2 | 1.2.9.2.1 | Should have Started | UW | Procure Installation Hardware Samples | Off-Ice Install: Procure Installation Hardware Samples |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2021-11-01 | 2022-08-01 | 53% | Off Ice | [5 empty] | Tosi LOE hours covered 1.2.1 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1907 | 1.2 | 1.2.9.2.2 | Started | UW | Preliminary Installation Hardware Sample Test | Off-Ice Install: Test Installation Hardware Sample | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2022-03-01 | 2022-06-01 | 53% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1908 | 1.2 | 1.2.9.2.3 | Not Started | UW | Preliminary Installation Procedure Draft | Off-Ice Install: Preliminary Installation Procedure Draft | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2022-03-01 | 2022-08-15 | 53% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1909 | 1.2 | 1.2.9.2.4 | Not Started | UW | Preliminary Installation Procedure Test | Off-Ice Install: Installation Procedure Test | Tosi/Karle | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2022-04-01 | 2022-08-15 | 53% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1909 | 1.2 | 1.2.9.2.4 | Not Started | PSL | Preliminary Installation Procedure Test | Off-Ice Install: Installation Procedure Test | Benson | 0.2222% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-04-01 | 2022-08-15 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1909 | 1.2 | 1.2.9.2.4 | Not Started | PSL | Preliminary Installation Procedure Test | Off-Ice Install: Installation Procedure Test |  | 0.8889% | Labor Hours | Labor - Task | TE |  |  |  | 77 | 77 | 0% | 2022-04-01 | 2022-08-15 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1910 | 1.2 | 1.2.9.2.5 | Started | PSL | Installation Hardware and Procedure Review | Off-Ice Install: Installation Hardware and Procedure Review |  | 0.8889% | Labor Hours | Labor - Task | EN-ME |  |  |  | 115 | 115 | 0% | 2022-09-15 | 2022-09-15 | 0% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1911 | 1.2 | 1.2.9.2.6 | Started | UW | Finalize Installation Hardware and Procedure | Off-Ice Install: Finalize Installation Hardware and Procedure | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2022-09-16 | 2022-10-14 | 53% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1913 | 1.2 | 1.2.9.2.8 | Started | UW | Procure Installation Hardware | Off-Ice Install: Procure Installation Hardware | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2022-11-04 | 2023-01-30 | 53% | Off Ice | [5 empty] | Dr. Tosi will procure. Labor hours covered in LOE 1.2.1.3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1913 | 1.2 | 1.2.9.2.8 | Started | UW | Procure Installation Hardware | Off-Ice Install: Procure Installation Hardware |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2022-11-04 | 2023-01-30 | 53% | Off Ice | C3 | [6 empty] | 36000 | 36000 | 36000 | [10 empty] | 0 | 36774 | 36774 | 36774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110322 | 0 | 110322 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110322 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1914 | 1.2 | 1.2.9.2.9 | Not Started | UW | Procure Installation Weights | Off-Ice Install: Procure Installation Weights | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2022-11-04 | 2023-01-04 | 53% | Off Ice | [5 empty] | Dr. Tosi will be primary on procurement with her labor hours covered in LOE 1.2.1.3. PSL Engineering support required for product review. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1914 | 1.2 | 1.2.9.2.9 | Not Started | UW | Procure Installation Weights | Off-Ice Install: Procure Installation Weights |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-11-04 | 2023-01-04 | 53% | Off Ice | C4 | [6 empty] | 3300 | 3300 | 3300 | [10 empty] | 0 | 3370.95 | 3370.95 | 3370.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10112.85 | 0 | 10112.85 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10112.85 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1915 | 1.2 | 1.2.9.2.10 | Not Started | UW | Receive, & Inspect Installation Materials | Off-Ice Install: Receive, & Inspect Installation Materials | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2023-03-01 | 2023-03-28 | 53% | Off Ice | [5 empty] | Tosi LOE hours covered 1.2.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1916 | 1.2 | 1.2.9.2.11 | Not Started | UW | Assemble Installation Kits | Off-Ice Install: Assemble Installation Kits | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2023-03-29 | 2023-06-20 | 53% | Off Ice | [5 empty] | Tosi LOE hours covered 1.2.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1919 | 1.2 | 1.2.9.3.1.1 | Not Started | UW | IME TOS Connectivity Tester Design & Initial Procurement for Prototype (2021-22) | Off-ice Install: IME Connectivity Tester Design & Initial Procurement for Prototype (2021-22) | Sandstrom + 1 | 0% | Labor Hours | Labor - LoE | EN-EE |  |  |  | 64 | 46 | 35% | 2022-06-01 | 2022-09-30 | 53% | Off Ice | [5 empty] | See IME estimate (Installation Monitor Equipment). Sandstrom LOE | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1919 | 1.2 | 1.2.9.3.1.1 | Not Started | UW | IME TOS Connectivity Tester Design & Initial Procurement for Prototype (2021-22) | Off-Ice Install: IME Connectivity Tester Design & Initial Procurement for Prototype (2021-22) |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-06-01 | 2022-09-30 | 53% | Off Ice | [5 empty] | 1 IME Depth Readout and all the Connectivity Tester (can't add separate line) | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1920 | 1.2 | 1.2.9.3.1.2 | Not Started | UW | IME TOS Connectivity Tester Development and System Integration (2022-23) | Off-Ice Install: IME Connectivity Tester Development and System Integration (2022-23) | Sandstrom | 0% | Labor Hours | Labor - LoE | SS |  |  |  | 64 | 66 | 35% | 2022-10-03 | 2023-10-02 | 53% | Off Ice | [5 empty] | WIPAC Engineering - LOE | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1924 | 1.2 | 1.2.9.3.2.1 | Not Started | UW | IME ICL Quad Connectivity Tester Design, Prototype, Production (2023-24) | Off-ice Install: IME ICL Quad Connectivity Tester Design, Prototype & Production (2023-24) | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2023-10-01 | 2024-10-03 | 53% | Off Ice | [5 empty] | 80 hours, LoE | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1924 | 1.2 | 1.2.9.3.2.1 | Not Started | UW | IME ICL Quad Connectivity Tester Design, Prototype, Production (2023-24) | Off-ice Install: IME ICL Quad Connectivity Tester Design, Prototype & Production (2023-24) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2023-10-01 | 2024-10-03 | 53% | Off Ice | C4 |  |  |  |  | IME ICL QCT | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 600 | 600 | 600 |  | 2000 | 1000 | [6 empty] | 0 | 0 | 626.0774 | 626.0774 | 626.0774 | 0 | 2086.9245 | 1043.4623 | 0 | 0 | 0 | 0 | 5008.6188 | 0 | 5008.6188 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5008.6188 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1924 | 1.2 | 1.2.9.3.2.1 | Not Started | UW | IME ICL Quad Connectivity Tester Design, Prototype, Production (2023-24) | Off-ice Install: IME ICL Quad Connectivity Tester Design, Prototype & Production (2023-24) | Domestic |  | Travel | Travel |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2023-10-01 | 2024-10-03 | 53% | Off Ice | C1 |  |  |  |  | IME ICL QCT 1 domestic travel to NTS at MSU | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 900 | 900 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.116 | 939.116 | 0 | 0 | 0 | 1878.2321 | 995.463 | 2873.695 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2873.695 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1927 | 1.2 | 1.2.9.3.3.1 | Not Started | PSL | IME Depth Readout Design & Initial Procurement for Prototype (2021-22) | Off-ice Install: IME Depth Readout Design & Initial Procurement for Prototype (2021-22) | Wisniewski | 4.444% | Labor Hours | Labor - Task | EN-EE |  |  |  | 115 | 115 | 0% | 2022-04-01 | 2022-09-30 | 0% | Off Ice | [5 empty] | PSL Labor copied to PY5 due to change in design (PY4 labor is mostly in house) See IME estimate | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1927 | 1.2 | 1.2.9.3.3.1 | Not Started | UW | IME Depth Readout Design & Initial Procurement for Prototype (2021-22) | Off-ice Install: IME Depth Readout Design & Initial Procurement for Prototype (2021-22) |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-04-01 | 2022-09-30 | 53% | Off Ice | [5 empty] | 1 IME Depth Readout and all the Connectivity Tester (can't add separate line) | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1928 | 1.2 | 1.2.9.3.3.2 | Not Started | PSL | IME Depth Readout Development and System Integration (2022-23) | Off-ice Install: IME Depth Readout Development and System Integration (2022-23) | Wisniewski | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0 | 2022-10-03 | 2023-10-02 | 0% | Off Ice | C3 |  |  |  |  | Duplicate system (1/TOS plus spares) | [7 empty] | 10 | 20 | 20 | 10 |  | 60 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 2349.45 | 2349.45 | 1174.725 | 0 | 7048.35 | 0 | 7048.35 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 1.2.9
1928 | 1.2 | 1.2.9.3.3.2 | Not Started | PSL | IME Depth Readout Development and System Integration (2022-23) | Off-ice Install: IME Depth Readout Development and System Integration (2022-23) | Domestic |  | Travel | Travel |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2022-10-03 | 2023-10-02 | 53% | Off Ice | C1 |  |  |  |  | 1 domestic trip ($1800/person) to MSU for testing with full length quad | [7 empty] | 450 | 450 | 450 | 450 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459.675 | 459.675 | 459.675 | 459.675 | 0 | 1838.7 | 974.511 | 2813.211 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2813.211 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1928 | 1.2 | 1.2.9.3.3.2 | Not Started | UW | IME Depth Readout Development and System Integration (2022-23) | Off-ice Install: IME Depth Readout Development and System Integration (2022-23) |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0% | 2022-10-03 | 2023-10-02 | 53% | Off Ice | C4 |  |  |  |  | Purchasing 2x materials for spares | [7 empty] | 1700 |  | 1700 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1736.55 | 0 | 1736.55 | 0 | 0 | 3473.1 | 0 | 3473.1 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3473.1 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1929 | 1.2 | 1.2.9.3.3.3 | Not Started | PSL | IME Depth Readout System Final Integration (2023-24) | Off-Ice Install: IME Depth Readout System Final Integration (2023-24) | Wisniewski | 0% | Labor Hours | Labor - Task | EN-EE |  |  | D - Expert Opinion | 115 | 115 | 0% | 2023-10-01 | 2024-07-04 | 0% | Off Ice | C3 |  |  |  |  | Test of all Paro Sensors | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 20 | 20 |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 1.2.9
1931 | 1.2 | 1.2.9.3.3.5 | Not Started | UW | Define Pressure Sensor Requirements | Off-Ice Install: Define Pressure Sensor Requirements | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2022-04-01 | 2022-04-28 | 53% | Off Ice | [5 empty] | Mostly by Tosi/Sandstrom (LOE), verification by PSL | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1932 | 1.2 | 1.2.9.3.3.6 | Not Started | UW | Procure Pressure Sensor Sample | Off-Ice Install: Procure Pressure Sensor Sample for Testing |  |  | CapEx | CapEx | [5 empty] | 1 | 0% | 2022-04-29 | 2022-05-19 | 53% | Off Ice | [5 empty] | May delay pressure sensor procurement if calibration shelf life duration in question | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1933 | 1.2 | 1.2.9.3.3.7 | Not Started | UW | Procure Pressure Sensors | Off-Ice Install: Procure Pressure Sensors | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 47.23 | 52 | 35% | 2024-02-01 | 2024-04-24 | 53% | Off Ice | [5 empty] | Large purchase (around 100k), sole source documentation needed. LoE Tosi | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1933 | 1.2 | 1.2.9.3.3.7 | Not Started | UW | Procure Pressure Sensors | Off-Ice Install: Procure Pressure Sensors |  |  | CapEx | CapEx |  |  |  | C - Engineering Buildup |  | 1 | 0% | 2024-02-01 | 2024-04-24 | 53% | Off Ice | C2 |  |  |  |  | May delay pressure sensor procurement if calibration shelf life duration in question. Vendor quote for 2022 is 11800/each, with increment of 3-5% / year | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 34932 | 34932 | 34932 | [7 empty] | 0 | 0 | 0 | 0 | 36450.2233 | 36450.2233 | 36450.2233 | 0 | 0 | 0 | 0 | 0 | 109350.67 | 0 | 109350.67 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109350.67 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1937 | 1.2 | 1.2.9.4.1.1 | Not Started | UW | Coordinate IDP Winch Loan or Winch Procurement | Off-Ice Install: Coordinate IDP Winch Loan or Winch Procurement | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2022-03-01 | 2022-09-30 | 53% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1939 | 1.2 | 1.2.9.4.1.3 | Not Started | UW | Coordinate Winch Training | Off-Ice Install: Coordinate Winch Training | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2022-10-03 | 2022-11-01 | 53% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1941 | 1.2 | 1.2.9.4.2.1 | Not Started | UW | Define Logbook Requirements | Off-Ice Install: Define Logbook Requirement | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2024-01-15 | 2024-02-13 | 53% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1942 | 1.2 | 1.2.9.4.2.2 | Not Started | UW | Develop Logbook | Off-Ice Install: Develop Logbook | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2024-04-17 | 2024-07-09 | 53% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1943 | 1.2 | 1.2.9.4.2.3 | Not Started | UW | Procure Logbook Tablets | Off-Ice Install: Procure Tablets for Logbook |  |  | CapEx | CapEx |  |  |  | D - Expert Opinion |  | 1 | 0 | 2024-04-17 | 2024-07-09 | 53% | Off Ice | C4 |  |  |  |  | two rugged tablets for logbook keeping | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1989 | 1989 | 1989 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2075.4464 | 2075.4464 | 2075.4464 | 0 | 0 | 0 | 6226.3392 | 0 | 6226.3392 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6226.3392 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1945 | 1.2 | 1.2.9.4.2.5 | Not Started | UW | Procure Laser Rangers, Tape Measures, Shop Lights, Helmets for Installation | Off-Ice Install: Procure Laser Rangers & various Installation Supplies |  |  | CapEx | CapEx |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2024-02-01 | 2024-06-05 | 53% | Off Ice | C3 |  |  |  |  | Laser ranges to measure well depth and distance between DOMs (2) | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1339 | 1339 | 1339 | 669 | 669 | [5 empty] | 0 | 0 | 0 | 0 | 1397.196 | 1397.196 | 1397.196 | 698.0762 | 698.0762 | 0 | 0 | 0 | 5587.7403 | 0 | 5587.7403 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5587.7403 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.9
1946 | 1.2 | 1.2.9.5 | Not Started | UW | Develop Installation Training Package | Off-Ice Install: Develop Training Package | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2025-01-15 | 2025-02-28 | 53% | Off Ice | [5 empty] | Develop training package | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1949 | 1.2 | 1.2.10.1.1 | Not Started | UW | FS1 Off-Ice Installation Training (Installers, including alternates) - Place Holder | Install FS1: FS1 Off-Ice Installation Training (Place holder) | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2023-06-07 | 2023-06-13 | 53% | Off Ice | [5 empty] | No off ice installation training (place holder) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.10
1950 | 1.2 | 1.2.10.1.2 | Not Started | UW | FS2 Off-Ice Installation Training (Installers, including alternates) | Install FS2: FS2 Off-Ice Installation Training | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2024-06-07 | 2024-06-13 | 53% | Off Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.10
1951 | 1.2 | 1.2.10.1.3 | Not Started | PSL | FS3 Off-Ice Installation Training (Drillers, Installers, Management, including alternates) | Install FS3: FS3 Off-Ice Installation Training: Drillers | PSL Driller | 0% | Labor Hours | Labor - Task | TE |  |  | D - Expert Opinion | 77 | 77 | 0% | 2025-08-04 | 2025-08-13 | 0% | Off Ice | C1 |  |  |  |  | 3x8 hours installation training (sensor handling, practice at the tower). Need (3+1 spare)x3=12 drillers | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 288 |  | 288 | 1.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23637.325 | 0 | 23637.325 | 0 | 23637.325 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23637.325 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 23637.325 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 1.2.10
1951 | 1.2 | 1.2.10.1.3 | Not Started | UW | FS3 Off-Ice Installation Training (Drillers, Installers, Management, including alternates) | Install FS3: FS3 Off-Ice Installation Training: Installers | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  |  | 0 | UW | 2025-08-04 | 2025-08-13 | 53% | Off Ice | [5 empty] | 9 installer training + 3 alternates: 2 days safety training, 3 days specific training | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [10 empty] | 240 |  | 240 | 1.6 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 240 | 1.2.10
1951 | 1.2 | 1.2.10.1.3 | Not Started | UW | FS3 Off-Ice Installation Training (Drillers, Installers, Management, including alternates) | Install FS3: FS3 Off-Ice Installation Training: Installers | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  |  | 0 | UW | 2025-08-04 | 2025-08-13 | 53% | Off Ice | [5 empty] | 9 installer training + 3 alternates: 2 days safety training, 3 days specific training | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [10 empty] | 240 |  | 240 | 1.6 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 240 | 1.2.10
1951 | 1.2 | 1.2.10.1.3 | Not Started | UW | FS3 Off-Ice Installation Training (Drillers, Installers, Management, including alternates) | Install FS3: FS3 Off-Ice Installation Training: Managers | Management Personnel FS3 | 0% | Labor Hours | Labor - Task | IK |  |  |  |  | 0 | UW | 2025-08-04 | 2025-08-13 | 53% | Off Ice | [5 empty] | 4 managers, only installation specific installation training (3 days). Marked as IK as all Management Personnel Labor is included elsewhere. | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [10 empty] | 96 |  | 96 | 0.64 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 96 | 1.2.10
1952 | 1.2 | 1.2.10.1.4 | Not Started | UW | FS3 Off-Ice Logging Winch Training (Installation Manager) | Install FS3: Off-Ice Logging Winch Training (Installation Manager) | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  |  | 47.23 | 52 | 35% | 2025-05-27 | 2025-05-27 | 53% | Off Ice | [5 empty] | installation lead gets trained on the IDP winch (1 day) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.10
1992 | 1.2 | 1.2.10.4.2 | Not Started | UW | PQ, ECW, Deployment Travel Costs Installation Team FS2 (Headcount 1) | Install FS2: Install Team FS2 PQ Costs (Headcount 1) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2024-06-01 | 2025-02-19 | 53% | On Ice | C1 |  |  |  |  | 1 - PQ @ $700/each (anticipated cost) | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365.2118 | 365.2118 | 0 | 0 | 730.4236 | 387.1245 | 1117.5481 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1117.5481 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.10
1992 | 1.2 | 1.2.10.4.2 | Not Started | UW | PQ, ECW, Deployment Travel Costs Installation Team FS2 (Headcount 1) | Install FS2: Install Team FS2 ECW Costs (Headcount 1) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2024-06-01 | 2025-02-19 | 53% | On Ice | C1 |  |  |  |  | 1 - ECW allowance @ $250/each | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130.4328 | 130.4328 | 260.8656 | 138.2587 | 399.1243 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399.1243 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.10
1992 | 1.2 | 1.2.10.4.2 | Not Started | UW | PQ, ECW, Deployment Travel Costs Installation Team FS2 (Headcount 1) | Install FS2: Install Team FS2 Deployment Travel Costs (Headcount 1) | Foreign |  | Travel | Travel |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2024-06-01 | 2025-02-19 | 53% | On Ice | C1 |  |  |  |  | 1 - International Travel (3 nights southbound, 2 nights northbound, plus per diem) @ $1800/each | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [9 empty] | 0 | 1151.1684 | 0 | 0 | 767.4456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1918.614 | 1016.8654 | 2935.4795 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2935.4795 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.10
2028 | 1.2 | 1.2.10.4.4.1 | Not Started | UW | Sensor Sleds Construction/Prep Oversight | Install FS2: Sensor Sleds Construction/Prep Oversight | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 35% | 2024-12-01 | 2024-12-05 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2031 | 1.2 | 1.2.10.4.4.4 | Not Started | UW | Sensor Testing Tent Prep Oversight | Install FS2: Sensor Testing Tent Prep Oversight | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 35% | 2024-12-01 | 2024-12-05 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2034 | 1.2 | 1.2.10.4.4.7 | Not Started | UW | Setup SPAT in tent | Install FS2: Setup SPAT | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 35% | 2024-12-17 | 2024-12-24 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2037 | 1.2 | 1.2.10.4.5.1 | Not Started | UW | Sensor Handling Facility Assembly Oversight | Install FS2: Sensor Handling Facility Assembly Oversight | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 35% | 2024-12-04 | 2024-12-23 | 53% | On Ice | [5 empty] | oversight of ASC activity, 2 hours/day, 16 working days | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 32 | [9 empty] | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.10
2041 | 1.2 | 1.2.10.4.5.5 | Not Started | UW | Position Sensor Handling Facility near Tower | Install FS2: Position Sensor Handling Facility near Tower | PSL Driller | 0% | Labor Hours | Labor - Task | TE |  |  |  | 0 | 29 | 35% | 2024-12-24 | 2024-12-24 | 53% | On Ice | [5 empty] | oversight of ASC activity, 2 hours/day, 16 working days | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2042 | 1.2 | 1.2.10.4.5.6 | Not Started | UW | Sensor Handling Dry Run | Install FS2: Sensor Handling Dry Run | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 35% | 2024-12-26 | 2024-12-27 | 53% | On Ice | [5 empty] | adjustment of rollers and tables, training | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 8 | [9 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.10
2044 | 1.2 | 1.2.10.4.6.1 | Not Started | UW | Receive and Inspect Installation Kits & Weights Shipments | Install FS2: Receive and Inspect Installation Kits & Weight Shipments | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-01-02 | 2025-01-06 | 53% | On Ice | [5 empty] | 1 person, 1/2 day (in kind) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2045 | 1.2 | 1.2.10.4.6.2 | Not Started | UW | Receive and Inspect String 87 & 88 Sensors, Calibration & Special Devices Shipments | Install FS2: Receive and Inspect String 87 & 88 Sensors, Calibration and Special Devices Shipments | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2024-12-15 | 2024-12-16 | 53% | On Ice | [5 empty] | 1 person, 2x1/2 day | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 6 | [9 empty] | 6 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1.2.10
2046 | 1.2 | 1.2.10.4.6.3 | Not Started | UW | Load String 87 Sensors on Sleds 1,2 for testing prior to storage | Load String 87 Sensors on Sleds 1,2 for testing prior to storage | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2024-12-26 | 2024-12-26 | 53% | On Ice | [5 empty] | support to USAP activity (spotter, placement) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2046 | 1.2 | 1.2.10.4.6.3 | Not Started | UW | Load String 87 Sensors on Sleds 1,2 for testing prior to storage | Load String 87 Sensors on Sleds 1,2 for testing prior to storage | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2024-12-26 | 2024-12-26 | 53% | On Ice | [5 empty] | support to USAP activity (spotter, placement) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2048 | 1.2 | 1.2.10.4.6.5 | Not Started | UW | Load String 88 Sensors on Sleds 3,4 for testing prior to storage | Load String 88 Sensors on Sleds 3,4 for testing prior to storage | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2024-12-27 | 2024-12-27 | 53% | On Ice | [5 empty] | support to USAP activity (spotter, placement) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2048 | 1.2 | 1.2.10.4.6.5 | Not Started | UW | Load String 88 Sensors on Sleds 3,4 for testing prior to storage | Load String 88 Sensors on Sleds 3,4 for testing prior to storage | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2024-12-27 | 2024-12-27 | 53% | On Ice | [5 empty] | support to USAP activity (spotter, placement) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2050 | 1.2 | 1.2.10.4.6.7 | Not Started | UW | Conduct South Pole Acceptance Testing (SPAT) String 87 | Install FS2: Conduct South Pole Acceptance Testing (SPAT) String 87 Sensors | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2024-12-26 | 2025-01-02 | 53% | On Ice | [5 empty] | one week | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.10
2050 | 1.2 | 1.2.10.4.6.7 | Not Started | UW | Conduct South Pole Acceptance Testing (SPAT) String 87 | Install FS2: Conduct South Pole Acceptance Testing (SPAT) String 87 Sensors | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2024-12-26 | 2025-01-02 | 53% | On Ice | [5 empty] | one week | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2051 | 1.2 | 1.2.10.4.6.8 | Not Started | UW | Conduct South Pole Acceptance Testing (SPAT) String 88 | Install FS2: Conduct South Pole Acceptance Testing (SPAT) String 88 Sensors | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-01-03 | 2025-01-10 | 53% | On Ice | [5 empty] | one week | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 54 | [8 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.10
2051 | 1.2 | 1.2.10.4.6.8 | Not Started | UW | Conduct South Pole Acceptance Testing (SPAT) String 88 | Install FS2: Conduct South Pole Acceptance Testing (SPAT) String 88 Sensors | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-01-03 | 2025-01-10 | 53% | On Ice | [5 empty] | one week | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 30 | [8 empty] | 30 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 1.2.10
2052 | 1.2 | 1.2.10.4.6.9 | Not Started | UW | Conduct South Pole Acceptance Testing (SPAT) Special Devices String 87-88 | Install FS2: Conduct South Pole Acceptance Testing (SPAT) String 87-88 Special Devices | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-01-13 | 2025-01-20 | 53% | On Ice | [5 empty] | one week | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 54 | [8 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.10
2052 | 1.2 | 1.2.10.4.6.9 | Not Started | UW | Conduct South Pole Acceptance Testing (SPAT) Special Devices String 87-88 | Install FS2: Conduct South Pole Acceptance Testing (SPAT) String 87-88 Special Devices | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-01-13 | 2025-01-20 | 53% | On Ice | [5 empty] | one week | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 54 | [8 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.10
2053 | 1.2 | 1.2.10.4.6.10 | Not Started | UW | IME deployment and integration | Install FS2: IME Deployment and Integration | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2024-12-18 | 2025-01-16 | 53% | On Ice | [5 empty] | 1 person part time on the task, with support from engineering team on site | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | 45 | [8 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.10
2053 | 1.2 | 1.2.10.4.6.10 | Not Started | PSL | IME deployment and integration | Install FS2: IME Deployment and Integration | Wisniewski | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 0 | 115 | 0 | 2024-12-18 | 2025-01-16 | 0% | On Ice | [5 empty] | 1 person part time on the task, with support from engineering team on site | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | 18 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.10
2059 | 1.2 | 1.2.10.4.7.5 | Not Started | MSU | Prep/Uncrate Cable Spools; Load on 953 Loader | Install FS2: Prep/Uncrate Cable Spools; Load onto 953 Loader | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0% | 2024-12-17 | 2024-12-26 | 55% | On Ice | [5 empty] | Assist with loading cable spool on fork 3.5 days (1/2 day per cable, interlaced with activities below) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 32 | [9 empty] | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 1.2.10
2061 | 1.2 | 1.2.10.4.7.7 | Not Started | UW | Install 7 Surface Cables into ICL Tower, Across Bridge, into ICL | Install FS2: Install 7 Surface Cables into ICL Tower, Across Bridge, into ICL | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2024-12-17 | 2024-12-26 | 53% | On Ice | [5 empty] | Estimate a full day prep, 1 day for cable 1, then 1/2 day for each other cable. Total 4 days. 4 people on the job, in addition to ASC. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 45 | [9 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.10
2061 | 1.2 | 1.2.10.4.7.7 | Not Started | MSU | Install 7 Surface Cables into ICL Tower, Across Bridge, into ICL | Install FS2: Install 7 Surface Cables into ICL Tower, Across Bridge, into ICL | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2024-12-17 | 2024-12-26 | 55% | On Ice | [5 empty] | Estimate a full day prep, 1 day for cable 1, then 1/2 day for each other cable. Total 4 days. 4 people on the job, in addition to ASC. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 45 | [9 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.10
2061 | 1.2 | 1.2.10.4.7.7 | Not Started | UW | Install 7 Surface Cables into ICL Tower, Across Bridge, into ICL | Install FS2: Install 7 Surface Cables into ICL Tower, Across Bridge, into ICL | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2024-12-17 | 2024-12-26 | 53% | On Ice | [5 empty] | Estimate a full day prep, 1 day for cable 1, then 1/2 day for each other cable. Total 4 days. 4 people on the job, in addition to ASC. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 1.2.10
2061 | 1.2 | 1.2.10.4.7.7 | Not Started | MSU | Install 7 Surface Cables into ICL Tower, Across Bridge, into ICL | Install FS2: Install 7 Surface Cables into ICL Tower, Across Bridge, into ICL | Shoolz | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 0 | 72 | 0% | 2024-12-17 | 2024-12-26 | 55% | On Ice | [5 empty] | Estimate a full day prep, 1 day for cable 1, then 1/2 day for each other cable. Total 4 days. 4 people on the job, in addition to ASC. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 45 | [9 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.10
2064 | 1.2 | 1.2.10.4.7.10 | Not Started | MSU | Prep Cables & Attach to Grounding System in ICL | Install FS2: Prep Cables & Attach to Grounding System in ICL | Shoolz | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 0 | 72 | 0% | 2024-12-27 | 2024-12-30 | 55% | On Ice | [5 empty] | 2.5 days 1 person (in kind) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 23 | [9 empty] | 23 | 0.15333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 1.2.10
2068 | 1.2 | 1.2.10.4.7.14 | Not Started | UW | Unspool & Lay Surface Cables from Tower to SJB Pits | Install FS2: Unspool & Lay Surface Cables from Tower to SJB Pits | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 35% | 2024-12-30 | 2024-12-31 | 53% | On Ice | [5 empty] | 2 days 2 people working with ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2068 | 1.2 | 1.2.10.4.7.14 | Not Started | MSU | Unspool & Lay Surface Cables from Tower to SJB Pits | Install FS2: Unspool & Lay Surface Cables from Tower to SJB Pits | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2024-12-30 | 2024-12-31 | 55% | On Ice | [5 empty] | 2 days 2 people working with ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2068 | 1.2 | 1.2.10.4.7.14 | Not Started | MSU | Unspool & Lay Surface Cables from Tower to SJB Pits | Install FS2: Unspool & Lay Surface Cables from Tower to SJB Pits | Shoolz | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 0 | 72 | 0 | 2024-12-30 | 2024-12-31 | 55% | On Ice | [5 empty] | 2 days 2 people working with ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2070 | 1.2 | 1.2.10.4.7.16 | Not Started | MSU | Install SJB's in Pits (2); Connect Cables | Install FS2: Install SJB's in Pits (2); Connect Cables | Shoolz | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 0 | 72 | 0 | 2025-01-02 | 2025-01-03 | 55% | On Ice | [5 empty] | 1 day, two people | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2070 | 1.2 | 1.2.10.4.7.16 | Not Started | MSU | Install SJB's in Pits (2); Connect Cables | Install FS2: Install SJB's in Pits (2); Connect Cables | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0% | 2025-01-02 | 2025-01-03 | 55% | On Ice | [5 empty] | 1 day, two people | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2073 | 1.2 | 1.2.10.4.7.19 | Not Started | MSU | Surface Cable Continuity Test | Install FS2: Surface Cable Continuity Test | Shoolz | 0% | Labor Hours | Labor - Task | EN-EE |  |  |  | 0 | 72 | 0 | 2025-01-07 | 2025-01-08 | 55% | On Ice | [5 empty] | 1 day, two people | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2073 | 1.2 | 1.2.10.4.7.19 | Not Started | MSU | Surface Cable Continuity Test | Install FS2: Surface Cable Continuity Test | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-01-07 | 2025-01-08 | 55% | On Ice | [5 empty] | 1 day, two people | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2076 | 1.2 | 1.2.10.4.8.1 | Not Started | MSU | ICL Upgrade Activities | Install FS2: Field Hubs, timing system, patch panels and patch cables installation | Halliday | 0% | Labor Hours | Labor - Task | PO |  |  |  | 0 | 31 | 0.31 | 2025-01-08 | 2025-02-03 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 135 | [8 empty] | 135 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 1.2.10
2076 | 1.2 | 1.2.10.4.8.1 | Not Started | MSU | ICL Upgrade Activities | Install FS2: Field Hubs, timing system, patch panels and patch cables installation | Krupczak | 0% | Labor Hours | Labor - Task | GR |  |  |  | 0 | 23 | 0.32 | 2025-01-08 | 2025-02-03 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 117 | 18 | [7 empty] | 135 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 1.2.10
2081 | 1.2 | 1.2.10.4.9.3 | Not Started | UW | Store 87 & 88 Sensors in Cryo Helium Bay for Winter | Install FS2: Store 87 & 88 Sensors in Cryo Helium Bay for Winter | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-01-16 | 2025-01-20 | 53% | On Ice | [5 empty] | 1 day 1 person (in kind) working with ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2081 | 1.2 | 1.2.10.4.9.3 | Not Started | UW | Store 87 & 88 Sensors in Cryo Helium Bay for Winter | Install FS2: Store 87 & 88 Sensors in Cryo Helium Bay for Winter | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-01-16 | 2025-01-20 | 53% | On Ice | [5 empty] | 1 day 1 person (in kind) working with ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2083 | 1.2 | 1.2.10.4.9.5 | Not Started | UW | Store 87 & 88 Special Devices and BCAs in ICL for Winter | Install FS2: Store 87 & 88 Special Devices and BCAs in ICL for Winter | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-01-16 | 2025-01-20 | 53% | On Ice | [5 empty] | 1 day 1 person (in kind) working with ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2083 | 1.2 | 1.2.10.4.9.5 | Not Started | UW | Store 87 & 88 Special Devices and BCAs in ICL for Winter | Install FS2: Store 87 & 88 Special Devices and BCAs in ICL for Winter | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-01-16 | 2025-01-20 | 53% | On Ice | [5 empty] | 1 day 1 person (in kind) working with ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2084 | 1.2 | 1.2.10.4.9.6 | Not Started | UW | Clean up Testing Tent & Store SPAT | Install FS2: Clean up Testing Tent & Store SPAT | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-01-21 | 2025-01-23 | 53% | On Ice | [5 empty] | 1 day 1 person (in kind) working with ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2084 | 1.2 | 1.2.10.4.9.6 | Not Started | UW | Clean up Testing Tent & Store SPAT | Install FS2: Clean up Testing Tent & Store SPAT | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-01-21 | 2025-01-23 | 53% | On Ice | [5 empty] | 1 day 1 person (in kind) working with ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2086 | 1.2 | 1.2.10.4.10 | Not Started | UW | Installation: On-Ice Labor (FS2) | Installation: On-Ice Labor (FS2) (Installation Lead) | Tosi | 0% | Labor Hours | Labor - LoE | SC |  |  | D - Expert Opinion | 34.99 | 52 | 35% | 2024-12-10 | 2025-02-05 | 53% | On Ice | C1 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 162 | 234 | [8 empty] | 396 | 2.64 | 0 | 0 | 8156.5751 | 11781.7196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19938.2947 | 10567.2962 | 30505.5908 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30505.5908 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 14769.1071 | 0 | 0 | 0 | 0 | 5169.1875 | 0 | 396 | 1.2.10
2092 | 1.2 | 1.2.10.5.2 | Not Started | UW | PQ, ECW, Deployment Travel Costs Install FS2 Installation Team | Install FS3: Install Team FS3 PQ Costs (Headcount 1) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2025-06-01 | 2026-02-18 | 53% | On Ice | C1 |  |  |  |  | 1 - PQ @ $700/each (anticipated cost) | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373.0638 | 373.0638 | 0 | 0 | 746.1277 | 395.4477 | 1141.5754 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1141.5754 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.10
2092 | 1.2 | 1.2.10.5.2 | Not Started | UW | PQ, ECW, Deployment Travel Costs Install FS2 Installation Team | Install FS3: Install Team FS3 ECW Costs (Headcount 1) |  |  | M & S | M & S |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2025-06-01 | 2026-02-18 | 53% | On Ice | C1 |  |  |  |  | 1 - ECW allowance @ $250/each | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133.2371 | 133.2371 | 266.4742 | 141.2313 | 407.7055 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407.7055 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.10
2092 | 1.2 | 1.2.10.5.2 | Not Started | UW | PQ, ECW, Deployment Travel Costs Install FS2 Installation Team | Install FS3: Install Team FS3 Deployment Costs (Headcount 1 + 9 in-kind) | Foreign |  | Travel | Travel |  |  |  | E - Extrapolation from Actuals |  | 1 | 0% | 2025-06-01 | 2026-02-18 | 53% | On Ice | C1 |  |  |  |  | 1 - International Travel (3 nights southbound, 2 nights northbound, plus per diem) @ $1800/each | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [9 empty] | 0 | 1175.9185 | 0 | 0 | 783.9457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1959.8642 | 1038.728 | 2998.5923 | 2998.5923 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.2.10
2125 | 1.2 | 1.2.10.5.4.1 | Not Started | UW | Prep Sensor Testing Tent for SPAT & De-Berm Sleds | Install FS3: Prep Sensor Testing Tent & De-Berm Sleds | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-11-21 | 2025-11-25 | 53% | On Ice | [5 empty] | 2 people (in kind) 1 day to prep tent, 2 people, 1 days to dig out sleds, work with ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.10
2127 | 1.2 | 1.2.10.5.4.3 | Not Started | UW | Prep Sensor Handling Facility | Install FS3: Prep Sensor Handling Facility | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-11-21 | 2025-11-25 | 53% | On Ice | [5 empty] | 2 people (in kind), one day, work with ASC | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 18 | [10 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2128 | 1.2 | 1.2.10.5.4.4 | Not Started | UW | On-ice Sensor Handling Training | Install FS3: On-ice sensor Handling Training | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-10 | 2025-12-10 | 53% | On Ice | [5 empty] | refresher on process, adjustment to rollers, crane practice | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2128 | 1.2 | 1.2.10.5.4.4 | Not Started | UW | On-ice Sensor Handling Training | Install FS3: On-ice sensor Handling Training | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-10 | 2025-12-10 | 53% | On Ice | [5 empty] | refresher on process, adjustment to rollers, crane practice, Install Personnel Shift 1 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2128 | 1.2 | 1.2.10.5.4.4 | Not Started | UW | On-ice Sensor Handling Training | Install FS3: On-ice sensor Handling Training | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-10 | 2025-12-10 | 53% | On Ice | [5 empty] | refresher on process, adjustment to rollers, crane practice, Install Personnel Shift 2 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2129 | 1.2 | 1.2.10.5.4.5 | Not Started | MSU | Receive and Inspect MCAs & load members | Install FS3: Receive and Inspect MCAs & load members | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-12-01 | 2025-12-03 | 55% | On Ice | [5 empty] | 2 ppl 1 day | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.10
2130 | 1.2 | 1.2.10.5.4.6 | Not Started | MSU | Receive and Inspect BCAs & String 89-93 Sensors | Install FS3: Receive and Inspect BCAs and String 89-93 Sensors | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-11-25 | 2025-11-26 | 55% | On Ice | [5 empty] | 2 ppl 1 day | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27 | [10 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.10
2131 | 1.2 | 1.2.10.5.4.7 | Not Started | UW | Take out String 87 Sensors from Storage; Load sensor String 87 on sleds 1 & 2 | Install FS3: Load sensor String 87 on sleds 1,2 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-11-21 | 2025-11-21 | 53% | On Ice | [5 empty] | oversight and direct loader, make sure pallets are lined up with AIP. 12 picks 1/2 day? | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2131 | 1.2 | 1.2.10.5.4.7 | Not Started | UW | Take out String 87 Sensors from Storage; Load sensor String 87 on sleds 1 & 2 | Install FS3: Load sensor String 87 on sleds 1,2 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-11-21 | 2025-11-21 | 53% | On Ice | [5 empty] | oversight and direct loader, make sure pallets are lined up with AIP. 12 picks 1/2 day? | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2133 | 1.2 | 1.2.10.5.4.9 | Not Started | UW | SPAT String 87 | Install FS3: SPAT String 87 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-11-26 | 2025-12-03 | 53% | On Ice | [5 empty] | 2 people at the computer (teacher/learner), then still 2 to connect/disconnect, 2x normal (2 ppl, 1 day) as first spat | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 45 | 18 | [9 empty] | 63 | 0.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 1.2.10
2133 | 1.2 | 1.2.10.5.4.9 | Not Started | UW | SPAT String 87 | Install FS3: SPAT String 87 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-11-26 | 2025-12-03 | 53% | On Ice | [5 empty] | 2 people at the computer (teacher/learner), then still 2 to connect/disconnect, 2x normal (2 ppl, 1 day) as first spat | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.10
2134 | 1.2 | 1.2.10.5.4.10 | Not Started | UW | Take out String 88 Sensors from Storage; Load sensor String 88 on sleds 3 & 4 | Install FS3: Load sensor String 88 on sleds 3,4 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-11-21 | 2025-11-22 | 53% | On Ice | [5 empty] | oversight and direct loader, make sure pallets are lined up with AIP. 12 picks 1/2 day? | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2134 | 1.2 | 1.2.10.5.4.10 | Not Started | UW | Take out String 88 Sensors from Storage; Load sensor String 88 on sleds 3 & 4 | Install FS3: Load sensor String 88 on sleds 3,4 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-11-21 | 2025-11-22 | 53% | On Ice | [5 empty] | oversight and direct loader, make sure pallets are lined up with AIP. 12 picks 1/2 day? | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 9 | [10 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2136 | 1.2 | 1.2.10.5.4.12 | Not Started | UW | SPAT String 88 | Install FS3: SPAT String 88 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-12-05 | 2025-12-12 | 53% | On Ice | [5 empty] | 2x12 hours shifts, 2 people | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 54 | [9 empty] | 54 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 1.2.10
2136 | 1.2 | 1.2.10.5.4.12 | Not Started | UW | SPAT String 88 | Install FS3: SPAT String 88 | SPAT Helper | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-05 | 2025-12-12 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 27 | 1.2.10
2137 | 1.2 | 1.2.10.5.4.13 | Not Started | UW | Excavation Pit #1 | Install FS3: Excavation Pit #1 | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-11 | 2025-12-15 | 53% | On Ice | [5 empty] | 1 day 2 ppl help ASC | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 18 | [9 empty] | 18 | 0.12 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 18 | 1.2.10
2139 | 1.2 | 1.2.10.5.4.15 | Not Started | UW | Dust Logger / Dust Logger Winch On-ice Test | Install FS3: Dust Logger and Dust Logger Winch Test and Integration | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-11-21 | 2025-12-01 | 53% | On Ice | [5 empty] | 1 day | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 45 | [10 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.10
2139 | 1.2 | 1.2.10.5.4.15 | Not Started | PSL | Dust Logger / Dust Logger Winch On-ice Test | Install FS3: Dust Logger and Dust Logger Winch Test and Integration | PSL Driller | 0% | Labor Hours | Labor - Task | TE |  |  |  | 0 | 77 | 0 | 2025-11-21 | 2025-12-01 | 0% | On Ice | [5 empty] | 1/2 day | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 | [10 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2140 | 1.2 | 1.2.10.5.4.16 | Not Started | UW | Installation Team On Ice Training and Installation Preparation | Install FS3: On-Ice Training and Installation Preparation | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-08 | 2025-12-12 | 53% | On Ice | [5 empty] | 5 days, on-ice training, preparation for installation, test of logbook | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 45 | [9 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.10
2140 | 1.2 | 1.2.10.5.4.16 | Not Started | MSU | Installation Team On Ice Training and Installation Preparation | Install FS3: On-Ice Training and Installation Preparation | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-12-08 | 2025-12-12 | 55% | On Ice | [5 empty] | 5 days, on-ice training, preparation for installation, test of logbook | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 45 | [9 empty] | 45 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 1.2.10
2140 | 1.2 | 1.2.10.5.4.16 | Not Started | UW | Installation Team On Ice Training and Installation Preparation | Install FS3: On-Ice Training and Installation Preparation | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-08 | 2025-12-12 | 53% | On Ice | [5 empty] | 5 days, on-ice training, preparation for installation, test of logbook | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 180 | [9 empty] | 180 | 1.2 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 180 | 1.2.10
2140 | 1.2 | 1.2.10.5.4.16 | Not Started | UW | Installation Team On Ice Training and Installation Preparation | Install FS3: On-Ice Training and Installation Preparation | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-08 | 2025-12-12 | 53% | On Ice | [5 empty] | 5 days, on-ice training, preparation for installation, test of logbook | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 180 | [9 empty] | 180 | 1.2 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 180 | 1.2.10
2141 | 1.2 | 1.2.10.5.4.17 | Not Started | UW | On-Ice Readiness Review for 1st Hole Drill/Deployment | Install FS3: On-Ice Readiness Review for 1st Hole Drill/Deployment | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-15 | 2025-12-15 | 53% | On Ice | [5 empty] | 8 hours | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2141 | 1.2 | 1.2.10.5.4.17 | Not Started | UW | On-Ice Readiness Review for 1st Hole Drill/Deployment | Install FS3: On-Ice Readiness Review for 1st Hole Drill/Deployment | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 46 | 0.35 | 2025-12-15 | 2025-12-15 | 53% | On Ice | [5 empty] | 8 hours | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2141 | 1.2 | 1.2.10.5.4.17 | Not Started | UW | On-Ice Readiness Review for 1st Hole Drill/Deployment | Install FS3: On-Ice Readiness Review for 1st Hole Drill/Deployment | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-15 | 2025-12-15 | 53% | On Ice | [5 empty] | 8 hours for 9 people | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2141 | 1.2 | 1.2.10.5.4.17 | Not Started | UW | On-Ice Readiness Review for 1st Hole Drill/Deployment | Install FS3: On-Ice Readiness Review for 1st Hole Drill/Deployment | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-15 | 2025-12-15 | 53% | On Ice | [5 empty] | 8 hours for 9 people | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2145 | 1.2 | 1.2.10.5.5.1.1 | Not Started | UW | Load String 87 Sensors in Sensor Handling Facility | Install FS3: Load String 87 Sensors in Sensor Handling Facility | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-03 | 2025-12-03 | 53% | On Ice | [5 empty] | 1 person on crane | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2145 | 1.2 | 1.2.10.5.5.1.1 | Not Started | UW | Load String 87 Sensors in Sensor Handling Facility | Install FS3: Load String 87 Sensors in Sensor Handling Facility | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-03 | 2025-12-03 | 53% | On Ice | [5 empty] | 1 spotter, 1 pallet jack, 2 get DHF ready for deployment | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2146 | 1.2 | 1.2.10.5.5.1.2 | Not Started | UW | Load String 87 Special/Calibration Devices, Rigging Hardware and BCAs in Sensor Handling Facility | Install FS3: Load String 87 Calibration/Special Devices, Rigging Hardware and BCAs in Sensor Handling Facility | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-03 | 2025-12-04 | 53% | On Ice | [5 empty] | All manual labor. Organize special devices and calibration devices and BCAs in TOS. One shift 9 hours, 5 people. | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2147 | 1.2 | 1.2.10.5.5.1.3 | Not Started | UW | Install String 87 / Hole 1 | Install FS3: Install String 87 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-17 | 2025-12-19 | 53% | On Ice | [5 empty] | 12 hours shift | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12 | [9 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2147 | 1.2 | 1.2.10.5.5.1.3 | Not Started | MSU | Install String 87 / Hole 1 | Install FS3: Install String 87 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-12-17 | 2025-12-19 | 55% | On Ice | [5 empty] | 12 hours shift | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12 | [9 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2147 | 1.2 | 1.2.10.5.5.1.3 | Not Started | UW | Install String 87 / Hole 1 | Install FS3: Install String 87 | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-17 | 2025-12-19 | 53% | On Ice | [5 empty] | day shift 4 people, 12 hours (in kind) + 3 drillers (taken into account in 1.2.8) | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 48 | [9 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2147 | 1.2 | 1.2.10.5.5.1.3 | Not Started | UW | Install String 87 / Hole 1 | Install FS3: Install String 87 | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-17 | 2025-12-19 | 53% | On Ice | [5 empty] | night shift 5 people, 12 hours (in kind) + 3 drillers (taken into account in 1.2.8) | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 48 | [9 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2149 | 1.2 | 1.2.10.5.5.1.5 | Not Started | UW | Anchor String 87 / Hole 1 | Install FS3: Anchor String 87 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-19 | 2025-12-19 | 53% | On Ice | [5 empty] | 1 hour: 1 person setting anchor | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | [9 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2149 | 1.2 | 1.2.10.5.5.1.5 | Not Started | UW | Anchor String 87 / Hole 1 | Install FS3: Anchor String 87 | PSL Driller | 0% | Labor Hours | Labor - Task | TE |  |  |  | 0 | 29 | 0.35 | 2025-12-19 | 2025-12-19 | 53% | On Ice | [5 empty] | 1 hour: 1 person driving TU-20 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | [9 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2150 | 1.2 | 1.2.10.5.5.1.6 | Not Started | UW | TOS Clean Up - Wait 12 hours for Anchor to Set | Install FS3: TOS Clean Up | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-19 | 2025-12-20 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 4 | 1.2.10
2151 | 1.2 | 1.2.10.5.5.1.7 | Not Started | UW | String 87 / Hole 1 Cable drag | Install FS3: Cable drag | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-20 | 2025-12-20 | 53% | On Ice | [5 empty] | 6 people, 4 hours | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 24 | [9 empty] | 24 | 0.16 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 24 | 1.2.10
2152 | 1.2 | 1.2.10.5.5.1.8 | Not Started | UW | Trench Hole 1 / String 87 to Pit #1 | Install FS3: Trench Hole 87 to Pit #1 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-20 | 2025-12-20 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2154 | 1.2 | 1.2.10.5.5.1.10 | Not Started | MSU | Connect in-ice Cable to SJB 87 in Pit #1 | Install FS3: Connect in-ice Cable to SJB 87 in Pit #1 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-12-20 | 2025-12-21 | 55% | On Ice | [5 empty] | 4 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2155 | 1.2 | 1.2.10.5.5.1.11 | Not Started | UW | Backfill Hole 1 / String 87 to Pit #1 | Install FS3: Backfill Hole 87 to Pit #1 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-21 | 2025-12-21 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2157 | 1.2 | 1.2.10.5.5.1.13 | Not Started | UW | Load Sensor String 89 (Hole 3) on Sleds 1 & 2 | Install FS3: Load Sensor String 89 on Sleds 1,2 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-12-17 | 2025-12-18 | 53% | On Ice | [5 empty] | 4h spotter for USAP | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2159 | 1.2 | 1.2.10.5.5.1.15 | Not Started | UW | SPAT String 89 | Install FS3: SPAT String 89 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-12-18 | 2025-12-21 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.10
2159 | 1.2 | 1.2.10.5.5.1.15 | Not Started | UW | SPAT String 89 | Install FS3: SPAT String 89 | SPAT Helper | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-18 | 2025-12-21 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 27 | 1.2.10
2161 | 1.2 | 1.2.10.5.5.2.1 | Not Started | UW | Load String 88 Sensors in Sensor Handling Facility | Install FS3: Load String 88 Sensors in Sensor Handling Facility | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-19 | 2025-12-20 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2161 | 1.2 | 1.2.10.5.5.2.1 | Not Started | UW | Load String 88 Sensors in Sensor Handling Facility | Install FS3: Load String 88 Sensors in Sensor Handling Facility | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-19 | 2025-12-20 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2162 | 1.2 | 1.2.10.5.5.2.2 | Not Started | UW | Load String 88 Calibration/Special Devices & BCAs in Sensor Handling Facility | Install FS3: Load String 88 Calibration/Special Devices in Sensor Handling Facility | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-20 | 2025-12-20 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2163 | 1.2 | 1.2.10.5.5.2.3 | Not Started | UW | Install String 88 / Hole 2 | Install FS3: Install String 88 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-23 | 2025-12-24 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12 | [9 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2163 | 1.2 | 1.2.10.5.5.2.3 | Not Started | MSU | Install String 88 / Hole 2 | Install FS3: Install String 88 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-12-23 | 2025-12-24 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12 | [9 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2163 | 1.2 | 1.2.10.5.5.2.3 | Not Started | UW | Install String 88 / Hole 2 | Install FS3: Install String 88 | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-23 | 2025-12-24 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 48 | [9 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2163 | 1.2 | 1.2.10.5.5.2.3 | Not Started | UW | Install String 88 / Hole 2 | Install FS3: Install String 88 | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-23 | 2025-12-24 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 48 | [9 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2165 | 1.2 | 1.2.10.5.5.2.5 | Not Started | UW | Anchor String 88 / Hole 2 | Install FS3: Anchor String 88 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-24 | 2025-12-24 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | [9 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2165 | 1.2 | 1.2.10.5.5.2.5 | Not Started | UW | Anchor String 88 / Hole 2 | Install FS3: Anchor String 88 | PSL Driller | 0% | Labor Hours | Labor - Task | TE |  |  |  | 0 | 29 | 0.35 | 2025-12-24 | 2025-12-24 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | [9 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2166 | 1.2 | 1.2.10.5.5.2.6 | Not Started | UW | TOS Clean Up - Wait 12 hours for Anchor to Set | Install FS3: TOS Clean Up | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-24 | 2025-12-25 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 12 | [9 empty] | 12 | 0.08 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 12 | 1.2.10
2168 | 1.2 | 1.2.10.5.5.2.8 | Not Started | UW | String 88 / Hole 2 Cable drag | Install FS3: Cable Drag | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-25 | 2025-12-26 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 24 | [9 empty] | 24 | 0.16 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 24 | 1.2.10
2169 | 1.2 | 1.2.10.5.5.2.9 | Not Started | MSU | Trench Hole 2 / String 88 to Pit #1 | Install FS3: Trench Hole 88 to Pit #1 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-12-26 | 2025-12-26 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2171 | 1.2 | 1.2.10.5.5.2.11 | Not Started | MSU | Connect in-ice Cable to SJB 88 in Pit #1 | Install FS3: Connect in-ice Cable to SJB 88 in Pit #1 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-12-26 | 2025-12-26 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2172 | 1.2 | 1.2.10.5.5.2.12 | Not Started | MSU | Backfill Hole 2 / String 88 to Pit #1 | Install FS3: Backfill Hole 88 to Pit #1 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-12-26 | 2025-12-26 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2174 | 1.2 | 1.2.10.5.5.2.14 | Not Started | UW | Load sensor String 90 (Hole 4) on sleds 3,4 | Install FS3: Load sensor String 90 on sleds 3,4 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-12-23 | 2025-12-24 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2176 | 1.2 | 1.2.10.5.5.2.16 | Not Started | UW | SPAT String 90 | Install FS3: SPAT String 90 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-12-24 | 2025-12-27 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.10
2176 | 1.2 | 1.2.10.5.5.2.16 | Not Started | UW | SPAT String 90 | Install FS3: SPAT String 90 | SPAT Helper | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-24 | 2025-12-27 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 27 | 1.2.10
2178 | 1.2 | 1.2.10.5.5.3.1 | Not Started | UW | Load String 89 (Hole 3) Sensors in Sensor Handling Facility | Install FS3: Load String 89 Sensors in Sensor Handling Facility | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-24 | 2025-12-25 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2178 | 1.2 | 1.2.10.5.5.3.1 | Not Started | UW | Load String 89 (Hole 3) Sensors in Sensor Handling Facility | Install FS3: Load String 89 Sensors in Sensor Handling Facility | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-24 | 2025-12-25 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2179 | 1.2 | 1.2.10.5.5.3.2 | Not Started | UW | Load String 89 (Hole 3) Calibration/Special Devices & BCAs in Sensor Handling Facility | Install FS3: Load String 89 Sensors in Sensor Handling Facility | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-25 | 2025-12-25 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2180 | 1.2 | 1.2.10.5.5.3.3 | Not Started | UW | Install String 89 / Hole 3 | Install FS3: Install String 89 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-26 | 2025-12-27 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12 | [9 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2180 | 1.2 | 1.2.10.5.5.3.3 | Not Started | MSU | Install String 89 / Hole 3 | Install FS3: Install String 89 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-12-26 | 2025-12-27 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12 | [9 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2180 | 1.2 | 1.2.10.5.5.3.3 | Not Started | UW | Install String 89 / Hole 3 | Install FS3: Install String 89 | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-26 | 2025-12-27 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 48 | [9 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2180 | 1.2 | 1.2.10.5.5.3.3 | Not Started | UW | Install String 89 / Hole 3 | Install FS3: Install String 89 | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-26 | 2025-12-27 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 48 | [9 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2182 | 1.2 | 1.2.10.5.5.3.5 | Not Started | UW | Anchor String 89 / Hole 3 | Install FS3: Anchor String 89 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-27 | 2025-12-27 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | [9 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2182 | 1.2 | 1.2.10.5.5.3.5 | Not Started | UW | Anchor String 89 / Hole 3 | Install FS3: Anchor String 89 | PSL Driller | 0% | Labor Hours | Labor - Task | TE |  |  |  | 0 | 29 | 0.35 | 2025-12-27 | 2025-12-27 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1 | [9 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2183 | 1.2 | 1.2.10.5.5.3.6 | Not Started | UW | TOS Clean Up - Wait 12 hours for Anchor to Set | Install FS3: TOS CLean Up | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-27 | 2025-12-28 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 4 | 1.2.10
2184 | 1.2 | 1.2.10.5.5.3.7 | Not Started | UW | String 89 / Hole 3 Cable drag | Install FS3: Cable Drag | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-28 | 2025-12-28 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 24 | [9 empty] | 24 | 0.16 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 24 | 1.2.10
2185 | 1.2 | 1.2.10.5.5.3.8 | Not Started | MSU | Trench Hole 3 / String 89 to Pit #1 | Install FS3: Trench Hole 89 to Pit #1 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-12-28 | 2025-12-28 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2187 | 1.2 | 1.2.10.5.5.3.10 | Not Started | MSU | Connect in-ice cable to SJB 89 in Pit #1 | Install FS3: Connect in-ice cable to SJB 89 in Pit #1 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-12-28 | 2025-12-28 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2188 | 1.2 | 1.2.10.5.5.3.11 | Not Started | MSU | Backfill Hole 3 / String 89 to Pit #1 | Install FS3: Backfill Hole 89 to Pit #1 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-12-28 | 2025-12-28 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2190 | 1.2 | 1.2.10.5.5.3.13 | Not Started | UW | Load sensor String 91 (Hole 5) on sleds 1 & 2 | Install FS3: Load sensor String 91 on sleds 1,2 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-12-26 | 2025-12-26 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | [9 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2192 | 1.2 | 1.2.10.5.5.3.15 | Not Started | UW | SPAT String 91 | Install FS3: SPAT String 91 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-12-26 | 2025-12-29 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.10
2192 | 1.2 | 1.2.10.5.5.3.15 | Not Started | UW | SPAT String 91 | Install FS3: SPAT String 91 | SPAT Helper | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-26 | 2025-12-29 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 27 | 1.2.10
2194 | 1.2 | 1.2.10.5.5.4.1 | Not Started | UW | Load String 90 (Hole 4) Sensors in Sensor Handling Facility | Install FS3: Load String 90 Sensors in Sensor Handling Facility | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-27 | 2025-12-28 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 12 | [9 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2194 | 1.2 | 1.2.10.5.5.4.1 | Not Started | UW | Load String 90 (Hole 4) Sensors in Sensor Handling Facility | Install FS3: Load String 90 Sensors in Sensor Handling Facility | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-27 | 2025-12-28 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2195 | 1.2 | 1.2.10.5.5.4.2 | Not Started | UW | Load String 90 (Hole 4) Calibration/Special Devices & BCAs in Sensor Handling Facility | Install FS3: Load String 90 Calibration/Special Devices in Sensor Handling Facility | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-28 | 2025-12-28 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 36 | [9 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2196 | 1.2 | 1.2.10.5.5.4.3 | Not Started | UW | Install String 90 | Install FS3: Install String 90 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2025-12-31 | 2026-01-01 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12 | [8 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2196 | 1.2 | 1.2.10.5.5.4.3 | Not Started | MSU | Install String 90 | Install FS3: Install String 90 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2025-12-31 | 2026-01-01 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12 | [8 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2196 | 1.2 | 1.2.10.5.5.4.3 | Not Started | UW | Install String 90 | Install FS3: Install String 90 | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-31 | 2026-01-01 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 48 | [8 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2196 | 1.2 | 1.2.10.5.5.4.3 | Not Started | UW | Install String 90 | Install FS3: Install String 90 | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-31 | 2026-01-01 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 48 | [8 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2198 | 1.2 | 1.2.10.5.5.4.5 | Not Started | UW | Anchor String 90 / Hole 4 | Install FS3: Anchor String 90 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2026-01-01 | 2026-01-01 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | [8 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2198 | 1.2 | 1.2.10.5.5.4.5 | Not Started | UW | Anchor String 90 / Hole 4 | Install FS3: Anchor String 90 | PSL Driller | 0% | Labor Hours | Labor - Task | TE |  |  |  | 0 | 29 | 0.35 | 2026-01-01 | 2026-01-01 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | [8 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2199 | 1.2 | 1.2.10.5.5.4.6 | Not Started | UW | TOS Clean Up - Wait 12 hours for Anchor to Set | Install FS3: TOS Clean Up and Wait for Anchor to Set | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-01 | 2026-01-02 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 4 | 1.2.10
2200 | 1.2 | 1.2.10.5.5.4.7 | Not Started | UW | String 90 / Hole 4 Cable drag | Install FS3: Cable Drag | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-02 | 2026-01-02 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 24 | [8 empty] | 24 | 0.16 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 24 | 1.2.10
2201 | 1.2 | 1.2.10.5.5.4.8 | Not Started | MSU | Trench Hole 4 / String 90 to Pit #1 | Install FS3: Trench Hole 90 to Pit #1 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-02 | 2026-01-02 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2203 | 1.2 | 1.2.10.5.5.4.10 | Not Started | MSU | Connect in-ice cable to SJB 90 in Pit #1 | Install FS3: Connect in-ice cable to SJB 90 in Pit #1 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-02 | 2026-01-02 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2204 | 1.2 | 1.2.10.5.5.4.11 | Not Started | MSU | Backfill Hole 4 / String 90 to Pit #1 | Install FS3: Backfill Hole 90 to Pit #1 | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-02 | 2026-01-03 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2206 | 1.2 | 1.2.10.5.5.4.13 | Not Started | UW | Backfill, Remove Temp Vault, Flag and Survey Pit #1 | Install FS3: Backfill, Remove Temp Vault, Flag and Survey Pit #1 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2026-01-02 | 2026-01-03 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2208 | 1.2 | 1.2.10.5.5.4.15 | Not Started | UW | Load Sensor String 92 (Hole 6) on Sleds 3 & 4 | Install FS3: Load Sensor String 92 on Sleds 3,4 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-12-31 | 2025-12-31 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2210 | 1.2 | 1.2.10.5.5.4.17 | Not Started | UW | SPAT String 92 | Install FS3: SPAT String 92 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2025-12-31 | 2026-01-03 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.10
2210 | 1.2 | 1.2.10.5.5.4.17 | Not Started | UW | SPAT String 92 | Install FS3: SPAT String 92 | SPAT Helper | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-12-31 | 2026-01-03 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 27 | 1.2.10
2212 | 1.2 | 1.2.10.5.5.5.1 | Not Started | MSU | Excavation Pit #2 (Assist) | Install FS3: Excavation Pit #2 (Assist) | Ng | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-03 | 2026-01-03 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2214 | 1.2 | 1.2.10.5.5.5.3 | Not Started | UW | Load String 91 (Hole 5) Sensors in Sensor Handling Facility | Install FS3: Load String 91 Sensors in Sensor Handling Facility | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  | D - Expert Opinion | 0 | 52 | 0.35 | 2026-01-01 | 2026-01-02 | 53% | Off Ice | C2 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2214 | 1.2 | 1.2.10.5.5.5.3 | Not Started | UW | Load String 91 (Hole 5) Sensors in Sensor Handling Facility | Install FS3: Load String 91 Sensors in Sensor Handling Facility | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-01 | 2026-01-02 | 53% | Off Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2215 | 1.2 | 1.2.10.5.5.5.4 | Not Started | UW | Load String 91 (Hole 5) Calibration/Special Devices & BCAs in Sensor Handling Facility | Install FS3: Load String 91 Calibration/Special Devices in Sensor Handling Facility | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-02 | 2026-01-02 | 53% | Off Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2216 | 1.2 | 1.2.10.5.5.5.5 | Not Started | UW | Install String 91 / Hole 5 | Install FS3: Install String 91 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2026-01-03 | 2026-01-04 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12 | [8 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2216 | 1.2 | 1.2.10.5.5.5.5 | Not Started | MSU | Install String 91 / Hole 5 | Install FS3: Install String 91 | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-03 | 2026-01-04 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12 | [8 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2216 | 1.2 | 1.2.10.5.5.5.5 | Not Started | UW | Install String 91 / Hole 5 | Install FS3: Install String 91 | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-03 | 2026-01-04 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 48 | [8 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2216 | 1.2 | 1.2.10.5.5.5.5 | Not Started | UW | Install String 91 / Hole 5 | Install FS3: Install String 91 | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-03 | 2026-01-04 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 48 | [8 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2218 | 1.2 | 1.2.10.5.5.5.7 | Not Started | UW | Anchor String 91 / Hole 5 | Install FS3: Anchor String 91 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2026-01-04 | 2026-01-04 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | [8 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2218 | 1.2 | 1.2.10.5.5.5.7 | Not Started | UW | Anchor String 91 / Hole 5 | Install FS3: Anchor String 91 | PSL Driller | 0% | Labor Hours | Labor - Task | TE |  |  |  | 0 | 29 | 0.35 | 2026-01-04 | 2026-01-04 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | [8 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2219 | 1.2 | 1.2.10.5.5.5.8 | Not Started | UW | TOS Clean Up - Wait 12 hours for Anchor to Set | Install FS3: TOS Clean Up & Wait for Anchor to Set | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-04 | 2026-01-04 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 4 | 1.2.10
2220 | 1.2 | 1.2.10.5.5.5.9 | Not Started | UW | String 91 / Hole 5 Cable drag | Install FS3: Cable Drag | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-04 | 2026-01-05 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 24 | [8 empty] | 24 | 0.16 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 24 | 1.2.10
2221 | 1.2 | 1.2.10.5.5.5.10 | Not Started | MSU | Trench Hole 5 / String 91 to Pit #2 | Install FS3: Trench Hole 91 to Pit #2 | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-05 | 2026-01-05 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2223 | 1.2 | 1.2.10.5.5.5.12 | Not Started | MSU | Connect in-ice Cable to SJB 91 in Pit #2 | Install FS3: Connect in-ice Cable to SJB 91 in Pit #2 | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-05 | 2026-01-05 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2225 | 1.2 | 1.2.10.5.5.5.14 | Not Started | MSU | Backfill Hole 5 / String 91 to Pit #2 (USAP) | Install FS3: Backfill Hole 91 to Pit #2 | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-05 | 2026-01-05 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2226 | 1.2 | 1.2.10.5.5.5.15 | Not Started | UW | Load Sensor String 93 (Hole 7) on Sleds 3 & 4 | Install FS3: Load Sensor String 93 on Sleds 3,4 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2026-01-03 | 2026-01-03 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2228 | 1.2 | 1.2.10.5.5.5.17 | Not Started | UW | SPAT String 93 | Install FS3: SPAT String 93 | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2026-01-03 | 2026-01-06 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.10
2228 | 1.2 | 1.2.10.5.5.5.17 | Not Started | UW | SPAT String 93 | Install FS3: SPAT String 93 | SPAT Helper | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-03 | 2026-01-06 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 27 | [8 empty] | 27 | 0.18 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 27 | 1.2.10
2230 | 1.2 | 1.2.10.5.5.6.1 | Not Started | UW | Load String 92 (Hole 6) Sensors in Sensor Handling Facility | Install FS3: Load String 92 Sensors in Sensor Handling Facility | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2026-01-04 | 2026-01-04 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2230 | 1.2 | 1.2.10.5.5.6.1 | Not Started | UW | Load String 92 (Hole 6) Sensors in Sensor Handling Facility | Install FS3: Load String 92 Sensors in Sensor Handling Facility | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-04 | 2026-01-04 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2231 | 1.2 | 1.2.10.5.5.6.2 | Not Started | UW | Load String 92 (Hole 6) Calibration/Special Devices & BCAs in Sensor Handling Facility | Install FS3: Load String 92 Calibration/Special Devices in Sensor Handling Facility | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-04 | 2026-01-05 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2232 | 1.2 | 1.2.10.5.5.6.3 | Not Started | UW | Set-up Logging Winch | Install FS3: Set-up Logging Winch | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2026-01-08 | 2026-01-08 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2233 | 1.2 | 1.2.10.5.5.6.4 | Not Started | UW | Dust Logging | Install FS3: Dust Logging | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2026-01-08 | 2026-01-08 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 24 | [8 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1.2.10
2235 | 1.2 | 1.2.10.5.5.6.6 | Not Started | UW | Install String 92 / Hole 6 | Install FS3: Install String 92 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2026-01-08 | 2026-01-09 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12 | [8 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2235 | 1.2 | 1.2.10.5.5.6.6 | Not Started | MSU | Install String 92 / Hole 6 | Install FS3: Install String 92 | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-08 | 2026-01-09 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12 | [8 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2235 | 1.2 | 1.2.10.5.5.6.6 | Not Started | UW | Install String 92 / Hole 6 | Install FS3: Install String 92 | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-08 | 2026-01-09 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 48 | [8 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2235 | 1.2 | 1.2.10.5.5.6.6 | Not Started | UW | Install String 92 / Hole 6 | Install FS3: Install String 92 | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-08 | 2026-01-09 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 48 | [8 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2237 | 1.2 | 1.2.10.5.5.6.8 | Not Started | UW | Anchor String 92 / Hole 6 | Install FS3: Anchor String 92 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2026-01-09 | 2026-01-09 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | [8 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2237 | 1.2 | 1.2.10.5.5.6.8 | Not Started | UW | Anchor String 92 / Hole 6 | Install FS3: Anchor String 92 | PSL Driller | 0% | Labor Hours | Labor - Task | TE |  |  |  | 0 | 29 | 0.35 | 2026-01-09 | 2026-01-09 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | [8 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2238 | 1.2 | 1.2.10.5.5.6.9 | Not Started | UW | TOS Clean Up - Wait 12 hours for Anchor to Set | Install FS3: TOS Clean Up and Wait for Anchor to Set | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-09 | 2026-01-10 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 4 | 1.2.10
2239 | 1.2 | 1.2.10.5.5.6.10 | Not Started | UW | String 92 / Hole 6 Cable drag | Install FS3: Cable Drag | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-10 | 2026-01-10 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 24 | [8 empty] | 24 | 0.16 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 24 | 1.2.10
2240 | 1.2 | 1.2.10.5.5.6.11 | Not Started | MSU | Trench Hole 6 / String 92 to Pit #2 | Install FS3: Trench Hole 92 to Pit #2 | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-10 | 2026-01-10 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2242 | 1.2 | 1.2.10.5.5.6.13 | Not Started | MSU | Connect in-ice Cable to SJB 92 in Pit #2 | Install FS3: Connect in-ice Cable to SJB 92 in Pit #2 | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-10 | 2026-01-11 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2243 | 1.2 | 1.2.10.5.5.6.14 | Not Started | MSU | Backfill Hole 6 / String 92 to Pit #2 | Install FS3: Backfill Hole 92 to Pit #2 | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-11 | 2026-01-11 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2246 | 1.2 | 1.2.10.5.5.7.1 | Not Started | UW | Load String 93 (Hole 7) Sensors into Sensor Handling Facility | Install FS3: Load String 93 Sensors into Sensor Handling Facility | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2026-01-09 | 2026-01-10 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2246 | 1.2 | 1.2.10.5.5.7.1 | Not Started | UW | Load String 93 (Hole 7) Sensors into Sensor Handling Facility | Install FS3: Load String 93 Sensors into Sensor Handling Facility | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-09 | 2026-01-10 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2247 | 1.2 | 1.2.10.5.5.7.2 | Not Started | UW | Load String 93 (Hole 7) Calibration/Special Devices & BCAs in Sensor Handling Facility | Install FS3: Load String 93 Calibration/Special Devices & BCAs into Sensor Handling Facility | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-10 | 2026-01-10 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 36 | [8 empty] | 36 | 0.24 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 36 | 1.2.10
2248 | 1.2 | 1.2.10.5.5.7.3 | Not Started | UW | Install String 93 / Hole 7 | Install FS3: Install String 93 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2026-01-11 | 2026-01-12 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12 | [8 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2248 | 1.2 | 1.2.10.5.5.7.3 | Not Started | MSU | Install String 93 / Hole 7 | Install FS3: Install String 93 | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-11 | 2026-01-12 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 12 | [8 empty] | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1.2.10
2248 | 1.2 | 1.2.10.5.5.7.3 | Not Started | UW | Install String 93 / Hole 7 | Install FS3: Install String 93 | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-11 | 2026-01-12 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 48 | [8 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2248 | 1.2 | 1.2.10.5.5.7.3 | Not Started | UW | Install String 93 / Hole 7 | Install FS3: Install String 93 | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-11 | 2026-01-12 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 48 | [8 empty] | 48 | 0.32 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 48 | 1.2.10
2250 | 1.2 | 1.2.10.5.5.7.5 | Not Started | UW | Anchor String 93 / Hole 7 | Install FS3: Anchor String 93 | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2026-01-12 | 2026-01-12 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | [8 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2250 | 1.2 | 1.2.10.5.5.7.5 | Not Started | UW | Anchor String 93 / Hole 7 | Install FS3: Anchor String 93 | PSL Driller | 0% | Labor Hours | Labor - Task | TE |  |  |  | 0 | 29 | 0.35 | 2026-01-12 | 2026-01-12 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | [8 empty] | 1 | 0.0066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.2.10
2251 | 1.2 | 1.2.10.5.5.7.6 | Not Started | UW | TOS Clean Up - Wait 12 hours for Anchor to Set | Install FS3: TOS Clean Up - Wait for Anchor to Set | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-12 | 2026-01-12 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 4 | 1.2.10
2252 | 1.2 | 1.2.10.5.5.7.7 | Not Started | UW | String 93 / Hole 7 Cable drag | Install FS3: Cable Drag | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-12 | 2026-01-12 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 24 | [8 empty] | 24 | 0.16 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 24 | 1.2.10
2253 | 1.2 | 1.2.10.5.5.7.8 | Not Started | MSU | Trench Hole 7 / String 93 to Pit #2 | Install FS3: Trench Hole 93 to Pit #2 | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-13 | 2026-01-13 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2255 | 1.2 | 1.2.10.5.5.7.10 | Not Started | MSU | Connect in-ice Cable to SJB 93 in Pit #2 | Install FS3: Connect in-ice Cable to SJB 93 in Pit #2 | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-13 | 2026-01-13 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2256 | 1.2 | 1.2.10.5.5.7.11 | Not Started | MSU | Backfill Hole 7 / String 93 to Pit #2 | Install FS3: Backfill Hole 93 to Pit #2 | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-13 | 2026-01-13 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2258 | 1.2 | 1.2.10.5.5.7.13 | Not Started | MSU | Backfill, Remove Temp Vault, Flag and Survey Pit #2 | Install FS3: Backfill, Remove Temp Vault, Flag and Survey Pit #2 | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-13 | 2026-01-13 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | [8 empty] | 4 | 0.026667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1.2.10
2261 | 1.2 | 1.2.10.5.6.1 | Not Started | UMD | M&O/Upgrade liaison [ongoing] | Install FS3: M&O/Upgrade liaison | Blaufuss | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.29 | 2025-12-07 | 2026-01-20 | 54.5% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 56 | 78 | [8 empty] | 134 | 0.89333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134 | 1.2.10
2262 | 1.2 | 1.2.10.5.6.2 | Not Started | UW | Update CPT installation firmware, software (pre-deployment) [1.5 days] | Install FS3: Update CPT Installation firmware software | Kelley | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.35 | 2025-12-17 | 2025-12-18 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 14 | [9 empty] | 14 | 0.093333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1.2.10
2263 | 1.2 | 1.2.10.5.6.3 | Not Started | UW | Final DOM power system configuration (pre-deployment) [0.5 day] | Install FS3: Final DOM power system config | Kelley | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.35 | 2025-12-18 | 2025-12-18 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5 | [9 empty] | 5 | 0.033333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1.2.10
2264 | 1.2 | 1.2.10.5.6.4 | Not Started | UW | CPT final pre-deployment checkout [1 day] | Install FS3: CPT Final Predeployment Checkout [1 day] | Kelley | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.35 | 2025-12-19 | 2025-12-19 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2265 | 1.2 | 1.2.10.5.6.5 | Not Started | UMD | Low-level Communications and Timing Commissioning: String 87 | Install FS3: Low level Comms and Timing Commissioning String 87 | Blaufuss | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.29 | 2025-12-22 | 2025-12-24 | 54.5% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 27 | [9 empty] | 27 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 1.2.10
2266 | 1.2 | 1.2.10.5.6.6 | Not Started | UMD | Low-level Communications and Timing Commissioning: String 88 | Install FS3: Low level Comms and Timing Commissioning String 88 | Blaufuss | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.29 | 2025-12-26 | 2025-12-26 | 54.5% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2267 | 1.2 | 1.2.10.5.6.7 | Not Started | UMD | Low-level Communications and Timing Commissioning: String 89 | Install FS3: Low level Comms and Timing Commissioning String 89 | Blaufuss | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.29 | 2025-12-29 | 2025-12-29 | 54.5% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 9 | [9 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2268 | 1.2 | 1.2.10.5.6.8 | Not Started | UMD | Low-level Communications and Timing Commissioning: String 90 | Install FS3: Low level Comms and Timing Commissioning String 90 | Blaufuss | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.29 | 2026-01-02 | 2026-01-02 | 54.5% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2269 | 1.2 | 1.2.10.5.6.9 | Not Started | UMD | Low-level Communications and Timing Commissioning: String 91 | Install FS3: Low level Comms and Timing Commissioning String 91 | Blaufuss | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.29 | 2026-01-05 | 2026-01-05 | 54.5% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2270 | 1.2 | 1.2.10.5.6.10 | Not Started | UMD | Low-level Communications and Timing Commissioning: String 92 | Install FS3: Low level Comms and Timing Commissioning String 92 | Blaufuss | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.29 | 2026-01-12 | 2026-01-12 | 54.5% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2271 | 1.2 | 1.2.10.5.6.11 | Not Started | UMD | Low-level Communications and Timing Commissioning: String 93 | Install FS3: Low level Comms and Timing Commissioning String 93 | Blaufuss | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.29 | 2026-01-12 | 2026-01-12 | 54.5% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2272 | 1.2 | 1.2.10.5.6.12 | Not Started | UW | ICL patch cabling / surface cabling / SJB debug support [ongoing] | Install FS3: ICL patch cabling / surface cabling/ SJB debug support | Kelley | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.35 | 2025-12-05 | 2026-01-20 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 40 | 78 | [8 empty] | 118 | 0.78667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 1.2.10
2272 | 1.2 | 1.2.10.5.6.12 | Not Started | MSU | ICL patch cabling / surface cabling / SJB debug support [ongoing] | Install FS3: ICL patch cabling / surface cabling/ SJB debug support | CPT EE | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.32 | 2025-12-05 | 2026-01-20 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 14 | [8 empty] | 14 | 0.093333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 1.2.10
2273 | 1.2 | 1.2.10.5.6.13 | Not Started | UW | FieldHub / DAQ software integration support [ongoing] | Install FS3: Field Hub/ DAQ Software integration support | Blaufuss | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.35 | 2025-12-05 | 2026-01-20 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 56 | 52 | [8 empty] | 108 | 0.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 1.2.10
2274 | 1.2 | 1.2.10.5.6.14 | Not Started | MSU | Enable FieldHub and power supply monitoring [1 day] | Install FS3: Enable Field Hub & Power Supply Monitoring | CPT SME | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.32 | 2026-01-13 | 2026-01-13 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2276 | 1.2 | 1.2.10.5.7.1 | Not Started | UW | Operational Debrief - String & Cable Installation | Install FS3: Operational Debrief - String & Cable Installation | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  |  | 0 | 52 | 0.35 | 2026-01-13 | 2026-01-14 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 | [8 empty] | 9 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1.2.10
2276 | 1.2 | 1.2.10.5.7.1 | Not Started | MSU | Operational Debrief - String & Cable Installation | Install FS3: Operational Debrief - String & Cable Installation | CPT SME | 0% | Labor Hours | Labor - Task | EN-ME |  |  |  | 0 | 62 | 0 | 2026-01-13 | 2026-01-14 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8 | [8 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.10
2276 | 1.2 | 1.2.10.5.7.1 | Not Started | UMD | Operational Debrief - String & Cable Installation | Install FS3: Operational Debrief - String & Cable Installation | Blaufuss | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.29 | 2026-01-13 | 2026-01-14 | 54.5% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8 | [8 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.10
2276 | 1.2 | 1.2.10.5.7.1 | Not Started | MSU | Operational Debrief - String & Cable Installation | Install FS3: Operational Debrief - String & Cable Installation | CPT SME | 0% | Labor Hours | Labor - Task | SS |  |  |  | 0 | 66 | 0.32 | 2026-01-13 | 2026-01-14 | 55% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8 | [8 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 1.2.10
2276 | 1.2 | 1.2.10.5.7.1 | Not Started | UW | Operational Debrief - String & Cable Installation | Install FS3: Operational Debrief - String & Cable Installation | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-13 | 2026-01-14 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 32 | [8 empty] | 32 | 0.21333 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 32 | 1.2.10
2276 | 1.2 | 1.2.10.5.7.1 | Not Started | UW | Operational Debrief - String & Cable Installation | Install FS3: Operational Debrief - String & Cable Installation | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-13 | 2026-01-14 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 40 | [8 empty] | 40 | 0.26667 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 40 | 1.2.10
2278 | 1.2 | 1.2.10.5.7.3 | Not Started | UW | Breakdown Sensor Packaging for Entrance into USAP Waste Stream | Install FS3: Breakdown Sensor Packaging for Entrance into USAP Waste Stream | Install Personnel Shift 1 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-14 | 2026-01-16 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 72 | [8 empty] | 72 | 0.48 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 72 | 1.2.10
2279 | 1.2 | 1.2.10.5.7.4 | Not Started | UW | Stow Installation Equipment | Install FS3: Stow Installation Equipment | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-14 | 2026-01-16 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 18 | 1.2.10
2280 | 1.2 | 1.2.10.5.7.5 | Not Started | UW | Crate Installation Retrograde and Deliver to Cargo | Install FS3: Crate Installation Retrograde and Deliver to Cargo | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2026-01-16 | 2026-01-20 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 18 | 1.2.10
2281 | 1.2 | 1.2.10.5.7.6 | Not Started | UW | Store SPAT Equipment | Install FS3: Store SPAT Equipment | Weber | 0% | Labor Hours | Labor - Task | SE |  |  |  | 0 | 55 | 0.35 | 2026-01-14 | 2026-01-16 | 53% | On Ice | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 18 | [8 empty] | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 1.2.10
2282 | 1.2 | 1.2.10.5.8 | Not Started | UW | Installation: On-Ice Labor (FS3) | Installation: On-Ice Labor (FS3) (Installation Lead) | Tosi | 0% | Labor Hours | Labor - Task | SC |  |  | D - Expert Opinion | 34.99 | 52 | 35% | 2025-11-20 | 2026-02-06 | 53% | On Ice | C1 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 108 | 234 | 216 | [8 empty] | 558 | 3.72 | 0 | 5554.6276 | 12035.0265 | 11109.2553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28698.9094 | 15210.422 | 43909.3314 | 43909.3314 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 21258.4514 | 0 | 0 | 0 | 0 | 7440.458 | 558 | 1.2.10
2282 | 1.2 | 1.2.10.5.8 | Not Started | UW | Installation: On-Ice Labor (FS3) | Installation: On-Ice Labor (FS3) Installation Night Shift Lead (in kind) | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-11-20 | 2026-02-06 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 234 | 216 | [8 empty] | 450 | 3 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 450 | 1.2.10
2282 | 1.2 | 1.2.10.5.8 | Not Started | UW | Installation: On-Ice Labor (FS3) | Installation: On-Ice Labor (FS3) SPAT Helper (1, in kind) | SPAT Helper | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-11-20 | 2026-02-06 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 216 | 126 | [8 empty] | 342 | 2.28 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 342 | 1.2.10
2282 | 1.2 | 1.2.10.5.8 | Not Started | UW | Installation: On-Ice Labor (FS3) | Installation: On-Ice Labor (FS3) Installers (4, day shift, in kind) | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-11-20 | 2026-02-06 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 720 | 612 | [8 empty] | 1332 | 8.88 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 1332 | 1.2.10
2282 | 1.2 | 1.2.10.5.8 | Not Started | UW | Installation: On-Ice Labor (FS3) | Installation: On-Ice Labor (FS3) Installers (3, night shift, in kind) | Install Personnel Shift 2 | 0% | Labor Hours | Labor - Task | IK |  |  |  | 0 | 0 | UW | 2025-11-20 | 2026-02-06 | 53% | On Ice | [18 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 | 0 |  |  | 540 | 459 | [8 empty] | 999 | 6.66 | [12 empty] | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | #INVALID OPERATION | 999 | 1.2.10

## Comments
Sheet | Escalation #s (PY3)1.0215;(PY4)1.04346;(PY5)1.0659;(PY6)1.08881;(PY7)1.11222;1(PY8).13614 | Jim Lowe | 02/20/22 8:18 AM