## M&O Activities sorted by Inst.
Sum of Grand Total |  |  |  | WBS L2
Institution | Labor Cat. | Names | Tasks | 2.1 Program Management | 2.2 Detector Operations & Maintenance | 2.3 Computing And Data Management | 2.4 Triggering And Filtering | 2.5 Data Quality, Reconstruction & Simulation Tools | Grand Total
ALBERTA | KE | GRANT, DARREN | Maintenance of IceCube-Photonics interface |  |  |  |  | 0.1 | 0.1
|  |  | TFT Board member |  |  |  | 0.1 |  | 0.1
|  |  | WestGrid computing |  |  | 0.1 |  |  | 0.1
| KE Total |  |  |  |  | 0.1 | 0.1 | 0.1 | 0.3
| GR | WOOD, TANIA | WestGrid computing |  |  | 0.2 |  |  | 0.2
| GR Total |  |  |  |  | 0.2 |  |  | 0.2
ALBERTA Total | [5 empty] | 0.3 | 0.1 | 0.1 | 0.5
BARBADOS | KE | SEUNARINE, SURUJ | Analysis of flasher runs for inice calibration of saturation, and flasher and Standard Candle runs for absolute energy calibration for cascades. |  |  |  |  | 0.15 | 0.15
|  |  | Work on cascade filter |  |  |  | 0.15 |  | 0.15
| KE Total | [5 empty] | 0.15 | 0.15 | 0.3
BARBADOS Total | [6 empty] | 0.15 | 0.15 | 0.3
BOCHUM | KE | BECKER, JULIA | Pubcom member | 0.1 |  |  |  |  | 0.1
|  |  | Update MMC from Java to C++ |  |  |  |  | 0.1 | 0.1
| KE Total |  |  | 0.1 |  |  |  | 0.1 | 0.2
| GR | OLIVO, MARTINO | Monte Carlo Validation |  |  |  |  | 0.1 | 0.1
|  | UBOCHUM GR | Detector Monitoring |  | 0.03 |  |  |  | 0.03
| GR Total |  |  |  | 0.03 |  |  | 0.1 | 0.13
BOCHUM Total |  |  |  | 0.1 | 0.03 |  |  | 0.2 | 0.33
BONN | KE | KOWALSKI, MAREK | Cascade WG Co-Chair |  |  |  | 0.25 |  | 0.25
|  |  | TFT Board member |  |  |  | 0.1 |  | 0.1
| KE Total | [5 empty] | 0.35 |  | 0.35
| PO | BOSSER, SEBASTIAN | Run Coordinator |  | 0.5 |  |  |  | 0.5
|  |  | TFT Board member |  |  |  | 0.1 |  | 0.1
| PO Total |  |  |  | 0.5 |  | 0.1 |  | 0.6
| GR | FRANCKOWIAK, ANNA | Alert System for follow-up |  |  |  | 0.1 |  | 0.1
|  | HOMRIER, ANDREAS | Alert System for follow-up |  |  |  | 0.1 |  | 0.1
|  | PANKNIN, SEBASTIAN | IC-40 L3 processing |  |  |  |  | 0.2 | 0.2
|  | UBONN GR | Detector Monitoring |  | 0.03 |  |  |  | 0.03
|  |  | Reconstruction/ Analysis tools |  |  |  |  | 0.2 | 0.2
| GR Total |  |  |  | 0.03 |  | 0.2 | 0.4 | 0.63
BONN Total |  |  |  |  | 0.53 |  | 0.65 | 0.4 | 1.58
CAU | KE | JAPARIDZE, GEORGE | Monitoring shifts |  | 0.015 |  |  |  | 0.015
| KE Total |  |  |  | 0.015 |  |  |  | 0.015
CAU Total |  |  |  |  | 0.015 |  |  |  | 0.015
CHIBA | KE | YOSHIDA, SHIGERU | Maintain Romeo, EHE Simulations, Calibration using Standard Candles |  |  |  |  | 0.2 | 0.2
| KE Total | [6 empty] | 0.2 | 0.2
| SC | ISHIHARA, AYA | EHE and Brights WG co-chair |  |  |  | 0.25 |  | 0.25
|  |  | EHE Filters |  |  |  | 0.15 |  | 0.15
|  | KEIICHI MASE | Maintain Romeo, EHE Simulations, Maintain reconstruction projects (Portia), MC/Data comparison for EHE-filtered and IceTop events, Standard Candle Analysis |  |  |  |  | 0.2 | 0.2
| SC Total | [5 empty] | 0.4 | 0.2 | 0.6
| GR | CHIBA GR | Detector Monitoring |  | 0.03 |  |  |  | 0.03
|  |  | Improve the Ice Model, Afterpulse Simulator, Standard Candle Analysis, Maintain reconstruction projects (Ophelia, ehe-star) |  |  |  |  | 0.2 | 0.2
| GR Total |  |  |  | 0.03 |  |  | 0.2 | 0.23
CHIBA Total |  |  |  |  | 0.03 |  | 0.4 | 0.6 | 1.03
DESY | KE | NAHNHAUER, ROLF | Acoustic R&D Support | 0.1 |  |  |  |  | 0.1
|  | SPIERING, CHRISTIAN | ExecCom member | 0.2 |  |  |  |  | 0.2
|  | WALTER, MICHAEL | Simulation Production Cluster |  |  | 0.2 |  |  | 0.2
| KE Total |  |  | 0.3 |  | 0.2 |  |  | 0.5
| SC | BENABDERRAHMANE, LOFTI | Deputy Monitoring Coordinator |  | 0.2 |  |  |  | 0.2
|  | BERGMANN, JENS | Simulation Production Cluster |  |  | 0.25 |  |  | 0.25
|  | DESY SC | Detector Monitoring |  | 0.06 |  |  |  | 0.06
|  | SULANKE, K.-H. | DAQ Firmware Support |  | 0.15 |  |  |  | 0.15
| SC Total |  |  |  | 0.41 | 0.25 |  |  | 0.66
| GR | ACHIM STOESSL | Flasher Analysis |  | 0.2 |  |  |  | 0.2
|  | DESY GR | Detector Monitoring |  | 0.12 |  |  |  | 0.12
|  |  | Simulation Production Cluster |  |  | 0.15 |  |  | 0.15
|  | EIKE MIDDELL | Flasher Analysis |  | 0.1 |  |  |  | 0.1
|  | FRANKE, ROBERT | Online Filter for Alerts |  |  |  | 0.1 |  | 0.1
|  |  | Rate Data Bank South Pole |  |  |  | 0.1 |  | 0.1
|  | KISLAT, FABIAN | Reconstruciton Coordinator (acting), Maintain Reconstruction Framework |  |  | 0.15 |  |  | 0.15
|  | MIDDELL, EIKE | Cascade Reconstruction |  |  |  |  | 0.3 | 0.3
| GR Total |  |  |  | 0.42 | 0.3 | 0.2 | 0.3 | 1.22
| AD | DESY AD | Host Fall Collaboration Meeting | 0 |  |  |  |  | 0
| AD Total |  |  | 0 |  |  |  |  | 0
| TE | DESY TE | European Data Center -Distributed Computing and Labor |  |  | 2 |  |  | 2
| TE Total |  |  |  |  | 2 |  |  | 2
DESY Total |  |  |  | 0.3 | 0.83 | 2.75 | 0.2 | 0.3 | 4.38
DTMND | SC | PIELOTH, DAMIAN | Coordinate GRID computing in Germany |  |  | 0.25 |  |  | 0.25
| SC Total |  |  |  |  | 0.25 |  |  | 0.25
| GR | DTMD GR | Detector Monitoring |  | 0.03 |  |  |  | 0.03
|  |  | Simulation Production |  |  | 0.4 |  |  | 0.4
|  | MILKE, NATALIE | Simulation Programs: noise-generator |  |  |  |  | 0.2 | 0.2
| GR Total |  |  |  | 0.03 | 0.4 |  | 0.2 | 0.63
DTMND Total |  |  |  |  | 0.03 | 0.65 |  | 0.2 | 0.88
EPFL | KE | EPFL KE | Acoustic R&D Support | 0.1 |  |  |  |  | 0.1
| KE Total |  |  | 0.1 |  |  |  |  | 0.1
| SC | EPFL SC | SLF, Low Energy, Energy reconstruction (development) |  |  |  |  | 0.25 | 0.25
| SC Total | [6 empty] | 0.25 | 0.25
| GR | EPFL GR | Detector Monitoring |  | 0.03 |  |  |  | 0.03
| GR Total |  |  |  | 0.03 |  |  |  | 0.03
EPFL Total |  |  |  | 0.1 | 0.03 |  |  | 0.25 | 0.38
GENT | SC | UGENT SC | Acoustic R&D Support | 0.05 |  |  |  |  | 0.05
|  |  | Support IceTop Simulations, IceTop Calibrations, IceTop Reconstruction |  |  |  |  | 0.1 | 0.1
| SC Total |  |  | 0.05 |  |  |  | 0.1 | 0.15
| GR | UGENT GR | Acoustic R&D Support | 0.05 |  |  |  |  | 0.05
|  |  | Detector Monitoring |  | 0.03 |  |  |  | 0.03
|  |  | Support IceTop Simulations, IceTop Calibrations, IceTop Reconstruction |  |  |  |  | 0.4 | 0.4
| GR Total |  |  | 0.05 | 0.03 |  |  | 0.4 | 0.48
GENT Total |  |  |  | 0.1 | 0.03 |  |  | 0.5 | 0.63
GTECH | KE | TABOADA, IGNACIO | Speakers Comm Chair | 0.25 |  |  |  |  | 0.25
|  |  | TFT Board Chair |  |  |  | 0.25 |  | 0.25
| KE Total |  |  | 0.25 |  |  | 0.25 |  | 0.5
| PO | TEPE, ANDREAS | Simulation Production |  |  | 0.2 |  |  | 0.2
| PO Total |  |  |  |  | 0.2 |  |  | 0.2
| GR | DAUGHHETEE, JACOB | Standard Candle Vertex and Energy Calibration |  | 0.2 |  |  |  | 0.2
|  | GTECH GR | Monitoring shifts |  | 0.03 |  |  |  | 0.03
| GR Total |  |  |  | 0.23 |  |  |  | 0.23
GTECH Total |  |  |  | 0.25 | 0.23 | 0.2 | 0.25 |  | 0.93
HUMBOLDT | KE | HUMB KE | Reconstruction/ Analysis tools |  |  |  |  | 0.1 | 0.1
|  | KOLANOSKI, HERMANN | CR-WG Co Chair |  |  |  | 0.25 |  | 0.25
| KE Total | [5 empty] | 0.25 | 0.1 | 0.35
| GR | HUMB GR | Detector Monitoring |  | 0.03 |  |  |  | 0.03
|  | KISLET, FABIAN | Reconstruction software manager |  |  |  |  | 0.25 | 0.25
| GR Total |  |  |  | 0.03 |  |  | 0.25 | 0.28
HUMBOLDT Total |  |  |  |  | 0.03 |  | 0.25 | 0.35 | 0.63
KU | KE | BESSON, DAVE | EMI - Radio R&D | 0.1 |  |  |  |  | 0.1
|  |  | Monitoring shifts |  | 0.02 |  |  |  | 0.02
| KE Total |  |  | 0.1 | 0.02 |  |  |  | 0.12
KU Total |  |  |  | 0.1 | 0.02 |  |  |  | 0.12
LBNL | KE | KIRYLUK,JOANNA | Cascade WG Co Chair |  |  |  | 0.25 |  | 0.25
|  | KLEIN,SPENCER | Diffuse WG Co-chair of |  |  |  | 0.25 |  | 0.25
|  |  | Pubcom member | 0.1 |  |  |  |  | 0.1
|  |  | Supervise LBNL effort | 0.05 |  |  |  |  | 0.05
|  | NYGREN,DAVID R | Track Engine Trigger |  | 0.1 |  |  |  | 0.1
| KE Total |  |  | 0.15 | 0.1 |  | 0.5 |  | 0.75
| SC | KIRYLUK,JOANNA | BadDomList |  | 0.2 |  |  |  | 0.2
|  |  | Flasher Runs |  | 0.1 |  |  |  | 0.1
|  |  | Simulation Production on PDSF |  |  | 0.2 |  |  | 0.2
| SC Total |  |  |  | 0.3 | 0.2 |  |  | 0.5
| PO | GERHARDT,LISA | Simulation Programs: cmc |  |  |  |  | 0.2 | 0.2
|  | LBNL PO | DOM simulator & calibrator |  |  |  |  | 0.35 | 0.35
|  |  | Monitoring shifts |  | 0.09 |  |  |  | 0.09
| PO Total |  |  |  | 0.09 |  |  | 0.55 | 0.64
| EN | STEZELBERGER,THORSTEN | Maintain DAQ Hardware (Hubs, DOR, Clocks, GPS,...) |  | 0.15 |  |  |  | 0.15
| EN Total |  |  |  | 0.15 |  |  |  | 0.15
LBNL Total |  |  |  | 0.15 | 0.64 | 0.2 | 0.5 | 0.55 | 2.04
MAINZ | KE | KÓPKE, LUTZ | ExecCom member | 0.2 |  |  |  |  | 0.2
| KE Total |  |  | 0.2 |  |  |  |  | 0.2
| SC | AHRENS, JENS | Simulation Production |  |  | 0.15 |  |  | 0.15
| SC Total |  |  |  |  | 0.15 |  |  | 0.15
| GR | KROLL, GÖSTA | SuperNova Operations |  | 0.5 |  |  |  | 0.5
|  | SCHATTO, KAI | Monitoring IceCube Live integration |  | 0.1 |  |  |  | 0.1
|  |  | Reconstruction Tools |  |  |  |  | 0.3 | 0.3
|  | UM GR | Detector Monitoring |  | 0.05 |  |  |  | 0.05
|  | WIEBE, KLAUS | Checking the low energy level 2 filter |  |  |  |  | 0.2 | 0.2
|  |  | Simulation Production |  |  | 0.2 |  |  | 0.2
| GR Total |  |  |  | 0.65 | 0.2 |  | 0.5 | 1.35
MAINZ Total |  |  |  | 0.2 | 0.65 | 0.35 |  | 0.5 | 1.7
MPI | KE | RESCONI, ELISA | Analysis Coordinator | 0.5 |  |  |  |  | 0.5
| KE Total |  |  | 0.5 |  |  |  |  | 0.5
| PO | MPI PO | Data Quality & DeepCore |  |  |  |  | 0.6 | 0.6
| PO Total | [6 empty] | 0.6 | 0.6
| GR | MPI GR | Detector Monitoring |  | 0.045 |  |  |  | 0.045
| GR Total |  |  |  | 0.045 |  |  |  | 0.045
MPI Total |  |  |  | 0.5 | 0.045 |  |  | 0.6 | 1.145
OSU | PO | OSU PO | Monitoring shifts |  | 0.02 |  |  |  | 0.02
|  |  | Outreach | 0.05 |  |  |  |  | 0.05
|  | ROTT, CARSTEN | Maintain good run list |  | 0.2 |  |  |  | 0.2
| PO Total |  |  | 0.05 | 0.22 |  |  |  | 0.27
OSU Total |  |  |  | 0.05 | 0.22 |  |  |  | 0.27
PSU | KE | COWEN, DOUG | Education & Outreach | 0.05 |  |  |  |  | 0.05
|  |  | ExecCom member | 0.2 |  |  |  |  | 0.2
|  |  | Hybrid/Tau WG Chair |  |  |  | 0.25 |  | 0.25
|  | DEYOUNG, TYCE | Deep Core WG - Co Chair |  |  |  | 0.25 |  | 0.25
|  |  | Education & Outreach | 0.05 |  |  |  |  | 0.05
| KE Total |  |  | 0.3 |  |  | 0.5 |  | 0.8
| PO | CABALLERO-MORA, KAREN | Coordination and Support for Grid and distributed computing |  |  | 0.25 |  |  | 0.25
|  |  | develop starting track reconstruction |  |  |  |  | 0.08 | 0.08
|  |  | Simulation Production |  |  | 0.165 |  |  | 0.165
|  | KOSKINEN, JASON | Coordinate Deep Core reconstruction for production |  |  |  |  | 0.12 | 0.12
|  |  | develop and verify Deep Core filters |  |  |  | 0.175 |  | 0.175
|  |  | Monitoring shifts |  | 0.03 |  |  |  | 0.03
| PO Total |  |  |  | 0.03 | 0.415 | 0.175 | 0.2 | 0.82
| GR | DUNKMAN, MATT | develop and verify Deep Core filters |  |  |  | 0.25 |  | 0.25
|  |  | develop starting track reconstruction - hybrid reco. |  |  |  |  | 0.25 | 0.25
|  |  | Monitoring shifts |  | 0.03 |  |  |  | 0.03
| GR Total |  |  |  | 0.03 |  | 0.25 | 0.25 | 0.53
PSU Total |  |  |  | 0.3 | 0.06 | 0.415 | 0.925 | 0.45 | 2.15
RWTH | KE | WIEBUSCH, CHRISTOPHER | Coordinate BMBF Funding | 0.1 |  |  |  |  | 0.1
| KE Total |  |  | 0.1 |  |  |  |  | 0.1
| PO | BOERSMA, DAVID RWTH | Gal Cen Filter & Moon Filter |  |  |  | 0.15 |  | 0.15
|  |  | Maintain Reconstruction Framework |  |  | 0.1 |  |  | 0.1
|  |  | muon channel WG Co. Chair |  |  |  | 0.25 |  | 0.25
|  |  | Reconstruction Coordinator |  |  |  |  | 0.15 | 0.15
|  | LAIHEM, KARIM | Acoustic R&D Support | 0.2 |  |  |  |  | 0.2
|  |  | MonteCarlo simulations of Cherenkov light yield |  |  | 0.1 |  |  | 0.1
| PO Total |  |  | 0.2 |  | 0.2 | 0.4 | 0.15 | 0.95
| GR | BISSOK, MARTIN | Gal Cen Filter |  |  |  | 0.1 |  | 0.1
|  | BLUMENTHAL, JAN | Muon reconstruction |  |  |  |  | 0.1 | 0.1
|  | EULER, SEBASTIAN. | Finite track reconstruction |  |  |  |  | 0.2 | 0.2
|  | PAUL, LARRISA | RASTA & SPATS monitoring |  | 0.1 |  |  |  | 0.1
|  |  | Simulation Production on cluster/GRID |  |  | 0.25 |  |  | 0.25
|  | RWTH GR | Development of processing scripts for L2/L1 processing |  |  |  |  | 0.2 | 0.2
|  |  | Development of the slow monopole trigger |  |  |  | 0.2 |  | 0.2
|  |  | Monitoring (3 weeks) |  | 0.09 |  |  |  | 0.09
|  | SCHUKRAFT, ANNE | Photonics Production |  |  | 0.25 |  |  | 0.25
|  | SCHUNCK, MATTHIAS | Energy Reconstruction |  |  |  |  | 0.2 | 0.2
|  |  | Simulation Production on cluster/GRID |  |  | 0.25 |  |  | 0.25
|  | WALLRAFF, MARIUS | New Feature Extractor |  |  |  |  | 0.3 | 0.3
| GR Total |  |  |  | 0.19 | 0.75 | 0.3 | 1 | 2.24
RWTH Total |  |  |  | 0.3 | 0.19 | 0.95 | 0.7 | 1.15 | 3.29
SU | KE | FINLEY, CHAD SU | Coordination with LIGO | 0.1 |  |  |  |  | 0.1
|  |  | Point Sou\rce WG Chair |  |  |  | 0.25 |  | 0.25
|  |  | Simulation Programs: neutrino-generator |  |  |  |  | 0.2 | 0.2
|  | HULTH, PER OLOF | ExecCom member | 0.2 |  |  |  |  | 0.2
|  |  | ICB Member | 0.05 |  |  |  |  | 0.05
|  |  | Low Energy DeepCore WG Co Chair |  |  |  | 0.25 |  | 0.25
|  | HULTQVIST, KLAS | ICB Member | 0.05 |  |  |  |  | 0.05
|  |  | Simulation Work, hit-maker |  |  |  |  | 0.1 | 0.1
|  | WALCK, CHRISTIAN | Publications Bookkeeping | 0.1 |  |  |  |  | 0.1
| KE Total |  |  | 0.5 |  |  | 0.5 | 0.3 | 1.3
| SC | SEO, SEON-HEE | Develop & verify filters |  |  |  | 0.05 |  | 0.05
|  |  | Photonics/Simulation Work |  |  |  |  | 0.15 | 0.15
|  | SU SC | Computing Resources |  |  | 0.4 |  |  | 0.4
| SC Total |  |  |  |  | 0.4 | 0.05 | 0.15 | 0.6
| GR | DANNINGER, MATTIAS | WIMP Trigger & Filter |  |  |  | 0.15 |  | 0.15
|  | SU GR | Detector Monitoring |  | 0.06 |  |  |  | 0.06
|  | ZOLL, MARCEL | UHE Trigger & Filter |  |  |  | 0.1 |  | 0.1
| GR Total |  |  |  | 0.06 |  | 0.25 |  | 0.31
SU Total |  |  |  | 0.5 | 0.06 | 0.4 | 0.8 | 0.45 | 2.21
SUBR | KE | FAZELY, ALI | GEANT Simulation |  |  |  |  | 0.15 | 0.15
|  |  | Reconstruction/ Analysis tools |  |  |  |  | 0.15 | 0.15
|  | IMLAY, RICHARD | Reconstruction/ Analysis tools |  |  |  |  | 0.15 | 0.15
|  |  | Simulation Programs |  |  |  |  | 0.15 | 0.15
| KE Total | [6 empty] | 0.6 | 0.6
| SC | TER-ANTONYAN, SAMVEL | Detector Monitoring |  | 0.015 |  |  |  | 0.015
|  |  | LONI Grid computing |  |  | 0.3 |  |  | 0.3
| SC Total |  |  |  | 0.015 | 0.3 |  |  | 0.315
SUBR Total |  |  |  |  | 0.015 | 0.3 |  | 0.6 | 0.915
UA | KE | TOALE, PATRICK | Software Coordinator | 0.75 |  |  |  |  | 0.75
|  | WILLIAMS, DAWN | Data Quality Lead |  |  |  |  | 0.15 | 0.15
|  |  | managing flasher runs and other calibrations (stage 2 geometry) |  | 0.15 |  |  |  | 0.15
| KE Total |  |  | 0.75 | 0.15 |  |  | 0.15 | 1.05
| PO | ZARZHITZKY, PAVEL | Monitoring shifts |  | 0.03 |  |  |  | 0.03
|  |  | Simulation verification |  |  |  |  | 0.3 | 0.3
| PO Total |  |  |  | 0.03 |  |  | 0.3 | 0.33
| GR | XU, DONGLIAN | DeepCore simulation verification |  |  |  |  | 0.1 | 0.1
|  |  | Improvements to low energy analysis framework |  |  |  |  | 0.1 | 0.1
|  |  | Low-energy cascade calibration with flashers |  | 0.1 |  |  |  | 0.1
|  |  | Monitoring shifts |  | 0.03 |  |  |  | 0.03
| GR Total |  |  |  | 0.13 |  |  | 0.2 | 0.33
UA Total |  |  |  | 0.75 | 0.31 |  |  | 0.65 | 1.71
UAA | KE | RAWLINS, KATHERINE | flat-ntuple; muon-bundle-reco; Snow correction for IceTop |  |  |  |  | 0.3 | 0.3
|  |  | Monitoring shifts |  | 0.02 |  |  |  | 0.02
| KE Total |  |  |  | 0.02 |  |  | 0.3 | 0.32
UAA Total |  |  |  |  | 0.02 |  |  | 0.3 | 0.32
UC | GR | UC GR | Detector Monitoring |  | 0.02 |  |  |  | 0.02
|  |  | Flasher Runs |  | 0.1 |  |  |  | 0.1
| GR Total |  |  |  | 0.12 |  |  |  | 0.12
UC Total |  |  |  |  | 0.12 |  |  |  | 0.12
UCB | KE | PRICE, BUFORD | Education & Outreach | 0.1 |  |  |  |  | 0.1
| KE Total |  |  | 0.1 |  |  |  |  | 0.1
| SC | FILIMONOV, KIRILL | Coordinate Monitoring |  | 0.5 |  |  |  | 0.5
|  |  | Pubcom member | 0.1 |  |  |  |  | 0.1
|  | UCB SC | Monitoring shifts |  | 0.015 |  |  |  | 0.015
|  | WOSCHNAGG, KURT | Calibration Lead |  | 0.15 |  |  |  | 0.15
|  |  | Diffuse / atmosnu WG chair |  |  |  | 0.25 |  | 0.25
|  |  | Maintain and Verify Simulation of Photon Propagation and update Ice Properties |  |  |  |  | 0.5 | 0.5
|  |  | Speakers Comm member | 0.1 |  |  |  |  | 0.1
| SC Total |  |  | 0.2 | 0.665 |  | 0.25 | 0.5 | 1.615
| GR | UCB GR | Calibration |  | 0.1 |  |  |  | 0.1
|  |  | Monitoring shifts |  | 0.015 |  |  |  | 0.015
| GR Total |  |  |  | 0.115 |  |  |  | 0.115
UCB Total |  |  |  | 0.3 | 0.78 |  | 0.25 | 0.5 | 1.83
UCI | PO | SILVERSTRI, ANDREA | Monitoring shifts |  | 0.01 |  |  |  | 0.01
| PO Total |  |  |  | 0.01 |  |  |  | 0.01
| GR | HANSON, JORDAN | Monitoring shifts |  | 0.01 |  |  |  | 0.01
| GR Total |  |  |  | 0.01 |  |  |  | 0.01
UCI Total |  |  |  |  | 0.02 |  |  |  | 0.02
UD | KE | GAISSER, TOM | ExecCom member | 0.2 |  |  |  |  | 0.2
|  | SECKEL, DAVID | TFT Board member |  |  |  | 0.1 |  | 0.1
|  | UD KE | DAQ Monitoring |  | 0.05 |  |  |  | 0.05
| KE Total |  |  | 0.2 | 0.05 |  | 0.1 |  | 0.35
| SC | UD SC | Coordinate IceTop Operations |  | 1 |  |  |  | 1
| SC Total |  |  |  | 1 |  |  |  | 1
| PO | BERGHAUS, PATRICK - UD | moun channel WG Co. Chair |  |  |  | 0.25 |  | 0.25
|  |  | TFT Board member |  |  |  | 0.1 |  | 0.1
|  | HUSSAIN, SHAHID | Ice Properties Simulation |  |  |  |  | 0.3 | 0.3
|  |  | IceTop Simulation Production |  |  | 0.15 |  |  | 0.15
|  | KUWABARA, TAKAO | Temp. & Pressure atmospheric monitoring |  | 0.25 |  |  |  | 0.25
| PO Total |  |  |  | 0.25 | 0.15 | 0.35 | 0.3 | 1.05
| GR | RUZYBAEV , BAKHTIYAR | Ice Properties Simulation |  |  |  |  | 0.3 | 0.3
|  | XU, CHEN | Simulation Programs: sim-services |  |  |  |  | 0.3 | 0.3
| GR Total | [6 empty] | 0.6 | 0.6
UD Total |  |  |  | 0.2 | 1.3 | 0.15 | 0.45 | 0.9 | 3
ULB | KE | BERTRAND, DANIEL | ExecCom member | 0.2 |  |  |  |  | 0.2
|  | HANSON, KAEL ULB | Data Acquisition |  | 0.2 |  |  |  | 0.2
|  |  | EMI/R&D | 0.1 |  |  |  |  | 0.1
|  |  | TFT Board member |  |  |  | 0.1 |  | 0.1
| KE Total |  |  | 0.3 | 0.2 |  | 0.1 |  | 0.6
| PO | MAROTTA, ALBERTO | Computer Cluster - simulation |  |  | 0.3 |  |  | 0.3
|  |  | Maintain and Operate Database Systems (I3OmDb) |  |  | 0.2 |  |  | 0.2
| PO Total |  |  |  |  | 0.5 |  |  | 0.5
| GR | ULB GR | Detector Monitoring |  | 0.03 |  |  |  | 0.03
|  |  | Study of Tau Filters at South Pole |  |  |  | 0.1 |  | 0.1
| GR Total |  |  |  | 0.03 |  | 0.1 |  | 0.13
ULB Total |  |  |  | 0.3 | 0.23 | 0.5 | 0.2 |  | 1.23
UMD | KE | HOFFMAN, KARA | Detector R&D | 0.2 |  |  |  |  | 0.2
|  | SULLIVAN, GREG | ExecCom member | 0.2 |  |  |  |  | 0.2
|  |  | Spokesperson | 0.3 |  |  |  |  | 0.3
|  | UMD KE | E&O | 0.1 |  |  |  |  | 0.1
| KE Total |  |  | 0.8 |  |  |  |  | 0.8
| SC | BLAUFUSS, ERIK | Core Software |  |  | 0 |  |  | 0
|  |  | filter requests, bandwidth, TFT Board Member |  |  |  | 0.3 |  | 0.3
|  |  | GRB WG Chair |  |  |  | 0.25 |  | 0.25
|  |  | Maintain PnF Software and Online Filters |  | 0.2 |  |  |  | 0.2
|  | SCHMIDT, TORSTEN | Maintain Core Analysis Framework (IceTray) |  |  | 0.5 |  |  | 0.5
|  |  | Maintain PnF Software and Online Filters |  | 0.25 |  |  |  | 0.25
| SC Total |  |  |  | 0.45 | 0.5 | 0.55 |  | 1.5
| PO | OLIVAS, ALEX | Exotics- WG chair |  |  |  | 0.25 |  | 0.25
|  |  | Pubcom member | 0.1 |  |  |  |  | 0.1
|  |  | Simulation Software Programs coordinator |  |  |  |  | 0.4 | 0.4
|  | UMD PO | Monitoring shifts |  | 0.03 |  |  |  | 0.03
|  | WISSING, HENRIKE | develop & test reconstruction |  |  |  |  | 0.125 | 0.125
|  |  | EHE and Brights WG co-chair |  |  |  | 0.25 |  | 0.25
|  |  | Maintain Detector Simulation (IceSim) |  |  |  |  | 0.125 | 0.125
|  |  | Pubcom member | 0.1 |  |  |  |  | 0.1
| PO Total |  |  | 0.2 | 0.03 |  | 0.5 | 0.65 | 1.38
| GR | CHRISTY, BRIAN | Simulation Production coordination |  |  | 0.25 |  |  | 0.25
|  | HELLAUER, ROBERT | Prepare datasets for filter testing and common MC datasets for testing |  |  |  | 0.2 |  | 0.2
|  | MEAGHER, KEVIN | Core Software |  |  | 0.5 |  |  | 0.5
|  | REDL, PETER | Maintain Detector Simulation (IceSim) |  |  |  |  | 0.25 | 0.25
|  |  | Online Filter Testing |  | 0.25 |  |  |  | 0.25
|  |  | Reconstruction/ Analysis tools |  |  |  |  | 0.25 | 0.25
|  | UMD GR | Core Software |  |  | 0.25 |  |  | 0.25
|  |  | Monitoring shifts |  | 0.06 |  |  |  | 0.06
| GR Total |  |  |  | 0.31 | 1 | 0.2 | 0.5 | 2.01
| CS | UMD CS | Maintain Core Software Repository |  |  | 0.25 |  |  | 0.25
| CS Total |  |  |  |  | 0.25 |  |  | 0.25
| TE | STRASZHEIM, TROY | Maintain Core Analysis Framework (IceTray) |  |  | 0.875 |  |  | 0.875
|  | UMD TE | Coordination and Support for Grid and distributed computing |  |  | 0.25 |  |  | 0.25
| TE Total |  |  |  |  | 1.125 |  |  | 1.125
UMD Total |  |  |  | 1 | 0.79 | 2.875 | 1.25 | 1.15 | 7.065
UMH | GR | KOHNEN, GEORGE | Detector Monitoring |  | 0.03 |  |  |  | 0.03
|  |  | IC database management |  |  | 0.3 |  |  | 0.3
| GR Total |  |  |  | 0.03 | 0.3 |  |  | 0.33
UMH Total |  |  |  |  | 0.03 | 0.3 |  |  | 0.33
UOX | KE | SARKAR, SUBIR | Detector Monitoring |  | 0.02 |  |  |  | 0.02
|  |  | Yellow Book-maintenance |  |  |  |  | 0.1 | 0.1
| KE Total |  |  |  | 0.02 |  |  | 0.1 | 0.12
UOX Total |  |  |  |  | 0.02 |  |  | 0.1 | 0.12
UU | KE | BOTNER, OLGA | Outreach | 0.05 |  |  |  |  | 0.05
|  |  | Pubcom Chair | 0.4 |  |  |  |  | 0.4
|  | DE LOS HEROS, CARLOS | TFT Board member |  |  |  | 0.1 |  | 0.1
|  |  | WIMP WG Chair |  |  |  | 0.25 |  | 0.25
|  | HALLGREN, ALLAN | Acoustic R&D Support | 0.1 |  |  |  |  | 0.1
|  |  | online filter development |  |  |  | 0.05 |  | 0.05
|  |  | Outreach | 0.05 |  |  |  |  | 0.05
|  |  | Speakers Comm member | 0.1 |  |  |  |  | 0.1
| KE Total |  |  | 0.7 |  |  | 0.4 |  | 1.1
| PO | MILLER, JONATHAN | Flasher Calibration |  | 0.2 |  |  |  | 0.2
|  |  | Simulation Programs: photonics |  |  |  |  | 0.05 | 0.05
| PO Total |  |  |  | 0.2 |  |  | 0.05 | 0.25
| GR | HENRIC, TAAVOLA | Online filter development & testing |  |  |  | 0.1 |  | 0.1
|  | STROM, RICKARD | Online filter development & testing |  |  |  | 0.1 |  | 0.1
|  | UU GR | Detector Monitoring |  | 0.03 |  |  |  | 0.03
| GR Total |  |  |  | 0.03 |  | 0.2 |  | 0.23
UU Total |  |  |  | 0.7 | 0.23 |  | 0.6 | 0.05 | 1.58
UW | KE | HALZEN, FRANCIS | Principle Investigator | 0.41633 |  |  |  |  | 0.41633
|  | KARLE, ALBRECHT | Associate Director for Science and Instrumentation | 0.41667 |  |  |  |  | 0.41667
|  | MARUYAMA, REINA | Supernova WG Chair |  |  |  | 0.25 |  | 0.25
|  | MONTARULI, TERESA | TFT Board member |  |  |  | 0.1 |  | 0.1
|  | WESTERHOFF, STEFAN | CR-WG Co Chair |  |  |  | 0.1 |  | 0.1
|  |  | Pubcom member | 0.1 |  |  |  |  | 0.1
|  | YECK, JAMES | Director of Operations | 0.75 |  |  |  |  | 0.75
| KE Total |  |  | 1.683 |  |  | 0.45 |  | 2.133
| SC | CHIRKIN, DMITRY | Direct photon tracking / iceproperties calibration 0.3 ; FE/pulse extractor 0.1 ; reco software 0.1 |  |  |  |  | 0.4 | 0.4
|  |  | Simulation Programs: mmc/mmc-icetray and ucr-icetray |  |  |  |  | 0.2 | 0.2
|  | DESIATI, PAOLO | Coordination of Simulation Production |  |  | 0.7 |  |  | 0.7
|  |  | TFT Board member |  |  |  | 0.1 |  | 0.1
|  | HILL, GARY | Maintain and Verify Simulation of Photon Propagation and update Ice Properties |  |  |  |  | 0.3 | 0.3
|  |  | Offline processing |  |  |  |  | 0.2 | 0.2
|  |  | Weekly call, ICC support | 0.2 |  |  |  |  | 0.2
|  | KRASBERG, MARK | DOM Cal Maintenance, DOM Monitoring snd Troubleshooting |  | 0.35 |  |  |  | 0.35
|  |  | Provide Real-time System Monitoring and Paging |  | 0.2 |  |  |  | 0.2
|  |  | Winterovers coordinator |  | 0.25 |  |  |  | 0.25
|  | LANDSMAN, YAEL HAGAR | Science Support | 0.25 |  |  |  |  | 0.25
|  | WENDT, CHRISTOPHER | DOM CAL Maintenance |  | 0.25 |  |  |  | 0.25
|  |  | Prepare and Evaluate Flasher Calibrations. Evaluate (DomCal) Calibration Runs and update Calibration constants |  | 0.27595 |  |  |  | 0.27595
| SC Total |  |  | 0.45 | 1.3259 | 0.7 | 0.1 | 1.1 | 3.6759
| PO | ABBASI, RASHA | DST data checking |  |  |  |  | 0.1 | 0.1
|  | AGUILAR SANCHEZ JUAN ANTONIO | GRB |  |  |  |  | 0.15 | 0.15
|  |  | low level moun data verification (data/mc) |  |  |  |  | 0.1 | 0.1
|  | AUFFENBERG, JAN | Energy Reconstruction |  |  |  |  | 0.15 | 0.15
|  |  | Offline Data Processing - EHE |  |  |  |  | 0.15 | 0.15
|  |  | Online filters (EHE) |  |  |  | 0.15 |  | 0.15
|  | HOSHINA, KOTOYO | nugen maintenance |  |  |  |  | 0.2 | 0.2
|  | KURAHASHI, NAOKO | IceTray Support (Q frame) |  |  | 0.15 |  |  | 0.15
|  |  | Offline Level 2 Processing |  |  |  |  | 0.2 | 0.2
|  |  | Online processing-muon channel |  |  | 0.2 |  |  | 0.2
|  | TOSCANO, SIMONA | Cascade data processing |  |  | 0.3 |  |  | 0.3
|  |  | Cascade Online filter |  |  |  | 0.1 |  | 0.1
|  | UW PO | Monitoring shifts |  | 0.12 |  |  |  | 0.12
| PO Total |  |  |  | 0.12 | 0.65 | 0.25 | 1.05 | 2.07
| GR | BAKER, MICHAEL | Stability (L2 Processing) |  | 0.1 |  |  |  | 0.1
|  | EISCH, JONATHAN | IceTop Simulation Production |  |  | 0.3 |  |  | 0.3
|  | FEINTZIG, JACOB | Ice Properties |  | 0.15 |  |  |  | 0.15
|  | GLADSTONE, LAURA | Moon Shadow |  | 0.1 |  |  |  | 0.1
|  |  | Reconstruction tools-Deep Core |  |  |  |  | 0.15 | 0.15
|  | RODRIGUES, JOAO-PAULO | Supernova simulation / moun energy reconstruction |  |  |  |  | 0.2 | 0.2
|  | SANTANDER, MARCOS | Moon Shadow |  | 0.15 |  |  |  | 0.15
|  | UW GR | Monitoring shifts |  | 0.12 |  |  |  | 0.12
|  | VAN SANTEN, JACOB | Calibration of DOM waveforms |  | 0.15 |  |  |  | 0.15
|  |  | IceTray Support (IZMA) |  |  | 0.15 |  |  | 0.15
|  |  | Online filters / SuperDST |  |  |  | 0.15 |  | 0.15
|  | WEAVER, CHRISTOPHER | DOM CAL Maintenance |  | 0.15 |  |  |  | 0.15
|  | WHITEHORN, NATHAN | Energy Reconstruction |  |  |  |  | 0.15 | 0.15
|  |  | Photonics tables |  |  |  |  | 0.2 | 0.2
| GR Total |  |  |  | 0.92 | 0.45 | 0.15 | 0.7 | 2.22
| MA | DUVERNOIS, MICHAEL | EMI, Instrumentation, I/F | 0.25 |  |  |  |  | 0.25
|  | HAUGEN, JAMES | USAP Support | 0.25 |  |  |  |  | 0.25
|  | LAITSCH, DENISE | Detector Operations Manager |  | 1 |  |  |  | 1
|  | MERCK, MARTIN | Computing Infrastructure Management | 1 |  |  |  |  | 1
|  | PELES, ADI | Resource Coordinator | 0.5 |  |  |  |  | 0.5
| MA Total |  |  | 2 | 1 |  |  |  | 3
| AD | MALKUS, EVELYN | Education & Outreach Coordination | 0.75 |  |  |  |  | 0.75
|  | RICHARDS, JOHN | Maintain and Operate Data Storage Infrastructure |  |  | 1 |  |  | 1
|  | UW AD | Administrative Support | 0.5 |  |  |  |  | 0.5
|  |  | Host Spring collaboration meeting | 0.5 |  |  |  |  | 0.5
| AD Total |  |  | 1.75 |  | 1 |  |  | 2.75
| SE | GLOWACKI, DAVID | Maintain DAQ Software Systems (incl. triggers, DOM SW, etc. up to Event Builder) |  | 1 |  |  |  | 1
|  | LAUNDRIE, ANDREW | EMI, Instrumentation, I/F | 0.25 |  |  |  |  | 0.25
|  |  | Engineering Support | 0.45 |  |  |  |  | 0.45
|  |  | Maintain South Pole Test System Hardware and Operating Systems |  | 0.1 |  |  |  | 0.1
|  | SANDSTROM, PERRY | EMI, Instrumentation, I/F | 0.15 |  |  |  |  | 0.15
|  |  | Engineering Support | 0.15 |  |  |  |  | 0.15
|  |  | Maintain DAQ Hardware (Hubs, DOR, Clocks, GPS,...) |  | 0.25 |  |  |  | 0.25
|  |  | Maintain South Pole Computing Hardware Infrastructure and operating systems |  | 0.25 |  |  |  | 0.25
| SE Total |  |  | 1 | 1.6 |  |  |  | 2.6
| CS | JACOBSEN, JOHN (NPX) | IceCube Live Maintenance and Upgrades |  | 0.85 |  |  |  | 0.85
|  |  | Maintain DAQ Hardware (Hubs, DOR, Clocks, GPS,...) |  | 0.15 |  |  |  | 0.15
|  | SOUNDARAPANDIAN, KARTHIK | Maintain South Pole Computing Hardware Infrastructure and operating systems |  | 0.75 |  |  |  | 0.75
|  |  | Maintain South Pole Test System Hardware and Operating Systems |  | 0.25 |  |  |  | 0.25
| CS Total |  |  |  | 2 |  |  |  | 2
| TE | BELLINGER, JIM | Maintain DAQ Software Systems |  | 0.25 |  |  |  | 0.25
|  |  | Organize and monitor the production of filtered science data. Organize the usage of data analysis computing storage. Migrate data to second tier storage |  |  | 0.5 |  |  | 0.5
|  |  | Support the development of data warehouse software |  |  | 0.25 |  |  | 0.25
|  | DIAZ-VELEZ, JUAN CARLOS | Maintain Simulation Production Software |  |  |  |  | 0.2 | 0.2
|  |  | Simulation Programs: diplopia |  |  | 0.8 |  |  | 0.8
|  | FADIRAN, OLADIPO | Maintain Data Processing Software |  |  | 0.2 |  |  | 0.2
|  |  | Simulation Production Coordination; production configurations, test production and web portal. |  |  | 0.6 |  |  | 0.6
|  |  | Transformation of Data for Long-Term Persistence and Archival, e.g., HDF5 Maintain Data Warehouse Standards, Software (Ingest), Data Access (FTP), and Web Interface |  |  | 0.2 |  |  | 0.2
|  | MEADE, PATRICK | Transfer Data from S. Pole to UW Data Warehouse and Archive at S. Pole Maintain Data Transfer SW (SPADE) Maintain Data Warehouse Standards, Software (Ingest), Data Access (FTP), and Web Interface |  |  | 0.5 |  |  | 0.5
|  |  | Unpacking, Decoding & Calibration of Raw Data (Level1); Run Common Reconstructions on UW IceCube Compute Cluster (Level2) |  |  | 0.5 |  |  | 0.5
|  | SCHULTZ, DAVID | Simulation Production |  |  | 1 |  |  | 1
|  | UW TE | Maintain Core High Performance Computing Systems |  |  | 0.44 |  |  | 0.44
|  |  | Maintain Data Center Infrastructure |  |  | 0.5 |  |  | 0.5
| TE Total |  |  |  | 0.25 | 5.49 |  | 0.2 | 5.94
| WO | UW WO | Operate Detector (Winter-Overs) |  | 3 |  |  |  | 3
| WO Total |  |  |  | 3 |  |  |  | 3
| EN | SKARLUPKA, HEATH | Maintain Core High Performance Computing Systems Coordination and Support for Grid and distributed computing |  |  | 1 |  |  | 1
|  | UW EN | Engineering Support | 0.1 |  |  |  |  | 0.1
|  | UW TE | Maintain Data Center Infrastructure |  |  | 1 |  |  | 1
|  | WISNIEWSKI, PAUL | Maintain Data Center Networking and Security |  |  | 0.75 |  |  | 0.75
|  |  | Networking and Security Maintenance |  | 0.25 |  |  |  | 0.25
| EN Total |  |  | 0.1 | 0.25 | 2.75 |  |  | 3.1
UW Total |  |  |  | 6.983 | 10.4659 | 11.04 | 0.95 | 3.05 | 32.489
UWRF | KE | MADSEN, JIM | Cosmic ray shower simulations and reconstruction |  |  |  |  | 0.1 | 0.1
|  |  | Teachers’ program and UWRF Upward Bound | 0.1 |  |  |  |  | 0.1
|  | SPICZAK, GLENN | IceTop tank Monitoring |  | 0.025 |  |  |  | 0.025
| KE Total |  |  | 0.1 | 0.025 |  |  | 0.1 | 0.225
| TE | UWRF TE | Teachers Program | 0.1 |  |  |  |  | 0.1
| TE Total |  |  | 0.1 |  |  |  |  | 0.1
UWRF Total |  |  |  | 0.2 | 0.025 |  |  | 0.1 | 0.325
VUB | KE | VUB KE | data quality verification |  |  |  |  | 0.25 | 0.25
|  |  | development of reconstruction tools (IcePack framework) |  |  |  |  | 0.25 | 0.25
| KE Total | [6 empty] | 0.5 | 0.5
| PO | BOSE, DEBANJAN | muon track reconstruction in IceCube and DeepCore, waveform feature extractor |  |  |  |  | 0.25 | 0.25
|  |  | verification Deep Core data quality |  |  |  |  | 0.25 | 0.25
|  | BUITIN,STIJN | Filter for Southern sky muons |  |  |  | 0.25 |  | 0.25
|  |  | muon track reconstruction in IceCube and DeepCore, waveform feature extractor |  |  |  |  | 0.125 | 0.125
|  |  | verification Deep Core data quality |  |  |  |  | 0.125 | 0.125
|  | LABARE, MATHIEU | Filter for Southern sky muons |  |  |  | 0.25 |  | 0.25
|  |  | muon track reconstruction in IceCube and DeepCore |  |  |  |  | 0.125 | 0.125
|  |  | verification Deep Core data quality |  |  |  |  | 0.125 | 0.125
|  | STRAHLER, ERIK | simulation of ice properties and DOM sensitivities |  |  | 0.25 |  |  | 0.25
|  |  | verification Deep Core data quality |  |  |  |  | 0.25 | 0.25
|  | VUB PO | Monitoring shifts |  | 0.06 |  |  |  | 0.06
| PO Total |  |  |  | 0.06 | 0.25 | 0.5 | 1.25 | 2.06
VUB Total |  |  |  |  | 0.06 | 0.25 | 0.5 | 1.75 | 2.56
WUPPERTAL | KE | HELBING, KLAUS | R&D Lead | 0.1 |  |  |  |  | 0.1
|  |  | Speakers Comm member | 0.1 |  |  |  |  | 0.1
|  | WUPPERTAL KE | RFI | 0.1 |  |  |  |  | 0.1
| KE Total |  |  | 0.3 |  |  |  |  | 0.3
| PO | KARG, TIMO | Acoustic Lead | 0.1 |  |  |  |  | 0.1
|  |  | Simulation Production |  |  | 0.2 |  |  | 0.2
| PO Total |  |  | 0.1 |  | 0.2 |  |  | 0.3
| GR | WUPPERTAL GR | AURA, SPATS, surface antenna operations (RICE) |  | 0.45 |  |  |  | 0.45
|  |  | New SUSY Filter |  |  |  | 0.2 |  | 0.2
|  |  | New SUSY Reconstruction, Simulation, Propagation, Monopole, Photonics |  |  |  |  | 0.5 | 0.5
|  |  | Simulation Production |  |  | 0.2 |  |  | 0.2
|  |  | South Pole EMI Monitoring |  | 0.15 |  |  |  | 0.15
| GR Total |  |  |  | 0.6 | 0.2 | 0.2 | 0.5 | 1.5
WUPPERTAL Total |  |  |  | 0.4 | 0.6 | 0.4 | 0.2 | 0.5 | 2.1
Grand Total |  |  |  | 13.783 | 18.6859 | 22.03 | 9.325 | 16.4 | 80.224