## WBS Staffing Matrix (TASKS)
WBS L2 | WBS L3 | US / Non-US | Institution | Labor Cat. | Names | Tasks | NSF M&O Core | NSF Base Grants | U.S. IN-KIND | Non U.S. In-Kind | Grand Total
2.1 Program Management | 2.1.1 Administration | US | GTECH | KE | TABOADA, IGNACIO | Chair of speakers’ committee |  |  | 0.25 |  | 0.25
2.1 Program Management | 2.1.1 Administration | US | LBNL | KE | KLEIN,SPENCER | Supervise LBNL effort | 0 |  |  |  | 0
2.1 Program Management | 2.1.1 Administration | US | LBNL | KE | KLEIN,SPENCER | Publications Comm. Member |  |  | 0.1 |  | 0.1
2.1 Program Management | 2.1.1 Administration | US | PSU | KE | COWEN, DOUG | ExecCom member |  |  | 0.2 |  | 0.2
2.1 Program Management | 2.1.1 Administration | US | UA | KE | TOALE, PATRICK | Software Coordinator |  |  | 0.75 |  | 0.75
2.1 Program Management | 2.1.1 Administration | US | UCB | KE | PRICE, BUFORD | Education & Outreach |  |  | 0.1 |  | 0.1
2.1 Program Management | 2.1.1 Administration | US | UCB | SC | WOSCHNAGG, KURT | Speakers Comm member |  | 0.1 |  |  | 0.1
2.1 Program Management | 2.1.1 Administration | US | UD | KE | GAISSER, TOM | Spokesperson |  |  | 0.3 |  | 0.3
2.1 Program Management | 2.1.1 Administration | US | UMD | KE | SULLIVAN, GREG | ExecCom member |  |  | 0.2 |  | 0.2
2.1 Program Management | 2.1.1 Administration | US | UMD | PO | OLIVAS, ALEX | Pubcom member |  | 0.1 |  |  | 0.1
2.1 Program Management | 2.1.1 Administration | US | UMD | PO | WISSING, HENRIKE | Pubcom member |  | 0.1 |  |  | 0.1
2.1 Program Management | 2.1.1 Administration | US | UW | KE | HALZEN, FRANCIS | Principle Investigator | 0.083 |  | 0.33333 |  | 0.41633
2.1 Program Management | 2.1.1 Administration | US | UW | KE | KARLE, ALBRECHT | Associate Director for Science | 0.083333 |  | 0.33333 |  | 0.41667
2.1 Program Management | 2.1.1 Administration | US | UW | KE | WESTERHOFF, STEFAN | Pubcom member |  |  | 0.1 |  | 0.1
2.1 Program Management | 2.1.1 Administration | US | UW | KE | YECK, JAMES | Project Director | 0.75 |  |  |  | 0.75
2.1 Program Management | 2.1.1 Administration | US | UW | SC | HILL, GARY | Weekly call, ICC support |  | 0.2 |  |  | 0.2
2.1 Program Management | 2.1.1 Administration | US | UW | MA | MERCK, MARTIN | Computing Infrastructure Management | 1 |  |  |  | 1
2.1 Program Management | 2.1.1 Administration | US | UW | MA | PELES, ADI | Resource Coordinator | 0.5 |  |  |  | 0.5
2.1 Program Management | 2.1.1 Administration | US | UW | AD | UW AD | Administrative Support | 0.5 |  |  |  | 0.5
2.1 Program Management | 2.1.1 Administration | US | UW | AD | UW AD | Host Spring collaboration meeting |  | 0.5 |  |  | 0.5
2.1 Program Management | 2.1.1 Administration | US | US Total |  |  |  | 3.2913 | 1 | 2.6667 |  | 6.583
2.1 Program Management | 2.1.1 Administration | Non-US | DESY | KE | SPIERING, CHRISTIAN | ExecCom member |  |  |  | 0.15 | 0.15
2.1 Program Management | 2.1.1 Administration | Non-US | DESY | AD | DESY AD | Host Fall Collaboration Meeting |  |  |  | 0 | 0
2.1 Program Management | 2.1.1 Administration | Non-US | MPI | KE | RESCONI, ELISA | Analysis Coordinator |  |  |  | 0.5 | 0.5
2.1 Program Management | 2.1.1 Administration | Non-US | RWTH | KE | WIEBUSCH, CHRISTOPHER | Coordinate BMBF Funding |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.1 Administration | Non-US | SU | KE | HULTH, PER OLOF | ExecCom member |  |  |  | 0.2 | 0.2
2.1 Program Management | 2.1.1 Administration | Non-US | SU | KE | HULTH, PER OLOF | Outreach |  |  |  | 0.15 | 0.15
2.1 Program Management | 2.1.1 Administration | Non-US | SU | KE | HULTH, PER OLOF | ICB Member |  |  |  | 0.05 | 0.05
2.1 Program Management | 2.1.1 Administration | Non-US | SU | KE | WALCK, CHRISTIAN | Pubcom member |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.1 Administration | Non-US | SU | SC | FINLEY, CHAD SU | Coordination with LIGO |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.1 Administration | Non-US | ULB | KE | BERTRAND, DANIEL | ExecCom member |  |  |  | 0.2 | 0.2
2.1 Program Management | 2.1.1 Administration | Non-US | UU | KE | BOTNER, OLGA | Outreach |  |  |  | 0.05 | 0.05
2.1 Program Management | 2.1.1 Administration | Non-US | UU | KE | BOTNER, OLGA | Pubcom Chair |  |  |  | 0.4 | 0.4
2.1 Program Management | 2.1.1 Administration | Non-US | UU | KE | HALLGREN, ALLAN | Outreach |  |  |  | 0.05 | 0.05
2.1 Program Management | 2.1.1 Administration | Non-US | UU | KE | HALLGREN, ALLAN | Speakers Comm member |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.1 Administration | Non-US | WUPPERTAL | KE | HELBING, KLAUS | Speakers Comm member |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.1 Administration | Non-US | MAINZ | KE | KÓPKE, LUTZ | ExecCom member |  |  |  | 0.15 | 0.15
2.1 Program Management | 2.1.1 Administration | Non-US | BONN | KE | KOWALSKI, MAREK | Pubcom member |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.1 Administration | Non-US | BOCHUM | KE | BECKER, JULIA | Pubcom member |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.1 Administration | Non-US | Non-US Total | [6 empty] | 2.6 | 2.6
2.1 Program Management | 2.1.1 Administration | WBS L3 Total |  |  |  |  | 3.2913 | 1 | 2.6667 | 2.6 | 9.183
2.1 Program Management | 2.1.2 Engineering And R&D Support | US | KU | KE | BESSON, DAVE | EMI - Radio R&D |  |  | 0.1 |  | 0.1
2.1 Program Management | 2.1.2 Engineering And R&D Support | US | UMD | KE | HOFFMAN, KARA | Detector R&D |  |  | 0.2 |  | 0.2
2.1 Program Management | 2.1.2 Engineering And R&D Support | US | UW | SC | LANDSMAN, YAEL HAGAR | Science Support | 0.25 |  |  |  | 0.25
2.1 Program Management | 2.1.2 Engineering And R&D Support | US | UW | SE | LAUNDRIE, ANDREW | EMI, Instrumentation, I/F | 0.25 |  |  |  | 0.25
2.1 Program Management | 2.1.2 Engineering And R&D Support | US | UW | SE | LAUNDRIE, ANDREW | Engineering Support | 0.65 |  |  |  | 0.65
2.1 Program Management | 2.1.2 Engineering And R&D Support | US | UW | SE | SANDSTROM, PERRY | EMI, Instrumentation, I/F | 0.25 |  |  |  | 0.25
2.1 Program Management | 2.1.2 Engineering And R&D Support | US | UW | SE | SANDSTROM, PERRY | Engineering Support | 0.25 |  |  |  | 0.25
2.1 Program Management | 2.1.2 Engineering And R&D Support | US | UW | EN | UW EN | Engineering Support | 0.1 |  |  |  | 0.1
2.1 Program Management | 2.1.2 Engineering And R&D Support | US | UW | TE | UW TE | EMI, Instrumentation, I/F | 0.25 |  |  |  | 0.25
2.1 Program Management | 2.1.2 Engineering And R&D Support | US | US Total |  |  |  | 2 | 0 | 0.3 |  | 2.3
2.1 Program Management | 2.1.2 Engineering And R&D Support | Non-US | DESY | KE | NAHNHAUER, ROLF | Acoustic R&D Support |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.2 Engineering And R&D Support | Non-US | EPFL | KE | EPFL KE | Acoustic R&D Support |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.2 Engineering And R&D Support | Non-US | RWTH | SC | RWTH SC | Acoustic R&D Support |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.2 Engineering And R&D Support | Non-US | ULB | KE | HANSON, KAEL ULB | EMI/R&D |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.2 Engineering And R&D Support | Non-US | UU | KE | HALLGREN, ALLAN | Acoustic R&D Support |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.2 Engineering And R&D Support | Non-US | WUPPERTAL | KE | HELBING, KLAUS | R&D Lead |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.2 Engineering And R&D Support | Non-US | WUPPERTAL | KE | WUPPERTAL KE | RFI |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.2 Engineering And R&D Support | Non-US | WUPPERTAL | PO | KARG, TIMO | Acoustic Lead |  |  |  | 0.1 | 0.1
2.1 Program Management | 2.1.2 Engineering And R&D Support | Non-US | GENT | SC | UGENT SC | Acoustic R&D Support |  |  |  | 0.05 | 0.05
2.1 Program Management | 2.1.2 Engineering And R&D Support | Non-US | GENT | GR | UGENT GR | Acoustic R&D Support |  |  |  | 0.05 | 0.05
2.1 Program Management | 2.1.2 Engineering And R&D Support | Non-US | Non-US Total | [6 empty] | 0.9 | 0.9
2.1 Program Management | 2.1.2 Engineering And R&D Support | WBS L3 Total |  |  |  |  | 2 | 0 | 0.3 | 0.9 | 3.2
2.1 Program Management | 2.1.3 Usap Support | US | UW | MA | PAULOS, ROBERT | USAP Support | 0.25 |  |  |  | 0.25
2.1 Program Management | 2.1.3 Usap Support | US | US Total |  |  |  | 0.25 |  |  |  | 0.25
2.1 Program Management | 2.1.3 Usap Support | WBS L3 Total |  |  |  |  | 0.25 |  |  |  | 0.25
2.1 Program Management | 2.1.4 Education & Outreach | US | OSU | PO | OSU PO | Outreach |  |  | 0.05 |  | 0.05
2.1 Program Management | 2.1.4 Education & Outreach | US | PSU | KE | COWEN, DOUG | Education & Outreach |  |  | 0.05 |  | 0.05
2.1 Program Management | 2.1.4 Education & Outreach | US | PSU | KE | DEYOUNG, TYCE | Education & Outreach |  |  | 0.05 |  | 0.05
2.1 Program Management | 2.1.4 Education & Outreach | US | UMD | KE | UMD KE | E&O |  |  | 0.1 |  | 0.1
2.1 Program Management | 2.1.4 Education & Outreach | US | UW | AD | MALKUS, EVELYN | Education & Outreach Coordination | 0.75 |  |  |  | 0.75
2.1 Program Management | 2.1.4 Education & Outreach | US | UW | AD | UW AD | Teachers | 0.25 |  |  |  | 0.25
2.1 Program Management | 2.1.4 Education & Outreach | US | UWRF | KE | MADSEN, JIM | Teachers’ program and UWRF Upward Bound |  |  | 0.1 |  | 0.1
2.1 Program Management | 2.1.4 Education & Outreach | US | UWRF | TE | UWRF TE | Teachers Program | 0.15 |  |  |  | 0.15
2.1 Program Management | 2.1.4 Education & Outreach | US | US Total |  |  |  | 1.15 | 0 | 0.35 |  | 1.5
2.1 Program Management | 2.1.4 Education & Outreach | WBS L3 Total |  |  |  |  | 1.15 | 0 | 0.35 |  | 1.5
2.1 Program Management | WBS L2 Total | [5 empty] | 6.6913 | 1 | 3.3167 | 3.5 | 14.133
2.2 Detector Operations & Maintenance | 2.2 Detector Operations & Maintenance | US | LBNL | KE | NYGREN,DAVID R | Track Engine Trigger |  |  | 0.1 |  | 0.1
2.2 Detector Operations & Maintenance | 2.2 Detector Operations & Maintenance | US | UW | MA | LAITSCH, DENISE | Detector Operations Manager | 0.875 |  |  |  | 0.875
2.2 Detector Operations & Maintenance | 2.2 Detector Operations & Maintenance | US | US Total |  |  |  | 0.875 | 0 | 0.1 |  | 0.975
2.2 Detector Operations & Maintenance | 2.2 Detector Operations & Maintenance | WBS L3 Total |  |  |  |  | 0.875 | 0 | 0.1 |  | 0.975
2.2 Detector Operations & Maintenance | 2.2.1 Run Coordination | US | UW | SC | KRASBERG, MARK | Winterovers coordinator | 0.25 |  |  |  | 0.25
2.2 Detector Operations & Maintenance | 2.2.1 Run Coordination | US | UW | WO | UW WO | Operate Detector (Winter-Overs) | 3 |  |  |  | 3
2.2 Detector Operations & Maintenance | 2.2.1 Run Coordination | US | US Total |  |  |  | 3.25 |  |  |  | 3.25
2.2 Detector Operations & Maintenance | 2.2.1 Run Coordination | Non-US | UC | GR | UC GR | Flasher Runs |  |  |  | 0.1 | 0.1
2.2 Detector Operations & Maintenance | 2.2.1 Run Coordination | Non-US | BONN | PO | BOESER SEBASTIAN | Run Coordinator |  |  |  | 0.5 | 0.5
2.2 Detector Operations & Maintenance | 2.2.1 Run Coordination | Non-US | Non-US Total | [6 empty] | 0.6 | 0.6
2.2 Detector Operations & Maintenance | 2.2.1 Run Coordination | WBS L3 Total |  |  |  |  | 3.25 |  |  | 0.6 | 3.85
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | US | LBNL | CS | BEATTIE,KEITH S | Maintain DAQ Software Systems (incl. triggers, DOM SW, etc. up to Event Builder) | 0 |  |  |  | 0
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | US | LBNL | EN | STEZELBERGER,THORSTEN | Maintain DAQ Hardware (Hubs, DOR, Clocks, GPS,...) | 0.15 |  |  |  | 0.15
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | US | UD | KE | UD KE | DAQ Monitoring |  |  | 0.05 |  | 0.05
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | US | UW | SC | KRASBERG, MARK | DOM Cal Maintenance, DOM Monitoring snd Troubleshooting | 0.35 |  |  |  | 0.35
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | US | UW | SC | KRASBERG, MARK | Provide Real-time System Monitoring and Paging | 0.2 |  |  |  | 0.2
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | US | UW | SC | WENDT, CHRISTOPHER | DOM CAL Maintenance | 0.25 |  |  |  | 0.25
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | US | UW | SE | GLOWACKI, DAVID | Maintain DAQ Software Systems (incl. triggers, DOM SW, etc. up to Event Builder) | 1 |  |  |  | 1
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | US | UW | SE | SANDSTROM, PERRY | Maintain DAQ Hardware (Hubs, DOR, Clocks, GPS,...) | 0.25 |  |  |  | 0.25
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | US | UW | CS | JACOBSEN, JOHN (NPX) | Maintain DAQ Hardware (Hubs, DOR, Clocks, GPS,...) | 0.15 |  |  |  | 0.15
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | US | UW | GR | WEAVER, CHRISTOPHER | DOM CAL Maintenance |  | 0.2 |  |  | 0.2
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | US | US Total |  |  |  | 2.35 | 0.2 | 0.05 |  | 2.6
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | Non-US | DESY | SC | SULANKE, K.-H. | DAQ Firmware Support |  |  |  | 0.15 | 0.15
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | Non-US | ULB | KE | HANSON, KAEL ULB | Data Acquisition |  |  |  | 0.2 | 0.2
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | Non-US | Non-US Total | [6 empty] | 0.35 | 0.35
2.2 Detector Operations & Maintenance | 2.2.2 Data Acquisition | WBS L3 Total |  |  |  |  | 2.35 | 0.2 | 0.05 | 0.35 | 2.95
2.2 Detector Operations & Maintenance | 2.2.3 Online Filter (Pnf) | US | UMD | SC | BLAUFUSS, ERIK | Maintain PnF Software and Online Filters | 0.2 |  |  |  | 0.2
2.2 Detector Operations & Maintenance | 2.2.3 Online Filter (Pnf) | US | UMD | SC | SCHMIDT, TORSTEN | Maintain PnF Software and Online Filters | 0.25 |  |  |  | 0.25
2.2 Detector Operations & Maintenance | 2.2.3 Online Filter (Pnf) | US | UMD | GR | REDL, PETER | Online Filter Testing |  | 0.25 |  |  | 0.25
2.2 Detector Operations & Maintenance | 2.2.3 Online Filter (Pnf) | US | US Total |  |  |  | 0.45 | 0.25 | 0 |  | 0.7
2.2 Detector Operations & Maintenance | 2.2.3 Online Filter (Pnf) | WBS L3 Total |  |  |  |  | 0.45 | 0.25 | 0 |  | 0.7
2.2 Detector Operations & Maintenance | 2.2.4 Sps Operations | US | UW | SE | SANDSTROM, PERRY | Maintain South Pole Computing Hardware Infrastructure and operating systems | 0.25 |  |  |  | 0.25
2.2 Detector Operations & Maintenance | 2.2.4 Sps Operations | US | UW | CS | SOUNDARAPANDIAN, KARTHIK | Maintain South Pole Computing Hardware Infrastructure and operating systems | 0.75 |  |  |  | 0.75
2.2 Detector Operations & Maintenance | 2.2.4 Sps Operations | US | UW | EN | WISNIEWSKI, PAUL | Networking and Security Maintenance | 0.25 |  |  |  | 0.25
2.2 Detector Operations & Maintenance | 2.2.4 Sps Operations | US | US Total |  |  |  | 1.25 |  |  |  | 1.25
2.2 Detector Operations & Maintenance | 2.2.4 Sps Operations | WBS L3 Total |  |  |  |  | 1.25 |  |  |  | 1.25
2.2 Detector Operations & Maintenance | 2.2.5 Spts Operations | US | UW | SE | LAUNDRIE, ANDREW | Maintain South Pole Test System Hardware and Operating Systems | 0.1 |  |  |  | 0.1
2.2 Detector Operations & Maintenance | 2.2.5 Spts Operations | US | UW | CS | SOUNDARAPANDIAN, KARTHIK | Maintain South Pole Test System Hardware and Operating Systems | 0.25 |  |  |  | 0.25
2.2 Detector Operations & Maintenance | 2.2.5 Spts Operations | US | UW | EN | UW EN | Maintain South Pole Test System Hardware and Operating Systems | 0.5 |  |  |  | 0.5
2.2 Detector Operations & Maintenance | 2.2.5 Spts Operations | US | US Total |  |  |  | 0.85 |  |  |  | 0.85
2.2 Detector Operations & Maintenance | 2.2.5 Spts Operations | WBS L3 Total |  |  |  |  | 0.85 |  |  |  | 0.85
2.2 Detector Operations & Maintenance | 2.2.6 Experiment Control | US | UW | CS | JACOBSEN, JOHN (NPX) | IceCube Live Maintenance and Upgrades | 0.85 |  |  |  | 0.85
2.2 Detector Operations & Maintenance | 2.2.6 Experiment Control | US | US Total |  |  |  | 0.85 |  |  |  | 0.85
2.2 Detector Operations & Maintenance | 2.2.6 Experiment Control | WBS L3 Total |  |  |  |  | 0.85 |  |  |  | 0.85
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | CAU | KE | JAPARIDZE, GEORGE | Monitoring shifts |  |  | 0.015 |  | 0.015
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | GTECH | GR | GTECH GR | Monitoring shifts |  |  | 0.03 |  | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | KU | KE | BESSON, DAVE | Monitoring shifts |  |  | 0.02 |  | 0.02
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | LBNL | SC | KIRYLUK,JOANNA | BadDomList |  | 0.2 |  |  | 0.2
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | LBNL | PO | LBNL PO | Monitoring shifts |  | 0.09 |  |  | 0.09
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | OSU | PO | OSU PO | Monitoring shifts |  |  | 0.02 |  | 0.02
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | OSU | PO | ROTT, CARSTEN | Maintain good run list |  |  | 0.2 |  | 0.2
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | OSU | GR | DAVIS, JAMES | Monitoring shifts |  |  | 0.01 |  | 0.01
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | PSU | PO | KOSKINEN, JASON | Monitoring shifts |  | 0.03 |  |  | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | PSU | GR | PSU GR | Monitoring shifts |  | 0.03 |  |  | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | SUBR | SC | TER-ANTONYAN, SAMVEL | Detector Monitoring |  |  | 0.015 |  | 0.015
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | UA | GR | XU, DONGLIAN | Monitoring shifts |  |  | 0.03 |  | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | UAA | KE | RAWLINS, KATHERINE | Monitoring shifts |  |  | 0.02 |  | 0.02
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | UCB | SC | FILIMONOV, KIRILL | Coordinate Monitoring |  | 0.5 |  |  | 0.5
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | UCB | SC | UCB SC | Monitoring shifts |  | 0.015 |  |  | 0.015
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | UCB | GR | UCB GR | Monitoring shifts |  | 0.015 |  |  | 0.015
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | UCI | PO | SILVERSTRI, ANDREA | Monitoring shifts |  |  | 0.01 |  | 0.01
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | UCI | GR | HANSON, JORDAN | Monitoring shifts |  |  | 0.01 |  | 0.01
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | UD | PO | KUWABARA, TAKAO | Temp. & Pressure atmospheric monitoring |  | 0.25 |  |  | 0.25
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | UMD | PO | UMD PO | Monitoring shifts |  | 0.03 |  |  | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | UMD | GR | UMD GR | Monitoring shifts |  | 0.06 |  |  | 0.06
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | UW | PO | UW PO | Monitoring shifts |  | 0.12 |  |  | 0.12
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | UW | GR | BAKER, MICHAEL | Stability |  | 0.1 |  |  | 0.1
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | UW | GR | UW GR | Monitoring shifts |  | 0.12 |  |  | 0.12
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | US | US Total |  |  |  |  | 1.56 | 0.38 |  | 1.94
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | CHIBA | GR | CHIBA GR | Detector Monitoring |  |  |  | 0.03 | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | DESY | SC | DESY SC | Detector Monitoring |  |  |  | 0.06 | 0.06
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | DESY | SC | BENABDERRAHMANE, LOFTI | Deputy Monitoring Coordinator |  |  |  | 0.2 | 0.2
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | DESY | GR | DESY GR | Detector Monitoring |  |  |  | 0.12 | 0.12
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | DTMND | GR | DTMD GR | Detector Monitoring |  |  |  | 0.03 | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | EPFL | GR | EPFL GR | Detector Monitoring |  |  |  | 0.03 | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | MPI | GR | MPI GR | Detector Monitoring |  |  |  | 0.045 | 0.045
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | RWTH | GR | RWTH GR | Monitoring (3 weeks) |  |  |  | 0.09 | 0.09
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | SU | GR | SU GR | Detector Monitoring |  |  |  | 0.06 | 0.06
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | UC | GR | UC GR | Detector Monitoring |  |  |  | 0.02 | 0.02
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | ULB | GR | ULB GR | Detector Monitoring |  |  |  | 0.03 | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | UMH | GR | KOHNEN, GEORGE | Detector Monitoring |  |  |  | 0.03 | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | UOX | KE | SARKAR, SUBIR | Detector Monitoring |  |  |  | 0.02 | 0.02
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | UU | GR | UU GR | Detector Monitoring |  |  |  | 0.03 | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | VUB | PO | VUB PO | Monitoring shifts |  |  |  | 0.06 | 0.06
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | VUB | GR | VUB GR | Detector Monitoring |  |  |  | 0.03 | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | WUPPERTAL | GR | WUPPERTAL GR | South Pole EMI Monitoring |  |  |  | 0.15 | 0.15
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | WUPPERTAL | GR | WUPPERTAL GR | AURA, SPATS, surface antenna operations (RICE) |  |  |  | 0.45 | 0.45
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | MAINZ | GR | UM GR | Detector Monitoring |  |  |  | 0.05 | 0.05
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | MAINZ | GR | SCHATTO, KAI | Monitoring IceCube Live integration |  |  |  | 0.35 | 0.35
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | HUMBOLDT | SC | HUMB SC | Detector Monitoring |  |  |  | 0.03 | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | GENT | GR | UGENT GR | Detector Monitoring |  |  |  | 0.03 | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | BONN | GR | UBONN GR | Detector Monitoring |  |  |  | 0.03 | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | BOCHUM | GR | UBOCHUM GR | Detector Monitoring |  |  |  | 0.03 | 0.03
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | Non-US | Non-US Total | [6 empty] | 2.005 | 2.005
2.2 Detector Operations & Maintenance | 2.2.7 Detector Monitoring | WBS L3 Total | [5 empty] | 1.56 | 0.38 | 2.005 | 3.945
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | US | GTECH | GR | DAUGHHETEE, JACOB | Standard Candle Vertex and Energy Calibration |  |  | 0.2 |  | 0.2
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | US | LBNL | SC | KIRYLUK,JOANNA | Flasher Runs |  | 0.1 |  |  | 0.1
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | US | UA | KE | WILLIAMS, DAWN | managing flasher runs and other calibrations (stage 2 geometry) |  |  | 0.15 |  | 0.15
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | US | UA | PO | ZARZHITZKY, PAVEL | taking flasher runs |  |  | 0.2 |  | 0.2
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | US | UA | GR | XU, DONGLIAN | geometry systematic |  |  | 0.25 |  | 0.25
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | US | UCB | SC | WOSCHNAGG, KURT | Calibration Lead |  | 0.15 |  |  | 0.15
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | US | UCB | GR | UCB GR | Calibration |  | 0.1 |  |  | 0.1
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | US | UW | SC | WENDT, CHRISTOPHER | Prepare and Evaluate Flasher Calibrations. Evaluate (DomCal) Calibration Runs. | 0.27595 |  |  |  | 0.27595
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | US | UW | GR | GLADSTONE, LAURA | Moon Shadow |  | 0.15 |  |  | 0.15
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | US | UW | GR | SANTANDER, MARCOS | Calibration with flashers |  | 0.2 |  |  | 0.2
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | US | US Total |  |  |  | 0.27595 | 0.7 | 0.8 |  | 1.7759
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | Non-US | DESY | GR | ACHIM STOESSL | Flasher Analysis |  |  |  | 0.2 | 0.2
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | Non-US | DESY | GR | EIKE MIDDELL | Flasher Analysis |  |  |  | 0.1 | 0.1
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | Non-US | UU | PO | MILLER, JONATHAN | Flasher Calibration |  |  |  | 0.2 | 0.2
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | Non-US | Non-US Total | [6 empty] | 0.5 | 0.5
2.2 Detector Operations & Maintenance | 2.2.8 Detector Calibration | WBS L3 Total |  |  |  |  | 0.27595 | 0.7 | 0.8 | 0.5 | 2.2759
2.2 Detector Operations & Maintenance | 2.2.9 Icetop Operations | US | UD | SC | UD SC | Coordinate IceTop Operations | 1 |  |  |  | 1
2.2 Detector Operations & Maintenance | 2.2.9 Icetop Operations | US | UWRF | KE | SPICZAK, GLENN | IceTop tank Monitoring |  |  | 0.025 |  | 0.025
2.2 Detector Operations & Maintenance | 2.2.9 Icetop Operations | US | UWRF | SC | TAMBURRO, ALESSIO | IceTop tank Monitoring |  |  | 0.025 |  | 0.025
2.2 Detector Operations & Maintenance | 2.2.9 Icetop Operations | US | US Total |  |  |  | 1 | 0 | 0.05 |  | 1.05
2.2 Detector Operations & Maintenance | 2.2.9 Icetop Operations | Non-US | HUMBOLDT | SC | WALDENMAIER, TILO | IceTop Operations |  |  |  | 0.1 | 0.1
2.2 Detector Operations & Maintenance | 2.2.9 Icetop Operations | Non-US | Non-US Total | [6 empty] | 0.1 | 0.1
2.2 Detector Operations & Maintenance | 2.2.9 Icetop Operations | WBS L3 Total |  |  |  |  | 1 | 0 | 0.05 | 0.1 | 1.15
2.2 Detector Operations & Maintenance | 2.2.10 Supernova Operations | Non-US | MAINZ | GR | KROLL, GÖSTA | SuperNova Operations |  |  |  | 0.5 | 0.5
2.2 Detector Operations & Maintenance | 2.2.10 Supernova Operations | Non-US | MAINZ | GR | WIEBE, KLAUS | SuperNova IceCube Live integration |  |  |  | 0.1 | 0.1
2.2 Detector Operations & Maintenance | 2.2.10 Supernova Operations | Non-US | Non-US Total | [6 empty] | 0.6 | 0.6
2.2 Detector Operations & Maintenance | 2.2.10 Supernova Operations | WBS L3 Total | [7 empty] | 0.6 | 0.6
2.2 Detector Operations & Maintenance | WBS L2 Total | [5 empty] | 11.1509 | 2.71 | 1.38 | 4.155 | 19.3959
2.3 Computing And Data Management | 2.3.1 Core Software | US | UMD | SC | BLAUFUSS, ERIK | Core Software |  | 0 |  |  | 0
2.3 Computing And Data Management | 2.3.1 Core Software | US | UMD | SC | SCHMIDT, TORSTEN | Maintain Core Analysis Framework (IceTray) | 0.5 |  |  |  | 0.5
2.3 Computing And Data Management | 2.3.1 Core Software | US | UMD | CS | UMD CS | Maintain Core Software Repository | 0.25 |  |  |  | 0.25
2.3 Computing And Data Management | 2.3.1 Core Software | US | UMD | GR | UMD GR | Core Software |  | 0.25 |  |  | 0.25
2.3 Computing And Data Management | 2.3.1 Core Software | US | UMD | GR | EHRLICH, RALF | Core Software |  | 0.5 |  |  | 0.5
2.3 Computing And Data Management | 2.3.1 Core Software | US | UMD | TE | STRASZHEIM, TROY | Maintain Core Analysis Framework (IceTray) | 0.875 |  |  |  | 0.875
2.3 Computing And Data Management | 2.3.1 Core Software | US | UW | TE | DIAZ-VELEZ, JUAN CARLOS | Simulation Programs: diplopia | 0.8 |  |  |  | 0.8
2.3 Computing And Data Management | 2.3.1 Core Software | US | UW | TE | FADIRAN, OLADIPO | Maintain Data Processing Software | 0.2 |  |  |  | 0.2
2.3 Computing And Data Management | 2.3.1 Core Software | US | UW | TE | UW TE | Maintain Data Processing Software | 0.3 |  |  |  | 0.3
2.3 Computing And Data Management | 2.3.1 Core Software | US | US Total |  |  |  | 2.925 | 0.75 | 0 |  | 3.675
2.3 Computing And Data Management | 2.3.1 Core Software | Non-US | RWTH | SC | RWTH SC | Maintain Reconstruction Framework |  |  |  | 0.1 | 0.1
2.3 Computing And Data Management | 2.3.1 Core Software | Non-US | RWTH | GR | RWTH GR | Maintain Reconstruction Framework |  |  |  | 0.15 | 0.15
2.3 Computing And Data Management | 2.3.1 Core Software | Non-US | ULB | PO | MAROTTA, ALBERTO | Maintain and Operate Database Systems (I3OmDb) |  |  |  | 0.2 | 0.2
2.3 Computing And Data Management | 2.3.1 Core Software | Non-US | Non-US Total | [6 empty] | 0.45 | 0.45
2.3 Computing And Data Management | 2.3.1 Core Software | WBS L3 Total |  |  |  |  | 2.925 | 0.75 | 0 | 0.45 | 4.125
2.3 Computing And Data Management | 2.3.2 Data Storage & Transfer | US | UW | EN | MACKENZIE, CYNTHIA | Transfer Data from S. Pole to UW Data Warehouse and Archive at S. Pole Maintain Data Transfer Software (SPADE) Maintain Data Warehouse Standards, Software (Ingest), Data Access (FTP), and Web Interface | 0.5 |  |  |  | 0.5
2.3 Computing And Data Management | 2.3.2 Data Storage & Transfer | US | UW | AD | RICHARDS, JOHN | Maintain and Operate Data Storage Infrastructure | 1 |  |  |  | 1
2.3 Computing And Data Management | 2.3.2 Data Storage & Transfer | US | UW | TE | FADIRAN, OLADIPO | Transformation of Data for Long-Term Persistence and Archival, e.g., HDF5 Maintain Data Warehouse Standards, Software (Ingest), Data Access (FTP), and Web Interface | 0.2 |  |  |  | 0.2
2.3 Computing And Data Management | 2.3.2 Data Storage & Transfer | US | UW | TE | MCGUIRE, PAUL | Maintain and Operate Data Storage Infrastructure | 0.5 |  |  |  | 0.5
2.3 Computing And Data Management | 2.3.2 Data Storage & Transfer | US | UW | TE | UW TE | Transformation of Data for Long-Term Persistence and Archival, e.g., HDF5 Maintain Data Warehouse Standards, Software (Ingest), Data Access (FTP), and Web Interface | 0.3 |  |  |  | 0.3
2.3 Computing And Data Management | 2.3.2 Data Storage & Transfer | US | UW | TE | MEADE, PATRICK | Transfer Data from S. Pole to UW Data Warehouse and Archive at S. Pole Maintain Data Transfer Software (SPADE) Maintain Data Warehouse Standards, Software (Ingest), Data Access (FTP), and Web Interface | 0.5 |  |  |  | 0.5
2.3 Computing And Data Management | 2.3.2 Data Storage & Transfer | US | US Total |  |  |  | 3 |  |  |  | 3
2.3 Computing And Data Management | 2.3.2 Data Storage & Transfer | WBS L3 Total |  |  |  |  | 3 |  |  |  | 3
2.3 Computing And Data Management | 2.3.3 Computing Resources | US | PSU | PO | PSU PO | Coordination and Support for Grid and distributed computing | 0.25 |  |  |  | 0.25
2.3 Computing And Data Management | 2.3.3 Computing Resources | US | SUBR | SC | TER-ANTONYAN, SAMVEL | LONI Grid computing |  |  | 0.3 |  | 0.3
2.3 Computing And Data Management | 2.3.3 Computing Resources | US | UMD | TE | UMD TE | Coordination and Support for Grid and distributed computing | 0.25 |  |  |  | 0.25
2.3 Computing And Data Management | 2.3.3 Computing Resources | US | UW | EN | BARNET, STEVE | 0.75 Maintain Core High Performance Computing Systems 0.25 Coordination and Support for Grid and distributed computing | 1 |  |  |  | 1
2.3 Computing And Data Management | 2.3.3 Computing Resources | US | UW | EN | BOGEN, DAVID | Maintain Data Center Infrastructure | 1 |  |  |  | 1
2.3 Computing And Data Management | 2.3.3 Computing Resources | US | UW | EN | WISNIEWSKI, PAUL | Maintain Data Center Networking and Security | 0.75 |  |  |  | 0.75
2.3 Computing And Data Management | 2.3.3 Computing Resources | US | UW | TE | MCGUIRE, PAUL | Maintain Data Center Infrastructure | 0.5 |  |  |  | 0.5
2.3 Computing And Data Management | 2.3.3 Computing Resources | US | UW | TE | UW TE | Maintain Core High Performance Computing Systems | 0.44 |  |  |  | 0.44
2.3 Computing And Data Management | 2.3.3 Computing Resources | US | US Total |  |  |  | 4.19 | 0 | 0.3 |  | 4.49
2.3 Computing And Data Management | 2.3.3 Computing Resources | Non-US | DESY | GR | KISLAT, FABIAN | Reconstruciton Coordinator (acting), Maintain Reconstruction Framework |  |  |  | 0.15 | 0.15
2.3 Computing And Data Management | 2.3.3 Computing Resources | Non-US | DESY | TE | DESY TE | European Data Center -Distributed Computing and Labor |  |  |  | 2 | 2
2.3 Computing And Data Management | 2.3.3 Computing Resources | Non-US | DTMND | SC | PIELOTH, DAMIAN | Coordinate GRID computing in Germany |  |  |  | 0.25 | 0.25
2.3 Computing And Data Management | 2.3.3 Computing Resources | Non-US | SU | SC | SU SC | Computing Resources |  |  |  | 0.5 | 0.5
2.3 Computing And Data Management | 2.3.3 Computing Resources | Non-US | UMH | GR | KOHNEN, GEORGE | IC database management |  |  |  | 0.3 | 0.3
2.3 Computing And Data Management | 2.3.3 Computing Resources | Non-US | Non-US Total | [6 empty] | 3.2 | 3.2
2.3 Computing And Data Management | 2.3.3 Computing Resources | WBS L3 Total |  |  |  |  | 4.19 | 0 | 0.3 | 3.2 | 7.69
2.3 Computing And Data Management | 2.3.4 Data Production Processing | US | UW | PO | TOSCANO, SIMONA | Cascade data processing |  | 0.35 |  |  | 0.35
2.3 Computing And Data Management | 2.3.4 Data Production Processing | US | UW | TE | MEADE, PATRICK | 0.2 Unpacking, Decoding and Calibration of Raw Data in the North (Level1) 0.3 Run Common Reconstructions on UW IceCube Compute Cluster (Level2) | 0.5 |  |  |  | 0.5
2.3 Computing And Data Management | 2.3.4 Data Production Processing | US | US Total |  |  |  | 0.5 | 0.35 | 0 |  | 0.85
2.3 Computing And Data Management | 2.3.4 Data Production Processing | Non-US | RWTH | GR | SCHUKRAFT, ANNE | Photonics Production |  |  |  | 0.25 | 0.25
2.3 Computing And Data Management | 2.3.4 Data Production Processing | Non-US | Non-US Total | [6 empty] | 0.25 | 0.25
2.3 Computing And Data Management | 2.3.4 Data Production Processing | WBS L3 Total |  |  |  |  | 0.5 | 0.35 | 0 | 0.25 | 1.1
2.3 Computing And Data Management | 2.3.5 Simulation Production | US | GTECH | PO | TEPE, ANDREAS | Simulation Production |  |  | 0.2 |  | 0.2
2.3 Computing And Data Management | 2.3.5 Simulation Production | US | LBNL | SC | KIRYLUK,JOANNA | Simulation Production on PDSF |  | 0.2 |  |  | 0.2
2.3 Computing And Data Management | 2.3.5 Simulation Production | US | PSU | PO | PSU PO | Simulation Production |  | 0.165 |  |  | 0.165
2.3 Computing And Data Management | 2.3.5 Simulation Production | US | UD | PO | HUSSAIN, SHAHID | IceTop Simulation Production |  | 0.15 |  |  | 0.15
2.3 Computing And Data Management | 2.3.5 Simulation Production | US | UMD | GR | CHRISTY, BRIAN | Simulation Production coordination |  | 0.25 |  |  | 0.25
2.3 Computing And Data Management | 2.3.5 Simulation Production | US | UW | SC | DESIATI, PAOLO | Coordination of Simulation Production | 0.7 |  |  |  | 0.7
2.3 Computing And Data Management | 2.3.5 Simulation Production | US | UW | PO | HOSHINA, K | Photon prop. Calibration |  | 0.1 |  |  | 0.1
2.3 Computing And Data Management | 2.3.5 Simulation Production | US | UW | GR | EISCH, JONATHAN | IceTop Simulation Production |  | 0.3 |  |  | 0.3
2.3 Computing And Data Management | 2.3.5 Simulation Production | US | UW | TE | FADIRAN, OLADIPO | 0.30 Coordination of Simulation Production 0.30 Maintain production configurations, manage test production and maintain web portal. | 0.6 |  |  |  | 0.6
2.3 Computing And Data Management | 2.3.5 Simulation Production | US | US Total |  |  |  | 1.3 | 1.17 | 0.2 |  | 2.665
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | DESY | KE | WALTER, MICHAEL | Simulation Production Cluster |  |  |  | 0.2 | 0.2
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | DESY | SC | BERGMANN, JENS | Simulation Production Cluster |  |  |  | 0.25 | 0.25
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | DESY | GR | DESY GR | Simulation Production Cluster |  |  |  | 0.15 | 0.15
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | DTMND | GR | DTMD GR | Simulation Production |  |  |  | 0.4 | 0.4
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | RWTH | SC | RWTH SC | Simulation Production on cluster/GRID |  |  |  | 0.1 | 0.1
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | RWTH | GR | RWTH GR | Simulation Production on cluster/GRID |  |  |  | 0.85 | 0.85
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | SU | GR | JOHANSSON, HENRIK | GRID/Simulation production & development |  |  |  | 0.2 | 0.2
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | ULB | PO | MAROTTA, ALBERTO | Computer Cluster - simulation |  |  |  | 0.3 | 0.3
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | VUB | PO | STRAHLER, ERIK | simulation of ice properties and DOM sensitivities |  |  |  | 0.25 | 0.25
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | ALBERTA | KE | GRANT, DARREN | WestGrid computing |  |  |  | 0.1 | 0.1
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | WUPPERTAL | PO | KARG, TIMO | Simulation Production |  |  |  | 0.2 | 0.2
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | WUPPERTAL | GR | WUPPERTAL GR | Simulation Production |  |  |  | 0.2 | 0.2
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | MAINZ | SC | AHRENS, JENS | Simulation Production |  |  |  | 0.15 | 0.15
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | MAINZ | GR | WIEBE, KLAUS | Simulation Production |  |  |  | 0.3 | 0.3
2.3 Computing And Data Management | 2.3.5 Simulation Production | Non-US | Non-US Total | [6 empty] | 3.65 | 3.65
2.3 Computing And Data Management | 2.3.5 Simulation Production | WBS L3 Total |  |  |  |  | 1.3 | 1.17 | 0.2 | 3.65 | 6.315
2.3 Computing And Data Management | WBS L2 Total | [5 empty] | 11.915 | 2.27 | 0.5 | 7.55 | 22.23
2.4 Triggering And Filtering | 2.4.1 Tft Coordination | US | UD | KE | SECKEL, DAVID | TFT Board member |  |  | 0.1 |  | 0.1
2.4 Triggering And Filtering | 2.4.1 Tft Coordination | US | UMD | SC | BLAUFUSS, ERIK | Coordinate process for filter requests, bandwidth | 0.3 |  |  |  | 0.3
2.4 Triggering And Filtering | 2.4.1 Tft Coordination | US | UMD | GR | UMD GR | Prepare datasets for filter testing and common MC datasets for testing |  | 0.2 |  |  | 0.2
2.4 Triggering And Filtering | 2.4.1 Tft Coordination | US | UW | KE | MONTARULI, TERESA | TFT Board member |  |  | 0.1 |  | 0.1
2.4 Triggering And Filtering | 2.4.1 Tft Coordination | US | US Total |  |  |  | 0.3 | 0.2 | 0.2 |  | 0.7
2.4 Triggering And Filtering | 2.4.1 Tft Coordination | Non-US | ULB | KE | HANSON, KAEL ULB | TFT Board member |  |  |  | 0.1 | 0.1
2.4 Triggering And Filtering | 2.4.1 Tft Coordination | Non-US | UU | KE | DE LOS HEROS, CARLOS | TFT Board member |  |  |  | 0.1 | 0.1
2.4 Triggering And Filtering | 2.4.1 Tft Coordination | Non-US | BONN | KE | KOWALSKI, MAREK | TFT Board member |  |  |  | 0.1 | 0.1
2.4 Triggering And Filtering | 2.4.1 Tft Coordination | Non-US | Non-US Total | [6 empty] | 0.3 | 0.3
2.4 Triggering And Filtering | 2.4.1 Tft Coordination | WBS L3 Total |  |  |  |  | 0.3 | 0.2 | 0.2 | 0.3 | 1
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | LBNL | KE | KLEIN,SPENCER | Co. Chair of Cascade WG |  |  | 0.25 |  | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | OSU | GR | DAVIS, JAMES | Vertical Events Filter |  |  | 0.15 |  | 0.15
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | PSU | KE | COWEN, DOUG | Hybrid/Tau WG Chair |  |  | 0.25 |  | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | PSU | KE | DEYOUNG, TYCE | Deep Core WG - Co Chair |  |  | 0.25 |  | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | PSU | PO | KOSKINEN, JASON | develop and verify Deep Core filters |  | 0.175 |  |  | 0.175
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | UCB | SC | WOSCHNAGG, KURT | Diffuse / atmosnu WG chair |  | 0.25 |  |  | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | UD | PO | BERGHAUS, PATRICK - UD | moun channel WG Co. Chair |  | 0.25 |  |  | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | UMD | SC | BLAUFUSS, ERIK | GRB WG Chair |  | 0.25 |  |  | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | UMD | PO | OLIVAS, ALEX | exotics- WG chair |  | 0.25 |  |  | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | UW | SC | MARUYAMA, REINA | Supernova WG Chair |  | 0.25 |  |  | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | UW | PO | AGUILAR SANCHEZ JUAN ANTONIO | muon filter |  | 0.15 |  |  | 0.15
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | UW | PO | TOSCANO, SIMONA | Cascade Online filter |  | 0.15 |  |  | 0.15
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | UW | GR | GLADSTONE, LAURA | Deep Core online Filter |  | 0.15 |  |  | 0.15
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | UW | GR | WHITEHORN, NATHAN | GRB Filter |  | 0.15 |  |  | 0.15
2.4 Triggering And Filtering | 2.4.2 Physics Filters | US | US Total |  |  |  |  | 2.025 | 0.9 |  | 2.925
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | CHIBA | KE | YOSHIDA, SHIGERU | EHE WG Lead |  |  |  | 0.25 | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | CHIBA | GR | ONO, MIO | EHE Filters |  |  |  | 0.15 | 0.15
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | DESY | GR | FRANKE, ROBERT | Online Filter for Alerts |  |  |  | 0.1 | 0.1
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | DESY | GR | FRANKE, ROBERT | Rate Data Bank South Pole |  |  |  | 0.1 | 0.1
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | RWTH | PO | BOERSMA, DAVID RWTH | Gal Cen Filter (Moon Filter) |  |  |  | 0.15 | 0.15
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | RWTH | PO | BOERSMA, DAVID RWTH | muon channel WG Co. Chair |  |  |  | 0.25 | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | SU | KE | HULTH, PER OLOF | Low Energy DeepCore WG Lead |  |  |  | 0.25 | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | SU | SC | SEO, SEON-HEE | Develop & verify filters |  |  |  | 0.05 | 0.05
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | SU | SC | FINLEY, CHAD SU | Point Sou\rce WG Lead |  |  |  | 0.25 | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | SU | GR | JOHANSSON, HENRIK | UHE Trigger & Filter |  |  |  | 0.1 | 0.1
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | SU | GR | DANNINGER, MATTIAS | WIMP Trigger & Filter |  |  |  | 0.15 | 0.15
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | ULB | GR | ULB GR | Study of Tau Filters at South Pole |  |  |  | 0.1 | 0.1
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | UU | KE | HALLGREN, ALLAN | online filter development |  |  |  | 0.05 | 0.05
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | UU | KE | DE LOS HEROS, CARLOS | WIMP WG Lead |  |  |  | 0.25 | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | UU | GR | HENRIC, TAAVOLA | Online filter development & testing |  |  |  | 0.1 | 0.1
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | UU | GR | STROM, RICKARD | Online filter development & testing |  |  |  | 0.1 | 0.1
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | VUB | PO | LABARE, MATHIEU | Filter for Southern sky muons |  |  |  | 0.25 | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | VUB | PO | SINGH, KALPANA | Filter for Southern sky muons |  |  |  | 0.25 | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | BARBADOS | KE | SEUNARINE, SURUJ | Work on cascade filter |  |  |  | 0.15 | 0.15
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | WUPPERTAL | GR | WUPPERTAL GR | New SUSY Filter |  |  |  | 0.2 | 0.2
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | HUMBOLDT | SC | WALDENMAIER, TILO | CR-WG Lead |  |  |  | 0.25 | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | HUMBOLDT | SC | WALDENMAIER, TILO | CR-WG Filter |  |  |  | 0.15 | 0.15
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | BONN | KE | KOWALSKI, MAREK | cascades WG Co-Lead |  |  |  | 0.25 | 0.25
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | BONN | GR | FRANCKOWIAK, ANNA | Alert System for follow-up |  |  |  | 0.1 | 0.1
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | BONN | GR | HOMRIER, ANDREAS | Alert System for follow-up |  |  |  | 0.1 | 0.1
2.4 Triggering And Filtering | 2.4.2 Physics Filters | Non-US | Non-US Total | [6 empty] | 4.1 | 4.1
2.4 Triggering And Filtering | 2.4.2 Physics Filters | WBS L3 Total | [5 empty] | 2.025 | 0.9 | 4.1 | 7.025
2.4 Triggering And Filtering | WBS L2 Total | [5 empty] | 0.3 | 2.225 | 1.1 | 4.4 | 8.025
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5 Data Quality, Reconstruction & Simulation Tools | Non-US | UC | SC | GROSS, ANDREAS | Data Quality, Reco. & Sim. Tools Coordinator ("Low-level" Analysis Coordinator) |  |  |  | 0.5 | 0.5
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5 Data Quality, Reconstruction & Simulation Tools | Non-US | BARBADOS | KE | SEUNARINE, SURUJ | Analysis of flasher runs for inice calibration of saturation, and flasher and Standard Candle runs for absolute energy calibration for cascades. |  |  |  | 0.15 | 0.15
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5 Data Quality, Reconstruction & Simulation Tools | Non-US | Non-US Total | [6 empty] | 0.65 | 0.65
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5 Data Quality, Reconstruction & Simulation Tools | WBS L3 Total | [7 empty] | 0.65 | 0.65
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | LBNL | PO | BUITIN,STIJN | DOM simulator & calibrator |  | 0.35 |  |  | 0.35
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | LBNL | PO | GERHARDT,LISA | Simulation Programs: cmc |  | 0.2 |  |  | 0.2
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | SUBR | KE | FAZELY, ALI | GEANT Simulation |  |  | 0.15 |  | 0.15
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | SUBR | KE | IMLAY, RICHARD | Simulation Programs |  |  | 0.15 |  | 0.15
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UA | PO | ZARZHITZKY, PAVEL | Simulation verification |  |  | 0.3 |  | 0.3
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UCB | SC | WOSCHNAGG, KURT | Maintain and Verify Simulation of Photon Propagation and update Ice Properties | 0.5 |  |  |  | 0.5
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UD | PO | HUSSAIN, SHAHID | Ice Properties Simulation |  | 0.3 |  |  | 0.3
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UD | GR | RUZYBAEV , BAKHTIYAR | Ice Properties Simulation |  | 0.3 |  |  | 0.3
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UD | GR | XU, CHEN | Simulation Programs: sim-services |  | 0.3 |  |  | 0.3
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UMD | PO | OLIVAS, ALEX | Simulation Software Programs coordinator | 0.4 |  |  |  | 0.4
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UMD | PO | WISSING, HENRIKE | Maintain Detector Simulation (IceSim) |  | 0.25 |  |  | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UMD | GR | REDL, PETER | Maintain Detector Simulation (IceSim) |  | 0.25 |  |  | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UW | SC | CHIRKIN, DMITRY | Simulation Programs: mmc/mmc-icetray &ucr-icetray |  | 0.2 |  |  | 0.2
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UW | SC | HILL, GARY | Maintain and Verify Simulation of Photon Propagation and update Ice Properties | 0.25 |  |  |  | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UW | PO | ABBASI, RASHA | DST data checking |  | 0.1 |  |  | 0.1
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UW | PO | AGUILAR SANCHEZ JUAN ANTONIO | low level moun data verification (data/mc) |  | 0.1 |  |  | 0.1
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UW | PO | UW PO | Maintain IceSim |  | 0.4 |  |  | 0.4
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UW | GR | WHITEHORN, NATHAN | Photonics tables |  | 0.1 |  |  | 0.1
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UW | GR | SANTANDER, MARCOS | Flasher Analysis |  | 0.15 |  |  | 0.15
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | UW | TE | DIAZ-VELEZ, JUAN CARLOS | Maintain Simulation Production Software | 0.2 |  |  |  | 0.2
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | US | US Total |  |  |  | 1.35 | 3 | 0.6 |  | 5.35
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | Non-US | DTMND | GR | MILKE, NATALIE | Simulation Programs: noise-generator |  |  |  | 0.2 | 0.2
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | Non-US | SU | KE | WALCK, CHRISTIAN | Photonics/Simulation Work |  |  |  | 0.05 | 0.05
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | Non-US | SU | KE | HULTQVIST, KLAS | Photonics/Simulation Work, hit-maker |  |  |  | 0.15 | 0.15
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | Non-US | SU | SC | FINLEY, CHAD SU | Simulation Programs: neutrino-generator |  |  |  | 0.2 | 0.2
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | Non-US | UOX | KE | SARKAR, SUBIR | Yellow Book-maintenance |  |  |  | 0.1 | 0.1
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | Non-US | UU | PO | MILLER, JONATHAN | Simulation Programs: photonics |  |  |  | 0.05 | 0.05
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | Non-US | GENT | SC | UGENT SC | Support IceTop Simulations, IceTop Calibrations, IceTop Reconstruction |  |  |  | 0.1 | 0.1
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | Non-US | GENT | GR | UGENT GR | Support IceTop Simulations, IceTop Calibrations, IceTop Reconstruction |  |  |  | 0.4 | 0.4
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | Non-US | BOCHUM | GR | OLIVO, MARTINO | Update MMC from Java to C++ |  |  |  | 0.25 | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | Non-US | Non-US Total | [6 empty] | 1.45 | 1.45
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.1 Simulation Programs | WBS L3 Total |  |  |  |  | 1.35 | 3 | 0.6 | 1.45 | 6.8
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | LBNL | KE | KLEIN,SPENCER | co-chair of Diffuse WG |  |  | 0.25 |  | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | PSU | PO | KOSKINEN, JASON | Coordinate Deep Core reconstruction for production |  | 0.12 |  |  | 0.12
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | PSU | PO | PSU PO | develop starting track reconstruction |  | 0.08 |  |  | 0.08
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | PSU | GR | HA, CHANG HYON | develop starting track reconstruction |  | 0.125 |  |  | 0.125
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | SUBR | KE | FAZELY, ALI | Reconstruction/ Analysis tools |  |  | 0.15 |  | 0.15
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | SUBR | KE | IMLAY, RICHARD | Reconstruction/ Analysis tools |  |  | 0.15 |  | 0.15
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | UAA | KE | RAWLINS, KATHERINE | flat-ntuple; muon-bundle-reco; Snow correction for IceTop |  |  | 0.3 |  | 0.3
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | UMD | PO | WISSING, HENRIKE | develop & test reconstruction |  | 0.25 |  |  | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | UMD | GR | REDL, PETER | Reconstruction/ Analysis tools |  | 0.25 |  |  | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | UW | SC | CHIRKIN, DMITRY | Direct photon tracking / iceproperties calibration 0.3 ; FE/pulse extractor 0.1 ; reco software 0.1 |  | 0.3 |  |  | 0.3
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | UW | GR | DUMM, JONATHAN | Reconstruction Tools |  | 0.15 |  |  | 0.15
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | UW | GR | RODRIGUES, JOAO-PAULO | Supernova simulation / moun energy reconstruction |  | 0.2 |  |  | 0.2
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | UWRF | KE | MADSEN, JIM | Cosmic ray shower simulations and reconstruction |  |  | 0.1 |  | 0.1
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | UWRF | SC | TAMBURRO, ALESSIO | Shower simulations, TankTop simulation |  |  | 0.2 |  | 0.2
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | US | US Total |  |  |  |  | 1.475 | 1.15 |  | 2.225
2.1 Program Management | 2.5.2 Reconstruction/ Analysis Tools | Non-US | RWTH | PO | BOERSMA, DAVID RWTH | Reconstruction Coordinator |  |  |  | 0.15 | 0.15
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | CHIBA | KE | CHIBA KE | Maintain Romeo, EHE Simulations |  |  |  | 0.2 | 0.2
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | CHIBA | SC | CHIBA SC | Maintain Romeo, EHE Simulations, Maintain reconstruction projects (Portia), MC/Data comparison for EHE-filtered and IceTop events, Standard Candle Analysis |  |  |  | 0.2 | 0.2
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | CHIBA | GR | CHIBA GR | Improve the Ice Model, Afterpulse Simulator, Standard Candle Analysis, Maintain reconstruction projects (Ophelia, ehe-star) |  |  |  | 0.2 | 0.2
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | DESY | GR | MIDDELL, EIKE | Cascade Reconstruction |  |  |  | 0.3 | 0.3
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | EPFL | SC | EPFL SC | SLF, Low Energy, Energy reconstruction (development) |  |  |  | 0.25 | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | RWTH | GR | RWTH GR | Reconstruction Software |  |  |  | 0.3 | 0.3
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | RWTH | GR | WALLRAFF, MARIUS | New Feature Extractor |  |  |  | 0.5 | 0.5
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | SU | SC | SEO, SEON-HEE | Photonics/Simulation Work |  |  |  | 0.15 | 0.15
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | VUB | KE | VUB KE | development of reconstruction tools (IcePack framework) |  |  |  | 0.25 | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | VUB | PO | BOSE, DEBANJAN | muon track reconstruction in IceCube and DeepCore, waveform feature extractor |  |  |  | 0.25 | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | VUB | PO | LABARE, MATHIEU | muon track reconstruction in IceCube and DeepCore |  |  |  | 0.125 | 0.125
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | VUB | PO | SINGH, KALPANA | muon track reconstruction in IceCube and DeepCore, waveform feature extractor |  |  |  | 0.125 | 0.125
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | ALBERTA | KE | GRANT, DARREN | Maintenance of IceCube-Photonics interface |  |  |  | 0.1 | 0.1
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | ALBERTA | PO | ALBERTA, PO | Maintenance of IceCube-Photonics interface |  |  |  | 0.3 | 0.3
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | WUPPERTAL | GR | WUPPERTAL GR | New SUSY Reconstruction, Simulation, Propagation, Monopole, Photonics |  |  |  | 0.5 | 0.5
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | MAINZ | GR | LÜNEMANN, JAN | Reconstruction Tools |  |  |  | 0.2 | 0.2
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | HUMBOLDT | SC | HUMB SC | Reconstruction/ Analysis tools |  |  |  | 0.1 | 0.1
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | BONN | GR | UBONN GR | Reconstruction/ Analysis tools |  |  |  | 0.2 | 0.2
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | BONN | GR | PANKNIN, SEBASTIAN | IC-40 L3 processing |  |  |  | 0.2 | 0.2
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | Non-US | Non-US Total | [6 empty] | 4.6 | 4.6
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.2 Reconstruction/ Analysis Tools | WBS L3 Total | [5 empty] | 1.475 | 1.15 | 4.6 | 6.825
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.3 Data Quality | US | OSU | PO | ROTT, CARSTEN | Data Quality |  |  | 0.1 |  | 0.1
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.3 Data Quality | US | UA | KE | WILLIAMS, DAWN | Data Quality Lead |  |  | 0.15 |  | 0.15
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.3 Data Quality | US | US Total |  |  |  |  | 0 | 0.25 |  | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.3 Data Quality | Non-US | MPI | PO | MPI PO | Data Quality & DeepCore |  |  |  | 0.6 | 0.6
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.3 Data Quality | Non-US | VUB | KE | VUB KE | data quality verification |  |  |  | 0.25 | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.3 Data Quality | Non-US | VUB | PO | STRAHLER, ERIK | verification Deep Core data quality |  |  |  | 0.25 | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.3 Data Quality | Non-US | VUB | PO | BOSE, DEBANJAN | verification Deep Core data quality |  |  |  | 0.25 | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.3 Data Quality | Non-US | VUB | PO | LABARE, MATHIEU | verification Deep Core data quality |  |  |  | 0.125 | 0.125
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.3 Data Quality | Non-US | VUB | PO | SINGH, KALPANA | verification Deep Core data quality |  |  |  | 0.125 | 0.125
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.3 Data Quality | Non-US | Non-US Total | [6 empty] | 1.6 | 1.6
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.3 Data Quality | WBS L3 Total | [5 empty] | 0 | 0.25 | 1.6 | 1.85
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.4 Offline Data Processing | US | UW | SC | HILL, GARY | Offline processing | 0.25 |  |  |  | 0.25
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.4 Offline Data Processing | US | UW | GR | DUMM, JONATHAN | Offline Data Processing |  | 0.15 |  |  | 0.15
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.4 Offline Data Processing | US | US Total |  |  |  | 0.25 | 0.15 | 0 |  | 0.4
2.5 Data Quality, Reconstruction & Simulation Tools | 2.5.4 Offline Data Processing | WBS L3 Total |  |  |  |  | 0.25 | 0.15 | 0 |  | 0.4
2.5 Data Quality, Reconstruction & Simulation Tools | WBS L2 Total | [5 empty] | 1.6 | 4.625 | 2 | 8.3 | 16.525
Grand Total | [6 empty] | 31.5073 | 12.83 | 8.2967 | 28.055 | 80.309