# IceCube Institutional Memorandum Of Understanding (MOU)

University of Alabama

Dawn Williams

Ph.D Scientists (Faculty   Scientist/Post Doc   Grads):      3 (2  1  3)

Scope of Work

| Labor Cat. | Names | WBS L3 | Tasks |  | Funds Source | WBS 2.1 | WBS 2.2 |  | WBS 2.3 |  | WBS 2.4 |  | WBS 2.5 | WBS 2.6 | Grand Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Program Coordination | Detector Maintenance & Operations |  | Computing & Data Management |  | Data Processing & Simulation |  | Software | Calibration |  |
| KE | Williams, Dawn | Administration | Alabama Institutional Lead |  | Inst. In-Kind | 0.05 |  |  |  |  |  |  |  |  | 0.05 |
|  |  | Education and Outreach | IceCube Outreach |  | Inst. In-Kind | 0.05 |  |  |  |  |  |  |  |  | 0.05 |
|  |  | Public Data Products | Convenor of Data release task force |  | M&O Core |  |  |  |  |  | 0.05 |  |  |  | 0.05 |
|  |  | Ice Properties | Supporting flasher runs and flasher analysis |  | Inst. In-Kind |  |  |  |  |  |  |  |  | 0.10 | 0.10 |
|  |  | Detector Calibration | Baseline and charge harvesting and DOMCal |  | M&O Core |  |  |  |  |  |  |  |  | 0.10 | 0.10 |
|  | Williams, Dawn Total |  |  |  |  | 0.1 |  |  |  |  | 0.05 |  |  | 0.20 | 0.35 |
|  | Santander, Marcos | Education and Outreach | IceCube Outreach |  | Inst. In-Kind | .05 |  |  |  |  |  |  |  |  | 0.05 |
|  |  | Administration | Realtime Oversight Committee member |  | Inst. In-Kind | 0.1 |  |  |  |  |  |  |  |  | 0.1 |
|  |  | Detector Monitoring | Online Moon shadow analysis (monitoring) |  | Inst. In-Kind |  | 0.1 |  |  |  |  |  |  |  | 0.1 |
|  |  | Reconstruction | Reconstruction validation - PSF studies |  | Inst. In-Kind |  |  |  |  |  |  |  | 0.05 |  | 0.05 |
|  | Santander, Marcos Total |  |  |  |  | 0.15 | 0.1 |  |  |  |  |  | 0.05 |  | 0.30 |
| PO | Kopper, Sandro | Simulation Software | Simulation Software: low energy double pulse |  | NSF Base Grant |  |  |  |  |  |  |  | 0.15 |  | 0.15 |
|  |  | Reconstruction | Reconstruction of tau neutrino events and BSM double pulse events |  | NSF Base Grant |  |  |  |  |  |  |  | 0.15 |  | 0.15 |
|  |  | Distributed Computing Resources | Connecting Alabama GPUs to the cluster |  | NSF Base Grant |  |  |  | 0.05 |  |  |  |  |  | 0.05 |
|  | Kopper, Sandro Total |  |  |  |  |  |  |  | 0.05 |  |  |  | 0.30 |  | 0.35 |
| GR | Pedek, Samantha | Detector Calibration | Domcal run vetting |  | NSF Base Grant |  |  |  |  |  |  |  |  | 0.25 | 0.25 |
|  |  | Reconstruction | Tau double pulse FFT algorithm |  | NSF Base Grant |  |  |  |  |  |  |  | 0.25 |  | 0.25 |
|  | Pedek, Samantha Total |  |  |  |  |  |  |  |  |  |  |  | 0.25 | 0.25 | 0.50 |
| GR | Goswami, Sreetama | Detector Monitoring | Online Moon shadow analysis (monitoring) |  | Inst. In-Kind |  |  |  |  |  |  |  |  | 0.1 | 0.1 |  |  |  |  |  |  | 0.1 |  |
|  |  | Detector Monitoring | Monitoring shifts (starting 2019) |  | Inst. In-Kind |  | 0.05 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Goswami, Sreetama Total |  |  |  |  |  |  | 0.05 |  |  |  |  |  | 0.1 | 0.15 |  |  |  |  |  |  |  |
| GR | Ghadimi, Ava | Detector Monitoring | Monitoring shifts (starting 2019) | Inst. In-Kind |  |  | 0.05 |  |  |  |  |  |  |  | 0.05 |  |  |  |  |  |  |  |
|  | Ghadimi, Ava Total |  |  |  |  |  | 0.05 |  |  |  |  |  |  |  | 0.05 |  |  |  |  |  |  |  |
| UA Total |  |  |  |  |  | 0.25 | 0.20 |  | 0.05 |  | 0.05 |  | 0.60 | 0.55 | 1.70 |

# Faculty:

Dawn Williams – Institutional Lead, Analysis Coordinator

# Marcos Santander – Multimessenger searches for neutrino sources

# Postdoc:

# Sandro Kopper – tau neutrino analysis, BSM double pulse analysis

# Ph.D. Students:

Samantha Pedek – vetting monthly domcal runs

Tau neutrino FFT algorithm

Thesis /Analysis topics: TBD (still taking classes)

Sreetama Goswami – Monitoring with Moon shadow analysis (starting work, still taking classes now). Monitoring shifts (starting in 2019).

Ava Ghadimi: Correlated multiwavelength observations (in particular hard X-rays and gamma rays) with neutrino detections. Monitoring shifts (starting in 2019)

# UA General M&O (non-science) IceCube Responsibilities and Contributions:

The Alabama Group’s major responsibilities and contributions towards maintenance and operations of the IceCube experiment include:

- Major responsibility for the following calibration group activities: flasher data collection and flasher analysis support, baseline and charge calibration

- Major responsibility for tau neutrino analysis

Analysis: The main analysis focus at the University of Alabama is searching for tau neutrinos and multimessenger searches for neutrino sources.

# Computing Resources

|  | 2018 |  | 2019 |  |
| --- | --- | --- | --- | --- |
|  | CPU Cores | GPU Cards | CPU Cores | GPU Cards |
| Pledged resources in the IceCube common cluster |  | 6 (Tesla K20m) |  | 6 (Tesla K20m) |

These GPUs are being used locally for flasher data ice model fitting and targeted muon simulation.

Upgrade

| Labor Cat. | Names | WBS L3 | Tasks | Funds Source | WBS 1.1 | WBS 1.2 | WBS 1.3 | WBS 1.4 | WBS 1.5 | WBS 1.6 | Grand Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Project Office | Gen2 EHWD | Deep Ice Sensor Modules | Comms Power Timing | Calibration and Characterization | M&O Data Systems Integration |  |
| KE | Williams, Dawn | 1.5.2 Calibration Assemblies | LED Flasher Design and Testing | Inst. In-Kind |  |  |  |  | 0.05 |  | 0.05 |
|  |  | 1.5.4 Calibration Management | L2 Management of Calibration and Characterization | Upgrade Core |  |  |  |  | 0.25 |  | 0.25 |
|  | Williams, Dawn Total |  |  |  |  |  |  |  | 0.30 |  | 0.30 |
| UA Total |  |  |  |  |  |  |  |  | 0.30 |  | 0.30 |