## 2020-2021
Project's Name |  | Types/items of fieldwork | Southbound cargo projection |  |  |  |  | Projected Population Profile (max per day in a half-month) |  |  |  | Total per season |  | Power & Bandwidth |  | Labor/support needed from ASC | Comments if any
Work Item number |  | Enter here what is absolutely needed (in black) for the subject season, "good to be accomplished" (in blue), or what the project envisions (in red - even not yet funded activities) | Weight (lbs) | Cubic Feet | Nov 1-15 | Nov 16-30 | Dec 1-15 | Dec 16-31 | Jan 1-15 | Jan 16-31 | Feb 1-15 | Total Team (not Σ left) | Self-Ticketers | kW | GB/day | For each item below - enter "YES" and provide details or enter "NO"
|  | Austral summer season FY 2021 (2020-2021) | 303950 | 24762 | 25 | 38 | 47 | 45 | 43 | 38 | 16 | 84 | 11 | 225 | 390 | Totals Per Season
|  | A-149-S Cargo and Population Total | 22000 | 0 | 6 | 13 | 13 | 13 | 12 | 12 | 6 | 24 | 0 | 80 | 160 |  | power equals current B3/BA use
BICEP Array A-149-S | 1 | BICEP Array BA2, BA3 receiver deployment | 14000 |  | 2 | 6 | 6 | 6 | 6 | 6 | 2 | 11 |  |  |  | NO
| 2 | BICEP Array / BICEP3 operations | 3000 |  | 4 | 6 | 6 | 6 | 6 | 6 | 4 | 12 |  |  |  | NO
| 3 | BART snowpad installation | 5000 |  |  | 1 | 1 | 1 |  |  |  | 1 |  |  |  | YES -equipment support for snowpad and footer installation
|  | A-379-S Cargo and Population Total | 6000 | 0 | 4 | 7 | 9 | 9 | 10 | 10 | 10 | 17 | 0 | 60 | 125 |  | Power is avg power, bandwidth is min bandwidth
SPT A-379-S | 1 | Winter-over relief and continued observing |  |  | 2 | 3 | 3 | 3 |  |  |  | 3 |  |  |  | NO
| 2 | Telescope and SPT-3G receiver maintenance | 4000 |  |  | 3 | 3 | 3 | 2 | 2 | 1 | 5 |  |  |  | NO
| 3 | EHT maintenance and training | 1200 | [5 empty] | 2 | 2 | 2 | 2 |  |  |  | NO
| 4 | Winter-overs and training |  |  |  |  | 2 | 2 | 5 | 5 | 5 | 5 |  |  |  | NO
| 5 | MAPO Machine Shop | 800 |  | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 |  |  |  | NO
|  | Station Projects - Cargo and Population Total | 5500 | 488 | 3 | 0 | 5 | 4 | 4 | 0 | 0 | 5 | 0 | 0 | 0
Station projects | 1 | Ice Tunnel Emergency Exit 2 of 4 | 0 | 0 |  |  | 4 | 4 | 4 |  |  | 4 |  |  |  | YES - ASC | Assumes cost is supported in FY21 APP/budget. These four individuals are part of the normal sustaining crew removing ice from the tunnel.
| 2 | Relocate Electrical Distribution Equipment from buried Bldg 68 to field facility | 5000 | 288 | [11 empty] | YES - ASC | Assumes cost is supported in FY21 APP/budget. Material Delivery to SP only this year
| 3 | Complete kitchen exhaust hood modifications | 0 | 0 |  |  | 1 |  |  |  |  | 1 |  |  |  | YES - ASC | Assumes cost is supported in FY21 APP/budget. Sheet metal worker
| 4 | SP Configure Hypertats for Surge Housing | Unknown | Unknown | [11 empty] | YES - ASC | Assumes cost is supported in FY21 APP/budget. Necessary to have capacity for station projects. This a precursor to most projects in 2022-2025, can be done in summer or winter.
| 5 | SP Hot Water Trencher | 500 | 200 | [11 empty] | YES - ASC | Assumes cost is supported in FY21 APP/budget. Equipment delivery only. IceCube like hot water trencher for Leidos use on all projects
| 6 | SP Master Plan site visit |  |  | 3 | [10 empty] | YES - ASC | Assumes 2 ASC staff and 1 NSF staff for 2 weeks in November.
|  | A-333-S Cargo and Population Total | 3450 | 274 | 2 | 5 | 7 | 6 | 4 | 3 | 0 | 18 | 6 | 75 | 105
ICNO M&O A-333-S | 2 | Computing and hub maintenance | 2000 | 128 | 1 | 1 | 3 | 3 | [7 empty] | YES — cargo handling, snow ramp
| 3 | Calibration | 150 | 32 |  | 1 | 1 | [8 empty] | NO
| 4 | DAQ / Engineering support | 150 | 32 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | NO
| 5 | M&O Upgrade support | 150 | 32 |  | 2 | 2 | 1 | 1 | [6 empty] | YES — ICL tower modifications | Supporting Upgrade surface cables
| 6 | Scintillator installation | 1000 | 50 |  |  |  | 1 | 2 | 1 | [5 empty] | YES — trenching, survey
| 7 | Radio installation | [13 empty] | YES — survey | Add-on to scintillator installation
| 8 | IceACT maintenance | [7 empty] | 1 | [5 empty] | NO
|  | A-334-S Cargo and Population Total | 267000 | 24000 | 10 | 13 | 13 | 13 | 13 | 13 | 0 | 20 | 5 | 10 | 0
ICNO Upgrade A-334-S | 1 | IceCube Upgrade | 267000 | 24000 | 10 | 13 | 13 | 13 | 13 | 13 | 0 |  |  |  |  | YES — Equipment: Dozer, Fork, Manlift, as needed throughout season | See integrated master project schedule on Smartsheets for all details
| 2 | EHWD drill refurbishment | [13 empty] | YES — Fuel: 1000 gals, delivered as-needed throughout the season | To be captured/requested in SIP
| 3 | ICL tower structural modifications | [13 empty] | YES — Trades-support: generator technician, electrician, plumber, welder, etc. | See integrated master project schedule on Smartsheets for all details
| 4 | Drill Camp SES & TOS pads - final preparations | [13 empty] | YES — Transportation: Dedicated or pooled van or truck, snowmobiles | To be captured/requested in SIP
| 5 | Cargo timely delivery | [13 empty] | YES — Cargo/Logistics: Timely delivery of all project cargo as required and captured on the IceCube master cargo spreadsheet | See "Upgrade Cargo Planning" worksheet on SharePoint for all details
Notes for IceCube Upgrade (A-334-S):
1. Cargo from Upgrade Cargo Planning worksheet in SP, rev Feb 4, 2020.
2. Population from On-Ice Org Charts 2019 to 2023 in SP, rev Feb 4, 2020.
3. Col M - Total based on Gen1 experience, it is assumed that half the positions will be for the full season and the remaining will require 2 deployments.
4. Self - ticketers match with In-Kind assumptions from On-Ice Org Charts 2019 to 2023.
Station Projects Not Shown Above - Needed:
Fleet enhancements to support project driven requirements - Procure in 20/21, ship to MCM 21/22, ship to SP 22/23
South Pole elevated station raise: Design 21/22, procure 22/23, ship to MCM 23/24, ship to SP 24/25 & 25/26, execute 26/27
SP Migrate Fire Panels from MXL to XLS- Procure in 21/22, ship to MCM 22/23, ship to SP 23/24, Install winter 24
MAPO Lift: Design 20/21, procure 21/22, ship to MCM 22/23, ship to SP 23/24, execute 24/25
Complete retrograde initiative of project tail waste materials from previous decade - should happen in FY21
Extend Rodwell 3 building viability, level, raise, extend lifespan to match replacement plan – Pre-project conceptual
Establish NOAA tower maintenance and replacement consensus and plan
Raise building 61: Design complete, Procure 20/21, ship to MCM 21/22, ship to SP 22/23, 23/24 lift
Replace Arches: MAY BE REQUIRED PRIOR TO ELEVATED STATION LIFT. SP Master Plan will inform timing of projects
Fleet and ITC projects could add 1 Minor ReCap project per season requiring 2 to 3 staff (ASC plus contractor and/or supplier reps) for durations 1 month per project in the middle of season, in each of 5 next seasons. Smaller ITC projects (1, 4, 5, 6, 7) are assumed to be consolidated trip visits (1 trip per season) of 8 projects into 5 annual trips:
1. South Pole HF Radio replacement
2. South Pole HF Antenna field replacement
3. SPO Fiber Optic
4. Industrial Controls Network Security Zone Redesign
5. WAN optimizer Replacement Project
6. HAM Radio replacement
7. LMR Radio System
6. HAM Radio replacement
7. LMR Radio System
8. Fleet enhancements Project-driven fleet requirements

## 2021-2022
Project's Name |  | Types/items of fieldwork | Southbound cargo projection |  |  |  |  | Projected Population Profile (max per day in a half-month) |  |  |  | Total per season |  | Power & Bandwidth |  | Labor/support needed from ASC | Comments if any
Work Item number |  | Enter here what is absolutely needed (in black) for the subject season, "good to be accomplished" (in blue), or what the project envisions (in red - even not yet funded activities) | Weight (lbs) | Cubic Feet | Nov 1-15 | Nov 16-30 | Dec 1-15 | Dec 16-31 | Jan 1-15 | Jan 16-31 | Feb 1-15 | Total Team (not Σ left) | Self-Ticketers | kW | GB/day | For each item below - enter "YES" and provide details or enter "NO"
|  | Austral summer season FY 2022 (2021-2022) | 344400 | 17848 | 31 | 55 | 65 | 65 | 62 | 55 | 21 | 104 | 12 | 225 | 510 | All Totals Per Season
|  | A-149-S Cargo and Population Total | 100000 | 0 | 7 | 17 | 17 | 17 | 17 | 16 | 9 | 29 | 0 | 80 | 280 |  | power equals current B3/BA use
BICEP Array A-149-S | 1 | BICEP Array BA4 receiver deployment | 7000 |  | 2 | 6 | 6 | 6 | 6 | 6 | 2 | 10 |  |  |  | NO
| 2 | BICEP Array / BICEP3 operations | 3000 |  | 4 | 6 | 6 | 6 | 6 | 6 | 4 | 10 |  |  |  | NO
| 3 | BART installation | 90000 |  | 1 | 5 | 5 | 5 | 5 | 4 | 3 | 9 |  |  |  | YES — crane, part-time plumbing and electrical support | Project personnel include construction coordinator plus full-time heavy carp/steel crew.
|  | A-379-S Cargo and Population Total | 6000 | 0 | 4 | 7 | 9 | 9 | 10 | 10 | 10 | 17 | 0 | 60 | 125 |  | Power is avg power, bandwidth is min bandwidth
SPT A-379-S | 1 | Winter-over relief and continued observing |  |  | 2 | 3 | 3 | 3 |  |  |  | 3 |  |  |  | NO
| 2 | Telescope and SPT-3G receiver maintenance | 4000 |  |  | 3 | 3 | 3 | 2 | 2 | 1 | 5 |  |  |  | NO
| 3 | EHT maintenance and training | 1200 | [5 empty] | 2 | 2 | 2 | 2 |  |  |  | NO
| 4 | Winter-overs and training |  |  |  |  | 2 | 2 | 5 | 5 | 5 | 5 |  |  |  | NO
| 5 | MAPO Machine Shop | 800 |  | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 |  |  |  | NO
|  | Station Projects - Cargo and Population Total | 57500 | 964 | 0 | 2 | 10 | 10 | 6 | 0 | 0 | 10 | 0 | 0 | 0
Station projects | 1 | Ice Tunnel Emergency Exit 3 of 4 | 0 | 0 |  |  | 4 | 4 | 4 |  |  | 4 |  |  |  | YES - ASC | Assumes cost is supported in FY22 APP/budget. Assumes all material already at SP. These four individuals are part of the normal sustaining crew removing ice from the tunnel.
| 2 | Blue Building Lift system and ARO raise | 57000 | 900 | [11 empty] | YES - ASC | Assumes cost is supported in FY22 APP/budget, an procurement supported in FY21.Material delivery only. Steel beams could be traveresed saving ~34,000#.
| 3 | Relocate Electrical Distribution Equipment from buried Bldg 68 to field facility | 0 | 0 |  | 2 | 3 | 3 | 2 |  |  | 3 |  |  |  | YES - ASC | Assumes cost is supported in FY22 APP/budget. These three individuals may be pulled from sustaining trades to minimize any increase in population
| 4 | IT Minor Projects - 1 of 5 (See Below) | 500 | 64 |  |  | 3 | 3 |  |  |  | 3 |  |  |  | YES - ASC | Planning assumptions, IT Minor project 1 of 5
|  | A-333-S Cargo and Population Total | 17900 | 1084 | 6 | 8 | 8 | 8 | 8 | 8 | 2 | 16 | 4 | 75 | 105
ICNO M&O A-333-S | 1 | Winterovers |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | NO
| 2 | Computing and hub maintenance | 3500 | 256 | 1 | 2 | 2 | 2 | [7 empty] | YES — cargo handling, snow ramp
| 3 | Calibration | 150 | 32 |  | 1 | 1 | [8 empty] | NO
| 4 | DAQ / Engineering support | 150 | 32 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | NO
| 5 | M&O Upgrade support | 1500 | 256 | 2 | 2 | 2 | 2 | [7 empty] | YES — surface cable installation support | ICL hardware for Upgrade integration
| 6 | Scintillator installation | 9800 | 312 |  |  |  | 1 | 4 | 3 | [5 empty] | YES — trenching, survey
| 7 | Radio installation | 2800 | 196 |  |  |  |  | 1 | 1 | [5 empty] | YES — survey | Add-on to scintillator installation
| 8 | IceACT maintenance | [7 empty] | 1 | [5 empty] | NO
|  | A-334-S Cargo and Population Total | 163000 | 15800 | 14 | 21 | 21 | 21 | 21 | 21 | 0 | 32 | 8 | 10 | 0
ICNO Upgrade A-334-S | 1 | IceCube Upgrade | 163000 | 15800 | 14 | 21 | 21 | 21 | 21 | 21 | [5 empty] | YES — Equipment: Dozer, Fork, Manlift, as needed throughout season | See integrated master project schedule on Smartsheets for all details
| 2 | EHWD drill integration, IV&T, hot water testing | [13 empty] | YES —Fuel: 4,850 gals, delivered as-needed throughout the season | To be captured/requested in SIP
| 3 | Drill 7 firn holes | [13 empty] | YES — Trades-support: generator technician, electrician, plumber, welder, etc. | See integrated master project schedule on Smartsheets for all details
| 4 | Install surface cables and junction boxes | [13 empty] | YES — Transportation: Dedicated or pooled van or truck, snowmobiles | To be captured/requested in SIP
| 5 | Receive and store 2 strings of instrumentation | [13 empty] | YES — Cargo/Logistics: Timely delivery of all project cargo as required and captured on the IceCube master cargo spreadsheet | See "Upgrade Cargo Planning" worksheet on SharePoint for all details
Notes for IceCube Upgrade (A-334-S):
1. Cargo from Upgrade Cargo Planning worksheet in SP, rev Feb 4, 2020.
2. Population from On-Ice Org Charts 2019 to 2023 in SP, rev Feb 4, 2020.
3. Col M - Total based on Gen1 experience, it is assumed that half the positions will be for the full season and the remaining will require 2 deployments.
4. Self - ticketers match with In-Kind assumptions from On-Ice Org Charts 2019 to 2023.
Station Projects Not Shown Above - Needed:
Fleet enhancements to support project driven requirements - Procure in 20/21, ship to MCM 21/22, ship to SP 22/23
South Pole elevated station raise: Design 21/22, procure 22/23, ship to MCM 23/24, ship to SP 24/25 & 25/26, execute 26/27
SP Migrate Fire Panels from MXL to XLS- Procure in 21/22, ship to MCM 22/23, ship to SP 23/24, Install winter 24
MAPO Lift: Design 20/21, procure 21/22, ship to MCM 22/23, ship to SP 23/24, execute 24/25
Extend Rodwell 3 building viability, level, raise, extend lifespan to match replacement plan – pre-cproject conceptual in FY2022
Establish NOAA tower maintenance and replacement consensus and plan
Raise building 61: Design complete, Procure 20/21, ship to MCM 21/22, ship to SP 22/23, 23/24 lift
Replace Arches: MAY BE REQUIRED PRIOR TO ELEVATED STATION LIFT. SP Master Plan will inform timing of projects
Fleet and ITC projects could add 1 Minor ReCap project per season requiring 2 to 3 staff (ASC plus contractor and/or supplier reps) for durations 1 month per project in the middle of season, in each of 5 next seasons. Smaller ITC projects (1, 4, 5, 6, 7) are assumed to be consolidated trip visits (1 trip per season) of 8 projects into 5 annual trips:
1. South Pole HF Radio replacement
2. South Pole HF Antenna field replacement
3. SPO Fiber Optic
4. Industrial Controls Network Security Zone Redesign
5. WAN optimizer Replacement Project
6. HAM Radio replacement
7. LMR Radio System

## 2022-2023
Project's Name |  | Types/items of fieldwork | Southbound cargo projection |  |  |  |  | Projected Population Profile (max per day in a half-month) |  |  |  | Total per season |  | Power & Bandwidth |  | Labor/support needed from ASC | Comments if any
Work Item number |  | Enter here what is absolutely needed (in black) for the subject season, "good to be accomplished" (in blue), or what the project envisions (in red - even not yet funded activities) | Weight (lbs) | Cubic Feet | Nov 1-15 | Nov 16-30 | Dec 1-15 | Dec 16-31 | Jan 1-15 | Jan 16-31 | Feb 1-15 | Total Team (not Σ left) | Self-Ticketers | kW | GB/day | For each item below - enter "YES" and provide details or enter "NO"
|  | Austral summer season FY 2023 (2022-2023) | 260300 | 10784 | 52 | 72 | 76 | 75 | 72 | 67 | 18 | 120 | 27 | 223 | 540
|  | A-149-S Cargo and Population Total | 18000 | 0 | 6 | 11 | 13 | 13 | 13 | 10 | 6 | 21 | 0 | 80 | 280 |  | power equals current B3/BA use
BICEP Array A-149-S | 1 | BICEP Array transfer to BART | 10000 |  | 2 | 4 | 4 | 4 | 4 | 4 | 2 | 8 |  |  |  | NO
| 2 | BICEP Array / BICEP3 operations | 3000 |  | 4 | 6 | 6 | 6 | 6 | 6 | 4 | 10 |  |  |  | NO
| 3 | Demolition of old MAPO tower/ recovery of first BA mount / BART#2 snowpad installation | 5000 |  |  | 1 | 3 | 3 | 3 |  |  | 3 |  |  |  | YES — crane for demo, equipment support for snowpad and footer installation
|  | A-379-S Cargo and Population Total | 6000 | 0 | 4 | 9 | 11 | 11 | 12 | 10 | 10 | 19 | 0 | 60 | 125 |  | Power is avg power, bandwidth is min bandwidth
SPT/TMA A-379-S | 1 | Winter-over relief and continued observing |  |  | 2 | 3 | 3 | 3 |  |  |  | 3 |  |  |  | NO
| 2 | Telescope and SPT-3G receiver maintenance | 4000 |  |  | 3 | 3 | 3 | 2 | 2 | 1 | 5 |  |  |  | NO
| 3 | EHT maintenance and training | 1200 | [5 empty] | 2 | 2 | 2 | 2 |  |  |  | NO
| 4 | Winter-overs and training |  |  |  |  | 2 | 2 | 5 | 5 | 5 | 5 |  |  |  | NO
| 5 | MAPO Machine Shop | 800 |  | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 |  |  |  | NO
| 6 | Install TMA Ice Pack (Support by USAP, bulldozer) |  |  |  | 2 | 2 | 2 | 2 |  |  | 2 |  |  |  | YES - All ASC support | Bulldozer to dig out pad and relayed it, same as was done for SPT.
|  | Station Projects - Cargo and Population Total | 101000
Station projects | 1 | Ice Tunnel Emergency Exit 4 of 4 | 0 | 0 |  |  | 4 | 4 | 4 |  |  | 4 |  |  |  | YES - ASC | Assumes cost is supported in FY23 APP/budget. Assumes all material already at SP. These four individuals are part of the normal sustaining crew removing ice from the tunnel.
| 2 | Blue Building Lift system and ARO raise - Execute | 1000 | 144 | 2 | 2 | 5 | 5 | 5 | 3 | 2 | 9 |  |  |  | YES - ASC | Complete ARO building lift. 4 of 9 population will be part of sustaining, dozer operators and carps. Assume 5 dedicated to this lifting project
| 3 | Fleet enhancements | 80000 | 2400 | [11 empty] | YES - ASC | Delivery only. Size/weight assumes two D8 dozers, but actual fleet delivery will be different, for estimating purposes only. Equipment may be able to be traveresed.
| 4 | Mitigate building 61 issues, ship to SP | 20000 | 300 | [11 empty] | YES - ASC | Delivery only. Size/weight is rough estimate takeoff from ARO estimate
|  | A-333-S Cargo and Population Total | 4300 | 384 | 6 | 8 | 8 | 7 | 3 | 3 | 2 | 14 | 2 | 75 | 105
ICNO M&O A-333-S | 1 | Winterovers |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | NO
| 2 | Computing and hub maintenance | 3500 | 256 | 1 | 2 | 2 | 2 | [7 empty] | YES — cargo handling, snow ramp
| 3 | Calibration | 150 | 32 |  | 1 | 1 | [8 empty] | NO
| 4 | DAQ / Engineering support | 150 | 32 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | NO
| 5 | M&O Upgrade support | 500 | 64 | 2 | 2 | 2 | 2 | [7 empty] | NO | Support Upgrade commissioning
|  | A-334-S Cargo and Population Total | 131000 | 10400 | 36 | 44 | 44 | 44 | 44 | 44 | 0 | 66 | 25 | 8 | 30
ICNO Upgrade A-334-S | 1 | IceCube Upgrade | 131000 | 10400 | 36 | 44 | 44 | 44 | 44 | 44 | 0 |  |  |  |  | YES — Equipment: Dozer, Fork, Manlift, as needed throughout season | See integrated master project schedule on Smartsheets for all details
| 2 | Drill 7 deep holes | [13 empty] | YES —Fuel: 65,900 gals, delivered as-needed throughout the season | To be captured/requested in SIP
| 3 | Install 7 Upgrade strings | [13 empty] | YES — Trades-support: generator technician, electrician, plumber, welder, etc. | See integrated master project schedule on Smartsheets for all details
| 4 | Dismantle and store the EHWD | [13 empty] | YES — Transportation: Dedicated or pooled van or truck, snowmobiles | To be captured/requested in SIP
| 5 | Cargo timely delivery | [13 empty] | YES — Cargo/Logistics: Timely delivery of all project cargo as required and captured on the IceCube master cargo spreadsheet | See "Upgrade Cargo Planning" worksheet on SharePoint for all details
Notes for IceCube Upgrade (A-334-S):
1. Cargo from Upgrade Cargo Planning worksheet in SP, rev Feb 4, 2020.
2. Population from On-Ice Org Charts 2019 to 2023 in SP, rev Feb 4, 2020.
3. Col M - Total based on Gen1 experience, it is assumed that half the positions will be for the full season and the remaining will require 2 deployments.
4. Self - ticketers match with In-Kind assumptions from On-Ice Org Charts 2019 to 2023.
Station Projects Not Shown Above - Needed:
South Pole elevated station raise: Design 21/22, procure 22/23, ship to MCM 23/24, ship to SP 24/25 & 25/26, execute 26/27
MAPO Lift: Design 20/21, procure 21/22, ship to MCM 22/23, ship to SP 23/24, execute 24/25
Extend Rodwell 3 building viability, level, raise, extend lifespan to match replacement plan – Planning and engineering could happen offiste in 2023
Establish NOAA tower maintenance and replacement consensus and plan
Mitigate building 61 issues, structural failure, electrical mis-wiring, genset repair or removal, building raise
Replace Arches: MAY BE REQUIRED PRIOR TO ELEVATED STATION LIFT. SP Master Plan will inform timing of projects
Fleet and ITC projects could add 1 Minor ReCap project per season requiring 2 to 3 staff (ASC plus contractor and/or supplier reps) for durations 1 month per project in the middle of season, in each of 5 next seasons. Smaller ITC projects (1, 4, 5, 6, 7) are assumed to be consolidated trip visits (1 trip per season) of 8 projects into 5 annual trips
1. South Pole HF Radio replacement
2. South Pole HF Antenna field replacement
3. SPO Fiber Optic
4. Industrial Controls Network Security Zone Redesign
5. WAN optimizer Replacement Project
6. HAM Radio replacement
7. LMR Radio System
8. Fleet enhancements Project-driven fleet requirements
SP Migrate Fire Panels from MXL to XLS- Procure in 21/22, ship to MCM 22/23, ship to SP 23/24, Install winter 24

## 2023-2024
Project's Name |  | Types/items of fieldwork | Southbound cargo projection |  |  |  |  | Projected Population Profile (max per day in a half-month) |  |  |  | Total per season |  | Power & Bandwidth |  | Labor/support needed from ASC | Comments if any
Work Item number |  | Enter here what is absolutely needed (in black) for the subject season, "good to be accomplished" (in blue), or what the project envisions (in red - even not yet funded activities) | Weight (lbs) | Cubic Feet | Nov 1-15 | Nov 16-30 | Dec 1-15 | Dec 16-31 | Jan 1-15 | Jan 16-31 | Feb 1-15 | Total Team (not Σ left) | Self-Ticketers | kW | GB/day | For each item below - enter "YES" and provide details or enter "NO"
|  | Austral summer season FY 2024 (2023-2024) | 1222300 | 11434 | 32 | 51 | 59 | 58 | 50 | 44 | 32 | 100 | 9 | 245 | 615
|  | A-149-S Cargo and Population Total | 93000 | 0 | 5 | 11 | 11 | 11 | 11 | 10 | 7 | 19 | 0 | 85 | 280
BICEP Array A-149-S |  | BICEP Array / BICEP3 operations | 3000 |  | 4 | 6 | 6 | 6 | 6 | 6 | 4 | 10 |  |  |  | NO
|  | BART installation #2, including re-use of first BA mount | 90000 |  | 1 | 5 | 5 | 5 | 5 | 4 | 3 | 9 |  |  |  | YES — crane, part-time plumbing and electrical support | Project personnel include construction coordinator plus full-time heavy carp/steel crew.
|  | A-379-S Cargo and Population Total | 736500 | 0 | 13 | 23 | 25 | 25 | 25 | 22 | 21 | 41 | 0 | 80 | 200 |  | Power is avg power, bandwidth is min bandwidth
SPT/TMA A-379-S | 1 | SPT-3G Decommissioning | 500 |  | 4 | 6 | [5 empty] | 6 |  |  |  | NO | SPT-3G M&O funding runs through end of 2023
| 2 | SPT4 camera deployment | 10000 |  |  | 4 | 8 | 8 | 8 | 6 | 4 | 12 |  |  |  | NO | Assumes new camera deploys in summer 23-24, and will require no ASC support beyond cargo
| 3 | EHT maintenance and training; Telescope Maintenance | 5200 |  |  | 3 | 3 | 3 | 2 | 2 | 2 | 5 |  |  |  | NO
| 4 | Winter-overs and training |  |  |  |  | 2 | 2 | 5 | 5 | 5 | 5 |  |  |  | NO
| 5 | MAPO Machine Shop | 800 |  | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 |  |  |  | NO
| 6 | Fly in TMA foundation materials | 330000 | [13 empty] | Need cargo delivered from skiway to construction site
| 7 | TMA foundation construction |  |  |  | 4 | 4 | 4 | 4 |  |  | 4 |  |  |  | YES — All ASC support | Need crane and operator, loader, manlift.
| 8 | Traverse in 3 TMA mirrors (ea. 4000 kgs including packaging), 1 azimuth bearing assembly (15,000 kgs steel structure no packaging container) | 60000 |  |  |  | 2 | 2 |  |  |  | 2 |  |  |  | YES — TMA staff | Unpack and check mirrors
| 9 | Fly in TMA High Bay materials | 330000 | [12 empty] | YES | Need cargo delivered from skiway to construction site.
| 10 | TMA High Bay Assembly |  |  | 7 | 5 | 5 | 5 | 5 | 8 | 8 | 5 |  |  |  | YES — All ASC staff | Need 2 cranes and operators, loader, manlift.
|  | Station Projects - Cargo and Population Total | 257500 | 650 | 2 | 3 | 9 | 9 | 5 | 3 | 2 | 13 | 1 | 0 | 0
Station projects | 1 | Snowpads for 3rd SAT tower and new laboratory building | 5000 |  |  | 1 | 1 | 1 |  |  |  | 1 | 1 |  |  | Equipment support for snowpad and footer installation
| 2 | Ship materials for 3rd SAT tower and new laboratory building | 250000 | [12 empty] | ASC-led operation (like MAPO/DSL) | Weight is rough estimate; vessel and traverse
| 3 | SP Migrate Fire Panels from MXL to XLS: ship to SP 23/24, Install winter 24 (Maybe other Fire Alarm Work) | 250 | 32 | [11 empty] | YES - ASC | Shipment only during the season, sustaining fire tech will do work over winter
| 4 | IT Minor Projects - 2 of 5 (See Below) | 500 | 64 |  |  | 3 | 3 |  |  |  | 3 |  |  |  | YES - ASC | Planning assumptions, IT Minor project 1 of 5
| 5 | MAPO Lift: ship to SP 23/24, execute 24/25 | 1500 | 504 | [11 empty] | YES - ASC | Assumes cost is supported in FY24 APP/budget, an procurement supported in FY23.Material delivery only. Less than ARO because we are assuming reuse from ARO job.
| 6 | Mitigate building 61 issues, execute | 250 | 50 | 2 | 2 | 5 | 5 | 5 | 3 | 2 | 9 |  |  |  | YES - ASC | Complete building 61 repair/reconfigure and lift. 4 of 9 population will be part of sustaining, dozer operators and carps. Assume 5 dedicated to this lifting project
|  | A-333-S Cargo and Population Total | 4300 | 384 | 6 | 8 | 8 | 7 | 3 | 3 | 2 | 18 | 5 | 80 | 135
ICNO M&O A-333-S | 1 | Winterovers |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | NO
| 2 | Computing and hub maintenance | 3500 | 256 | 1 | 2 | 2 | 2 | [7 empty] | YES — cargo handling, snow ramp
| 3 | Calibration | 150 | 32 |  | 1 | 1 | [8 empty] | NO
| 4 | DAQ / Engineering support | 150 | 32 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | NO
| 5 | M&O Upgrade support | 500 | 64 | 2 | 2 | 2 | 2 | [7 empty] | NO | Support Upgrade commissioning
|  | A-334-S Cargo and Population Total | 131000 | 10400 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 9 | 3 | 0 | 0
ICNO Upgrade A-334-S | 1 | IceCube Upgrade | 131000 | 10400 | 6 | 6 | 6 | 6 | 6 | 6 | [5 empty] | YES —Equipment: Dozer, Fork, Manlift, as needed throughout season | See integrated master project schedule on Smartsheets for all details
| 2 | Upgrade decommissioning | [13 empty] | YES — Trades-support: generator technician, electrician, plumber, welder, etc. | See integrated master project schedule on Smartsheets for all details
| 3 | Property & vehicle ownership issues | [13 empty] | YES — Transportation: Dedicated or pooled van or truck, snowmobiles | To be captured/requested in SIP
Notes for IceCube Upgrade (A-334-S):
1. Cargo from Upgrade Cargo Planning worksheet in SP, rev Feb 4, 2020.
2. Population from On-Ice Org Charts 2019 to 2023 in SP, rev Feb 4, 2020.
3. Col M - Total based on Gen1 experience, it is assumed that half the positions will be for the full season and the remaining will require 2 deployments.
4. Self - ticketers match with In-Kind assumptions from On-Ice Org Charts 2019 to 2023.
Station Projects Not Shown Above - Needed:
South Pole elevated station raise: Design 21/22, procure 22/23, ship to MCM 23/24, ship to SP 24/25 & 25/26, execute 26/27
Extend Rodwell 3 building viability, level, raise, extend lifespan to match replacement plan – Planning and engineering could happen offiste in 2023
Establish NOAA tower maintenance and replacement consensus and plan
Replace Arches: MAY BE REQUIRED PRIOR TO ELEVATED STATION LIFT. SP Master Plan will inform timing of projects
Fleet and ITC projects could add 1 Minor ReCap project per season requiring 2 to 3 staff (ASC plus contractor and/or supplier reps) for durations 1 month per project in the middle of season, in each of 5 next seasons. Smaller ITC projects (1, 4, 5, 6, 7) are assumed to be consolidated trip visits (1 trip per season) of 8 projects into 5 annual trips:
1. South Pole HF Radio replacement
2. South Pole HF Antenna field replacement
3. SPO Fiber Optic
4. Industrial Controls Network Security Zone Redesign
5. WAN optimizer Replacement Project
6. HAM Radio replacement
7. LMR Radio System
8. Fleet enhancements Project-driven fleet requirements

## 2024-2025
Project's Name |  | Types/items of fieldwork | Southbound cargo projection |  |  |  |  | Projected Population Profile (max per day in a half-month) |  |  |  | Total per season |  | Power & Bandwidth |  | Labor/support needed from ASC | Comments if any
Work Item number |  | Enter here what is absolutely needed (in black) for the subject season, "good to be accomplished" (in blue), or what the project envisions (in red - even not yet funded activities) | Weight (lbs) | Cubic Feet | Nov 1-15 | Nov 16-30 | Dec 1-15 | Dec 16-31 | Jan 1-15 | Jan 16-31 | Feb 1-15 | Total Team (not Σ left) | Self-Ticketers | kW | GB/day | For each item below - enter "YES" and provide details or enter "NO"
|  | Austral summer season FY 2025 (2024-2025) | 608950 | 1152 | 20 | 50 | 62 | 64 | 63 | 57 | 42 | 100 | 14 | 333 | 1085
|  | A-149-S Cargo and Population Total | 23000 | 0 | 6 | 12 | 12 | 12 | 12 | 12 | 6 | 20 | 0 | 130 | 530
BICEP/Keck | 1 | BICEP Array / BICEP3 operations | 3000 |  | 4 | 6 | 6 | 6 | 6 | 6 | 4 | 10 |  |  |  | NO
| 2 | Receiver deployment on BART#2 | 20000 |  | 2 | 6 | 6 | 6 | 6 | 6 | 2 | 10 |  |  |  | NO
|  | A-379-S Cargo and Population Total | 468000 | 0 | 6 | 20 | 26 | 28 | 32 | 31 | 29 | 41 | 0 | 120 | 320 |  | Power is avg power, bandwidth is min bandwidth
SPT/TMA | 1 | Winter-over relief and Telescope maintenance |  |  | 2 | 3 | 3 | 3 |  |  |  | 3 |  |  |  | NO
| 2 | SPT4 receiver maintenance | 4000 |  |  | 4 | 8 | 8 | 8 | 6 | 3 | 12 |  |  |  | NO | Assumes SPT4 camera needs fairly significant improvements after 1st season
| 3 | EHT maintenance and training | 1200 | [5 empty] | 2 | 2 | 2 | 2 |  |  |  | NO
| 4 | Winter-overs and training |  |  |  |  | 2 | 2 | 5 | 5 | 5 | 5 |  |  |  | NO
| 5 | MAPO Machine Shop | 800 |  | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 |  |  |  | NO
| 6 | Fly in TMA Telescope materials | 440000 | [12 empty] | ?? | Need cargo delivered from skiway to construction site
| 7 | TMA Assembly |  |  |  | 10 | 10 | 10 | 12 | 12 | 12 | 12 |  |  |  | YES — 8 ASC staff, remainder TMA | Need 2 cranes & operators, loader, manlift.
| 8 | TMA Telescope Commissioning | [5 empty] | 2 | 2 | 3 | 3 | 3 |  |  |  | NO - only TMA staff
| 9 | Fly in TMA Camera equipment | 22000 | [12 empty] | ??
| 10 | TMA Camera Commissioning |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  | NO — only TMA staff
|  | Station Projects - Cargo and Population Total | 106000 | 139 | 3 | 9 | 15 | 15 | 10 | 7 | 5 | 21 | 9 | 0 | 0
Station projects | 1 | Install 3rd SAT tower | 90000 |  | 1 | 5 | 5 | 5 | 5 | 4 | 3 | 9 | 9 |  |  | YES - crane, part-time plumbing and electrical support | Project personnel include construction coordinator plus full-time heavy carp/steel crew.
| 2 | IT Minor Projects - 3 of 5 (See Below) | 500 | 64 |  |  | 3 | 3 |  |  |  | 3 |  |  |  | YES - ASC | Planning assumptions, IT Minor project 1 of 5
| 3 | Snowpads for 4th, 5th, and 6th SAT towers | 15000 |  |  | 2 | 2 | 2 | [7 empty] | YES - equipment support for snowpad and footer installation
| 4 | South Pole elevated station raise: Ship | unknown | unknown | [12 empty] | Shipment only
| 5 | MAPO Lift | 500 | 75 | 2 | 2 | 5 | 5 | 5 | 3 | 2 | 9 |  |  |  | YES - ASC | Complete MAPO building lift. 4 of 9 population will be part of sustaining, dozer operators and carps. Assume 5 dedicated to this lifting project
|  | A-333-S Cargo and Population Total | 11950 | 1013 | 5 | 9 | 9 | 9 | 9 | 7 | 2 | 18 | 5 | 83 | 235
ICNO M&O A-333-S | 1 | Winterovers |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  |  | NO | Renewal M&O proposal
| 2 | Computing and hub maintenance | 6500 | 384 | 2 | 2 | 2 | 2 | [7 empty] | YES - cargo handling, snow ramp | Includes Upgrade hubs
| 3 | Calibration | 150 | 32 |  | 1 | 1 | 1 | 2 | 1 | [5 empty] | NO | Includes Upgrade calibration
| 4 | DAQ / Engineering support | 150 | 32 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | NO
| 5 | Scintillator maintenance | 750 | 80 |  |  |  |  | 1 | 1 | [5 empty] | NO
| 6 | Radio maintenance | 400 | 21 | [5 empty] | 1 | [5 empty] | NO
| 7 | IceACT maintenance | 250 | 64 | [5 empty] | 1 | [5 empty] | NO
| 8 | DOMHub replacement | 3750 | 400 |  | 3 | 3 | 3 | 3 | [6 empty] | NO
| 9 | Gen2 Construction Pole Season 1 (Preparation) | 330000 |  | 10 | 20 | 20 | 20 | 20 | 10
|  | A-334-S Cargo and Population Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ICNO Upgrade A-334-S | 1 | IceCube Upgrade (placeholder if needed)
Station Projects Not Shown Above - Needed:
Extend Rodwell 3 building viability, level, raise, extend lifespan to match replacement plan – field work
Establish NOAA tower maintenance and replacement consensus and plan
Replace Arches: MAY BE REQUIRED PRIOR TO ELEVATED STATION LIFT. SP Master Plan will inform timing of projects
Fleet and ITC projects could add 1 Minor ReCap project per season requiring 2 to 3 staff (ASC plus contractor and/or supplier reps) for durations 1 month per project in the middle of season, in each of 5 next seasons. Smaller ITC projects (1, 4, 5, 6, 7) are assumed to be consolidated trip visits (1 trip per season) of 8 projects into 5 annual trips:
1. South Pole HF Radio replacement
2. South Pole HF Antenna field replacement
3. SPO Fiber Optic
4. Industrial Controls Network Security Zone Redesign
5. WAN optimizer Replacement Project
6. HAM Radio replacement
7. LMR Radio System
8. Fleet enhancements Project-driven fleet requirements