## Storage Summary
IceCube Upgrade - Winter Storage Requirements
Type of Storage: | Winter 2020 |  | Winter 2021 |  | Winter 2022
| Weight | Cube | Weight | Cube | Weight | Cube
McMurdo: Indoor, Heated | 0 | 0 | 0 | 0 | 1800 | 192
McMurdo: Indoor, Unheated | 0 | 0 | 0 | 0 | 0 | 0
McMurdo: Outdoor | 173440 | 15536.9566 | 32400 | 3272 | 87500 | 3257.474
McMurdo: TOTAL | 173440 | 15536.9566 | 32400 | 3272 | 89300 | 3449.474
South Pole: Indoor, Heated | 0 | 0 | 0 | 0 | 12150 | 1974.7153
South Pole: Indoor, Unheated | 0 | 0 | 0 | 0 | 0 | 0
South Pole: Outdoor | 0 | 0 | 0 | 0 | 5000 | 352
South Pole: TOTAL | 0 | 0 | 0 | 0 | 17150 | 2326.7153
2019-07-19
* All weight in pounds, all cube in feet
** This list does NOT include cargo considered "pass thru", requiring only temporary staging until movement to South Pole
*** Current plan reflects Drill Hose winter cold-store in ZCM 2021, and winter DNF at NPX in 2022

## Cargo Shipped 2019
Date | Crate ID | DNF? | ROS McMurdo | ROS South Pole | Contents
2019-09-21 | MV-10 | No | 9313 |  | Generator and PDM Upgrade Tools, Parts, Supplies
2019-09-21 | ICU-01M | DNF | 9313 |  | DNF Tools for McMurdo Gen and PDM Upgrade
2019-09-21 | BAT-1M | DNF | 9313 |  | DNF DeWalt 18V and 20V Batteries, Label Maker
2019-09-21 | BAT-2 | DNF |  | 9327 | DNF Batteries for Duvernois and Zernick
2019-09-21 | CR-1 | No |  | 9327 | 2 Crescents for Drill Tower
2019-09-26 | ICU-02 | No |  | 9320 | Jaemar Winch, HPP#4, Safety Equipment
2019-09-26 | ICU-03 | No |  | 9320 | 50HP Motor and Stand, Fuel and Water Hoses, Driller Bike
2019-09-26 | ICU-04 | No |  | 9320 | Vacuum Canisters, Burner, Burner Repair Kit
2019-09-26 | SN-1 | No |  | 9320 | Snowmobile- Polaris Wide Track 550
2019-09-26 | SN-2 | No |  | 9320 | Snowmobile- Polaris Wide Track 550
2019-09-26 | MV-11 | No |  | 9320 | 20' Container - ICU-02, ICU-03, ICU-04, SN-1, SN-2 Inside
2019-09-26 | ICU-05 | DNF |  | 9320 | DNF Safety Equipment
2019-09-26 | ICU-06 | DNF |  | 9320 | DNF Allen Bradley Motor Drives, Tools and Equipment

## Sheet X
Container Type | Description of Container Contents | Number of containers with same characteristics | Individual Container Weight (lbs) | Total Weight (lbs) | L (in) | W (in) | H (in) | Total Cubes (cf) | Wt & Cu Confirmed? (L2/Date) | Keep Dry | Do Not Freeze (DNF) | Hazardous | Spec. Hndlg | Drift? | Shipping to NPX Origin | Depart Origin Target Date | Expected arrival at Port Hueneme (must meet RDD for ROS) | Transit Time: Origin to PTH (days) | Ship Method - PTH to Christchurch | Ship Method to McMurdo (ZCM) | Arrive ZCM | Ship method to Pole (NPX) | ROS date to NPX | Total Transit Time: PTH to NPX (days) | Long-Term Storage Required? | Storage Start Date | Storage End Date | Storage Location - South Pole - McMurdo - None | Storage Season | Storage Type - Indoor, Heated - Indoor, Unheated - Outdoor
Wood Spool | Drill Hose (from PSL) (DNDF) 4@4800#, 350cu | 4 | 4800 | 19200 | 96 | 96 | 72 | 1536 | TH |  |  |  | DNDF-ZCM | Yes | PSL | 2020-11-01 | 2020-11-11 | 10 | Vessel 2020 | Vessel 2020 | 2021-02-01 | Air 2021 | 2022-02-05 |  | Yes | 2022-02-05 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated | Cryo Storage
Wood Spool | Drill Hose (from Italy) (DNDF) 8@4800#, 350cu | 8 | 4800 | 38400 | 96 | 96 | 72 | 3072 | TH |  |  |  | DNDF-ZCM | Yes | Italy | 2020-11-01 |  |  | ComSur 2020 | Vessel 2020 | 2021-02-01 | Air 2021 | 2022-02-05 |  | Yes | 2022-02-05 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated
Steel Spool | Main Cable Assembly 87 | 1 | 15000 | 15000 | 93 | 95 | 93 | 475.4948 | TDY 9/11/19 | 1 |  |  | None | No | MSU | 2021-09-15 | 2021-09-30 | 15 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 | 2022-02-05 |  | Yes | 2022-02-05 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated
Steel Spool | Main Cable Assembly 88 | 1 | 15000 | 15000 | 93 | 95 | 93 | 475.4948 | TDY 9/11/19 | 1 |  |  | None | No | MSU | 2021-09-15 | 2021-09-30 | 15 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 | 2022-02-05 |  | Yes | 2022-02-05 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated
Cardboard overcarton | 108 mDOMs 87 - 88: overcartons of 4 units | 27 | 250 | 6750 | 48 | 48 | 36 | 1296 |  | 1 | 1 |  | None | No | DESY / MSU |  |  | 0 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 | 2021-11-20 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated | Other Storage (B2 Mezanine?)
Cardboard overcarton | 88 D-Eggs 87 - 88: overcartons of 4 units | 22 | 250 | 5500 | 48 | 48 | 36 | 1056 |  | 1 | 1 |  | None | No | Chiba |  |  | 0 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 | 2021-11-20 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated
Cardboard overcarton | 8 PDOMs 87 - 88: overcartons of 8 units | 1 | 400 | 400 | 42 | 42 | 45 | 45.9375 |  | 1 | 1 |  | None | No | UW |  |  | 0 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 | 2021-11-20 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated
Cardboard overcarton | 28 POCAMs 87 - 93 | 7 | 200 | 1400 | 42 | 42 | 30 | 214.375 |  | 1 |  |  | None | No | Munich |  |  | 0 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 | 2022-02-05 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated
Cardboard overcarton | 12 Pencil Beams 87 - 93 | 3 | 200 | 600 | 42 | 42 | 30 | 91.875 |  | 1 |  |  | None | No | UW |  |  | 0 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 | 2022-02-05 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated
Wood Crate | Special Devices 87 - 88 | 2 | 250 | 500 | 42 | 42 | 36 | 73.5 |  | 1 | 1 |  | None | No | Various |  |  | 0 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 | 2021-11-20 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated
Hardigg Case | Depth Sensors (Paro) 87 - 93 | 1 | 400 | 400 | 30 | 30 | 24 | 12.5 |  | 1 |  |  | None | No | PSL |  |  | 0 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 | 2022-02-01 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated
|  |  |  | 103150 |  |  |  | 8349.1771

## Drill Hose Logistics
|  | 2019 |  |  | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023
Drill Hose - Delivery Options |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S
Option-1 (Preferred)
| New Hose, Procurement | 2019 O: Procurement
| New Hose, Drop Ship IVG (Italy) to CHC - (9 spools) | 2020 S: Ship/Store; 2020 D: Vessel
| PSL Hose, Vessel, PTH - ZCM - (4 spools) | 2020 N: Vessel
| Storage in McMurdo (Outdoor Cold) - (13 spools) | 2021 F: Store McMurdo (Outdoor Cold)
| Fly ZCM to NPX (9 spools), leave 4 spools in McMurdo | 2021 N: FLY
| Install onto Hose reel at Pole, leave spares in McMurdo | 2022 J: Install
| Storage at South Pole on hose reel | 2022 M: Store at NPX (DNDF on reel)
| Fly ZCM to NPX (4 spools) Drill, Retro to Storage | 2022 N: DRILL
Option-2 (Old-Preferred)
| New Hose, Procurement | 2019 O: Procurement
| New Hose, Drop Ship IVG (Italy) to CHC - (9 spools) | 2020 S: Ship/Store; 2020 D: Vessel
| PSL Hose, Vessel, PTH - ZCM - (4 spools) | 2020 N: Vessel
| Storage in McMurdo (Outdoor Cold) - (13 spools) | 2021 F: Store McMurdo (Outdoor Cold)
| Fly ZCM to NPX - (13 spools) | 2021 D: FLY
| Storage at South Pole (Cryo?) - (13 spools) | 2022 F: Store at NPX (DNF)
| Install & Drill, Retro to Storage | 2022 N: Install
Option-2 (Risky)
| New Hose, Procurement | 2019 O: Procurement
| New Hose, Drop Ship IVG (Italy) to CHC - (9 spools) | 2020 S: Ship/Store; 2020 D: Vessel
| PSL Hose, Vessel, PTH - ZCM - (4 spools) | 2020 N: Vessel
| Storage in McMurdo (Outdoor Cold) - (13 spools) | 2021 F: Store in McMurdo (Outdoor Cold)
| Fly ZCM to NPX | 2022 N: Fly
Install (just in time) & Drill, Retro to Storage | bar: 2022 N to 2023 J
Option-3 (Not desired)
| New Hose, Procurement | 2019 O: Procurement
| New Hose, Drop Ship IVG (Italy) to CHC - (9 spools) | 2020 S: Ship - CHC
| PSL Hose, Vessel, PTH - CHC - (4 spools) | 2020 N: VSL
| Storage in Christchurch, NZ | 2020 D: Store in Christchurch
| Fly CHC to ZCM (C-17) | 2022 O: C17
| Fly ZCM to NPX | 2022 N: Fly
Install (just in time) & Drill, Retro to Storage | bar: 2022 N to 2023 J

## Cargo Summary
Transport Summary by Method by Season (do not edit)
Method of Transport | 2019/20 | 2020/21 | 2021/22 | 2022/23 | TOTAL
Vessel to McMurdo | 0 | 94800 | 87500 | 0 | 182300
ComSur to CHC | 0 | 73825 | 71350 | 42300 | 187475
ComAir to CHC | 0 | 0 | 3000 | 3600 | 6600
C-17 to McMurdo | 0 | 30625 | 86150 | 45900 | 162675
Traverse ZCM to NPX | 0 | 110840 | 51200 | 0 | 162040
Fly LC-130 ZCM to NPX | 0 | 40025 |  | 152600 | 192625
Estimated Flights (23,800/ea) | 0 | 1.6817 | 0 | 6.4118 | 8.0935
* All weight in pounds
- Traverse consists only of EHWD Generator modules, IFD, and over-sized SALSA equipment
- Does NOT include fuel (cargo only)

## All Cargo to NPX
ID # | WBS L2 | Container Type | Description of Container Contents | Number of containers with same characteristics | Individual Container Weight (lbs) | Total Weight (lbs) | L (in) | W (in) | H (in) | Total Cubes (cf) | Wt & Cu Confirmed? (L2/Date) | Keep Dry | Do Not Freeze (DNF) | Hazardous | Spec. Hndlg | Drift? | Shipping to NPX Origin | Depart Origin Target Date | Expected arrival at Port Hueneme (must meet RDD for ROS) | Transit Time: Origin to PTH (days) | Ship Method - PTH to Christchurch | Ship Method to McMurdo (ZCM) | Arrive ZCM | Ship method to Pole (NPX) | Season Ship Priority, 1 = top priority and then count up | Season Traverse Priority, 1 = top priority and then count up | Traverse Note | ROS date to NPX | Total Transit Time: PTH to NPX (days) | Long-Term Storage Required? | Storage Start Date | Storage End Date | Storage Location - South Pole - McMurdo - None | Storage Season | Storage Type - Indoor, Heated - Indoor, Unheated - Outdoor | Note | Added information related to traverse
3 | 1.2 | Wood Crate | Repair/Replacement Parts (2020/21), MHP, PHS, Pumps, MDS parts, | 4 | 1000 | 4000 | 96 | 48 | 48 | 512 |  | 1 |  |  | None | Yes | PSL | 2020-09-25 | 2020-10-05 | 10 | ComSur 2020 | C17-2020 | 2020-11-14 | Air 2020 |  |  |  | 2020-11-21 |  | No
4 | 1.2 | Wood Crate | Repair/Replacement Parts (2020/21) - DO NOT FREEZE | 1 | 1000 | 1000 | 96 | 48 | 48 | 128 |  | 1 | 1 |  | DNF | No | PSL | 2020-09-25 | 2020-10-05 | 10 | ComSur 2020 | C17-2020 | 2020-11-14 | Air 2020 |  |  |  | 2020-11-21 |  | No
5 | 1.2 | ISO Container | Generator-1 (at ZCM, came vessel Feb 2020) | 1 | 22000 | 22000 | 240 | 96 | 96 | 1280 | TH |  |  |  | None | No | ZCM | 2020-11-01 | -- | -- | -- | -- | -- | Traverse 2020 |  | 2 | SPOT1 | 2020-11-28 |  | Yes | 2020-02-01 | 2020-11-01 | McMurdo | Winter 2020 | Outdoor
6 | 1.2 | Wood Crate | Motor Drives, Control System Equipment (2020) | 3 | 1500 | 4500 | 96 | 48 | 48 | 384 |  | 1 | 1 |  | DNF | No | PSL | 2020-09-25 | 2020-10-05 | 10 | ComSur 2020 | C17-2020 | 2020-11-14 | Air 2020 |  |  |  | 2020-11-28 |  | No
7 | 1.2 | Sled/Skis | UNL - Flat Rack/Ski-Sled System # 1 - 40'L, ISO2 (Gen2&3 on now) | 1 | 20000 | 20000 | 480 | 96 | 96 | 2560 |  |  |  |  | None | N/A | ZCM | -- | -- | -- | -- | -- | -- | TBD |  |  |  | TBD |  | Yes | 2019-10-01 | TBD | McMurdo | Winter 2020 | Outdoor
8 | 1.2 | ISO Container | Generator-2 (currently on 40' UNL Flat Rack #1 w/Gen3) -> move to ASC flatrack | 1 | 22000 | 22000 | 240 | 96 | 96 | 1280 | TH |  |  |  | None | No | ZCM | 2020-11-01 | -- | -- | -- | -- | -- | Traverse 2020 |  | 1 | SPOT1 | 2020-11-28 |  | Yes | 2020-02-01 | 2020-11-01 | McMurdo | Winter 2020 | Outdoor
9 | 1.2 | ISO Container | Generator-3 (currently on 40' UNL Flat Rack #1 w/Gen2) -> move to ASC flatrack | 1 | 22000 | 22000 | 240 | 96 | 96 | 1280 | TH |  |  |  | None | No | ZCM | 2020-11-01 | -- | -- | -- | -- | -- | Traverse 2020 |  | 3 | SPOT1 | 2020-11-28 |  | Yes | 2020-02-01 | 2020-11-01 | McMurdo | Winter 2020 | Outdoor
10 | 1.2 | ISO Container | UNL - Reel Container - 40' long, on ISO2 (NOT Hercable) | 1 | 20000 | 20000 | 480 | 96 | 96 | 2560 |  |  |  |  | None | N/A | ZCM | -- | -- | -- | -- | -- | -- | TBD |  |  |  | TBD |  | Yes | 2019-10-01 | TBD | McMurdo | Winter 2020/21 | Outdoor
11 | 1.2 | ISO Container | UNL - HPU-1 - 40' long, on ISO2-C (NOT Hercable) | 1 | 28000 | 28000 | 480 | 96 | 96 | 2560 |  |  |  |  | None | N/A | ZCM | -- | -- | -- | -- | -- | -- | Traverse 2020 |  | 10 | SPOT1 | 2020-12-26 |  | Yes | 2019-10-01 | 2020-12-31 | McMurdo | Winter 2020 | Outdoor
12 | 1.2 | ISO Container | UNL - HPU-2 - 40' long, on ISO2 (NOT Hercable) | 1 | 28000 | 28000 | 480 | 96 | 96 | 2560 |  |  |  |  | None | N/A | ZCM | -- | -- | -- | -- | -- | -- | TBD |  |  |  | TBD |  | Yes | 2019-10-01 | TBD | McMurdo | Winter 2020/21 | Outdoor
13 | 1.2 | Sled/Skis | UNL - Flat Rack/Ski-Sled System #3 - 20'L (can not locate) | 1 | 14000 | 14000 | 240 | 96 | 96 | 1280 |  |  |  |  | None | N/A | ZCM | -- | -- | -- | -- | -- | -- | Traverse 2021 |  |  |  | TBD |  | Yes | 2019-10-01 | TBD | McMurdo | Winter 2020 | Outdoor
14 | 1.2 | Sled/Skis | UNL - Flat Rack/Ski-Sled System #2 - 40'L, ISO2 (Fuel tower, panel, on now) | 1 | 20000 | 20000 | 480 | 96 | 96 | 2560 |  |  |  |  | None | N/A | ZCM | -- | -- | -- | -- | -- | -- | TBD |  |  |  | TBD |  | Yes | 2019-10-01 | TBD | McMurdo | Winter 2020 | Outdoor
15 | 1.2 | Loose Equip | Fuel Tower, Day Tank (currently on UNL flat rack #2) -> move to ASC flatrack | 1 | 1500 | 1500 | 96 | 72 | 120 | 480 |  |  |  |  | None | Yes | ZCM | -- | -- | -- | -- | -- | -- | Traverse 2020 |  | 4 | SPOT1 | 2020-11-28 |  | Yes | 2020-02-01 | 2020-11-01 | McMurdo | Winter 2020 | Outdoor
16 | 1.2 | Loose Equip | Electrical Panels (on UNL flat rack #2 - remove and fly to NPX 11/19) | 2 | 400 | 800 | 48 | 48 | 96 | 256 |  |  |  |  | None | Yes | ZCM | -- | -- | -- | -- | -- | -- | Air 2020 |  |  |  | 2020-11-21 |  | No
17 | 1.2 | Loose Equip | Hose Crimper (on UNL flat rack) - retroed to WI 20/21, will ship back in crate | 1 | 800 | 800 | 36 | 36 | 72 | 54 |  |  |  |  | None | Yes | PSL | 2020-09-25 | 2020-10-05 | 10 | ComSur 2020 | C17-2020 | 2020-11-14 | Air 2020 |  |  |  | 2020-11-21 |  | No
18 | 1.2 | Loose Equip | Cable Tensioner (Bull Wheel) | 1 | 800 | 800 | 48 | 48 | 72 | 96 |  |  |  |  | None | Yes | PSL | 2021-08-30 | 2021-09-14 | 15 | ComSur2021 | C17-2021 | 2021-11-01 | Traverse 2021 |  | 3 | SPOT2 | 2021-12-31 |  | No
19 | 1.2 | Secure Equip | Independent Firn Drill (IFD) | 1 | 11972 | 11972 | 264 | 94 | 97 | 1393.0278 | TB 4/7/20 |  |  |  | Glycol | No | ZCM | 2020-11-01 | -- | -- | -- | -- | -- | Traverse 2020 |  | 7 | SPOT1 | 2020-12-26 |  | Yes | 2020-02-01 | 2020-12-31 | McMurdo | Winter 2020 | Outdoor
20 | 1.2 | Loose Equip | 287B Cat Skidsteer | 1 | 9600 | 9600 | 96 | 96 | 96 | 512 |  |  |  |  | None | Yes | ZCM | 2020-11-01 | -- | -- | -- | -- | -- | Air 2020 |  |  |  | 2020-12-31 |  | Yes | 2020-02-01 | 2020-12-31 | McMurdo | Winter 2020 | Outdoor
21 | 1.2 | Loose Equip | Snowmobiles x 2 | 2 | 1100 | 2200 | 96 | 48 | 48 | 256 |  |  |  |  | None | Yes | PSL | 2020-09-25 | 2020-10-05 | 10 | ComSur 2020 | C17-2020 | 2020-11-14 | Air 2020 |  |  |  | 2020-12-31 |  | No
22 | 1.2 | Wood Crate | Filtration Sub-Components, Spares | 1 | 2000 | 2000 | 96 | 48 | 48 | 128 |  |  |  |  | None | Yes | PSL | 2020-11-01 | 2020-11-11 | 10 | Vessel 2020 | Vessel 2020 | 2021-02-01 | Air 2021 |  |  |  | 2021-11-20 |  | Yes | 2021-02-01 | 2021-11-20 | McMurdo | Winter 2021 | Outdoor
23 | 1.2 | Wood Crate | Computers, Networking Equipment (DNF) | 2 | 500 | 1000 | 48 | 48 | 48 | 128 |  | 1 | 1 |  | DNF | No | PSL | 2021-09-18 | 2021-10-01 | 13 | ComAir 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2021-11-20 |  | No
24 | 1.2 | Wood Crate | Motor Drives, Control System Equipment | 2 | 1000 | 2000 | 96 | 48 | 48 | 256 |  | 1 | 1 |  | DNF | No | PSL | 2021-09-18 | 2021-10-01 | 13 | ComAir 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2021-11-20 |  | No
25 | 1.2 | Wood Crate | Repair/Replacement Parts (2021-22), Pumps, Replacement Parts | 4 | 1500 | 6000 | 96 | 48 | 48 | 512 |  |  |  |  | None | Yes | PSL | 2021-09-18 | 2021-10-01 | 13 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2021-11-20 |  | No
26 | 1.2 | Wood Crate | Repair/Replacement Parts (2021/22) - DO NOT FREEZE | 1 | 400 | 400 | 48 | 48 | 48 | 64 |  | 1 | 1 |  | DNF | No | PSL | 2021-09-18 | 2021-10-01 | 13 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2021-11-20 |  | No
27 | 1.2 | Wood Crate | Cables, Main Feeder, Bldg Interconnects | 2 | 2500 | 5000 | 96 | 48 | 48 | 256 |  |  |  |  | None | Yes | PSL | 2021-09-18 | 2021-10-01 | 13 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2021-11-20 |  | No
28 | 1.2 | Wood Crate | TOS/Tower Refabricated items | 1 | 2000 | 2000 | 96 | 48 | 48 | 128 |  |  |  |  | None | Yes | PSL | 2020-11-01 | 2020-11-11 | 10 | Vessel 2020 | Vessel 2020 | 2021-02-01 | Air 2021 |  |  |  | 2021-11-27 |  | Yes | 2021-02-01 | 2021-11-27 | McMurdo | Winter 2021 | Outdoor
29 | 1.2 | Wood Crate | MSHR Spare Parts | 1 | 1500 | 1500 | 48 | 48 | 48 | 64 |  |  |  |  | None | Yes | PSL | 2020-11-01 | 2020-11-11 | 10 | Vessel 2020 | Vessel 2020 | 2021-02-01 | Air 2021 |  |  |  | 2021-11-27 |  | Yes | 2021-02-01 | 2021-11-27 | McMurdo | Winter 2021 | Outdoor
30 | 1.2 | Drums | Glycol - Provided by ASC? (4x55 gal) | 1 | 2000 | 2000 | 72 | 72 | 72 | 216 | TH |  |  |  | Glycol | Yes | PSL | 2020-11-01 | 2020-11-11 | 10 | Vessel 2020 | Vessel 2020 | 2021-02-01 | Air 2021 |  |  |  | 2021-12-31 |  | Yes | 2021-02-01 | 2021-11-27 | McMurdo | Winter 2021 | Outdoor
31 | 1.2 | Wood Crate | Drill Head | 1 | 600 | 600 | 192 | 24 | 24 | 64 | TH |  | 1 |  | DNF | No | PSL | 2021-09-18 | 2021-10-01 | 13 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2022-02-05 |  | Yes | 2021-11-13 | 2022-02-05 | McMurdo | Winter 2022 | Indoor, Heated
32 | 1.2 | Wood Crate | Drill Head | 1 | 600 | 600 | 192 | 24 | 24 | 64 | TH |  | 1 |  | DNF | No | PSL | 2021-09-18 | 2021-10-01 | 13 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2022-02-05 |  | Yes | 2021-11-13 | 2022-02-05 | McMurdo | Winter 2022 | Indoor, Heated
33 | 1.2 | Wood Crate | Drill Head | 1 | 600 | 600 | 192 | 24 | 24 | 64 | TH |  | 1 |  | DNF | No | PSL | 2021-09-18 | 2021-10-01 | 13 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2022-02-05 |  | Yes | 2021-11-13 | 2022-02-05 | McMurdo | Winter 2022 | Indoor, Heated
34 | 1.2 | Secure Equip | Main Drill Cable Reel (with drill cable) | 1 | 8000 | 8000 | 192 | 96 | 96 | 1024 |  |  |  |  | None | Yes | PSL | 2021-08-30 | 2021-09-14 | 15 | ComSur2021 | C17-2021 | 2021-11-01 | Traverse 2021 |  | 1 | SPOT2 | 2021-12-31 |  | No
35 | 1.2 | Wood Spool | Cable, Drill, Spare on Spool | 1 | 3000 | 3000 | 72 | 72 | 72 | 216 |  |  |  |  | None | Yes | PSL | 2021-08-30 | 2021-09-14 | 15 | ComSur2021 | C17-2021 | 2021-11-01 | Traverse 2021 |  | 7 | SPOT2 | 2021-12-31 |  | No
36 | 1.2 | Secure Equip | Return Water Cable Reel | 1 | 3500 | 3500 | 72 | 72 | 72 | 216 |  |  |  |  | None | Yes | PSL | 2020-11-01 | 2020-11-11 | 10 | Vessel 2020 | Vessel 2020 | 2021-02-01 | Traverse 2021 |  | 2 | SPOT2 | 2021-12-31 |  | Yes | 2021-02-01 | 2021-12-31 | McMurdo | Winter 2021 | Outdoor
37 | 1.2 | Wood Spool | Cable, Combo | 1 | 3000 | 3000 | 72 | 72 | 72 | 216 |  |  |  |  | None | Yes | PSL | 2020-11-01 | 2020-11-11 | 10 | Vessel 2020 | Vessel 2020 | 2021-02-01 | Traverse 2021 |  | 8 | SPOT2 | 2021-12-31 |  | Yes | 2021-02-01 | 2021-12-31 | McMurdo | Winter 2021 | Outdoor
38 | 1.2 | Wood Crate | Repair/Replacement Parts (2022/23), Last minute Parts | 2 | 1500 | 3000 | 96 | 48 | 48 | 256 |  |  |  |  | None | Yes | PSL | 2022-09-18 | 2022-10-01 | 13 | ComAir 2022 | C17-2022 | 2022-11-09 | Air 2022 |  |  |  | 2022-11-16 |  | No
39 | 1.2 | Wood Crate | Repair/Replacement Parts (2022/23) - DO NOT FREEZE | 1 | 600 | 600 | 96 | 48 | 48 | 128 |  |  | 1 |  | DNF | No | PSL | 2022-09-18 | 2022-10-02 | 14 | ComAir 2022 | C17-2022 | 2022-11-09 | Air 2022 |  |  |  | 2022-11-16 |  | No
40 | 1.2 | Wood Spool | Drill Hose (from PSL) (DNDF) 4@4800#, 350cu | 4 | 4800 | 19200 | 92 | 92 | 72 | 1410.6667 | TH |  |  |  | DNDF-ZCM | Yes | PSL | 2020-11-01 | 2020-11-11 | 10 | Vessel 2020 | Vessel 2020 | 2021-02-01 | Air 2022 |  |  |  | 2022-11-16 |  | Yes | 2021-02-01 | 2022-12-01 | McMurdo | Winter 2021/2022 | DNDF, min -50C
41 | 1.2 | Wood Spool | Drill Hose (from Italy) (DNDF) 9@4800#, 350cu | 9 | 4800 | 43200 | 92 | 92 | 72 | 3174 | TH |  |  |  | DNDF-ZCM | Yes | Italy | 2020-08-01 |  |  | ComSur 2020 | Vessel 2020 | 2021-02-01 | Air 2021 |  |  |  | 2021-11-27 |  | Yes | 2021-02-01 | 2021-12-01 | McMurdo | Winter 2021 | DNDF, min -50C | Heated on Hose reel at NPX Winter 2022
42 | 1.4 | Wood Crate | String Hardware 87 - 88 | 2 | 1500 | 3000 | 96 | 48 | 48 | 256 |  | 1 |  |  | None | Yes | PSL | 2021-09-01 | 2021-09-16 | 15 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2022-02-05 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | Winter 2022 | Outdoor
43 | 1.4 | Wood Crate | String Hardware 89 - 93 | 5 | 1500 | 7500 | 96 | 48 | 48 | 640 |  | 1 |  |  | None | Yes | PSL | 2021-11-15 | 2021-11-30 | 15 | Vessel 2021 | Vessel 2021 | 2022-02-01 | Air 2022 |  |  |  | 2022-11-26 |  | Yes | 2022-02-01 | 2022-11-26 | McMurdo | Winter 2022 | Outdoor
44 | 1.4 | Wood Crate | Deployment Weights 87 - 93 | 7 | 500 | 3500 | 36 | 24 | 24 | 84 | N | 1 |  |  | None | Yes | PSL | 2020-11-15 | 2020-11-30 | 15 | Vessel 2020 | Vessel 2020 | 2021-02-01 | Air 2021 |  |  |  | 2022-02-05 |  | Yes | 2021-02-01 | 2022-02-05 | McMurdo | Winter 2021 | Outdoor
45 | 1.4 | Steel Spool | Main Cable Assembly 87 | 1 | 15000 | 15000 | 93 | 95 | 93 | 475.4948 | TDY 9/11/19 | 1 |  |  | DNDF | No | MSU | 2021-09-15 | 2021-09-30 | 15 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2022-02-05 |  | Yes | 2022-02-05 | 2022-12-01 | South Pole | Winter 2022 | DNDF, min -40C
46 | 1.4 | Steel Spool | Main Cable Assembly 88 | 1 | 15000 | 15000 | 93 | 95 | 93 | 475.4948 | TDY 9/11/19 | 1 |  |  | DNDF | No | MSU | 2021-09-15 | 2021-09-30 | 15 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2022-02-05 |  | Yes | 2022-02-05 | 2022-12-01 | South Pole | Winter 2022 | DNDF, min -40C
47 | 1.4 | Steel Spool | Main Cable Assembly 89 | 1 | 15000 | 15000 | 93 | 95 | 93 | 475.4948 | TDY 9/11/19 | 1 |  |  | None | No | MSU | 2021-11-15 | 2021-11-30 | 15 | Vessel 2021 | Vessel 2021 | 2022-02-01 | Air 2022 |  |  |  | 2022-11-26 |  | Yes | 2022-02-01 | 2022-11-26 | McMurdo | Winter 2022 | Outdoor
48 | 1.4 | Steel Spool | Main Cable Assembly 90 | 1 | 15000 | 15000 | 93 | 95 | 93 | 475.4948 | TDY 9/11/19 | 1 |  |  | None | No | MSU | 2021-11-15 | 2021-11-30 | 15 | Vessel 2021 | Vessel 2021 | 2022-02-01 | Air 2022 |  |  |  | 2022-11-26 |  | Yes | 2022-02-01 | 2022-11-26 | McMurdo | Winter 2022 | Outdoor
49 | 1.4 | Steel Spool | Main Cable Assembly 91 | 1 | 15000 | 15000 | 93 | 95 | 93 | 475.4948 | TDY 9/11/19 | 1 |  |  | None | No | MSU | 2021-11-15 | 2021-11-30 | 15 | Vessel 2021 | Vessel 2021 | 2022-02-01 | Air 2022 |  |  |  | 2022-11-26 |  | Yes | 2022-02-01 | 2022-11-26 | McMurdo | Winter 2022 | Outdoor
50 | 1.4 | Steel Spool | Main Cable Assembly 92 | 1 | 15000 | 15000 | 93 | 95 | 93 | 475.4948 | TDY 9/11/19 | 1 |  |  | None | No | MSU | 2021-11-15 | 2021-11-30 | 15 | Vessel 2021 | Vessel 2021 | 2022-02-01 | Air 2022 |  |  |  | 2022-11-26 |  | Yes | 2022-02-01 | 2022-11-26 | McMurdo | Winter 2022 | Outdoor
51 | 1.4 | Steel Spool | Main Cable Assembly 93 | 1 | 15000 | 15000 | 93 | 95 | 93 | 475.4948 | TDY 9/11/19 | 1 |  |  | None | No | MSU | 2021-11-15 | 2021-11-30 | 15 | Vessel 2021 | Vessel 2021 | 2022-02-01 | Air 2022 |  |  |  | 2022-11-26 |  | Yes | 2022-02-01 | 2022-11-26 | McMurdo | Winter 2022 | Outdoor
52 | 1.4 | Wood Crate | Breakout Cable Assemblies 87 - 88 | 2 | 1000 | 2000 | 72 | 48 | 24 | 96 | TDY 6/6/19 | 1 |  |  | None | No | MSU | 2021-09-01 | 2021-09-16 | 15 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2022-02-05 |  | Yes | 2022-02-05 | 2022-12-01 | South Pole | Winter 2022 | Outdoor
53 | 1.4 | Wood Crate | Breakout Cable Assemblies 89 - 93 | 5 | 1000 | 5000 | 72 | 48 | 24 | 240 | TDY 6/6/19 | 1 |  |  | None | No | MSU | 2021-11-15 | 2021-11-30 | 15 | Vessel 2021 | Vessel 2021 | 2022-02-01 | Air 2022 |  |  |  | 2022-11-26 |  | Yes | 2022-02-01 | 2022-11-26 | McMurdo | Winter 2022 | Outdoor
54 | 1.4 | Wood Crate | Surface Cable Assemblies 87 - 93 | 7 | 1000 | 7000 | 72 | 72 | 72 | 1512 | TDY 6/6/19 | 1 |  |  | None | No | MSU | 2021-09-01 | 2021-09-16 | 15 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2021-11-20 |  | No |  |  | None | None | None
55 | 1.4 | Wood Crate | Surface Junction Boxes 87 - 93 | 2 | 1000 | 2000 | 96 | 48 | 48 | 256 | TDY 6/6/19 | 1 |  |  | None | No | MSU | 2021-09-01 | 2021-09-16 | 15 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2021-11-20 |  | No |  |  | None | None | None
56 | 1.3 | Cardboard overcarton | 111 + 17 spares mDOMs 87 - 88: overcartons of 8 units | 16 | 500 | 8000 | 40 | 48 | 46 | 817.7778 |  | 1 | 1 |  | DNF | No | DESY / MSU |  |  | 0 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2021-11-20 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated
57 | 1.3 | Cardboard overcarton | 78 + 18 spares D-Eggs 87 - 88: overcartons of 8 units | 12 | 250 | 3000 | 40 | 48 | 66 | 880 |  | 1 | 1 |  | DNF | No | Chiba |  |  | 0 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2021-11-20 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated
58 | 1.3 | Cardboard overcarton | 2 PDOMs + 3 Pencil Beams + 3 spares for 87 - 88: overcarton of 8 just like in Gen1 | 1 | 400 | 400 | 42 | 42 | 45 | 45.9375 |  | 1 | 1 |  | DNF | No | UW |  |  | 0 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2021-11-20 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated
59 | 1.3 | Wood Crate | 21 Special Devices of 7 types (excluding PDOMs and Pencil Beams) 87 - 88 | 3 | 250 | 750 | 42 | 48 | 66 | 231 |  | 1 | 1 |  | DNF | No | Various |  |  | 0 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2021-11-20 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | Winter 2022 | Indoor, Heated
60 | 1.5 | Cardboard overcarton | 17 + XX spares POCAMs 89 - 93 (TO BE UPDATED) | 7 | 200 | 1400 | 42 | 42 | 30 | 214.375 |  | 1 |  |  |  | No | Munich |  |  | 0 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2022-02-05 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | None
61 | 1.5 | Cardboard overcarton | 8 + XX spares Pencil Beams 89 - 93 (TO BE UPDATED) | 3 | 200 | 600 | 42 | 42 | 30 | 91.875 |  | 1 |  |  |  | No | UW | 2021-08-31 | 2021-09-16 | 16 | ComSur 2021 | C17-2021 | 2021-11-13 | Air 2021 |  |  |  | 2022-02-05 |  | Yes | 2021-11-13 | 2022-12-01 | South Pole | None
62 | 1.3 | Cardboard overcarton | 285 + 11 spares mDOMs 89 - 93 overcartons of 8 | 37 | 500 | 18500 | 48 | 48 | 36 | 1776 |  | 1 |  |  |  | No | DESY / MSU |  |  | 0 | ComSur 2022 | C17-2022 | 2022-11-10 | Air 2022 |  |  |  | 2022-11-19 |  | No |  |  |  | None
63 | 1.3 | Cardboard overcarton | 197 + 11 spares D-Eggs 89 - 93 overcartons of 8 | 26 | 500 | 13000 | 48 | 48 | 36 | 1248 |  | 1 |  |  |  | No | Chiba |  |  | 0 | ComSur 2022 | C17-2022 | 2022-11-10 | Air 2022 |  |  |  | 2022-11-19 |  | No |  |  |  | None
64 | 1.3 | Cardboard overcarton | 12 PDOMs 89-93 + 8 PBS overcartons of 8 (like Gen1) + 4 spares in total (TBD) | 3 | 400 | 1200 | 42 | 42 | 45 | 137.8125 |  | 1 |  |  |  | No | UW |  |  |  | ComSur 2022 | C17-2022 | 2022-11-10 | Air 2022 |  |  |  | 2022-11-19 |  | No |  |  |  | None
65 | 1.3 | Wood Crate | 58 Special Devices 89-93 (7 types, no PB, no pDOM) + 6 spares in total (TBD) overcartons or crates of 8 | 8 | 300 | 2400 | 42 | 42 | 36 | 294 |  | 1 |  |  |  | No | Various |  |  | 0 | ComSur 2022 | C17-2022 | 2022-11-10 | Air 2022 |  |  |  | 2022-11-19 |  | No |  |  |  | None
66 | 1.4 | Wood Crate | Field Hubs 87 - 93 | 1 | 2000 | 2000 | 96 | 48 | 48 | 128 | TDY 6/5/19 | 1 | 1 |  | DNF | No | DESY | 2022-09-01 | 2022-09-25 | 24 | ComSur 2022 | C17-2022 | 2022-11-10 | Air 2022 |  |  |  | 2022-11-19 |  | No |  |  |  |  | Indoor, Heated (ICL)
67 | 1.6 | Wood Crate | Miscellaneous Scientific Equipment | 2 | 1500 | 3000 | 48 | 48 | 48 | 128 | EKB - May 21 | 1 | 1 |  | DNF | No | UW |  |  | 0 | ComSur 2022 | C17-2022 | 2022-11-10 | Air 2022 |  |  |  | 2022-11-19 |  | No
68 | 1.6 | Wood Crate | Computing Infrastructure | 2 | 1100 | 2200 | 96 | 48 | 48 | 256 | EKB - May21 | 1 | 1 |  | DNF | No | UW |  |  | 0 | ComSur 2022 | C17-2022 | 2022-11-10 | Air 2022 |  |  |  | 2022-11-19 |  | No
69 | 1.2 | ISO Container | 20' Milvan Container (empty) | 1 | 4000 | 4000 | 240 | 96 | 96 | 1280 |  |  |  |  | None | Yes | ZCM | 2020-12-01 | -- | -- | -- | -- | -- | Traverse 2021 |  | 9 | SPOT2 | 2021-12-31 |  | Yes | 2020-02-01 | 2021-12-31 | McMurdo | Winter 2020/21 | Outdoor
70 | 1.2 | Loose Equip | Generator Hoods in ZCM (2x exhaust) (currently on UNL flat rack #2) -> move to ASC flatrack | 2 | 200 | 400 | 72 | 36 | 36 | 108 |  |  |  |  | None | Yes | ZCM | -- | -- | -- | -- | -- | -- | Traverse 2020 |  | 5 | SPOT1 | 2020-11-28 |  | Yes | 2020-02-01 | 2020-11-01 | McMurdo | Winter 2020 | Outdoor
71 | 1.2 | Loose Equip | Generator Hoods new (5x) | 5 | 300 | 1500 | 108 | 36 | 48 | 540 |  |  |  |  | None | Yes | UW | 2020-11-01 | 2020-11-11 | 10 | Vessel 2020 | Vessel 2020 | 2021-02-01 | Traverse 2021 |  | 4 | SPOT2 | 2021-12-31 |  | Yes | 2021-02-01 | 2021-12-31 | McMurdo | Winter 2021 | Outdoor
72 | 1.2 | Loose Equip | Independent Firn Drill (IFD) Sheave (in ZCM) | 1 | 920 | 920 | 97 | 44 | 63 | 155.6042 | TB 4/7/20 |  |  |  | None | No | ZCM | 2020-11-01 | -- | -- | -- | -- | -- | Traverse 2020 |  | 8 | SPOT1 | 2020-12-26 |  | Yes | 2020-02-01 | 2020-12-31 | McMurdo | Winter 2020 | Outdoor
73 | 1.2 | Wood Crate | Independent Firn Drill (IFD) Drillhead (in ZCM) | 1 | 1048 | 1048 | 125 | 33 | 37 | 88.3247 | TB 4/7/20 |  |  |  | None | No | ZCM | 2020-11-01 | -- | -- | -- | -- | -- | Traverse 2020 |  | 9 | SPOT1 | 2020-12-26 |  | Yes | 2020-02-01 | 2020-12-31 | McMurdo | Winter 2020 | Outdoor
74 | 1.2 | Wood Crate | Independent Firn Drill (IFD) DNF | 1 | 500 | 500 | 36 | 36 | 36 | 27 |  | 1 | 1 |  | DNF | No | UW | 2020-09-25 | 2020-10-05 | 10 | ComSur 2020 | C17-2020 | 2020-11-14 | Air 2020 |  |  |  | 2020-12-26 |  | No
75 | 1.2 | Loose Equip | TU-20 Shaft | 1 | 400 | 400 | 120 | 48 | 24 | 80 |  |  |  |  | None | Yes | UW | 2020-11-01 | 2020-11-11 | 10 | Vessel 2020 | Vessel 2020 | 2021-02-01 | Traverse 2021 |  | 10 | SPOT2 | 2021-12-31 |  | Yes | 2021-02-01 | 2021-12-31 | McMurdo | Winter 2021 | Outdoor
76 | 1.2 | Hartigg | Antarctic Rodwell Aparatus DNF | 1 | 400 | 400 | 36 | 36 | 36 | 27 |  | 1 | 1 |  | DNF | No | UW | 2020-09-25 | 2020-10-05 | 10 | ComSur 2020 | C17-2020 | 2020-11-14 | Air 2020 |  |  |  | 2020-12-31 |  | No
77 | 1.2 | Wood Crate | Antarctic Rodwell Aparatus Drillheads | 1 | 825 | 825 | 120 | 25 | 30 | 52.0833 |  |  |  |  | None | No | UW | 2020-09-25 | 2020-10-05 | 10 | ComSur 2020 | C17-2020 | 2020-11-14 | Air 2020 |  |  |  | 2020-12-31 |  | No
78 | 1.2 | Secure Equip | Antarctic Rodwell Aparatus White Generator | 1 | 3000 | 3000 | 168 | 96 | 96 | 896 |  |  |  |  | None | No | UW | 2020-09-25 | 2020-10-05 | 10 | ComSur 2020 | C17-2020 | 2020-11-14 | Air 2020 |  |  |  | 2020-12-31 |  | No
79 | 1.2 | Wood Crate | Antarctic Rodwell Aparatus Crate | 1 | 2500 | 2500 | 96 | 48 | 48 | 128 |  |  |  |  | None | Yes | UW | 2020-09-25 | 2020-10-05 | 10 | ComSur 2020 | C17-2020 | 2020-11-14 | Air 2020 |  |  |  | 2020-12-31 |  | No
80 | 1.2 | Pallet | Fall Restraints | 1 | 1500 | 1500 | 96 | 48 | 48 | 128 |  |  |  |  | None | Yes | UW | 2020-09-25 | 2020-10-05 | 10 | ComSur 2020 | C17-2020 | 2020-11-14 | Air 2020 |  |  |  | 2020-11-21 |  | No
81 | 1.2 | Pallet | 20' Skis (5x sets) - stack onto Generator buildings | 1 | 1000 | 1000 | 240 | 96 | 48 | 640 |  |  |  |  | None | Yes | UW | 2020-08-30 | 2020-09-14 | 15 | ComSur 2020 | C17-2020 | 2020-11-01 | Traverse 2020 |  | 6 | SPOT1 | 2020-11-28 |  | No
82 | 1.2 | Loose Equip | 287B Forks | 1 | 400 | 400 | 72 | 77 | 36 | 115.5 | TB 4/7/20 |  |  |  | None | Yes | UW | 2020-09-25 | 2020-10-05 | 10 | ComSur 2020 | C17-2020 | 2020-11-14 | Air 2020 |  |  |  | 2020-12-31 |  | No
83 | 1.2 | ISO Container | DOM Handling Facility (DHF) | 1 | 12000 | 12000 | 240 | 96 | 96 | 1280 |  |  |  |  | None | Yes | UW | 2020-11-01 | 2020-11-11 | 10 | Vessel 2020 | Vessel 2020 | 2021-02-01 | Traverse 2021 |  | 5 | SPOT2 | 2021-12-31 |  | Yes | 2021-02-01 | 2021-12-31 | McMurdo | Winter 2021 | Outdoor
84 | 1.2 | Pallet | DOM Sleds (2x) | 1 | 1000 | 1000 | 240 | 96 | 24 | 320 |  |  |  |  | None | Yes | UW | 2020-11-01 | 2020-11-11 | 10 | Vessel 2020 | Vessel 2020 | 2021-02-01 | Traverse 2021 |  | 6 | SPOT2 | 2021-12-31 |  | Yes | 2021-02-01 | 2021-12-31 | McMurdo | Winter 2021 | Outdoor
85 | 1.2 | Mini Milvan | Repair/Replacement Parts (2020/21), MHP, PHS, Pumps, MDS parts, | 2 | 4000 | 8000 | 96 | 96 | 96 | 1024 |  |  |  |  | None | Yes | PSL | 2020-09-25 | 2020-10-05 | 10 | ComSur 2020 | C17-2020 | 2020-11-14 | Air 2020 |  |  |  | 2020-11-21 |  | No
|  |  | TOTAL by AIR to NPX via Herc | 215 |  | 321175 |  |  |  | 24073.4913
|  |  | TOTAL by TRAVERSE to NPX via SPoT2, SPoT3 or Science | 26 |  | 162040 |  |  |  | 15812.9566
|  |  | GRAND TOTAL | 241 |  | 483215 |  |  |  | 39886.4479
Change Log:
1. Changed all instrumentation to air between McMurdo and Pole. Keep it simple. Hutch 6/4/19
2. Added Storage requirements columns. Hutch 6/5/19
3. Changed Gen3 and PDM transport method from Traverse to Air 2020, also changed ROS to earlier. Hutch 11/20/19
4. Added 2 UNL Flat Racks (40' and 20') for traversing IceCube equipment to NPX in 2020. Hutch 11/20/219
5. Added UNL - HPU#2 (40' container). Hutch 11/20/19
6. Reworked all Implementation cargo. Hutch 2/7/20
7. Complete rework of all Implementation cargo, added items 70-84. Benson 4/8/2020
8. Had to swap color coding of ship method (blue <-> green) to match now established TraverseDetails tab. Benson 4/8/2020
9. More adjustments to implementation cargo, mainly traverse items. Benson 4/8/2020
10. Reduced ID#3 qty from 6 to 4, added ID#85 qty 2. Flagged red until updated in 20/21 SIP - unflag when SIP updated. Benson 4/15/2020 (unflagged Benson 4/23)
11. Updated drill hose logistics (ID#40&41)

## TraverseDetails
TRAVERSE (ONLY) DETAILS
2020-04-08
Postion = 40'
(X) = backup plan
[5 empty] | 2020-2021 | [10 empty] | 2021-2022
ID From All Cargo to NPX tab | Item | 2020 Location | Priority |  | LC130 | TRAVERSE | [9 empty] | LC130 | TRAVERSE
[6 empty] | SPOT 1 |  |  |  | SPOT 2 |  |  | SPOT 3 |  |  |  | SPOT 1 |  |  | SPOT 2 |  |  | SPOT 3
[6 empty] | Position 1 | Position 2 | Position 3 | Position 4 | Position 1 | Position 2 | Position 3 | Position 1 | Position 2 | Position 3 |  | Position 1 | Position 2 | Position 3 | Position 1 | Position 2 | Position 3 | Position 1 | Position 2 | Position 3
8 | Generator 2 | McM | 1 | on UNL flatrack 1 with ISO2. Need to move onto ASC flatrack. Needs alum skis @ NPX |  | X
5 | Generator 1 | McM | 2 | Need to move onto ASC flatrack. Needs alum skis @ NPX. |  | X
9 | Generator 3 | McM | 3 | on UNL flatrack 1 with ISO2. Need to move onto ASC flatrack. Needs alum skis @ NPX |  |  | X
15 | Fuel Tower Day Tank | McM | 4 | on UNL flatrack 2 with ISO2, bolted and strappped, 1/2 full. Need to move onto ASC flatrack |  |  | X
70 | Gen Hoods in ZCM (2x exhaust) | McM | 5 | on UNL flatrack 2 with ISO2. Need to move onto ASC flatrack. |  |  | X
81 | 20' Skis (5x sets) | PSL | 6 | Need to arrive before or with Generators, STACK on top of generators |  | X | X
19 | Independent Firn Drill (IFD) | McM | 7 | Need to move onto ASC flatrack. Herc = waiver? |  |  |  | X
72 | IFD Sheave | McM | 8 | Need to move onto ASC flatrack |  |  |  | X
73 | IFD Head | McM | 9 | Need to move onto ASC flatrack |  |  |  | X
11 | HPU1 (UNL) | McM | 10 | Repair needed at ZCM (2020). Already on ISO2-C |  |  |  |  | X
34 | Main Drill Cable Reel (MDCR) | PSL | 1 | Large heavy winch | [15 empty] | X
36 | Return Water Cable Reel | PSL | 2 | Large heavy winch | [15 empty] | X
18 | Cable Tensioner (Bull Wheel) | PSL | 3 | Large heavy winch | [15 empty] | X
71 | Gen Hoods NEW (5x) | PSL | 4 | Put some Gen Hoods and TU20 shaft inside empty milvan (ID 69) | [16 empty] | X
83 | DOM Handling Facility (DHF) | PSL | 5 | 20' MECC-style (for now) - on 2020/21 vessel, 21/22 traverse | [17 empty] | X
84 | DOM sleds (2x) | PSL | 6 | Needed at Pole 21/22 | [17 empty] | X
35 | Drill cable (spare) | PSL | 7 | Large wooden spool | [15 empty] | X
37 | Spare Combo Cable | PSL | 8 | Large wooden spool | [15 empty] | X
69 | 20' Milvan Container (empty) | McM | 9 | Put some Gen Hoods (ID 71) inside | [16 empty] | X
75 | TU20 Shaft | PSL | 10 | Long pallet, put inside empty milvan (ID 69) | [16 empty] | X
7 | UNL Flatrack 1 with ISO2 | McM |  | Stack with Flatrack 2 + 2sets ISO2. Reassessing need at Pole
14 | UNL Flatrack 2 with ISO2 | McM |  | Stack with Flatrack 1 + 2sets ISO2. Reassessing need at Pole
12 | HPU2 (UNL) | McM |  | Repair needed at ZCM (?), put on ISO3 to traverse DO NOT LIFT. Maybe extract heaters and leave container
10 | RCU (UNL) | McM |  | Repair needed at ZCM (?), put on ISO3 to traverse. Reassessing need at Pole