## 19_20
Count | Event # | Name | E-Mail address | Broad Support Type | Role / details | Background | Institution | First timer? | Labor Type | Ticket Type | Pipeline - PQ Packet Sent | Current SIP - PQ Status | Pipeline - CHC to ZCM | Arrival at Pole (depends on Herc) | Departure from Pole (depends on Herc) | Pipeline - ZCM to CHC | Days at Pole | Comments
1 | A-333-S | John Kelley | jkelley@icecube.wisc.edu | M&O | M&O Lead / FieldHub upgrade, assorted tasks | Scientist | UW-Madison | No | M&O | Comm | 2019-05-09 | 2020-08-16 | 2019-12-16 | 2019-12-17 | 2020-01-04 | 2020-01-06 | 18
2 | A-333-S | Matt Kauer | mkauer@icecube.wisc.edu | M&O | Scintillator Lead / panel refurb | Scientist | UW-Madison | No | M&O | Comm | 2019-05-09 | 2020-09-11 | 2019-12-30 | 2019-12-31 | 2020-01-30 | 2020-01-31 | 30
3 | A-333-S | Frank Schroeder | fgs@udel.edu | M&O | Radio SME / panel refurb | Scientist | U-Delaware | Yes | M&O | Self | 2019-05-13 | 2020-10-22 | 2020-01-07 | 2020-01-08 | 2020-01-30 | 2020-01-31 | 22
4 | A-333-S | Ralf Auer | rauer@icecube.wisc.edu | M&O | WO Mgr / assorted tasks | Prof | UW-Madison | No | M&O | Comm | 2019-05-09 | 2020-06-26 | 2019-11-06 | 2019-11-07 | 2020-01-04 | 2020-01-06 | 58
5 | A-333-S | Anna Pollmann | anna.pollmann@uni-wuppertal.de | M&O | SpiceCORE2 | Postdoc | Wuppertal | No | M&O | Self | 2019-05-09 | 2020-09-06 | 2019-11-18 | 2019-11-19 | 2019-12-16 | 2019-12-17 | 27
6 | A-333-S | Andrew Shultz | andjshultz@gmail.com | M&O | SpiceCORE3 | Student | Kansas | Yes | M&O | Comm | 2019-07-17 | 2020-10-24 | 2019-11-25 | 2019-11-26 | 2019-12-19 | 2019-12-20 | 23
7 | A-333-S | Dave Glowacki | dglo@icecube.wisc.edu | M&O | DAQ SME / WO support | Prof | UW-Madison | No | M&O | Comm | 2019-07-08 | 2019-12-15 | 2019-11-11 | 2019-11-12 | 2019-11-28 | 2019-11-29 | 16
8 | A-333-S | Jim Koehler | koehlerdesignworks@gmail.com | M&O | IDDO SpiceCORE1 Lead | Prof | IDDO | No | M&O | Comm | 2019-06-20 | 2020-09-26 | 2019-11-18 | 2019-11-19 | 2019-12-19 | 2019-12-20 | 30
9 | A-333-S | Matthias Plum | matthias.plum@icecube.wisc.edu | M&O | IceACT Lead | Postdoc | Marquette | Yes | M&O | Comm | 2019-07-09 | 2020-09-23 | 2020-01-07 | 2020-01-08 | 2020-01-30 | 2020-01-31 | 22
10 | A-333-S | Chris Tung | ctung6@gatech.edu | M&O | Helper1 / DOMHub, calibration | Student | Georgia Tech | Yes | M&O | Comm | 2019-07-11 |  | 2019-12-16 | 2019-12-17 | 2020-01-04 | 2020-01-06 | 18 | John's partner
11 | A-333-S | Marie Oehler | marie.oehler@kit.edu | M&O | Helper2 / IceACT, Scint support | Student | KIT | Yes | M&O | Self | 2019-07-10 | 2020-10-17 | 2020-01-07 | 2020-01-08 | 2020-01-30 | 2020-01-31 | 22 | Matt's partner
12 | A-333-S | Jannes Brostean-Kaiser | jannes@physik.hu-berlin.de | M&O | SpiceCORE4 | Student | DESY Zeuthen | Yes | M&O | Self | 2019-07-17 | 2020-10-18 | 2019-11-18 | 2019-11-19 | 2019-12-16 | 2019-12-17 | 27
13 | A-333-S | Steve Sclafani | steve.sclafani@icecube.wisc.edu | M&O | Helper3 / Server replacement | Student | Drexel | Yes | M&O | Self | 2019-07-10 | 2020-08-13 | 2019-11-11 | 2019-11-12 | 2019-12-10 | 2019-12-11 | 28 | Ralf's partner
14 | A-333-S | Yuya Makino | ymakino@icecube.wisc.edu | M&O | Winterover1 | Prof | UW-Madison | Yes | M&O | Comm | 2019-02-22 | 2020-08-21 | 2019-11-04 | 2019-11-05 | 2020-10-31 | 2020-11-01 | 361
15 | A-333-S | John Hardin | john.hardin@icecube.wisc.edu | M&O | Winterover2 | Prof | UW-Madison | Yes | M&O | Comm | 2019-02-25 | 2020-05-23 | 2019-11-04 | 2019-11-05 | 2020-10-31 | 2020-11-01 | 361
16 | A-333-S | Jocelyn Argueta |  | M&O | PolarTREC teacher | Prof | UW - River Falls | Yes | M&O | Comm | 2019-07-25 | 2020-09-24 | 2019-11-28 | 2019-11-30 | 2019-12-27 | 2019-12-28 | 27
1 | A-334-S (ZCM and NPX) | Dennis Duling | dulingde@yahoo.com | Drilling | Drill Lead1 | Prof | UW-Madison | No | Project | Comm | 2019-05-10 | 2020-09-17 | 2019-10-23 | 2019-10-24 | 2020-01-30 | 2020-01-31 | 98 | Dennis & Barb work with Rick Abrams & Darrell in McMurdo on Generators (most of November)
2 | A-334-S | Mike Zernick | mzernick@icecube.wisc.edu | Mgmt&Safety | Quality & Safety Mgr2a | Prof | UW-Madison | No | Project | Comm | 2019-05-14 | 2020-10-22 | 2019-11-18 | 2019-11-19 | 2019-12-12 | 2019-12-13 | 23 | 1st 1/2 season, split with Barb
3 | A-334-S | Barb Birrittella | bbirrittella@wisc.edu | Drilling | Driller2b | Prof | UW-Madison | No | Project | Comm | 2019-05-10 | 2020-09-04 | 2019-11-06 | 2019-11-07 | 2019-12-19 | 2019-12-20 | 42 | 2nd 1/2 season, split with Mike (in McMurdo Nov 3-Dec-3)
4 | A-334-S | Delia Tosi | detosi@icecube.wisc.edu | Drilling | Driller3a | Prof | UW-Madison | No | Project | Comm | 2019-05-14 | 2020-08-07 | 2019-11-25 | 2019-11-26 | 2020-01-04 | 2020-01-06 | 39 | 1st 1/2 season, split with Andy
5 | A-334-S | Andy Laundrie | awlaundrie@wisc.edu | Drilling | Driller3b | Prof | UW-Madison | No | Project | Comm | 2019-05-10 | 2020-09-20 | 2019-12-16 | 2019-12-17 | 2020-01-30 | 2020-01-31 | 44 | 2nd 1/2 season, split w/Delia
6 | A-334-S | Kael Hanson | kael.hanson@icecube.wisc.edu | Mgmt&Safety | PI4a | Prof | UW-Madison | No | Project | Comm | 2019-05-10 | 2020-10-25 | 2019-11-13 | 2019-11-14 | 2019-12-02 | 2019-12-03 | 18 | 1st 1/2 sessaon
7 | A-334-S | Paul Wisneiwski | pawnipi@gmail.com | Drilling | Driller4b | Prof | UW-Madison | No | Project | Comm | 2019-05-16 | 2020-08-19 | 2019-12-16 | 2019-12-17 | 2020-01-30 | 2020-01-31 | 44 | 2nd 1/2 season, split with TBA1
8 | A-334-S | TBD |  |  | Driller5 | [5 empty] | 2019-05-14 |  | 2019-11-13 | 2019-11-14 | 2020-01-30 | 2020-01-31 | 77
9 | A-334-S | Dar Gibson | dargibson@yahoo.com | Drilling | Driller6 | Prof | UW-Madison | No | Project | Comm | 2019-05-10 | 2020-09-25 | 2019-11-13 | 2019-11-14 | 2020-01-30 | 2020-01-31 | 77 | Full season
10 | A-334-S | Graham Roberts | cm3h2o@gmail.com | Drilling | Driller7 | Prof | UW-Madison | Yes | Project | Comm | 2019-05-10 | 2020-09-25 | 2019-11-18 | 2019-11-19 | 2020-01-30 | 2020-01-31 | 72 | Full season (sent request to ASC for CHC-ZCM date of 10/30; His ZCM-NPX date stays the same).
11 | A-334-S | Lexi Oxborough (PSL) | oxborough@wisc.edu | Drilling | Driller8b | Prof | UW-Madison | Yes | Project | Comm | 2019-07-22 | 2020-09-16 | 2019-12-16 | 2019-12-17 | 2020-01-30 | 2020-01-31 | 44 | 2nd 1/2 season
12 | A-334-S | Jacob Nesbit (PSL) | jnesbit@wisc.edu | Drilling | Driller9 | Prof | UW-Madison | Yes | Project | Comm | 2019-07-03 | 2020-09-11 | 2019-11-18 | 2019-11-19 | 2020-01-30 | 2020-01-31 | 72 | Full season
13 | A-334-S | Jeanne Edwards (PSL) | jeanne.edwards@icecube.wisc.edu | Drilling | Driller10b | Prof | UW-Madison | No | Project | Comm | 2019-07-10 | 2020-10-21 | 2019-12-16 | 2019-12-17 | 2020-01-30 | 2020-01-31 | 44 | 2nd 1/2 season
14 | A-334-S | Ase Torgilsson | ase.tor.4791@gmail.com | Drilling | Driller11 | Prof | UW-Madison | Yes | Project | Comm | [6 empty] | 0 | Requested On-Ice Nov 18, Off-Ice Jan 7
15 | A-334-S | Erik Ejdepalm | erik.ejdepalm@protonmail.com | Drilling | Driller12 | Prof | Uppsala | Yes | In-kind | Self-Ticket | 2019-07-02 |  | 2019-11-13 | 2019-11-14 | 2020-01-30 | 2020-01-31 | 77 | Full season - from Sweden
16 | A-334-S (ZCM only) | Richard Abrams | abramsrichard22@yahoo.com | Drilling | Generator Rehab | Prof | UW-Madison | No | Project | Comm | 2019-05-23 | 2020-10-24 | 2019-11-06 | 2019-11-07 | 2019-12-12 | 2019-12-13 | 35 | McMurdo only!
17 | A-334-S (ZCM only) | Darrell Hamilton | dhamilton@psl.wisc.edu | Drilling | Generator Rehab | Prof | UW-Madison | No | Project | Comm | 2019-05-10 | 2020-10-24 | 2019-11-06 | 2019-11-07 | 2019-12-12 | 2019-12-13 | 35 | McMurdo only!
18 | A-334-M (ZCM only) | Brent Folmer (electrician sub-contractor) | bfolmer@westphalec.com | Drilling | Generator Rehab | Prof | UW-Madison | No | Project | Comm |  | 2020-10-25 | [5 empty] | McMurdo only!
19 | A-334-S | James Roth | roth@bartol.udel.edu | Drilling | Driller 8a | Prof | U-Delaware | No | Project | Comm | [7 empty] | Requested 11/18 - 12/20 (change to 12/16)
|  | Notes and Change Log: |  |  | Backups: |  |  |  | 333 Pipeline report date> | 081319 |  | PQ Status: Date = PQ'ed, empty = not PQ'ed
|  | 1. Labor types are Project, In-kind, M&O |  |  | Sebastián Sánchez Herrera (MSU) | sanch373@msu.edu |  |  | 334 Pipeline report date> | 073119
|  | 2. Ticket types are Comm (ASC supplied, NSF sponsored) or Self (institution supplied) |  |  | Ase Torgilsson, Driller (Uppsala) | ase.tor.4791@gmail.com
|  | 3. Backgrounds are Student, Post-doc, Scientist or Professional |  |  | Tom Hutchings, Manager (UW) | hutch@icecube.wisc.edu
|  | 4. JK 5/21/19: fill in M&O SMEs, WOs, SPICECore4 is SME not helper |  |  | Terry Benson, Engineer (UW) | tbenson@psl.wisc.edu
|  | 5. TH 5/23 - Added arrival/departure dates for drill team |  |  | Xu Zhai, Engineer/Driller (UW) | xzhai@wisc.edu
|  | 6. TH 5/23 - Replaced Darrell with Delia Tosi, changed dates |  |  | Michel Kluger, WO
|  | 7. TH 5/23 - Replaced TBA2 w/Lexi Oxborough |  |  | Lance Riley, WO |  | PQ'ed 5/21/20
8. TH 5/23 - Replaced TBA3 w/Jacob Nesbit
9. TH 5/23 - Replaced TBA4 w/Jeanne Edwards
10. JK 6/19: Added helpers (Oehler, Tung, and Sclafani, backup Sanchez)
11. JK 6/19: Added M&O e-mail addresses
12. JK 6/19: Fix spelling of A. Shultz
13. TH 6/20: Replaced TBD6 with Erik Ejdepalm (driller)
14. TH 6/20: Added "backup driller" Ase
15. JH 6/26: Changed TBD2 departure to Dec 20 from Dec 16
16. TH 6/26: Added email addresses
17. JH 7/4: Added Jim Koehler (IDDO)
18. JH 7/16: Sync'ed with Pipeline, added some new columns
19. JH 7/18: Sync'ed with Pipeline report date of 071619, added Abrams and Hanson (TBA1) to 334
20. TH 7/18: Added alts, added Darrell for ZCM,
21. JH 8/1: Sync'ed with Pipeline. Added Jocelyn as primary, Michel and Lance as WO backups.
22. JK 8/6: Add Hardin and Hanson e-mails
23. JH 8/7: Adjusted Pole arrival/departure dates
24. JH 8/14: Adjusted Sclafani to match new Pipeline dates
25. JH 8/20: Synced to Pipeline for 333, synced PQ status to PolarICE
26. JH 8/28: PQ sync for 333 in preparation for Readiness Review
27. TH 9/10: Added Brent Folmer to McMurdo team
28. TH 9/13: Added James Roth as 8a - 1st 1/2 season at NPX
29. TH 9/18: Added Ase Torgilsson (Swede) (req 11/18 - 01/06)
30. TH 9/23: Removed Jonas Kalin from on-ice plan (communicated to ASC 9/19)
31. JK 9/30: Removed Shultz comment about A-340, not relevant any more
32. JH 10/09: Updated PQ status
33. JH 10/29: Updated PQ status
Formulas:
Arrival at Pole (depends on Herc) = [Pipeline - CHC to ZCM]+1
Departure from Pole (depends on Herc) = [Pipeline - ZCM to CHC]-1

## 21_22
Count | Name | Broad Support Type | Get to Dedicated 8 deployers in this column | Role | Background | Institution | First timer? | Labor Type | Ticket Type | Day Shift | Night Shift | Arrival | Departure | Comments
1 | Albrecht Karle | Mgmt&Safety |  | On-Ice Lead | Prof | UW-Madison | No | In-kind | Comm | 1 |  | early | late | could split season with another person TBD
2 | Mike Zernick | Mgmt&Safety |  | Quality & Safety Mgr | Prof | UW-Madison | No | Proj full | Comm | 1 |  | early | late
3 | Tom Hutchings | Mgmt&Safety |  | Drill and Install Mgr | Prof | UW-Madison | No | Proj full | Comm | 1 |  | early | late
4 | Delia Tosi | Deployment | D1, Overall install lead | String Install Lead Day | Scientist | UW-Madison | No | Proj seasonal | Comm | 1 |  | early | late
5 | TBD1 | Deployment | D2, Senior person | String Installer | Scientist |  |  | In-kind |  | 1
6 | TBD2 | Deployment | D3 | String Installer + SME |  | Chiba |  | In-kind | Self | 1
7 | TBD3 | Deployment | D4 | String Installer + SME |  | DESY |  | In-kind | Self | 1
8 | TBD4 | Deployment | D5 | String Installer | Student |  |  | In-kind |  | 1
9 | Gary Hill | Deployment | N1, Senior person | String Install Lead Night | Scientist | Adelade |  | In-kind | Self |  | 1
10 | TBD5 | Deployment | N2 | String Installer + SME |  | Chiba |  | In-kind | Self |  | 1
11 | TBD6 | Deployment | N3 | String Installer + SME |  | MSU |  | In-kind | Comm |  | 1
12 | TBD7 | Deployment | N4 | String Installer | Student |  |  | In-kind |  |  | 1
13 | TBD8 | Deployment | N5 | String Installer | Student |  |  | In-kind |  |  | 1
14 | John Kelley | Other | D6 | IDF / ICL / M&O Lead | Prof | UW-Madison | No | M&O | Comm | 1 |  |  |  | Split with Ty DeYoung?
15 | Perry Sandstrom | Other | D6 | Project Engineer | Prof | UW-Madison | No | M&O | Comm | 1
16 | Chris Ng | Other | D6 | SME - Engineer | Prof | MSU | Yes | Proj full | Comm | 1 |  |  |  | Could split season with Brian Ferguson
17 | Ralf Auer / TBD9 | Other |  | SME - M&O / C&V |  | UW-Madison / TBD | No | M&O | Comm | 1
18 | TBD10 | Other |  | SME - Cal / M&O |  |  |  | M&O |  |  | 1 |  |  | Could be N6
19 | TBD11 | Other |  | SME - Cal / M&O |  |  |  | M&O |  |  | 1 |  |  | Could be N6
20 | TBD12 | Other |  | Winterover | Prof | UW-Madison |  | M&O |  | 1
21 | TBD13 | Other |  | Winterover | Prof | UW-Madison |  | M&O |  |  | 1
22 | Dennis Duling | Drilling |  | Drill Lead + Shift 1 Lead | Prof | UW-Madison | No | Proj full | Comm | 1
23 | TBD14 | Drilling |  | Shift 1 Deputy Drill Lead | Prof |  |  | Proj full
24 | TBD15 | Drilling |  | Shift 1 Driller |  |  |  | Proj seasonal
25 | TBD16 | Drilling |  | Shift 1 Driller |  |  |  | Proj seasonal
26 | TBD17 | Drilling |  | Shift 1 Driller |  |  |  | Proj seasonal
27 | TBD18 | Drilling |  | Shift 1 Driller |  |  |  | In-kind
28 | TBD19 | Drilling |  | Shift 1 Driller |  |  |  | In-kind
29 | TBD20 | Drilling |  | Shift 1 Driller |  |  |  | In-kind | Self
30 | TBD21 | Drilling | D7 | Shift 1 Driller |  |  |  | In-kind | Self
31 | TBD22 | Drilling | D8 | Shift 1 Driller |  |  |  | In-kind | Self
32 | TBD23 | Drilling |  | Shift 2 Drill Lead | Prof | UW-Madison |  | Proj full
33 | TBD24 | Drilling |  | Shift 2 Deputy Drill Lead | Prof | UW-Madison |  | Proj full
34 | TBD25 | Drilling |  | Shift 2 Driller |  |  |  | Proj full
35 | TBD26 | Drilling |  | Shift 2 Driller |  |  |  | Proj seasonal
36 | TBD27 | Drilling |  | Shift 2 Driller |  |  |  | Proj seasonal
37 | TBD28 | Drilling |  | Shift 2 Driller |  |  |  | In-kind
38 | TBD29 | Drilling |  | Shift 2 Driller |  |  |  | In-kind
39 | TBD30 | Drilling | N6 | Shift 2 Driller |  |  |  | In-kind | Self
40 | TBD31 | Drilling | N7 | Shift 2 Driller |  |  |  | In-kind | Self
41 | TBD32 | Drilling | N8 | Shift 2 Driller |  |  |  | In-kind | Self
42 | TBD33 | Drilling |  | Shift 3 Drill Lead | Prof | UW-Madison |  | Proj full
43 | TBD34 | Drilling |  | Shift 3 Deputy Drill Lead | Prof | UW-Madison |  | Proj full
44 | TBD35 | Drilling |  | Shift 3 Driller |  |  |  | Proj seasonal
45 | TBD36 | Drilling |  | Shift 3 Driller |  |  |  | Proj seasonal
46 | TBD37 | Drilling |  | Shift 3 Driller |  |  |  | Proj seasonal
47 | TBD38 | Drilling |  | Shift 3 Driller |  |  |  | In-kind
48 | TBD39 | Drilling |  | Shift 3 Driller |  |  |  | In-kind
49 | TBD40 | Drilling | N6 | Shift 3 Driller |  |  |  | In-kind | Self
50 | TBD41 | Drilling | N7 | Shift 3 Driller |  |  |  | In-kind | Self
51 | TBD42 | Drilling | N8 | Shift 3 Driller |  |  |  | In-kind | Self
Notes:
1. Labor types are Proj full, Proj seasonal, In-kind, M&O
2. Ticket types are Comm (ASC supplied, NSF sponsored) or Self (institution supplied)
3. Backgrounds are Student, Post-doc, Scientist or Professional
Note on I17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I'd say Proj full Reply: OK, I'll change it, we could then pick another person for the M&O designator Reply: or have 7 getting their paychecks via M&O contract
Not done, do not look

## 22_23
Count | Name | Broad Support Type | Get to Dedicated 8 deployers in this column | Role | Background | Institution | First timer? | Labor Type | Ticket Type | Day Shift | Night Shift | Arrival | Departure | Comments
1 | Albrecht Karle | Mgmt&Safety |  | On-Ice Lead | Prof | UW-Madison | No | In-kind | Comm | 1 |  | early | late | could split season with another person TBD
2 | Mike Zernick | Mgmt&Safety |  | Quality & Safety Mgr | Prof | UW-Madison | No | Project | Comm | 1 |  | early | late
3 | Tom Hutchings | Mgmt&Safety |  | Drill and Install Mgr | Prof | UW-Madison | No | Project | Comm | 1 |  | early | late
4 | Delia Tosi | Deployment | D1, Overall install lead | String Install Lead Day | Scientist | UW-Madison | No | Project | Comm | 1 |  | early | late
5 | TBD1 | Deployment | D2, Senior person | String Installer | Scientist |  |  | In-kind |  | 1
6 | TBD2 | Deployment | D3 | String Installer + SME |  | Chiba |  | In-kind | Self | 1
7 | TBD3 | Deployment | D4 | String Installer + SME |  | DESY |  | In-kind | Self | 1
8 | TBD4 | Deployment | D5 | String Installer | Student |  |  | In-kind |  | 1
9 | Gary Hill | Deployment | N1, Senior person | String Install Lead Night | Scientist | Adelade |  | In-kind | Self |  | 1
10 | TBD5 | Deployment | N2 | String Installer + SME |  | Chiba |  | In-kind | Self |  | 1
11 | TBD6 | Deployment | N3 | String Installer + SME |  | MSU |  | In-kind | Comm |  | 1
12 | TBD7 | Deployment | N4 | String Installer | Student |  |  | In-kind |  |  | 1
13 | TBD8 | Deployment | N5 | String Installer | Student |  |  | In-kind |  |  | 1
14 | John Kelley | Other |  | IDF / ICL / M&O Lead | Prof | UW-Madison | No | M&O | Comm | 1 |  |  |  | Split with Ty DeYoung?
15 | Perry Sandstrom | Other |  | Project Engineer | Prof | UW-Madison | No | M&O | Comm | 1
16 | Chris Ng | Other |  | SME - Engineer | Prof | MSU | Yes | Project | Comm | 1 |  |  |  | Could split season with Brian Ferguson
17 | Ralf Auer / TBD9 | Other |  | SME - M&O only |  | UW-Madison / TBD | No | M&O | Comm | 1
18 | TBD10 | Other |  | SME - Cal / M&O |  |  |  | M&O |  |  | 1 |  |  | Could be N6
19 | TBD11 | Other |  | SME - Cal / M&O |  |  |  | M&O |  |  | 1 |  |  | Could be N6
20 | TBD12 | Other |  | Winterover | Prof | UW-Madison |  | M&O |  | 1
21 | TBD13 | Other |  | Winterover | Prof | UW-Madison |  | M&O |  |  | 1
22 | Dennis Duling | Drilling |  | Drill Lead + Shift 1 Lead | Prof | UW-Madison | No | Project | Comm | 1
23 | TBD14 | Drilling |  | Shift 1 Deputy Drill Lead | Prof |  |  | Project
24 | TBD15 | Drilling |  | Shift 1 Driller |  |  |  | Project
25 | TBD16 | Drilling |  | Shift 1 Driller |  |  |  | Project
26 | TBD17 | Drilling |  | Shift 1 Driller |  |  |  | Project
27 | TBD18 | Drilling |  | Shift 1 Driller |  |  |  | In-kind
28 | TBD19 | Drilling |  | Shift 1 Driller |  |  |  | In-kind
29 | TBD20 | Drilling | D6 | Shift 1 Driller |  |  |  | In-kind | Self
30 | TBD21 | Drilling | D7 | Shift 1 Driller |  |  |  | In-kind | Self
31 | TBD22 | Drilling | D8 | Shift 1 Driller |  |  |  | In-kind | Self
32 | TBD23 | Drilling |  | Shift 2 Drill Lead | Prof | UW-Madison |  | Project
33 | TBD24 | Drilling |  | Shift 2 Deputy Drill Lead | Prof | UW-Madison |  | Project
34 | TBD25 | Drilling |  | Shift 2 Driller |  |  |  | Project
35 | TBD26 | Drilling |  | Shift 2 Driller |  |  |  | Project
36 | TBD27 | Drilling |  | Shift 2 Driller |  |  |  | Project
37 | TBD28 | Drilling |  | Shift 2 Driller |  |  |  | In-kind
38 | TBD29 | Drilling |  | Shift 2 Driller |  |  |  | In-kind
39 | TBD30 | Drilling | N6 | Shift 2 Driller |  |  |  | In-kind | Self
40 | TBD31 | Drilling | N7 | Shift 2 Driller |  |  |  | In-kind | Self
41 | TBD32 | Drilling | N8 | Shift 2 Driller |  |  |  | In-kind | Self
42 | TBD33 | Drilling |  | Shift 3 Drill Lead | Prof | UW-Madison |  | Project
43 | TBD34 | Drilling |  | Shift 3 Deputy Drill Lead | Prof | UW-Madison |  | Project
44 | TBD35 | Drilling |  | Shift 3 Driller |  |  |  | Project
45 | TBD36 | Drilling |  | Shift 3 Driller |  |  |  | Project
46 | TBD37 | Drilling |  | Shift 3 Driller |  |  |  | Project
47 | TBD38 | Drilling |  | Shift 3 Driller |  |  |  | In-kind
48 | TBD39 | Drilling |  | Shift 3 Driller |  |  |  | In-kind
49 | TBD40 | Drilling | N6 | Shift 3 Driller |  |  |  | In-kind | Self
50 | TBD41 | Drilling | N7 | Shift 3 Driller |  |  |  | In-kind | Self
51 | TBD42 | Drilling | N8 | Shift 3 Driller |  |  |  | In-kind | Self
Notes:
1. Labor types are Project, Project, In-kind, M&O
2. Ticket types are Comm (ASC supplied, NSF sponsored) or Self (institution supplied)
3. Backgrounds are Student, Post-doc, Scientist or Professional
Note on I17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I'd say Proj full Reply: OK, I'll change it, we could then pick another person for the M&O designator Reply: or have 7 getting their paychecks via M&O contract

## 20_21 Hutch
Count | Name | Broad Support Type | Role | Deployment Requirements | Institution | First timer? | Labor Type | Ticket Type | Pipeline - PQ Packet Sent | Current SIP - PQ Status | Pipeline - CHC to ZCM | Arrival at Pole (depends on Herc) | Departure from Pole (depends on Herc) | Pipeline - ZCM to CHC | Days at Pole | Comments
1 | Mike Zernick | Mgmt&Safety | Quality & Safety Mgr | After holidays to end | UW-Madison | No | Proj full | Comm | [7 empty] | After new year until early Feb
| TBD - Implementation Mgr | Mgmt&Safety | Drill and Install Mgr | Start to holidays | UW-Madison | No | Proj full | Comm | [7 empty] | Opening to just before Christmas
2 | Dennis Duling | Drilling | Drill Leader | Full Season | UW-Madison | No | Proj full | Comm
3 | Dar Gibson | Drilling | Drill Leader | Full Season | UW-Madison | No | Proj full | Comm
4 | Jonas Kalin | Drilling | Drill Leader | Full Season | UW-Madison | No | Proj full | Comm
5 | Graham Roberts | Drilling | Drill Team | Full Season | UW-Madison | No | Proj seasonal | Comm
6 | Paul Wisneiwski | Drilling | Drill Team | ??? | UW-Madison | No | Proj full | Comm
| Barb Birrittella | Drilling | Drill Team | 2nd 1/2 season | UW-Madison | No | Proj full | Comm
7 | James Roth | Drilling | Drill Team | 1/2 Season | U-Del | No | In-kind | Comm
| Jake Nesbit | Drilling | Drill Team | 1/2 Season | UW-Madison | No | Proj full | Comm
8 | TBD | Drilling | Drill Team | Full Season |  |  |  | Comm
9 | Jeanne Edwards | Drilling | Drill Team | 1/2 Season | UW-Madison | No | Proj full | Comm
| Brent Folmer | Drilling | Drill Team | overlap w/gen-tech, stay on | Sub-Contractor | No | Contractor | Comm
10 | Erik Ejdepalm | Drilling | Drill Team | Full Season | Sweden | No | Proj full | Self
11 | Ase Torgilsson | Drilling | Drill Team | Full Season | Sweden | No | Proj full | Self
12 | Delia Tosi | Deployment | Install Leader | ??? | UW-Madison | No | Proj full | Comm
| Generator Technician | Drilling | Drill Team | 1st 1/2 season | Sub-Contractor | Yes | Contractor | Comm
McMurdo | Need a cargo person here
McMurdo | Short term for fab/repairs
Alternates | Terry Benson
Xu Zhai
Darrell Hamilton
Curtis Moore
Rickard
Jim Koehler
Jeff Lemery
Paul Anker
Frederik Sorqvist
Jayred
Shawntel
Notes:
1. Labor types are Proj full, Proj seasonal, In-kind, M&O
2. Ticket types are Comm (ASC supplied, NSF sponsored) or Self (institution supplied)
3. Backgrounds are Student, Post-doc, Scientist or Professional
Dar, Terry - I have transferred most of this information to the 20_21 tab. We need to work on question marks in deployment requirements column. Don't update this sheet anymore. Go to 20_21 and make changes there for now.

## 20_21
Count | Event # | Name | E-Mail address | Broad Support Type | Role / details | Background | Institution | First timer? | Labor Type | Ticket Type | Pipeline - PQ Packet Sent | Current SIP - PQ Status | Pipeline - CHC to ZCM | Arrival at Pole (depends on Herc) | Departure from Pole (depends on Herc) | Pipeline - ZCM to CHC | Days at Pole | Comments |  | 2020-11-07 | 2020-11-14 | 2020-11-21 | 2020-11-28 | 2020-12-05 | 2020-12-12 | 2020-12-19 | 2020-12-26 | 2021-01-02 | 2021-01-09 | 2021-01-16 | 2021-01-23 | 2021-01-30 | 2021-02-06
1 | A-333-S | TBD1 |  | M&O | Winterover 1 |  |  |  | M&O |  |  |  |  | 2020-10-29 | 2021-11-10 |  | 377 | bar: 2020-11-07 to 2021-02-06
2 | A-333-S | TBD2 |  | M&O | Winterover 2 |  |  |  | M&O |  |  |  |  | 2020-10-29 | 2021-11-10 |  | 377 | bar: 2020-11-07 to 2021-02-06
3 | A-333-S | Ralf Auer | ralf.auer@icecube.wisc.edu | M&O | Computing / Hub Maintenance 1 | Prof | UW - Madison | No | M&O | Comm |  |  |  | 2020-11-10 | 2021-01-05 |  | 56 | bar: 2020-11-14 to 2021-01-02
4 | A-333-S | Jeff Weber | jeff.weber@icecube.wisc.edu | M&O | DAQ / Engineering Support 1 | Prof | UW - Madison | Yes | M&O | Comm |  |  |  | 2020-11-10 | 2020-12-07 |  | 27 | bar: 2020-11-14 to 2020-12-05
5 | A-333-S | TBD3 |  | M&O | Computing / Hub Maintenance 2 |  |  |  | M&O |  |  |  |  | 2020-12-07 | 2021-01-05 |  | 29 | bar: 2020-12-12 to 2021-01-02
6 | A-333-S | TBD4 |  | M&O | Computing / Hub Maintenance 3 (Helper1) |  |  |  | M&O |  |  |  |  | 2020-12-07 | 2021-01-05 |  | 29 | bar: 2020-12-12 to 2021-01-02
7 | A-333-S | TBD5 |  | M&O | Spare1 |  |  |  | M&O |  |  |  |  | 2020-12-04 | 2020-12-21 |  | 17 | Hard to split computing / hub maint to a 4th person. Backpocket to SIP. | bar: 2020-12-05 to 2020-12-19
8 | A-333-S | TBD6 |  | M&O | Spare2 |  |  |  | M&O |  |  |  |  | 2020-12-07 | 2021-01-12 |  | 36 | Backpocket to SIP. Maybe ARA focused? | bar: 2020-12-12 to 2021-01-09
9 | A-333-S | TBD7 |  | M&O | Calibration 1 (Helper2) |  |  |  | M&O |  |  |  |  | 2020-11-17 | 2020-12-18 |  | 31 | bar: 2020-11-21 to 2020-12-12
10 | A-333-S | Delia Tosi | delia.tosi@icecube.wisc.edu | M&O | DAQ / Engineering Support 2 | Scientist | UW-Madison | No | M&O | Comm |  |  |  | 2021-01-05 | 2021-01-29 |  | 24 | bar: 2021-01-09 to 2021-01-23
11 | A-333-S | TBD8 |  | M&O | Scint / Radio Mainentance 1 |  |  |  | M&O |  |  |  |  | 2021-01-05 | 2021-01-29 |  | 24 | bar: 2021-01-09 to 2021-01-23
12 | A-333-S | TBD9 |  | M&O | Scint / Radio Mainentance 2 |  |  |  | M&O |  |  |  |  | 2021-01-05 | 2021-01-26 |  | 21 | bar: 2021-01-09 to 2021-01-16
13 | A-333-S | TBD10 |  | M&O | Scint / Radio Mainentance 3 (Helper3) |  |  |  | M&O |  |  |  |  | 2021-01-12 | 2021-02-04 |  | 23 | bar: 2021-01-16 to 2021-01-30
14 | A-333-S | TBD11 |  | M&O | IceACT Maintenance 1 |  |  |  | M&O |  |  |  |  | 2021-01-12 | 2021-02-04 |  | 23 | bar: 2021-01-16 to 2021-01-30
15 | A-333-S | Elaine Krebs | elainemariak@gmail.com | M&O | PolarTREC 1 | Prof | UW-Madison | Yes | M&O | Comm |  |  |  | 2020-11-17 | 2020-12-11 |  | 24 | Does not count in IceCube population
[19 empty] | Total Count | 2 | 4 | 5 | 5 | 6 | 8 | 7 | 6 | 6 | 6 | 7 | 6 | 4 | 2
[19 empty] | Ops Notice | 6 | 5 | 7 | 7 | 9 | 9 | 9 | 9 | 8 | 8 | 8 | 6 | 6 | 2
1 | A-334-S | Mike Zernick | michael.zernick@icecube.wisc.edu | Mgmt&Safety | Quality & Safety Mgr 1a | Prof | UW-Madison | No | Proj full | Comm |  |  |  | 2020-11-10 | 2020-12-18
2 | A-334-S | TBD1 - Implementation Mgr |  | Mgmt&Safety | Drill and Install Mgr 1b | Prof | UW-Madison | No | Proj full | Comm |  |  |  | 2020-12-18 | 2021-01-29
3 | A-334-S | Dar Gibson | dar.gibson@icecube.wisc.edu | Drilling | Drill Lead 2 | Prof | UW-Madison | No | Proj full | Comm |  |  |  | 2020-11-10 | 2021-01-29
4 | A-334-S | Jonas Kalin | jonas.kalin@gmail.com | Drilling | Drill Team 3 | Prof | UW-Madison | No | Proj full | Comm |  |  |  | 2020-11-10 | 2021-01-29
5 | A-334-S | Graham Roberts | cm3h2o@gmail.com | Drilling | Drill Team 4 | Prof | UW-Madison | No | Proj full | Comm |  |  |  | 2020-11-10 | 2021-01-29
6 | A-334-S | Lexi Oxborough | oxborough@wisc.edu | Drilling | Drill Team 5 | Prof | UW-Madison | No | Proj full | Comm |  |  |  | 2020-11-10 | 2021-01-29
7 | A-334-S | Jake Nesbit | jnesbit@wisc.edu | Drilling | Drill Team 6a | Prof | UW-Madison | No | Proj full | Comm |  |  |  | 2020-11-10 | 2020-12-18
8 | A-334-S | Barb Birrittella | bbirrittella@wisc.edu | Drilling | Drill Team 6b | Prof | UW-Madison | No | Proj full | Comm |  |  |  | 2020-12-18 | 2021-01-19
9 | A-334-S | Jeanne Edwards | jmedwards5@wisc.edu | Drilling | Drill Team 7a | Prof | UW-Madison | No | Proj full | Comm |  |  |  | 2020-11-10 | 2020-12-18
10 | A-334-S | Xu Zhai | xzhai@wisc.edu | Drilling | Drill Team 7b | Prof | UW-Madison | Yes | Proj full | Comm |  |  |  | 2020-12-18 | 2021-01-29
11 | A-334-S | James Roth | roth@bartol.udel.edu | Drilling | Drill Team 8a | Prof | U-Delaware | No | In-kind | Comm |  |  |  | 2020-11-10 | 2020-12-18
12 | A-334-S | Paul Wisniewski | paul.wisniewski@icecube.wisc.edu | Drilling | Drill Team 8b | Prof | UW-Madison | No | Proj full | Comm |  |  |  | 2020-12-18 | 2021-01-29
13 | A-334-S | TBD2 - Electrician |  | Drilling | Drill Team 9a | Prof | Sub-Contractor | No | Contractor | Comm |  |  |  | 2020-11-10 | 2020-12-18
14 | A-334-S | Åse Torgilsson | ase.tor.4791@gmail.com | Drilling | Drill Team 9b | Prof | UW-Madison | No | Proj seasonal | Comm |  |  |  | 2020-12-18 | 2021-01-29
15 | A-334-S | Erik Ejdepalm | erik.ejdepalm@protonmail.com | Drilling | Drill Team 10 | Prof | UW-Madison | No | Proj seasonal | Comm |  |  |  | 2020-11-10 | 2021-01-29
16 | A-334-S | TBD3 - Driller |  | Drilling | Drill Team 11a | Prof | UW-Madison | No | Proj full | Comm |  |  |  | 2020-11-10 | 2020-12-18
17 | A-334-S | TBD4 - Driller |  | Drilling | Drill Team 11b | Prof | UW-Madison | No | Proj full | Comm |  |  |  | 2020-12-18 | 2021-01-29
18 | A-334-S | TBD5 - Generator Technician |  | Drilling | Drill Team 12a | Prof | Sub-Contractor | Yes | Contractor | Comm |  |  |  | 2020-11-10 | 2020-12-18
19 | A-334-S | Chris Ng | christopher.ng@icecube.wisc.edu | Installation | Install 12b | Prof | MSU | Yes | Proj | Comm |  |  |  | 2021-01-05 | 2021-01-29
1 | A-334-M | Dennis Duling | dulingde@yahoo.com | Drilling | Drill Team MCM 1 | Prof | UW-Madison | No | Proj full | Comm
|  | Notes and Change Log: |  |  | Backups: |  |  |  | 333 Pipeline report date> | None |  | PQ Status: Date = PQ'ed, empty = not PQ'ed
|  | 1. Labor types are Project, In-kind, M&O |  |  | Terry Benson | tbenson@psl.wisc.edu |  |  | 334 Pipeline report date> | None
|  | 2. Ticket types are Comm (ASC supplied, NSF sponsored) or Self (institution supplied) |  |  | Jeff Lemery | jlemery@psl.wisc.edu
|  | 3. Backgrounds are Student, Post-doc, Scientist or Professional |  |  | Brent Folmer | bfolmer@westphalec.com
|  | 4. JH 3/24: Initial cleanup prior to SIP submission. Import info from 20_21 Hutch tab. Incorporate JK suggestions. |  |  | Farshid Feyzi | farshid.feyzi@icecube.wisc.edu
5. JH 3/25: More cleanup, added columns at far right to total pop during the season, added row to compare to Ops Notice.