## ICU_cargo MASTER INPUT SHEET
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Gen 1 - housed in 20' container | Power generation unit 1 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 2 - housed in 20' container | Power generation unit 2 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 3 - housed in 20' container | Power generation unit 3 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | - | In McMurdo |  | SPoT | 2022-12-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | 287 Loader | Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use | 114 | 77 | 96 | 1 | 487.6667 | 10273 | 10273 | actual |  | U. Wisc. Madison |  | In McMurdo | 2019-11-15 | Truck | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2022-12-01 | No* | In McMurdo | FY23 intra | D. Gibson | 2021-10-07 | I. McEwen | 2021-10-07 | *Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use
1.2 |  | Gen hoods Discharge Hoods - currently staged in McMurdo | Generator air discharge hoods , sheet metal, loose - stored on berm at SPOTSA | 108 | 53 | 60 | 2 | 397.5 | 330 | 660 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo |  |  | In McMurdo |  | - | In McMurdo |  | LC-130/SPoT | 2024-01-01 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Testing/limited operation of Gens can be accomplished without hoods - Hoods required for the drill season
1.2 |  | Firn Drill | Bermed in McM - will require McM fork or crane support. | 264 | 94 | 97 | 1 | 1393.0278 | 12000 | 12000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA
1.2 |  | Firn Drill Components - 1 | Firn drill sheave. Required Field Season 2 for final refit & functional testing | 97 | 44 | 63 | 1 | 155.6042 | 920 | 920 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Firn Drill Components - 2 | Firn drill drillhead. Required Field Season 2 for final refit & functional testing | 125 | 33 | 37 | 1 | 88.3247 | 1048 | 1048 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Weight stack and crates | Bermed in McM - will require McM fork support. Drill head weight stack and remaining bermed crates at SPoTSA | 120 | 48 | 48 | 1 | 160 | 600 | 600 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-15 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack
1.2 |  | Fuel Tower | Bermed in McM - will require McM fork or crane support. | 96 | 72 | 120 | 1 | 480 | 1500 | 1500 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack - overland shipment preferred due to complexities of air transport certification - can be laid on side once drained
1.2 |  | HPU 1 | HPU 1 (University of Nebraska - Lincoln asset) - 40' container housing heating plant on ISO sled | 480 | 96 | 102 | 1 | 2720 | 28000 | 28000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2024-01-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | HPU 1 integration with Rodwell system required before drill season on it's own sled which will require evaluation and repair - Stored at SPOTSA
|  | McMurdo totals: |  |  |  | TEU=> | 10.4644 | 9962.1233 |  | 121001
1.2 |  | Container Ski Stack (comprised of 5 sleds) - currently staged in Pt. Hueneme | Five sets of aluminum skis for 20' containers - stacked. Aluminum skis for drill containers. Required onsite for local movement of Gens and PDM. | 240 | 96 | 96 | 1 | 1280 | 4255 | 4255 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | No* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *While this shipment is not on the critical path additional ASC crane support will be required to overcome delayed arrival or sleds furnished from the South Pole inventory
1.2 |  | Generator Intake Hood - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 174 | 53 | 96 | 3 | 1537 | 586.6667 | 1760 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Generator Discharge Hoods - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 108 | 53 | 60 | 2 | 397.5 | 1210 | 2420 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 9 Spools - 348 cf / 3532 lbs each - Shipped from Italy | 92 | 92 | 70.5 | 9 | 3107.875 | 3531.5556 | 31784 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-08-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 3 Spools - 348 cf / 5001 lbs each - Shipped from PSL | 92 | 92 | 70.5 | 3 | 1035.9583 | 5001 | 15003 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
|  | Pt. Hueneme totals: |  |  |  | TEU=> | 7.7293 | 7358.3333 |  | 55222
1.2 |  | 8' Refit Container | Priority refit materials including tools, flowmeter assemblies, motor drive installation kits, hardware, fittings, sensors, & consumables | 96 | 86 | 96 | 1 | 458.6667 | 5600 | 5600 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130 | 2022-11-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | 8' container moves with contents by LC130 or is broken down for movement by Basler
1.2 |  | 20' Refit Container A | Refit materials incl. submersible pumps, hardware, filtration components, fall arrest towers, tools, & hose crimper | 240 | 96 | 102 | 1 | 1360 | 17500 | 17500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | 20' Refit Container B | Bulky materials incl. cable trays, vertical turbine pumps, vertical turbine pump motors, ladders, water tank doghouse/railing materials, 287 forks, generator parts, TU20 shaft, & drill weight stack | 240 | 96 | 102 | 1 | 1360 | 15500 | 15500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | ARA Trailer | Enclosed trailer on skis housing 35kw generator | 192 | 96 | 88 | 1 | 938.6667 | 4860 | 4860 | actual | FLAMMABLE liquid power engine | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *If this shipment is delayed 480 volt power generation support will be required in FW YR 1 by the contractor. Aside from the CRREL generator (far larger than required with high fuel burn rate) the capacity does not currently exist at the Pole.
1.2 |  | Return Water Cable Reel (RWCR) | Smaller reel - can fit in 20' container. Required onsite in FY23 for final integration and pre-drill activites | 112 | 80 | 80 | 1 | 414.8148 | 4000 | 4000 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight from Gen 1 shipment information see picture
1.2 |  | Main Cable Reel (MCR) | Required onsite in FY23 for final integration and pre-drill activites. Large cable reel - will require flat rack on vessel | 140 | 96 | 95 | 1 | 738.8889 | 12500 | 12500 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FS Y1 for final integration and pre-drill activities
1.2 |  | Controls infrastructure - Motor drives, PLCs, electrical hardware, and motor drive mounting kits | Components and equipment to support field season 1 controls system tasking - ComSur - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight estimated
1.4 |  | ICL power and timing electronics | 1 crate containing rackmount electronics for power and timing systems - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 600 | 600 | estimated | DNF | U. Wisc. Madison | 2023-08-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12
1.4 |  | ICL patch cables and patch panels | Standard vessel shipping - can overwinter in McM if shipped earlier - Do Not Deep Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNDF [TBD] | U. Wisc. Madison | 2023-06-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12 | (*) storage in McMurdo pending low temperature test
1.2 |  | ARA Drill System Components - Crate 1 | ARA (Antarctic Rodwell Appartus) - downhole pump controller, ePump controller, splash cam kit, and accessories - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | ARA Drill System Components - Crate 2 | ARA (Antarctic Rodwell Appartus) - new downhole pumps, spares, accessories and tools | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Camp Hose - currently staged at PSL | Two spools of hose - 348 cf / 4990 lbs each. Required for SES set-up - no DNDF requirement. | 92 | 92 | 71 | 2 | 695.537 | 4990 | 9980 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY22 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Bull wheel | Bull wheel assembly - used to install main cable on reel in event of main cable damage/failure | 88 | 58 | 97 | 1 | 286.5093 | 2880 | 2880 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2024-02-01 | No | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight and cube used from Gen 1 shipping label still on bull wheel.
1.2 |  | Load member cable reel | Cable Reel used to deploy downhole load member during string installation | 84 | 60 | 48 | 1 | 140 | 3800 | 3800 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-15 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 for integration - recent addition, still in development
1.2 |  | DOM Handling Facility (DHF) | Standard vessel shipping - can overwinter in McM. | 240 | 96 | 96 | 1 | 1280 | 12000 | 12000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Sensor Handling Facility construction scheduled to begin mid-December FY24
1.2 |  | Spare Combo cable | Spare cable for Return Water Cable Reel - on spool | 72 | 72 | 72 | 1 | 216 | 3000 | 3000 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Spare Drill Cable | Standard vessel shipping - can overwinter in McM. Cable on steel spool. | 83 | 83 | 61 | 1 | 243.1881 | 6835 | 6835 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Computing/controls components | Computing and controls equipment (Motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 to support controls system tasking
1.2 |  | Driller resupply/refit components - 8' Container | 8' Mini Milvan; Consumables/drill components | 96 | 86 | 96 | 1 | 458.6667 | 6500 | 6500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season - 8' container moves with contents overland or by air
1.2 |  | Drill refit components | Single crate. Consumables/drill refit components | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated |  | U. Wisc. Madison |  | UWM-PTH | 2023-08-01 | Truck | PTH - CHC |  | Comsur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season
1.2 |  | Drill Heads DNF - X | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-02-12 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | One drill head shipped one year early for ull system wet-test
1.2 |  | Drill Heads DNF - Y | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Heads DNF - R | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Computing/controls components | Computing and controls equipment (Sensor, motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-15 | Yes | FY25 inter | FY25 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Installation Hardware 87-93 | Installation hardware for winterover storage at Pole | 96 | 48 | 48 | 7 | 896 | 1000 | 7000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.2 |  | Installation Weights 87-93 | Installation weights for winterover storage at Pole | 36 | 24 | 24 | 7 | 84 | 785.7143 | 5500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.5 |  | Calibration/Special Devices 87-88 | 3+1 PencilBeams from UW, 2+1 pDOM and 1+1 LOMs - Do Not Deep Freeze | 58 | 38 | 41 | 1 | 52.294 | 836 | 836 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from UW (4+1 Radio Pulsers (all strings) 1+1 Radio Receivers, 3+1 FOM) - Do Not Deep Freeze | 63 | 40 | 42 | 1 | 61.25 | 677 | 677 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 4+1 Radio Pulser, weight 50 kg. 1+1 Radio receiver, assume mDOM weight, 3+1 FOM (assume mDOM weight) + 2ftx2ftx4ft FOM box (50 lbs). Special Devices from UW. FTS, seismometer missing from estimate. 250 lbs crate estimate
1.2 |  | Misc. Science Equipment - FY24 | Scientific and test equipment (SPAT, DCM et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-10-08 | D. Tosi | 2021-10-08
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from UW (4+1 FOM,2+1 Radio Receivers, 11+1 LOM + seismometer*) - Do Not Deep Freeze | 81 | 56 | 51 | 1 | 133.875 | 1797 | 1797 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 21 Special Devices from USA (11+ 1 LOM, 4+1 FOM, 2+1 RR, FTS ? , seismometer), assume mDOM weight. 200 lbs wood crate. FTS not included. (*) Seismometer not yet in CMD
1.5 |  | Calibration/Special Devices 89-93 | 8+1 PencilBeams, 12+1 pDOMs from UW - Do Not Deep Freeze | 75 | 56.5 | 41 | 1 | 100.5425 | 1602 | 1602 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-05 | 8+1 PencilBeams for strings 89-93, 12+1 pDOMs, assume mDOM weight. 244 lbs crate.
1.2 |  | Misc. Science Equipment - FY25 | Scientific and test equipment (Handheld test devices, Paros, et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-12-01 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | D. Tosi | 2021-10-08
1.5 |  | Dust logging device | Blue Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-18 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Green Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-19 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 24 | 24 | 1 | 8.6667 | 120 | 120 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-20 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 23 | 20 | 1 | 6.9213 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-21 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Logging winch | Winch to be used for Dust Logging | 86 | 60 | 68 | 1 | 203.0556 | 3500 | 3500 | IDP deep logging winch for reference |  | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.5 |  | Logging winch control box | Control Box for winch for Dust Logging - sensitive equipment - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 400 | 400 | IDP deep logging winch for reference | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
|  | U. Wisconsin totals: |  |  |  | TEU=> | 12.1277 | 11545.5987 |  | 148947
1.4 |  | Surface Junction Boxes | Surface Junction Boxes can overwinter in McM if shipped earlier. 7 junction boxes | 66 | 30 | 14 | 7 | 112.2917 | 200 | 1400 | preliminary |  | MSU | 2022-11-01 | MSU-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-10 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | Each is 66" x 30" x 14", each is 112 lbs. Assume Folding crate
1.4 |  | Surface Cable Assemblies | Palletized wooden cable drums (Qty: 7). Can overwinter in MCM. | 48 | 65 | 71 | 7 | 897.3611 | 1335.7143 | 9350 | actual |  | MSU | 2021-11-30 | MSU-PTH | 2022-12-01 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-11-20 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Breakout cables for strings 87-88 | Standard vessel shipping. 2 wooden crates containing spooled breakout cable assemblies - 96 cf / 1,000 lbs each - Do Not Deep Freeze | 72 | 48 | 48 | 2 | 192 | 1000 | 2000 | estimated | DNDF[-40C](*) | MSU | 2023-02-28 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | Preliminary estimate of weight and size. Pre-staging string 87-88 equipment in cryo or ICL. - if shipping to Pole not possible before end of 23/24 season could overwinter in McM (at an increased risk and pending low temperature test)
1.4 |  | Breakout cables for strings 89-93 | Stored in McMurdo FY24. 5 wooden crates containing spooled breakout cable assemblies - 96 cf/ 1,000 lbs each (preliminary) - Do Not Deep Freeze | 72 | 48 | 48 | 5 | 480 | 1000 | 5000 | estimated | DNDF[-40C](*) | MSU | 2023-05-22 | MSU-PTH | 2023-06-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-11-25 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-09-20 | Preliminary estimate of weight and size. (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) load members 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 47 | 47 | 39 | 7 | 348.9913 | 766 | 5362 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) cables 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 96 | 96 | 96 | 7 | 3584 | 15000 | 105000 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 25 | 1277.7778 | 573 | 14325 | final weight(**) | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 28 kg/boxed + 35kg pallet, assume 8 mDOMs/pallet (189 to be deployed + 11 spares)(*)Assumed to be shipped in 2x20' HC (5115 lbs, 238inx96inx114in) or a 40 ft HC, purchased by MSU or loaned in PTH (container weight not included)
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) containers (TBD) - Do Not Deep Freeze | 238 | 96 | 114 | 0 | 0 | 5115 | 0 | see notes in item above | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | Assume 2x20HC containers for transport on COMSUR (TBC). Pallets could be loaded to 53 ft truck and loaded into a loaned container in PTH but this would increase touch points (and risk)
|  | MSU Totals: |  |  |  | TEU=> | 7.2399 | 6892.4219 |  | 142437
1.3 |  | DM-Ice | DM-ice (two modules for string 89 and 90) - Do Not Deep Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNDF [-40C] | Yale |  | Yale-PTH |  | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | M. Kauer | 2021-09-20 | D. Tosi | 2021-09-20
|  | Other Institutions Totals: |  |  |  |  | 0.067227 | 64 |  | 1500
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (spares included) - Do Not Deep Freeze | 40 | 48 | 46 | 16 | 817.7778 | 573 | 9168 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - 116 to be deployed + 12 spares - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (SPARES) - Do Not Deep Freeze | 40 | 48 | 46 | 0 | 0 | 573 | 0 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from DESY/Germany/Sweden (8 WOMs, 0 Abalone) + spares - Do Not Deep Freeze | 40 | 21 | 64 | 1 | 31.1111 | 701 | 701 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 8 WOMs (no spares) - AH not included for now. Assume 150 lbs crate.
1.5 |  | Calibration Devices 87-88 | Calibration devices for 2 strings from DESY/Germany/Sweden (4+2 POCAMs, 3+1 Acoustic sensors, 2+1 Swedish Cameras) - Do Not Deep Freeze | 62 | 38 | 41 | 1 | 55.9005 | 836 | 836 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 87-88 = 2+1 Sweden Camera + 3+1 Acoustic Module + 4+1 POCAM, including spares, 200 lbs crate
1.4 |  | FieldHub electronics | Required onsite for FY24 installation. 1 crate containing readout electronics for installation in ICL - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 275 | 275 | preliminary | DNF | DESY | 2023-08-01 | DESY-CHC | 2023-08-15 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | No | FY24 inter | FY24 intra | J. Kelley | 2021-10-13 | D. Tosi | 2021-10-13 | Field Hubs are 442mm x 480mm x 133 mm (17.4" x 18.9" x 5.2") and weight maybe 10 lb each. 100 lbs crate.
1.3 |  | String Sensors 89-93 | Optical sensors for 5 strings from Germany (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 12 | 613.3333 | 573 | 6876 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is (28kg/sensor boxed) + 35kg pallet, assume 8 mDOMs/pallet - 190 to be deployed + 10 spares. (**) shipped in 20 HC container. Container not included in weight as pallets will be taken out.
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from DESY/Germany/Sweden (6 WOMs, 3 Abalone Hubs or WOM Traps) no spares - Do Not Deep Freeze | 32 | 31 | 89 | 1 | 51.0926 | 1035 | 1035 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 6 Special Devices from Germany 6 (WOM + 0 AH) including 0 spare for each. Assume 170 lbs crate.
1.5 |  | Calibration Devices 89-93 | Calibration for 5 strings from DESY/Germany/Sweden (17+2 POCAMs, 7+ 1 Acoustic sensors, 3+ 1 Swedish Cameras) including spares - Do Not Deep Freeze | 62 | 48 | 44 | 1 | 75.7778 | 1694 | 1694 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 89-93 = 3+1 Sweden Camera,7+1 + Acoustic Module,17 +1 POCAM, including spares, 200 lbs crate
|  | DESY/Aachen/TUM/Sweden etc Totals: |  |  |  | TEU=> | 1.7784 | 1692.9931 |  | 20585
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 4 | 335 | 794 | 3176 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter (SPARES - TBD) - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 1 | 83.75 | 794 | 794 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 4 | 469 | 1168.5 | 4674 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter (SPARES - TBD)- Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 1 | 117.25 | 1168.5 | 1168.5 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 8 sensors in McMurdo overwinter - Do Not Deep Freeze | 45 | 48 | 67 | 10 | 837.5 | 794 | 7940 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 12 sensors in McMurdo overwinter - Do Not Deep Freeze | 63 | 48 | 67 | 10 | 1172.5 | 1168.5 | 11685 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
|  | Chiba Totals: |  |  |  | TEU=> | 3.167 | 3015 |  | 29437.5
1.2 |  | Field Season 1 Fuel | Fuel to support FY23 field season - Base fuel |  |  |  | 3191 | 426.5746 | 6.8 | 21698.8 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 1 Fuel Contingency | Fuel to support FY23 field season - Contingency |  |  |  | 452 | 60.4236 | 6.8 | 3073.6 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel | Fuel to support FY24 field season - Base fuel, firn drilling & over winter heating |  |  |  | 18178 | 2430.045 | 6.8 | 123610.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel Contingency | Fuel to suppport FY24 field season - Contingency |  |  |  | 2373 | 317.2239 | 6.8 | 16136.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel | Fuel to support FY25 field season - Base fuel & deep drilling |  |  |  | 62694 | 8380.9682 | 6.8 | 426319.2 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel Contingency | Fuel to suppport FY25 field season - Contingency |  |  |  | 8473 | 1132.6753 | 6.8 | 57616.4 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
|  | Fuel Totals: |  |  |  | TEU=> | 13.3907 | 12747.9106 |  | 648454.8
|  |  | All IC/Upgrade cargo volume: |  |  | TEU=> | 55.9647 | 53278.3808 |  | 1167584.3
Legend:
|  | Cargo Item | Item to be procured or fabricated
|  | Description | Brief description of item
|  | Owner/Guardian | UWIsc/ICNO-U Project Team member responsible for completion
|  | Completion Date | Date in PMB for completion (mm/dd/yy)
|  | Shipment Date | Date in PMB for shipment (mm/dd/yy)
|  | Weight | Pounds (lbs)
|  | Dimensions | L x W x H (inches) or cubic feet
|  | General Assumption | All cargo is destined for South Pole
|  | Routing Options | Port Hueneme>>Christchurch>>McMurdo
|  | Transportation Options | USAP Vessel, Commercial ship or air carrier (COMSUR or COMAIR), C-17 (CHC-MCM), LC-130 or SPoT (MCM-SPA)
|  | Month for Items expected at South Pole | Needed on-site date (Nov, Dec, or Jan)
|  | Work Package | Grouping by WPs could be done after the "cargo pipeline" is set by the item's "origin"
|  | Basis of Estimate | Estimate (expert guess), Preliminary (based on design), Actual (as built)
|  | FS1 | Field season to finishing EHWD refurbishment
|  | FS2 | Pre-drilling season: staging Drill Camp, firn holes shallow drilling
|  | FS3 | The season of drilling deep ice holes & deploying DOMs
|  | DNF | Do Not Freeze
|  | DNDF | Do Not Deep Freeze [min Temperature for storage] - for storage temp > -53C
CROSS CHECKS |  | cubic feet | lbs | Cells will be green if all the cargo is taken into account
inter-continental |  | 53278.3808 | 1167584.3
intra-continental |  | 53278.3808 | 1167584.3
CROSS CHECKS |  | cubic feet | lbs | Cells will be green if all the cargo is taken into account
inter-continental |  | 53278.3808 | 1167584.3
intra-continental |  | 53278.3808 | 1167584.3
start | end | McMurdo label | Pole label
2021-11-01 | 2022-02-15 | FY22 inter | FY23 intra
2022-11-01 | 2023-02-15 | FY23 inter | FY23 intra
2023-11-01 | 2024-02-15 | FY24 inter | FY24 intra
2024-11-01 | 2025-02-15 | FY25 inter | FY25 intra
Note on G13: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G19: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G58: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G67: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G78: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G85: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G92: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G93: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet

## Southbound by Season (UNLINKED)
FY22 Intercontinental
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Container Ski Stack (comprised of 5 sleds) - currently staged in Pt. Hueneme | Five sets of aluminum skis for 20' containers - stacked. Aluminum skis for drill containers. Required onsite for local movement of Gens and PDM. | 240 | 96 | 96 | 1 | 1280 | 4255 | 4255 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | No* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *While this shipment is not on the critical path additional ASC crane support will be required to overcome delayed arrival or sleds furnished from the South Pole inventory
1.2 |  | 8' Refit Container | Priority refit materials including tools, flowmeter assemblies, motor drive installation kits, hardware, fittings, sensors, & consumables | 96 | 86 | 96 | 1 | 458.6667 | 5600 | 5600 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130 | 2022-11-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | 8' container moves with contents by LC130 or is broken down for movement by Basler
1.2 |  | 20' Refit Container A | Refit materials incl. submersible pumps, hardware, filtration components, fall arrest towers, tools, & hose crimper | 240 | 96 | 102 | 1 | 1360 | 17500 | 17500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | 20' Refit Container B | Bulky materials incl. cable trays, vertical turbine pumps, vertical turbine pump motors, ladders, water tank doghouse/railing materials, 287 forks, generator parts, TU20 shaft, & drill weight stack | 240 | 96 | 102 | 1 | 1360 | 15500 | 15500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | ARA Trailer | Enclosed trailer on skis housing 35kw generator | 192 | 96 | 88 | 1 | 938.6667 | 4860 | 4860 | actual | FLAMMABLE liquid power engine | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | *If this shipment is delayed 480 volt power generation support will be required in FW YR 1 by the contractor. Aside from the CRREL generator (far larger than required with high fuel burn rate) the capacity does not currently exist at the Pole.
1.2 |  | Return Water Cable Reel (RWCR) | Smaller reel - can fit in 20' container. Required onsite in FY23 for final integration and pre-drill activites | 112 | 80 | 80 | 1 | 414.8148 | 4000 | 4000 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Weight from Gen 1 shipment information see picture
1.2 |  | Main Cable Reel (MCR) | Required onsite in FY23 for final integration and pre-drill activites. Large cable reel - will require flat rack on vessel | 140 | 96 | 95 | 1 | 738.8889 | 12500 | 12500 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Required onsite in FS Y1 for final integration and pre-drill activities
1.2 |  | Camp Hose - currently staged at PSL | Two spools of hose - 348 cf / 4990 lbs each. Required for SES set-up - no DNDF requirement. | 92 | 92 | 71 | 2 | 695.537 | 4990 | 9980 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY22 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
|  | Totals | [5 empty] | 7246.5741 |  | 74195 | [18 empty] | #NAME? | #NAME?
#NAME?
FY23 Intercontinental
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Generator Intake Hood - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 174 | 53 | 96 | 3 | 1537 | 586.6667 | 1760 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477
1.2 |  | Generator Discharge Hoods - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 108 | 53 | 60 | 2 | 397.5 | 1210 | 2420 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 9 Spools - 348 cf / 3532 lbs each - Shipped from Italy | 92 | 92 | 70.5 | 9 | 3107.875 | 3531.5556 | 31784 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-08-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 3 Spools - 348 cf / 5001 lbs each - Shipped from PSL | 92 | 92 | 70.5 | 3 | 1035.9583 | 5001 | 15003 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.2 |  | Controls infrastructure - Motor drives, PLCs, electrical hardware, and motor drive mounting kits | Components and equipment to support field season 1 controls system tasking - ComSur - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Weight estimated
1.2 |  | ARA Drill System Components - Crate 1 | ARA (Antarctic Rodwell Appartus) - downhole pump controller, ePump controller, splash cam kit, and accessories - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477
1.2 |  | ARA Drill System Components - Crate 2 | ARA (Antarctic Rodwell Appartus) - new downhole pumps, spares, accessories and tools | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477
1.2 |  | Bull wheel | Bull wheel assembly - used to install main cable on reel in event of main cable damage/failure | 88 | 58 | 97 | 1 | 286.5093 | 2880 | 2880 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2024-02-01 | No | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight and cube used from Gen 1 shipping label still on bull wheel.
1.2 |  | Load member cable reel | Cable Reel used to deploy downhole load member during string installation | 84 | 60 | 48 | 1 | 140 | 3800 | 3800 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-15 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 for integration - recent addition, still in development
1.2 |  | DOM Handling Facility (DHF) | Standard vessel shipping - can overwinter in McM. | 240 | 96 | 96 | 1 | 1280 | 12000 | 12000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Sensor Handling Facility construction scheduled to begin mid-December FY24
1.2 |  | Drill Heads DNF - X | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-02-12 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | One drill head shipped one year early for ull system wet-test
1.4 |  | Surface Junction Boxes | Surface Junction Boxes can overwinter in McM if shipped earlier. 7 junction boxes | 66 | 30 | 14 | 7 | 112.2917 | 200 | 1400 | preliminary |  | MSU | 2022-11-01 | MSU-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-10 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | Each is 66" x 30" x 14", each is 112 lbs. Assume Folding crate
1.4 |  | Surface Cable Assemblies | Palletized wooden cable drums (Qty: 7). Can overwinter in MCM. | 48 | 65 | 71 | 7 | 897.3611 | 1335.7143 | 9350 | actual |  | MSU | 2021-11-30 | MSU-PTH | 2022-12-01 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-11-20 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.2 |  | Field Season 1 Fuel | Fuel to support FY23 field season - Base fuel |  |  |  | 3191 | 426.5746 | 6.8 | 21698.8 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 1 Fuel Contingency | Fuel to support FY23 field season - Contingency |  |  |  | 452 | 60.4236 | 6.8 | 3073.6 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
|  | Totals | [5 empty] | 9729.4936 |  | 111629.4 | [18 empty] | #NAME? | #NAME?
#NAME?
FY23 Intracontinental
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Gen 2 - housed in 20' container | Power generation unit 2 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 3 - housed in 20' container | Power generation unit 3 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | - | In McMurdo |  | SPoT | 2022-12-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | 287 Loader | Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use | 114 | 77 | 96 | 1 | 487.6667 | 10273 | 10273 | actual |  | U. Wisc. Madison |  | In McMurdo | 2019-11-15 | Truck | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2022-12-01 | No* | In McMurdo | FY23 intra | D. Gibson | 2021-10-07 | I. McEwen | 2021-10-07 | *Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use
1.2 |  | Fuel Tower | Bermed in McM - will require McM fork or crane support. | 96 | 72 | 120 | 1 | 480 | 1500 | 1500 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack - overland shipment preferred due to complexities of air transport certification - can be laid on side once drained
1.2 |  | Container Ski Stack (comprised of 5 sleds) - currently staged in Pt. Hueneme | Five sets of aluminum skis for 20' containers - stacked. Aluminum skis for drill containers. Required onsite for local movement of Gens and PDM. | 240 | 96 | 96 | 1 | 1280 | 4255 | 4255 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | No* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *While this shipment is not on the critical path additional ASC crane support will be required to overcome delayed arrival or sleds furnished from the South Pole inventory
1.2 |  | 8' Refit Container | Priority refit materials including tools, flowmeter assemblies, motor drive installation kits, hardware, fittings, sensors, & consumables | 96 | 86 | 96 | 1 | 458.6667 | 5600 | 5600 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130 | 2022-11-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | 8' container moves with contents by LC130 or is broken down for movement by Basler
1.2 |  | 20' Refit Container A | Refit materials incl. submersible pumps, hardware, filtration components, fall arrest towers, tools, & hose crimper | 240 | 96 | 102 | 1 | 1360 | 17500 | 17500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | 20' Refit Container B | Bulky materials incl. cable trays, vertical turbine pumps, vertical turbine pump motors, ladders, water tank doghouse/railing materials, 287 forks, generator parts, TU20 shaft, & drill weight stack | 240 | 96 | 102 | 1 | 1360 | 15500 | 15500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | ARA Trailer | Enclosed trailer on skis housing 35kw generator | 192 | 96 | 88 | 1 | 938.6667 | 4860 | 4860 | actual | FLAMMABLE liquid power engine | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | *If this shipment is delayed 480 volt power generation support will be required in FW YR 1 by the contractor. Aside from the CRREL generator (far larger than required with high fuel burn rate) the capacity does not currently exist at the Pole.
1.2 |  | Return Water Cable Reel (RWCR) | Smaller reel - can fit in 20' container. Required onsite in FY23 for final integration and pre-drill activites | 112 | 80 | 80 | 1 | 414.8148 | 4000 | 4000 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Weight from Gen 1 shipment information see picture
1.2 |  | Main Cable Reel (MCR) | Required onsite in FY23 for final integration and pre-drill activites. Large cable reel - will require flat rack on vessel | 140 | 96 | 95 | 1 | 738.8889 | 12500 | 12500 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Required onsite in FS Y1 for final integration and pre-drill activities
1.2 |  | Controls infrastructure - Motor drives, PLCs, electrical hardware, and motor drive mounting kits | Components and equipment to support field season 1 controls system tasking - ComSur - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Weight estimated
1.2 |  | ARA Drill System Components - Crate 1 | ARA (Antarctic Rodwell Appartus) - downhole pump controller, ePump controller, splash cam kit, and accessories - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477
1.2 |  | ARA Drill System Components - Crate 2 | ARA (Antarctic Rodwell Appartus) - new downhole pumps, spares, accessories and tools | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477
1.2 |  | Drill Heads DNF - X | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-02-12 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | One drill head shipped one year early for ull system wet-test
1.2 |  | Field Season 1 Fuel | Fuel to support FY23 field season - Base fuel |  |  |  | 3191 | 426.5746 | 6.8 | 21698.8 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 1 Fuel Contingency | Fuel to support FY23 field season - Contingency |  |  |  | 452 | 60.4236 | 6.8 | 3073.6 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
|  | Totals | [5 empty] | 11173.7019 |  | 151220.4 | [18 empty] | #NAME? | #NAME?
#NAME?
#NAME?
FY24 Intercontinental
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.4 |  | ICL power and timing electronics | 1 crate containing rackmount electronics for power and timing systems - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 600 | 600 | estimated | DNF | U. Wisc. Madison | 2023-08-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12
1.4 |  | ICL patch cables and patch panels | Standard vessel shipping - can overwinter in McM if shipped earlier - Do Not Deep Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNDF [TBD] | U. Wisc. Madison | 2023-06-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12 | (*) storage in McMurdo pending low temperature test
1.2 |  | Spare Combo cable | Spare cable for Return Water Cable Reel - on spool | 72 | 72 | 72 | 1 | 216 | 3000 | 3000 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Spare Drill Cable | Standard vessel shipping - can overwinter in McM. Cable on steel spool. | 83 | 83 | 61 | 1 | 243.1881 | 6835 | 6835 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Computing/controls components | Computing and controls equipment (Motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 to support controls system tasking
1.2 |  | Driller resupply/refit components - 8' Container | 8' Mini Milvan; Consumables/drill components | 96 | 86 | 96 | 1 | 458.6667 | 6500 | 6500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season - 8' container moves with contents overland or by air
1.2 |  | Drill refit components | Single crate. Consumables/drill refit components | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated |  | U. Wisc. Madison |  | UWM-PTH | 2023-08-01 | Truck | PTH - CHC |  | Comsur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season
1.2 |  | Drill Heads DNF - Y | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Heads DNF - R | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Installation Hardware 87-93 | Installation hardware for winterover storage at Pole | 96 | 48 | 48 | 7 | 896 | 1000 | 7000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.2 |  | Installation Weights 87-93 | Installation weights for winterover storage at Pole | 36 | 24 | 24 | 7 | 84 | 785.7143 | 5500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.5 |  | Calibration/Special Devices 87-88 | 3+1 PencilBeams from UW, 2+1 pDOM and 1+1 LOMs - Do Not Deep Freeze | 58 | 38 | 41 | 1 | 52.294 | 836 | 836 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from UW (4+1 Radio Pulsers (all strings) 1+1 Radio Receivers, 3+1 FOM) - Do Not Deep Freeze | 63 | 40 | 42 | 1 | 61.25 | 677 | 677 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 4+1 Radio Pulser, weight 50 kg. 1+1 Radio receiver, assume mDOM weight, 3+1 FOM (assume mDOM weight) + 2ftx2ftx4ft FOM box (50 lbs). Special Devices from UW. FTS, seismometer missing from estimate. 250 lbs crate estimate
1.2 |  | Misc. Science Equipment - FY24 | Scientific and test equipment (SPAT, DCM et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-10-08 | D. Tosi | 2021-10-08
1.4 |  | Breakout cables for strings 87-88 | Standard vessel shipping. 2 wooden crates containing spooled breakout cable assemblies - 96 cf / 1,000 lbs each - Do Not Deep Freeze | 72 | 48 | 48 | 2 | 192 | 1000 | 2000 | estimated | DNDF[-40C](*) | MSU | 2023-02-28 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | Preliminary estimate of weight and size. Pre-staging string 87-88 equipment in cryo or ICL. - if shipping to Pole not possible before end of 23/24 season could overwinter in McM (at an increased risk and pending low temperature test)
1.4 |  | Breakout cables for strings 89-93 | Stored in McMurdo FY24. 5 wooden crates containing spooled breakout cable assemblies - 96 cf/ 1,000 lbs each (preliminary) - Do Not Deep Freeze | 72 | 48 | 48 | 5 | 480 | 1000 | 5000 | estimated | DNDF[-40C](*) | MSU | 2023-05-22 | MSU-PTH | 2023-06-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-11-25 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 1900-01-19 | Preliminary estimate of weight and size. (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) load members 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 47 | 47 | 39 | 7 | 348.9913 | 766 | 5362 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung |  | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) cables 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 96 | 96 | 96 | 7 | 3584 | 15000 | 105000 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (spares included) - Do Not Deep Freeze | 40 | 48 | 46 | 16 | 817.7778 | 573 | 9168 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - 116 to be deployed + 12 spares - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (SPARES) - Do Not Deep Freeze | 40 | 48 | 46 | 0 | 0 | 573 | 0 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from DESY/Germany/Sweden (8 WOMs, 0 Abalone) + spares - Do Not Deep Freeze | 40 | 21 | 64 | 1 | 31.1111 | 701 | 701 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 8 WOMs (no spares) - AH not included for now. Assume 150 lbs crate.
1.5 |  | Calibration Devices 87-88 | Calibration devices for 2 strings from DESY/Germany/Sweden (4+2 POCAMs, 3+1 Acoustic sensors, 2+1 Swedish Cameras) - Do Not Deep Freeze | 62 | 38 | 41 | 1 | 55.9005 | 836 | 836 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 87-88 = 2+1 Sweden Camera + 3+1 Acoustic Module + 4+1 POCAM, including spares, 200 lbs crate
1.4 |  | FieldHub electronics | Required onsite for FY24 installation. 1 crate containing readout electronics for installation in ICL - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 275 | 275 | preliminary | DNF | DESY | 2023-08-01 | DESY-CHC | 2023-08-15 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | No | FY24 inter | FY24 intra | J. Kelley | 2021-10-13 | D. Tosi | 2021-10-13 | Field Hubs are 442mm x 480mm x 133 mm (17.4" x 18.9" x 5.2") and weight maybe 10 lb each. 100 lbs crate.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 4 | 335 | 794 | 3176 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter (SPARES - TBD) - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 1 | 83.75 | 794 | 794 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 4 | 469 | 1168.5 | 4674 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter (SPARES - TBD)- Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 1 | 117.25 | 1168.5 | 1168.5 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.2 |  | Field Season 2 Fuel | Fuel to support FY24 field season - Base fuel, firn drilling & over winter heating |  |  |  | 18178 | 2430.045 | 6.8 | 123610.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel Contingency | Fuel to suppport FY24 field season - Contingency |  |  |  | 2373 | 317.2239 | 6.8 | 16136.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
|  | Totals | [5 empty] | 12025.4483 |  | 319669.3 | [18 empty] | #NAME? | #NAME?
#NAME?
FY24 Intracontinental
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Gen 1 - housed in 20' container | Power generation unit 1 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen hoods Discharge Hoods - currently staged in McMurdo | Generator air discharge hoods , sheet metal, loose - stored on berm at SPOTSA | 108 | 53 | 60 | 2 | 397.5 | 330 | 660 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo |  |  | In McMurdo |  | - | In McMurdo |  | LC-130/SPoT | 2024-01-01 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Testing/limited operation of Gens can be accomplished without hoods - Hoods required for the drill season
1.2 |  | Firn Drill | Bermed in McM - will require McM fork or crane support. | 264 | 94 | 97 | 1 | 1393.0278 | 12000 | 12000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA
1.2 |  | Firn Drill Components - 1 | Firn drill sheave. Required Field Season 2 for final refit & functional testing | 97 | 44 | 63 | 1 | 155.6042 | 920 | 920 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Firn Drill Components - 2 | Firn drill drillhead. Required Field Season 2 for final refit & functional testing | 125 | 33 | 37 | 1 | 88.3247 | 1048 | 1048 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Weight stack and crates | Bermed in McM - will require McM fork support. Drill head weight stack and remaining bermed crates at SPoTSA | 120 | 48 | 48 | 1 | 160 | 600 | 600 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-15 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack
1.2 |  | HPU 1 | HPU 1 (University of Nebraska - Lincoln asset) - 40' container housing heating plant on ISO sled | 480 | 96 | 102 | 1 | 2720 | 28000 | 28000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2024-01-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | HPU 1 integration with Rodwell system required before drill season on it's own sled which will require evaluation and repair - Stored at SPOTSA
1.2 |  | Generator Intake Hood - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 174 | 53 | 96 | 3 | 1537 | 586.6667 | 1760 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477
1.2 |  | Generator Discharge Hoods - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 108 | 53 | 60 | 2 | 397.5 | 1210 | 2420 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 9 Spools - 348 cf / 3532 lbs each - Shipped from Italy | 92 | 92 | 70.5 | 9 | 3107.875 | 3531.5556 | 31784 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-08-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 3 Spools - 348 cf / 5001 lbs each - Shipped from PSL | 92 | 92 | 70.5 | 3 | 1035.9583 | 5001 | 15003 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.4 |  | ICL power and timing electronics | 1 crate containing rackmount electronics for power and timing systems - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 600 | 600 | estimated | DNF | U. Wisc. Madison | 2023-08-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12
1.4 |  | ICL patch cables and patch panels | Standard vessel shipping - can overwinter in McM if shipped earlier - Do Not Deep Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNDF [TBD] | U. Wisc. Madison | 2023-06-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12 | (*) storage in McMurdo pending low temperature test
1.2 |  | Camp Hose - currently staged at PSL | Two spools of hose - 348 cf / 4990 lbs each. Required for SES set-up - no DNDF requirement. | 92 | 92 | 71 | 2 | 695.537 | 4990 | 9980 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY22 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Bull wheel | Bull wheel assembly - used to install main cable on reel in event of main cable damage/failure | 88 | 58 | 97 | 1 | 286.5093 | 2880 | 2880 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2024-02-01 | No | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight and cube used from Gen 1 shipping label still on bull wheel.
1.2 |  | Load member cable reel | Cable Reel used to deploy downhole load member during string installation | 84 | 60 | 48 | 1 | 140 | 3800 | 3800 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-15 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 for integration - recent addition, still in development
1.2 |  | DOM Handling Facility (DHF) | Standard vessel shipping - can overwinter in McM. | 240 | 96 | 96 | 1 | 1280 | 12000 | 12000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Sensor Handling Facility construction scheduled to begin mid-December FY24
1.2 |  | Spare Combo cable | Spare cable for Return Water Cable Reel - on spool | 72 | 72 | 72 | 1 | 216 | 3000 | 3000 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Spare Drill Cable | Standard vessel shipping - can overwinter in McM. Cable on steel spool. | 83 | 83 | 61 | 1 | 243.1881 | 6835 | 6835 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Computing/controls components | Computing and controls equipment (Motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 to support controls system tasking
1.2 |  | Driller resupply/refit components - 8' Container | 8' Mini Milvan; Consumables/drill components | 96 | 86 | 96 | 1 | 458.6667 | 6500 | 6500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season - 8' container moves with contents overland or by air
1.2 |  | Drill refit components | Single crate. Consumables/drill refit components | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated |  | U. Wisc. Madison |  | UWM-PTH | 2023-08-01 | Truck | PTH - CHC |  | Comsur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season
1.2 |  | Drill Heads DNF - Y | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Heads DNF - R | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Installation Hardware 87-93 | Installation hardware for winterover storage at Pole | 96 | 48 | 48 | 7 | 896 | 1000 | 7000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.2 |  | Installation Weights 87-93 | Installation weights for winterover storage at Pole | 36 | 24 | 24 | 7 | 84 | 785.7143 | 5500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.5 |  | Calibration/Special Devices 87-88 | 3+1 PencilBeams from UW, 2+1 pDOM and 1+1 LOMs - Do Not Deep Freeze | 58 | 38 | 41 | 1 | 52.294 | 836 | 836 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from UW (4+1 Radio Pulsers (all strings) 1+1 Radio Receivers, 3+1 FOM) - Do Not Deep Freeze | 63 | 40 | 42 | 1 | 61.25 | 677 | 677 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 4+1 Radio Pulser, weight 50 kg. 1+1 Radio receiver, assume mDOM weight, 3+1 FOM (assume mDOM weight) + 2ftx2ftx4ft FOM box (50 lbs). Special Devices from UW. FTS, seismometer missing from estimate. 250 lbs crate estimate
1.2 |  | Misc. Science Equipment - FY24 | Scientific and test equipment (SPAT, DCM et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-10-08 | D. Tosi | 2021-10-08
1.4 |  | Surface Junction Boxes | Surface Junction Boxes can overwinter in McM if shipped earlier. 7 junction boxes | 66 | 30 | 14 | 7 | 112.2917 | 200 | 1400 | preliminary |  | MSU | 2022-11-01 | MSU-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-10 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | Each is 66" x 30" x 14", each is 112 lbs. Assume Folding crate
1.4 |  | Surface Cable Assemblies | Palletized wooden cable drums (Qty: 7). Can overwinter in MCM. | 48 | 65 | 71 | 7 | 897.3611 | 1335.7143 | 9350 | actual |  | MSU | 2021-11-30 | MSU-PTH | 2022-12-01 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-11-20 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Breakout cables for strings 87-88 | Standard vessel shipping. 2 wooden crates containing spooled breakout cable assemblies - 96 cf / 1,000 lbs each - Do Not Deep Freeze | 72 | 48 | 48 | 2 | 192 | 1000 | 2000 | estimated | DNDF[-40C](*) | MSU | 2023-02-28 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | Preliminary estimate of weight and size. Pre-staging string 87-88 equipment in cryo or ICL. - if shipping to Pole not possible before end of 23/24 season could overwinter in McM (at an increased risk and pending low temperature test)
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (spares included) - Do Not Deep Freeze | 40 | 48 | 46 | 16 | 817.7778 | 573 | 9168 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - 116 to be deployed + 12 spares - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (SPARES) - Do Not Deep Freeze | 40 | 48 | 46 | 0 | 0 | 573 | 0 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from DESY/Germany/Sweden (8 WOMs, 0 Abalone) + spares - Do Not Deep Freeze | 40 | 21 | 64 | 1 | 31.1111 | 701 | 701 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 8 WOMs (no spares) - AH not included for now. Assume 150 lbs crate.
1.5 |  | Calibration Devices 87-88 | Calibration devices for 2 strings from DESY/Germany/Sweden (4+2 POCAMs, 3+1 Acoustic sensors, 2+1 Swedish Cameras) - Do Not Deep Freeze | 62 | 38 | 41 | 1 | 55.9005 | 836 | 836 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 87-88 = 2+1 Sweden Camera + 3+1 Acoustic Module + 4+1 POCAM, including spares, 200 lbs crate
1.4 |  | FieldHub electronics | Required onsite for FY24 installation. 1 crate containing readout electronics for installation in ICL - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 275 | 275 | preliminary | DNF | DESY | 2023-08-01 | DESY-CHC | 2023-08-15 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | No | FY24 inter | FY24 intra | J. Kelley | 2021-10-13 | D. Tosi | 2021-10-13 | Field Hubs are 442mm x 480mm x 133 mm (17.4" x 18.9" x 5.2") and weight maybe 10 lb each. 100 lbs crate.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 4 | 335 | 794 | 3176 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter (SPARES - TBD) - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 1 | 83.75 | 794 | 794 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 4 | 469 | 1168.5 | 4674 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter (SPARES - TBD)- Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 1 | 117.25 | 1168.5 | 1168.5 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.2 |  | Field Season 2 Fuel | Fuel to support FY24 field season - Base fuel, firn drilling & over winter heating |  |  |  | 18178 | 2430.045 | 6.8 | 123610.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel Contingency | Fuel to suppport FY24 field season - Contingency |  |  |  | 2373 | 317.2239 | 6.8 | 16136.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
|  | Totals | [5 empty] | 23376.946 |  | 359912.3 | [18 empty] | #NAME? | #NAME?
#NAME?
#NAME?
#NAME?
FY25 Intercontinental
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Computing/controls components | Computing and controls equipment (Sensor, motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-15 | Yes | FY25 inter | FY25 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from UW (4+1 FOM,2+1 Radio Receivers, 11+1 LOM + seismometer*) - Do Not Deep Freeze | 81 | 56 | 51 | 1 | 133.875 | 1797 | 1797 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 21 Special Devices from USA (11+ 1 LOM, 4+1 FOM, 2+1 RR, FTS ? , seismometer), assume mDOM weight. 200 lbs wood crate. FTS not included. (*) Seismometer not yet in CMD
1.5 |  | Calibration/Special Devices 89-93 | 8+1 PencilBeams, 12+1 pDOMs from UW - Do Not Deep Freeze | 75 | 56.5 | 41 | 1 | 100.5425 | 1602 | 1602 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-05 | 8+1 PencilBeams for strings 89-93, 12+1 pDOMs, assume mDOM weight. 244 lbs crate.
1.2 |  | Misc. Science Equipment - FY25 | Scientific and test equipment (Handheld test devices, Paros, et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-12-01 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | D. Tosi | 2021-10-08
1.5 |  | Dust logging device | Blue Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-18 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Green Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-19 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 24 | 24 | 1 | 8.6667 | 120 | 120 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-20 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 23 | 20 | 1 | 6.9213 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-21 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Logging winch | Winch to be used for Dust Logging | 86 | 60 | 68 | 1 | 203.0556 | 3500 | 3500 | IDP deep logging winch for reference |  | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.5 |  | Logging winch control box | Control Box for winch for Dust Logging - sensitive equipment - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 400 | 400 | IDP deep logging winch for reference | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 25 | 1277.7778 | 573 | 14325 | final weight(**) | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 28 kg/boxed + 35kg pallet, assume 8 mDOMs/pallet (189 to be deployed + 11 spares)(*)Assumed to be shipped in 2x20' HC (5115 lbs, 238inx96inx114in) or a 40 ft HC, purchased by MSU or loaned in PTH (container weight not included)
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) containers (TBD) - Do Not Deep Freeze | 238 | 96 | 114 | 0 | 0 | 5115 | 0 | see notes in item above | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | Assume 2x20HC containers for transport on COMSUR (TBC). Pallets could be loaded to 53 ft truck and loaded into a loaned container in PTH but this would increase touch points (and risk)
1.3 |  | DM-Ice | DM-ice (two modules for string 89 and 90) - Do Not Deep Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNDF [-40C] | Yale |  | Yale-PTH |  | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | M. Kauer | 2021-09-20 | D. Tosi | 2021-09-20
1.3 |  | String Sensors 89-93 | Optical sensors for 5 strings from Germany (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 12 | 613.3333 | 573 | 6876 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - 190 to be deployed + 10 spares. (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from DESY/Germany/Sweden (6 WOMs, 3 Abalone Hubs or WOM Traps) no spares - Do Not Deep Freeze | 32 | 31 | 89 | 1 | 51.0926 | 1035 | 1035 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 6 Special Devices from Germany 6 (WOM + 0 AH) including 0 spare for each. Assume 170 lbs crate.
1.5 |  | Calibration Devices 89-93 | Calibration for 5 strings from DESY/Germany/Sweden (17+2 POCAMs, 7+ 1 Acoustic sensors, 3+ 1 Swedish Cameras) including spares - Do Not Deep Freeze | 62 | 48 | 44 | 1 | 75.7778 | 1694 | 1694 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 89-93 = 3+1 Sweden Camera,7+1 + Acoustic Module,17 +1 POCAM, including spares, 200 lbs crate
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 8 sensors in McMurdo overwinter - Do Not Deep Freeze | 45 | 48 | 67 | 10 | 837.5 | 794 | 7940 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 12 sensors in McMurdo overwinter - Do Not Deep Freeze | 63 | 48 | 67 | 10 | 1172.5 | 1168.5 | 11685 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.2 |  | Field Season 3 Fuel | Fuel to support FY25 field season - Base fuel & deep drilling |  |  |  | 62694 | 8380.9682 | 6.8 | 426319.2 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel Contingency | Fuel to suppport FY25 field season - Contingency |  |  |  | 8473 | 1132.6753 | 6.8 | 57616.4 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
|  | Totals | [5 empty] | 14314.7415 |  | 541089.6 | [18 empty] | #NAME? | #NAME?
FY25 Intracontinental
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Computing/controls components | Computing and controls equipment (Sensor, motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-15 | Yes | FY25 inter | FY25 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from UW (4+1 FOM,2+1 Radio Receivers, 11+1 LOM + seismometer*) - Do Not Deep Freeze | 81 | 56 | 51 | 1 | 133.875 | 1797 | 1797 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 21 Special Devices from USA (11+ 1 LOM, 4+1 FOM, 2+1 RR, FTS ? , seismometer), assume mDOM weight. 200 lbs wood crate. FTS not included. (*) Seismometer not yet in CMD
1.5 |  | Calibration/Special Devices 89-93 | 8+1 PencilBeams, 12+1 pDOMs from UW - Do Not Deep Freeze | 75 | 56.5 | 41 | 1 | 100.5425 | 1602 | 1602 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-05 | 8+1 PencilBeams for strings 89-93, 12+1 pDOMs, assume mDOM weight. 244 lbs crate.
1.2 |  | Misc. Science Equipment - FY25 | Scientific and test equipment (Handheld test devices, Paros, et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-12-01 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | D. Tosi | 2021-10-08
1.5 |  | Dust logging device | Blue Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-18 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Green Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-19 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 24 | 24 | 1 | 8.6667 | 120 | 120 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-20 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 23 | 20 | 1 | 6.9213 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-21 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Logging winch | Winch to be used for Dust Logging | 86 | 60 | 68 | 1 | 203.0556 | 3500 | 3500 | IDP deep logging winch for reference |  | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.5 |  | Logging winch control box | Control Box for winch for Dust Logging - sensitive equipment - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 400 | 400 | IDP deep logging winch for reference | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.4 |  | Breakout cables for strings 89-93 | Stored in McMurdo FY24. 5 wooden crates containing spooled breakout cable assemblies - 96 cf/ 1,000 lbs each (preliminary) - Do Not Deep Freeze | 72 | 48 | 48 | 5 | 480 | 1000 | 5000 | estimated | DNDF[-40C](*) | MSU | 2023-05-22 | MSU-PTH | 2023-06-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-11-25 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-09-20 | Preliminary estimate of weight and size. (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) load members 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 47 | 47 | 39 | 7 | 348.9913 | 766 | 5362 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) cables 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 96 | 96 | 96 | 7 | 3584 | 15000 | 105000 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 25 | 1277.7778 | 573 | 14325 | final weight(**) | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 28 kg/boxed + 35kg pallet, assume 8 mDOMs/pallet (189 to be deployed + 11 spares)(*)Assumed to be shipped in 2x20' HC (5115 lbs, 238inx96inx114in) or a 40 ft HC, purchased by MSU or loaned in PTH (container weight not included)
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) containers (TBD) - Do Not Deep Freeze | 238 | 96 | 114 | 0 | 0 | 5115 | 0 | see notes in item above | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | Assume 2x20HC containers for transport on COMSUR (TBC). Pallets could be loaded to 53 ft truck and loaded into a loaned container in PTH but this would increase touch points (and risk)
1.3 |  | DM-Ice | DM-ice (two modules for string 89 and 90) - Do Not Deep Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNDF [-40C] | Yale |  | Yale-PTH |  | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | M. Kauer | 2021-09-20 | D. Tosi | 2021-09-20
1.3 |  | String Sensors 89-93 | Optical sensors for 5 strings from Germany (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 12 | 613.3333 | 573 | 6876 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is (28kg/sensor boxed) + 35kg pallet, assume 8 mDOMs/pallet - 190 to be deployed + 10 spares. (**) shipped in 20 HC container. Container not included in weight as pallets will be taken out.
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from DESY/Germany/Sweden (6 WOMs, 3 Abalone Hubs or WOM Traps) no spares - Do Not Deep Freeze | 32 | 31 | 89 | 1 | 51.0926 | 1035 | 1035 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 6 Special Devices from Germany 6 (WOM + 0 AH) including 0 spare for each. Assume 170 lbs crate.
1.5 |  | Calibration Devices 89-93 | Calibration for 5 strings from DESY/Germany/Sweden (17+2 POCAMs, 7+ 1 Acoustic sensors, 3+ 1 Swedish Cameras) including spares - Do Not Deep Freeze | 62 | 48 | 44 | 1 | 75.7778 | 1694 | 1694 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 89-93 = 3+1 Sweden Camera,7+1 + Acoustic Module,17 +1 POCAM, including spares, 200 lbs crate
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 8 sensors in McMurdo overwinter - Do Not Deep Freeze | 45 | 48 | 67 | 10 | 837.5 | 794 | 7940 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 12 sensors in McMurdo overwinter - Do Not Deep Freeze | 63 | 48 | 67 | 10 | 1172.5 | 1168.5 | 11685 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.2 |  | Field Season 3 Fuel | Fuel to support FY25 field season - Base fuel & deep drilling |  |  |  | 62694 | 8380.9682 | 6.8 | 426319.2 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel Contingency | Fuel to suppport FY25 field season - Contingency |  |  |  | 8473 | 1132.6753 | 6.8 | 57616.4 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
|  | Totals | [5 empty] | 18727.7328 |  | 656451.6 | [18 empty] | #NAME? | #NAME?
#NAME?

## Retro
WBS | Retrograde | Conveyance | Details | Contents | Outyear Pole Retro | On A2 Critical Path? | Cube [cf] | Weight [lbs]
1.2 | 8' container | USAP Air + COMSUR | Multiple crates - DNF | Retrograde components and equipment | Ship north by station close FY23 | Yes | 384 | 7500
1.2 | Misc. science equipment | USAP Air + COMSUR | Multiple crates - DNF | Scientific and test equipment | Ship north by station close FY23 | Yes | 256 | 4000
| TOTAL | [5 empty] | 640 | 11500
WBS | Retrograde | Conveyance | Details | Contents | Outyear Pole Retro | On A2 Critical Path? | Cube [cf] | Weight [lbs]
1.2 | 8' container | USAP Air + COMSUR | Multiple crates - DNF | Retrograde components and equipment | Ship north by station close FY24 | Yes | 384 | 7200
1.3-1.6 | Misc. science equipment | USAP Air + COMSUR | Multiple crates - DNF | Scientific and test equipment | Ship north by station close FY24 | Yes | 256 | 4000
| TOTAL | [5 empty] | 640 | 11200
WBS | Retrograde | Conveyance | Details | Contents | Outyear Pole Retro | On A2 Critical Path? | Cube [cf] | Weight [lbs]
1.2 | Drill hose | USAP Air + COMSUR | Must overwinter in McM - DNDF | 13 hose spools: 352 cf / 4800 lbs each | Ship north by station close FY25 | Yes | 4585 | 62400
1.2 | Tools and equipment | USAP Air + COMSUR | Multiple crates - DNF | Retrograde tools and equipment | Ship north by station close FY25 | No | 1360 | 17000
1.5 | Logging winch | USAP Air + COMSUR | Loan for one season only - Expedite return to IDP | IDP supplied logging winch | Ship north by station close FY25 with CONUS arrival by April 1, 2025 | No | 203 | 3500
1.5 | Logging winch control box | USAP Air + COMSUR | Loan for one season only - Expedite return to IDP - DNF | IDP supplied logging winch control box | Ship north by station close FY25 with CONUS arrival by April 1, 2025 | No | 48 | 400
1.2 | Drill heads | USAP Air + COMSUR | DNF | 3 Drill heads | Ship north by station close FY25 | No | 192 | 1800
1.3-1.6 | Misc. science equipment | USAP Air + COMSUR | Multiple crates - DNF | Scientific and test equipment | Ship north by station close FY25 | No | 256 | 4000
1.3 | Spare mDOMs | USAP Air + COMSUR | 3 pallets | 21 mDOMs (3 pallets) |  | No | 153 | 1719
1.3 | Spare D-Eggs pallet 1 | USAP Air + COMSUR | 1 pallet | 8 Spare D-Eggs |  | No | 84 | 794
1.3 | Spare D-Eggs pallet 2 | USAP Air + COMSUR | 1 pallet | 12 Spare D-Eggs |  | No | 117 | 1169
| TOTAL | [5 empty] | 6998 | 92782

## InMcMurdo
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Gen 1 - housed in 20' container | Power generation unit 1 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 2 - housed in 20' container | Power generation unit 2 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 3 - housed in 20' container | Power generation unit 3 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | - | In McMurdo |  | SPoT | 2022-12-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | 287 Loader | Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use | 114 | 77 | 96 | 1 | 487.6667 | 10273 | 10273 | actual |  | U. Wisc. Madison |  | In McMurdo | 2019-11-15 | Truck | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2022-12-01 | No* | In McMurdo | FY23 intra | D. Gibson | 2021-10-07 | I. McEwen | 2021-10-07 | *Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use
1.2 |  | Gen hoods Discharge Hoods - currently staged in McMurdo | Generator air discharge hoods , sheet metal, loose - stored on berm at SPOTSA | 108 | 53 | 60 | 2 | 397.5 | 330 | 660 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo |  |  | In McMurdo |  | - | In McMurdo |  | LC-130/SPoT | 2024-01-01 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Testing/limited operation of Gens can be accomplished without hoods - Hoods required for the drill season
1.2 |  | Firn Drill | Bermed in McM - will require McM fork or crane support. | 264 | 94 | 97 | 1 | 1393.0278 | 12000 | 12000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA
1.2 |  | Firn Drill Components - 1 | Firn drill sheave. Required Field Season 2 for final refit & functional testing | 97 | 44 | 63 | 1 | 155.6042 | 920 | 920 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Firn Drill Components - 2 | Firn drill drillhead. Required Field Season 2 for final refit & functional testing | 125 | 33 | 37 | 1 | 88.3247 | 1048 | 1048 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Weight stack and crates | Bermed in McM - will require McM fork support. Drill head weight stack and remaining bermed crates at SPoTSA | 120 | 48 | 48 | 1 | 160 | 600 | 600 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-15 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack
1.2 |  | Fuel Tower | Bermed in McM - will require McM fork or crane support. | 96 | 72 | 120 | 1 | 480 | 1500 | 1500 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack - overland shipment preferred due to complexities of air transport certification - can be laid on side once drained
1.2 |  | HPU 1 | HPU 1 (University of Nebraska - Lincoln asset) - 40' container housing heating plant on ISO sled | 480 | 96 | 102 | 1 | 2720 | 28000 | 28000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2024-01-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | HPU 1 integration with Rodwell system required before drill season on it's own sled which will require evaluation and repair - Stored at SPOTSA
|  | McMurdo totals: |  |  |  | TEU=> | 10.4644 | 9962.1233 |  | 121001
1.2 |  | Container Ski Stack (comprised of 5 sleds) - currently staged in Pt. Hueneme | Five sets of aluminum skis for 20' containers - stacked. Aluminum skis for drill containers. Required onsite for local movement of Gens and PDM. | 240 | 96 | 96 | 1 | 1280 | 4255 | 4255 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | No* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *While this shipment is not on the critical path additional ASC crane support will be required to overcome delayed arrival or sleds furnished from the South Pole inventory
1.2 |  | Generator Intake Hood - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 174 | 53 | 96 | 3 | 1537 | 586.6667 | 1760 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477
1.2 |  | Generator Discharge Hoods - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 108 | 53 | 60 | 2 | 397.5 | 1210 | 2420 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 9 Spools - 348 cf / 3532 lbs each - Shipped from Italy | 92 | 92 | 70.5 | 9 | 3107.875 | 3531.5556 | 31784 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-08-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 3 Spools - 348 cf / 5001 lbs each - Shipped from PSL | 92 | 92 | 70.5 | 3 | 1035.9583 | 5001 | 15003 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
|  | Pt. Hueneme totals: |  |  |  | TEU=> | 7.7293 | 7358.3333 |  | 55222
1.2 |  | 8' Refit Container | Priority refit materials including tools, flowmeter assemblies, motor drive installation kits, hardware, fittings, sensors, & consumables | 96 | 86 | 96 | 1 | 458.6667 | 5600 | 5600 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130 | 2022-11-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | 8' container moves with contents by LC130 or is broken down for movement by Basler
1.2 |  | 20' Refit Container A | Refit materials incl. submersible pumps, hardware, filtration components, fall arrest towers, tools, & hose crimper | 240 | 96 | 102 | 1 | 1360 | 17500 | 17500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | 20' Refit Container B | Bulky materials incl. cable trays, vertical turbine pumps, vertical turbine pump motors, ladders, water tank doghouse/railing materials, 287 forks, generator parts, TU20 shaft, & drill weight stack | 240 | 96 | 102 | 1 | 1360 | 15500 | 15500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | ARA Trailer | Enclosed trailer on skis housing 35kw generator | 192 | 96 | 88 | 1 | 938.6667 | 4860 | 4860 | actual | FLAMMABLE liquid power engine | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | *If this shipment is delayed 480 volt power generation support will be required in FW YR 1 by the contractor. Aside from the CRREL generator (far larger than required with high fuel burn rate) the capacity does not currently exist at the Pole.
1.2 |  | Return Water Cable Reel (RWCR) | Smaller reel - can fit in 20' container. Required onsite in FY23 for final integration and pre-drill activites | 112 | 80 | 80 | 1 | 414.8148 | 4000 | 4000 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Weight from Gen 1 shipment information see picture
1.2 |  | Main Cable Reel (MCR) | Required onsite in FY23 for final integration and pre-drill activites. Large cable reel - will require flat rack on vessel | 140 | 96 | 95 | 1 | 738.8889 | 12500 | 12500 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Required onsite in FS Y1 for final integration and pre-drill activities
1.2 |  | Controls infrastructure - Motor drives, PLCs, electrical hardware, and motor drive mounting kits | Components and equipment to support field season 1 controls system tasking - ComSur - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Weight estimated
1.4 |  | ICL power and timing electronics | 1 crate containing rackmount electronics for power and timing systems - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 600 | 600 | estimated | DNF | U. Wisc. Madison | 2023-08-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12
1.4 |  | ICL patch cables and patch panels | Standard vessel shipping - can overwinter in McM if shipped earlier - Do Not Deep Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNDF [TBD] | U. Wisc. Madison | 2023-06-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12 | (*) storage in McMurdo pending low temperature test
1.2 |  | ARA Drill System Components - Crate 1 | ARA (Antarctic Rodwell Appartus) - downhole pump controller, ePump controller, splash cam kit, and accessories - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477
1.2 |  | ARA Drill System Components - Crate 2 | ARA (Antarctic Rodwell Appartus) - new downhole pumps, spares, accessories and tools | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477
1.2 |  | Camp Hose - currently staged at PSL | Two spools of hose - 348 cf / 4990 lbs each. Required for SES set-up - no DNDF requirement. | 92 | 92 | 71 | 2 | 695.537 | 4990 | 9980 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY22 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Bull wheel | Bull wheel assembly - used to install main cable on reel in event of main cable damage/failure | 88 | 58 | 97 | 1 | 286.5093 | 2880 | 2880 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2024-02-01 | No | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight and cube used from Gen 1 shipping label still on bull wheel.
1.2 |  | Load member cable reel | Cable Reel used to deploy downhole load member during string installation | 84 | 60 | 48 | 1 | 140 | 3800 | 3800 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-15 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 for integration - recent addition, still in development
1.2 |  | DOM Handling Facility (DHF) | Standard vessel shipping - can overwinter in McM. | 240 | 96 | 96 | 1 | 1280 | 12000 | 12000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Sensor Handling Facility construction scheduled to begin mid-December FY24
1.2 |  | Spare Combo cable | Spare cable for Return Water Cable Reel - on spool | 72 | 72 | 72 | 1 | 216 | 3000 | 3000 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Spare Drill Cable | Standard vessel shipping - can overwinter in McM. Cable on steel spool. | 83 | 83 | 61 | 1 | 243.1881 | 6835 | 6835 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Computing/controls components | Computing and controls equipment (Motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 to support controls system tasking
1.2 |  | Driller resupply/refit components - 8' Container | 8' Mini Milvan; Consumables/drill components | 96 | 86 | 96 | 1 | 458.6667 | 6500 | 6500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season - 8' container moves with contents overland or by air
1.2 |  | Drill refit components | Single crate. Consumables/drill refit components | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated |  | U. Wisc. Madison |  | UWM-PTH | 2023-08-01 | Truck | PTH - CHC |  | Comsur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season
1.2 |  | Drill Heads DNF - X | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-02-12 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | One drill head shipped one year early for ull system wet-test
1.2 |  | Drill Heads DNF - Y | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Heads DNF - R | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Computing/controls components | Computing and controls equipment (Sensor, motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-15 | Yes | FY25 inter | FY25 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Installation Hardware 87-93 | Installation hardware for winterover storage at Pole | 96 | 48 | 48 | 7 | 896 | 1000 | 7000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.2 |  | Installation Weights 87-93 | Installation weights for winterover storage at Pole | 36 | 24 | 24 | 7 | 84 | 785.7143 | 5500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.5 |  | Calibration/Special Devices 87-88 | 3+1 PencilBeams from UW, 2+1 pDOM and 1+1 LOMs - Do Not Deep Freeze | 58 | 38 | 41 | 1 | 52.294 | 836 | 836 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from UW (4+1 Radio Pulsers (all strings) 1+1 Radio Receivers, 3+1 FOM) - Do Not Deep Freeze | 63 | 40 | 42 | 1 | 61.25 | 677 | 677 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 4+1 Radio Pulser, weight 50 kg. 1+1 Radio receiver, assume mDOM weight, 3+1 FOM (assume mDOM weight) + 2ftx2ftx4ft FOM box (50 lbs). Special Devices from UW. FTS, seismometer missing from estimate. 250 lbs crate estimate
1.2 |  | Misc. Science Equipment - FY24 | Scientific and test equipment (SPAT, DCM et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-10-08 | D. Tosi | 2021-10-08
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from UW (4+1 FOM,2+1 Radio Receivers, 11+1 LOM + seismometer*) - Do Not Deep Freeze | 81 | 56 | 51 | 1 | 133.875 | 1797 | 1797 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 21 Special Devices from USA (11+ 1 LOM, 4+1 FOM, 2+1 RR, FTS ? , seismometer), assume mDOM weight. 200 lbs wood crate. FTS not included. (*) Seismometer not yet in CMD
1.5 |  | Calibration/Special Devices 89-93 | 8+1 PencilBeams, 12+1 pDOMs from UW - Do Not Deep Freeze | 75 | 56.5 | 41 | 1 | 100.5425 | 1602 | 1602 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-05 | 8+1 PencilBeams for strings 89-93, 12+1 pDOMs, assume mDOM weight. 244 lbs crate.
1.2 |  | Misc. Science Equipment - FY25 | Scientific and test equipment (Handheld test devices, Paros, et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-12-01 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | D. Tosi | 2021-10-08
1.5 |  | Dust logging device | Blue Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-18 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Green Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-19 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 24 | 24 | 1 | 8.6667 | 120 | 120 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-20 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 23 | 20 | 1 | 6.9213 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-21 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Logging winch | Winch to be used for Dust Logging | 86 | 60 | 68 | 1 | 203.0556 | 3500 | 3500 | IDP deep logging winch for reference |  | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.5 |  | Logging winch control box | Control Box for winch for Dust Logging - sensitive equipment - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 400 | 400 | IDP deep logging winch for reference | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
|  | U. Wisconsin totals: |  |  |  | TEU=> | 12.1277 | 11545.5987 |  | 148947
1.4 |  | Surface Junction Boxes | Surface Junction Boxes can overwinter in McM if shipped earlier. 7 junction boxes | 66 | 30 | 14 | 7 | 112.2917 | 200 | 1400 | preliminary |  | MSU | 2022-11-01 | MSU-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-10 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | Each is 66" x 30" x 14", each is 112 lbs. Assume Folding crate
1.4 |  | Surface Cable Assemblies | Palletized wooden cable drums (Qty: 7). Can overwinter in MCM. | 48 | 65 | 71 | 7 | 897.3611 | 1335.7143 | 9350 | actual |  | MSU | 2021-11-30 | MSU-PTH | 2022-12-01 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-11-20 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Breakout cables for strings 87-88 | Standard vessel shipping. 2 wooden crates containing spooled breakout cable assemblies - 96 cf / 1,000 lbs each - Do Not Deep Freeze | 72 | 48 | 48 | 2 | 192 | 1000 | 2000 | estimated | DNDF[-40C](*) | MSU | 2023-02-28 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | Preliminary estimate of weight and size. Pre-staging string 87-88 equipment in cryo or ICL. - if shipping to Pole not possible before end of 23/24 season could overwinter in McM (at an increased risk and pending low temperature test)
1.4 |  | Breakout cables for strings 89-93 | Stored in McMurdo FY24. 5 wooden crates containing spooled breakout cable assemblies - 96 cf/ 1,000 lbs each (preliminary) - Do Not Deep Freeze | 72 | 48 | 48 | 5 | 480 | 1000 | 5000 | estimated | DNDF[-40C](*) | MSU | 2023-05-22 | MSU-PTH | 2023-06-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-11-25 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-09-20 | Preliminary estimate of weight and size. (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) load members 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 47 | 47 | 39 | 7 | 348.9913 | 766 | 5362 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) cables 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 96 | 96 | 96 | 7 | 3584 | 15000 | 105000 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 25 | 1277.7778 | 573 | 14325 | final weight(**) | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 28 kg/boxed + 35kg pallet, assume 8 mDOMs/pallet (189 to be deployed + 11 spares)(*)Assumed to be shipped in 2x20' HC (5115 lbs, 238inx96inx114in) or a 40 ft HC, purchased by MSU or loaned in PTH (container weight not included)
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) containers (TBD) - Do Not Deep Freeze | 238 | 96 | 114 | 0 | 0 | 5115 | 0 | see notes in item above | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | Assume 2x20HC containers for transport on COMSUR (TBC). Pallets could be loaded to 53 ft truck and loaded into a loaned container in PTH but this would increase touch points (and risk)
|  | MSU Totals: |  |  |  | TEU=> | 7.2399 | 6892.4219 |  | 142437
1.3 |  | DM-Ice | DM-ice (two modules for string 89 and 90) - Do Not Deep Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNDF [-40C] | Yale |  | Yale-PTH |  | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | M. Kauer | 2021-09-20 | D. Tosi | 2021-09-20
|  | Other Institutions Totals: |  |  |  |  | 0.067227 | 64 |  | 1500
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (spares included) - Do Not Deep Freeze | 40 | 48 | 46 | 16 | 817.7778 | 573 | 9168 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - 116 to be deployed + 12 spares - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (SPARES) - Do Not Deep Freeze | 40 | 48 | 46 | 0 | 0 | 573 | 0 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from DESY/Germany/Sweden (8 WOMs, 0 Abalone) + spares - Do Not Deep Freeze | 40 | 21 | 64 | 1 | 31.1111 | 701 | 701 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 8 WOMs (no spares) - AH not included for now. Assume 150 lbs crate.
1.5 |  | Calibration Devices 87-88 | Calibration devices for 2 strings from DESY/Germany/Sweden (4+2 POCAMs, 3+1 Acoustic sensors, 2+1 Swedish Cameras) - Do Not Deep Freeze | 62 | 38 | 41 | 1 | 55.9005 | 836 | 836 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 87-88 = 2+1 Sweden Camera + 3+1 Acoustic Module + 4+1 POCAM, including spares, 200 lbs crate
1.4 |  | FieldHub electronics | Required onsite for FY24 installation. 1 crate containing readout electronics for installation in ICL - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 275 | 275 | preliminary | DNF | DESY | 2023-08-01 | DESY-CHC | 2023-08-15 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | No | FY24 inter | FY24 intra | J. Kelley | 2021-10-13 | D. Tosi | 2021-10-13 | Field Hubs are 442mm x 480mm x 133 mm (17.4" x 18.9" x 5.2") and weight maybe 10 lb each. 100 lbs crate.
1.3 |  | String Sensors 89-93 | Optical sensors for 5 strings from Germany (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 12 | 613.3333 | 573 | 6876 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is (28kg/sensor boxed) + 35kg pallet, assume 8 mDOMs/pallet - 190 to be deployed + 10 spares. (**) shipped in 20 HC container. Container not included in weight as pallets will be taken out.
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from DESY/Germany/Sweden (6 WOMs, 3 Abalone Hubs or WOM Traps) no spares - Do Not Deep Freeze | 32 | 31 | 89 | 1 | 51.0926 | 1035 | 1035 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 6 Special Devices from Germany 6 (WOM + 0 AH) including 0 spare for each. Assume 170 lbs crate.
1.5 |  | Calibration Devices 89-93 | Calibration for 5 strings from DESY/Germany/Sweden (17+2 POCAMs, 7+ 1 Acoustic sensors, 3+ 1 Swedish Cameras) including spares - Do Not Deep Freeze | 62 | 48 | 44 | 1 | 75.7778 | 1694 | 1694 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 89-93 = 3+1 Sweden Camera,7+1 + Acoustic Module,17 +1 POCAM, including spares, 200 lbs crate
|  | DESY/Aachen/TUM/Sweden etc Totals: |  |  |  | TEU=> | 1.7784 | 1692.9931 |  | 20585
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 4 | 335 | 794 | 3176 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter (SPARES - TBD) - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 1 | 83.75 | 794 | 794 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 4 | 469 | 1168.5 | 4674 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter (SPARES - TBD)- Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 1 | 117.25 | 1168.5 | 1168.5 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 8 sensors in McMurdo overwinter - Do Not Deep Freeze | 45 | 48 | 67 | 10 | 837.5 | 794 | 7940 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 12 sensors in McMurdo overwinter - Do Not Deep Freeze | 63 | 48 | 67 | 10 | 1172.5 | 1168.5 | 11685 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
|  | Chiba Totals: |  |  |  | TEU=> | 3.167 | 3015 |  | 29437.5
1.2 |  | Field Season 1 Fuel | Fuel to support FY23 field season - Base fuel |  |  |  | 3191 | 426.5746 | 6.8 | 21698.8 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 1 Fuel Contingency | Fuel to support FY23 field season - Contingency |  |  |  | 452 | 60.4236 | 6.8 | 3073.6 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel | Fuel to support FY24 field season - Base fuel, firn drilling & over winter heating |  |  |  | 18178 | 2430.045 | 6.8 | 123610.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel Contingency | Fuel to suppport FY24 field season - Contingency |  |  |  | 2373 | 317.2239 | 6.8 | 16136.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel | Fuel to support FY25 field season - Base fuel & deep drilling |  |  |  | 62694 | 8380.9682 | 6.8 | 426319.2 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 44483 | I. McEwen | 44483
1.2 |  | Field Season 3 Fuel Contingency | Fuel to suppport FY25 field season - Contingency |  |  |  | 8473 | 1132.6753 | 6.8 | 57616.4 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 44483 | I. McEwen | 44483
|  | Fuel Totals: |  |  |  | TEU=> | 13.3907 | 12747.9106 |  | 648454.8
|  |  | All IC/Upgrade cargo volume: |  |  | TEU=> | 55.9647 | 53278.3808 |  | 1167584.3
|  | total volume [cubic feet] | total weight [lbs]
Total Cargo for selected items |  | 9962.1233 | 121001
Total Cargo according to dates |  | 9962.1233 | 121001
Start date |  | End date
2020-11-01 |  | 2021-11-01

## FY22 inter
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Gen 1 - housed in 20' container | Power generation unit 1 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 2 - housed in 20' container | Power generation unit 2 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 3 - housed in 20' container | Power generation unit 3 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | - | In McMurdo |  | SPoT | 2022-12-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | 287 Loader | Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use | 114 | 77 | 96 | 1 | 487.6667 | 10273 | 10273 | actual |  | U. Wisc. Madison |  | In McMurdo | 2019-11-15 | Truck | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2022-12-01 | No* | In McMurdo | FY23 intra | D. Gibson | 2021-10-07 | I. McEwen | 2021-10-07 | *Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use
1.2 |  | Gen hoods Discharge Hoods - currently staged in McMurdo | Generator air discharge hoods , sheet metal, loose - stored on berm at SPOTSA | 108 | 53 | 60 | 2 | 397.5 | 330 | 660 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo |  |  | In McMurdo |  | - | In McMurdo |  | LC-130/SPoT | 2024-01-01 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Testing/limited operation of Gens can be accomplished without hoods - Hoods required for the drill season
1.2 |  | Firn Drill | Bermed in McM - will require McM fork or crane support. | 264 | 94 | 97 | 1 | 1393.0278 | 12000 | 12000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA
1.2 |  | Firn Drill Components - 1 | Firn drill sheave. Required Field Season 2 for final refit & functional testing | 97 | 44 | 63 | 1 | 155.6042 | 920 | 920 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Firn Drill Components - 2 | Firn drill drillhead. Required Field Season 2 for final refit & functional testing | 125 | 33 | 37 | 1 | 88.3247 | 1048 | 1048 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Weight stack and crates | Bermed in McM - will require McM fork support. Drill head weight stack and remaining bermed crates at SPoTSA | 120 | 48 | 48 | 1 | 160 | 600 | 600 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-15 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack
1.2 |  | Fuel Tower | Bermed in McM - will require McM fork or crane support. | 96 | 72 | 120 | 1 | 480 | 1500 | 1500 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack - overland shipment preferred due to complexities of air transport certification - can be laid on side once drained
1.2 |  | HPU 1 | HPU 1 (University of Nebraska - Lincoln asset) - 40' container housing heating plant on ISO sled | 480 | 96 | 102 | 1 | 2720 | 28000 | 28000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2024-01-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | HPU 1 integration with Rodwell system required before drill season on it's own sled which will require evaluation and repair - Stored at SPOTSA
|  | McMurdo totals: |  |  |  | TEU=> | 10.4644 | 9962.1233 |  | 121001
1.2 |  | Container Ski Stack (comprised of 5 sleds) - currently staged in Pt. Hueneme | Five sets of aluminum skis for 20' containers - stacked. Aluminum skis for drill containers. Required onsite for local movement of Gens and PDM. | 240 | 96 | 96 | 1 | 1280 | 4255 | 4255 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | No* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *While this shipment is not on the critical path additional ASC crane support will be required to overcome delayed arrival or sleds furnished from the South Pole inventory
1.2 |  | Generator Intake Hood - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 174 | 53 | 96 | 3 | 1537 | 586.6667 | 1760 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477
1.2 |  | Generator Discharge Hoods - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 108 | 53 | 60 | 2 | 397.5 | 1210 | 2420 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 9 Spools - 348 cf / 3532 lbs each - Shipped from Italy | 92 | 92 | 70.5 | 9 | 3107.875 | 3531.5556 | 31784 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-08-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 3 Spools - 348 cf / 5001 lbs each - Shipped from PSL | 92 | 92 | 70.5 | 3 | 1035.9583 | 5001 | 15003 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
|  | Pt. Hueneme totals: |  |  |  | TEU=> | 7.7293 | 7358.3333 |  | 55222
1.2 |  | 8' Refit Container | Priority refit materials including tools, flowmeter assemblies, motor drive installation kits, hardware, fittings, sensors, & consumables | 96 | 86 | 96 | 1 | 458.6667 | 5600 | 5600 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130 | 2022-11-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | 8' container moves with contents by LC130 or is broken down for movement by Basler
1.2 |  | 20' Refit Container A | Refit materials incl. submersible pumps, hardware, filtration components, fall arrest towers, tools, & hose crimper | 240 | 96 | 102 | 1 | 1360 | 17500 | 17500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | 20' Refit Container B | Bulky materials incl. cable trays, vertical turbine pumps, vertical turbine pump motors, ladders, water tank doghouse/railing materials, 287 forks, generator parts, TU20 shaft, & drill weight stack | 240 | 96 | 102 | 1 | 1360 | 15500 | 15500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | ARA Trailer | Enclosed trailer on skis housing 35kw generator | 192 | 96 | 88 | 1 | 938.6667 | 4860 | 4860 | actual | FLAMMABLE liquid power engine | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *If this shipment is delayed 480 volt power generation support will be required in FW YR 1 by the contractor. Aside from the CRREL generator (far larger than required with high fuel burn rate) the capacity does not currently exist at the Pole.
1.2 |  | Return Water Cable Reel (RWCR) | Smaller reel - can fit in 20' container. Required onsite in FY23 for final integration and pre-drill activites | 112 | 80 | 80 | 1 | 414.8148 | 4000 | 4000 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight from Gen 1 shipment information see picture
1.2 |  | Main Cable Reel (MCR) | Required onsite in FY23 for final integration and pre-drill activites. Large cable reel - will require flat rack on vessel | 140 | 96 | 95 | 1 | 738.8889 | 12500 | 12500 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FS Y1 for final integration and pre-drill activities
1.2 |  | Controls infrastructure - Motor drives, PLCs, electrical hardware, and motor drive mounting kits | Components and equipment to support field season 1 controls system tasking - ComSur - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Weight estimated
1.4 |  | ICL power and timing electronics | 1 crate containing rackmount electronics for power and timing systems - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 600 | 600 | estimated | DNF | U. Wisc. Madison | 2023-08-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12
1.4 |  | ICL patch cables and patch panels | Standard vessel shipping - can overwinter in McM if shipped earlier - Do Not Deep Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNDF [TBD] | U. Wisc. Madison | 2023-06-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12 | (*) storage in McMurdo pending low temperature test
1.2 |  | ARA Drill System Components - Crate 1 | ARA (Antarctic Rodwell Appartus) - downhole pump controller, ePump controller, splash cam kit, and accessories - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477
1.2 |  | ARA Drill System Components - Crate 2 | ARA (Antarctic Rodwell Appartus) - new downhole pumps, spares, accessories and tools | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477
1.2 |  | Camp Hose - currently staged at PSL | Two spools of hose - 348 cf / 4990 lbs each. Required for SES set-up - no DNDF requirement. | 92 | 92 | 71 | 2 | 695.537 | 4990 | 9980 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY22 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Bull wheel | Bull wheel assembly - used to install main cable on reel in event of main cable damage/failure | 88 | 58 | 97 | 1 | 286.5093 | 2880 | 2880 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2024-02-01 | No | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight and cube used from Gen 1 shipping label still on bull wheel.
1.2 |  | Load member cable reel | Cable Reel used to deploy downhole load member during string installation | 84 | 60 | 48 | 1 | 140 | 3800 | 3800 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-15 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 for integration - recent addition, still in development
1.2 |  | DOM Handling Facility (DHF) | Standard vessel shipping - can overwinter in McM. | 240 | 96 | 96 | 1 | 1280 | 12000 | 12000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Sensor Handling Facility construction scheduled to begin mid-December FY24
1.2 |  | Spare Combo cable | Spare cable for Return Water Cable Reel - on spool | 72 | 72 | 72 | 1 | 216 | 3000 | 3000 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Spare Drill Cable | Standard vessel shipping - can overwinter in McM. Cable on steel spool. | 83 | 83 | 61 | 1 | 243.1881 | 6835 | 6835 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Computing/controls components | Computing and controls equipment (Motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 to support controls system tasking
1.2 |  | Driller resupply/refit components - 8' Container | 8' Mini Milvan; Consumables/drill components | 96 | 86 | 96 | 1 | 458.6667 | 6500 | 6500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season - 8' container moves with contents overland or by air
1.2 |  | Drill refit components | Single crate. Consumables/drill refit components | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated |  | U. Wisc. Madison |  | UWM-PTH | 2023-08-01 | Truck | PTH - CHC |  | Comsur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season
1.2 |  | Drill Heads DNF - X | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-02-12 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | One drill head shipped one year early for ull system wet-test
1.2 |  | Drill Heads DNF - Y | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Heads DNF - R | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Computing/controls components | Computing and controls equipment (Sensor, motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-15 | Yes | FY25 inter | FY25 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Installation Hardware 87-93 | Installation hardware for winterover storage at Pole | 96 | 48 | 48 | 7 | 896 | 1000 | 7000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.2 |  | Installation Weights 87-93 | Installation weights for winterover storage at Pole | 36 | 24 | 24 | 7 | 84 | 785.7143 | 5500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.5 |  | Calibration/Special Devices 87-88 | 3+1 PencilBeams from UW, 2+1 pDOM and 1+1 LOMs - Do Not Deep Freeze | 58 | 38 | 41 | 1 | 52.294 | 836 | 836 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from UW (4+1 Radio Pulsers (all strings) 1+1 Radio Receivers, 3+1 FOM) - Do Not Deep Freeze | 63 | 40 | 42 | 1 | 61.25 | 677 | 677 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 4+1 Radio Pulser, weight 50 kg. 1+1 Radio receiver, assume mDOM weight, 3+1 FOM (assume mDOM weight) + 2ftx2ftx4ft FOM box (50 lbs). Special Devices from UW. FTS, seismometer missing from estimate. 250 lbs crate estimate
1.2 |  | Misc. Science Equipment - FY24 | Scientific and test equipment (SPAT, DCM et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-10-08 | D. Tosi | 2021-10-08
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from UW (4+1 FOM,2+1 Radio Receivers, 11+1 LOM + seismometer*) - Do Not Deep Freeze | 81 | 56 | 51 | 1 | 133.875 | 1797 | 1797 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 21 Special Devices from USA (11+ 1 LOM, 4+1 FOM, 2+1 RR, FTS ? , seismometer), assume mDOM weight. 200 lbs wood crate. FTS not included. (*) Seismometer not yet in CMD
1.5 |  | Calibration/Special Devices 89-93 | 8+1 PencilBeams, 12+1 pDOMs from UW - Do Not Deep Freeze | 75 | 56.5 | 41 | 1 | 100.5425 | 1602 | 1602 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-05 | 8+1 PencilBeams for strings 89-93, 12+1 pDOMs, assume mDOM weight. 244 lbs crate.
1.2 |  | Misc. Science Equipment - FY25 | Scientific and test equipment (Handheld test devices, Paros, et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-12-01 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | D. Tosi | 2021-10-08
1.5 |  | Dust logging device | Blue Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-18 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Green Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-19 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 24 | 24 | 1 | 8.6667 | 120 | 120 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-20 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 23 | 20 | 1 | 6.9213 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-21 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Logging winch | Winch to be used for Dust Logging | 86 | 60 | 68 | 1 | 203.0556 | 3500 | 3500 | IDP deep logging winch for reference |  | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.5 |  | Logging winch control box | Control Box for winch for Dust Logging - sensitive equipment - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 400 | 400 | IDP deep logging winch for reference | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
|  | U. Wisconsin totals: |  |  |  | TEU=> | 12.1277 | 11545.5987 |  | 148947
1.4 |  | Surface Junction Boxes | Surface Junction Boxes can overwinter in McM if shipped earlier. 7 junction boxes | 66 | 30 | 14 | 7 | 112.2917 | 200 | 1400 | preliminary |  | MSU | 2022-11-01 | MSU-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-10 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | Each is 66" x 30" x 14", each is 112 lbs. Assume Folding crate
1.4 |  | Surface Cable Assemblies | Palletized wooden cable drums (Qty: 7). Can overwinter in MCM. | 48 | 65 | 71 | 7 | 897.3611 | 1335.7143 | 9350 | actual |  | MSU | 2021-11-30 | MSU-PTH | 2022-12-01 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-11-20 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Breakout cables for strings 87-88 | Standard vessel shipping. 2 wooden crates containing spooled breakout cable assemblies - 96 cf / 1,000 lbs each - Do Not Deep Freeze | 72 | 48 | 48 | 2 | 192 | 1000 | 2000 | estimated | DNDF[-40C](*) | MSU | 2023-02-28 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | Preliminary estimate of weight and size. Pre-staging string 87-88 equipment in cryo or ICL. - if shipping to Pole not possible before end of 23/24 season could overwinter in McM (at an increased risk and pending low temperature test)
1.4 |  | Breakout cables for strings 89-93 | Stored in McMurdo FY24. 5 wooden crates containing spooled breakout cable assemblies - 96 cf/ 1,000 lbs each (preliminary) - Do Not Deep Freeze | 72 | 48 | 48 | 5 | 480 | 1000 | 5000 | estimated | DNDF[-40C](*) | MSU | 2023-05-22 | MSU-PTH | 2023-06-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-11-25 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-09-20 | Preliminary estimate of weight and size. (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) load members 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 47 | 47 | 39 | 7 | 348.9913 | 766 | 5362 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) cables 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 96 | 96 | 96 | 7 | 3584 | 15000 | 105000 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 25 | 1277.7778 | 573 | 14325 | final weight(**) | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 28 kg/boxed + 35kg pallet, assume 8 mDOMs/pallet (189 to be deployed + 11 spares)(*)Assumed to be shipped in 2x20' HC (5115 lbs, 238inx96inx114in) or a 40 ft HC, purchased by MSU or loaned in PTH (container weight not included)
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) containers (TBD) - Do Not Deep Freeze | 238 | 96 | 114 | 0 | 0 | 5115 | 0 | see notes in item above | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | Assume 2x20HC containers for transport on COMSUR (TBC). Pallets could be loaded to 53 ft truck and loaded into a loaned container in PTH but this would increase touch points (and risk)
|  | MSU Totals: |  |  |  | TEU=> | 7.2399 | 6892.4219 |  | 142437
1.3 |  | DM-Ice | DM-ice (two modules for string 89 and 90) - Do Not Deep Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNDF [-40C] | Yale |  | Yale-PTH |  | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | M. Kauer | 2021-09-20 | D. Tosi | 2021-09-20
|  | Other Institutions Totals: |  |  |  |  | 0.067227 | 64 |  | 1500
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (spares included) - Do Not Deep Freeze | 40 | 48 | 46 | 16 | 817.7778 | 573 | 9168 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - 116 to be deployed + 12 spares - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (SPARES) - Do Not Deep Freeze | 40 | 48 | 46 | 0 | 0 | 573 | 0 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from DESY/Germany/Sweden (8 WOMs, 0 Abalone) + spares - Do Not Deep Freeze | 40 | 21 | 64 | 1 | 31.1111 | 701 | 701 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 8 WOMs (no spares) - AH not included for now. Assume 150 lbs crate.
1.5 |  | Calibration Devices 87-88 | Calibration devices for 2 strings from DESY/Germany/Sweden (4+2 POCAMs, 3+1 Acoustic sensors, 2+1 Swedish Cameras) - Do Not Deep Freeze | 62 | 38 | 41 | 1 | 55.9005 | 836 | 836 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 87-88 = 2+1 Sweden Camera + 3+1 Acoustic Module + 4+1 POCAM, including spares, 200 lbs crate
1.4 |  | FieldHub electronics | Required onsite for FY24 installation. 1 crate containing readout electronics for installation in ICL - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 275 | 275 | preliminary | DNF | DESY | 2023-08-01 | DESY-CHC | 2023-08-15 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | No | FY24 inter | FY24 intra | J. Kelley | 2021-10-13 | D. Tosi | 2021-10-13 | Field Hubs are 442mm x 480mm x 133 mm (17.4" x 18.9" x 5.2") and weight maybe 10 lb each. 100 lbs crate.
1.3 |  | String Sensors 89-93 | Optical sensors for 5 strings from Germany (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 12 | 613.3333 | 573 | 6876 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is (28kg/sensor boxed) + 35kg pallet, assume 8 mDOMs/pallet - 190 to be deployed + 10 spares. (**) shipped in 20 HC container. Container not included in weight as pallets will be taken out.
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from DESY/Germany/Sweden (6 WOMs, 3 Abalone Hubs or WOM Traps) no spares - Do Not Deep Freeze | 32 | 31 | 89 | 1 | 51.0926 | 1035 | 1035 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 6 Special Devices from Germany 6 (WOM + 0 AH) including 0 spare for each. Assume 170 lbs crate.
1.5 |  | Calibration Devices 89-93 | Calibration for 5 strings from DESY/Germany/Sweden (17+2 POCAMs, 7+ 1 Acoustic sensors, 3+ 1 Swedish Cameras) including spares - Do Not Deep Freeze | 62 | 48 | 44 | 1 | 75.7778 | 1694 | 1694 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 89-93 = 3+1 Sweden Camera,7+1 + Acoustic Module,17 +1 POCAM, including spares, 200 lbs crate
|  | DESY/Aachen/TUM/Sweden etc Totals: |  |  |  | TEU=> | 1.7784 | 1692.9931 |  | 20585
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 4 | 335 | 794 | 3176 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter (SPARES - TBD) - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 1 | 83.75 | 794 | 794 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 4 | 469 | 1168.5 | 4674 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter (SPARES - TBD)- Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 1 | 117.25 | 1168.5 | 1168.5 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 8 sensors in McMurdo overwinter - Do Not Deep Freeze | 45 | 48 | 67 | 10 | 837.5 | 794 | 7940 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 12 sensors in McMurdo overwinter - Do Not Deep Freeze | 63 | 48 | 67 | 10 | 1172.5 | 1168.5 | 11685 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
|  | Chiba Totals: |  |  |  | TEU=> | 3.167 | 3015 |  | 29437.5
1.2 |  | Field Season 1 Fuel | Fuel to support FY23 field season - Base fuel |  |  |  | 3191 | 426.5746 | 6.8 | 21698.8 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 1 Fuel Contingency | Fuel to support FY23 field season - Contingency |  |  |  | 452 | 60.4236 | 6.8 | 3073.6 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel | Fuel to support FY24 field season - Base fuel, firn drilling & over winter heating |  |  |  | 18178 | 2430.045 | 6.8 | 123610.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel Contingency | Fuel to suppport FY24 field season - Contingency |  |  |  | 2373 | 317.2239 | 6.8 | 16136.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel | Fuel to support FY25 field season - Base fuel & deep drilling |  |  |  | 62694 | 8380.9682 | 6.8 | 426319.2 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 44483 | I. McEwen | 44483
1.2 |  | Field Season 3 Fuel Contingency | Fuel to suppport FY25 field season - Contingency |  |  |  | 8473 | 1132.6753 | 6.8 | 57616.4 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 44483 | I. McEwen | 44483
|  | Fuel Totals: |  |  |  | TEU=> | 13.3907 | 12747.9106 |  | 648454.8
|  |  | All IC/Upgrade cargo volume: |  |  | TEU=> | 55.9647 | 53278.3808 |  | 1167584.3
|  | total volume [cubic feet] | total weight [lbs]
Total Cargo for selected items |  | 7246.5741 | 74195
Total Cargo according to dates |  | 7246.5741 | 74195
Start date | End date
2021-11-01 | 2022-02-15
Note on G13: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G19: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G58: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G66: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G76: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G83: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G84: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet

## FY23 inter
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Gen 1 - housed in 20' container | Power generation unit 1 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 2 - housed in 20' container | Power generation unit 2 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 3 - housed in 20' container | Power generation unit 3 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | - | In McMurdo |  | SPoT | 2022-12-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | 287 Loader | Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use | 114 | 77 | 96 | 1 | 487.6667 | 10273 | 10273 | actual |  | U. Wisc. Madison |  | In McMurdo | 2019-11-15 | Truck | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2022-12-01 | No* | In McMurdo | FY23 intra | D. Gibson | 2021-10-07 | I. McEwen | 2021-10-07 | *Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use
1.2 |  | Gen hoods Discharge Hoods - currently staged in McMurdo | Generator air discharge hoods , sheet metal, loose - stored on berm at SPOTSA | 108 | 53 | 60 | 2 | 397.5 | 330 | 660 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo |  |  | In McMurdo |  | - | In McMurdo |  | LC-130/SPoT | 2024-01-01 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Testing/limited operation of Gens can be accomplished without hoods - Hoods required for the drill season
1.2 |  | Firn Drill | Bermed in McM - will require McM fork or crane support. | 264 | 94 | 97 | 1 | 1393.0278 | 12000 | 12000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA
1.2 |  | Firn Drill Components - 1 | Firn drill sheave. Required Field Season 2 for final refit & functional testing | 97 | 44 | 63 | 1 | 155.6042 | 920 | 920 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Firn Drill Components - 2 | Firn drill drillhead. Required Field Season 2 for final refit & functional testing | 125 | 33 | 37 | 1 | 88.3247 | 1048 | 1048 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Weight stack and crates | Bermed in McM - will require McM fork support. Drill head weight stack and remaining bermed crates at SPoTSA | 120 | 48 | 48 | 1 | 160 | 600 | 600 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-15 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack
1.2 |  | Fuel Tower | Bermed in McM - will require McM fork or crane support. | 96 | 72 | 120 | 1 | 480 | 1500 | 1500 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack - overland shipment preferred due to complexities of air transport certification - can be laid on side once drained
1.2 |  | HPU 1 | HPU 1 (University of Nebraska - Lincoln asset) - 40' container housing heating plant on ISO sled | 480 | 96 | 102 | 1 | 2720 | 28000 | 28000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2024-01-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | HPU 1 integration with Rodwell system required before drill season on it's own sled which will require evaluation and repair - Stored at SPOTSA
|  | McMurdo totals: |  |  |  | TEU=> | 10.4644 | 9962.1233 |  | 121001
1.2 |  | Container Ski Stack (comprised of 5 sleds) - currently staged in Pt. Hueneme | Five sets of aluminum skis for 20' containers - stacked. Aluminum skis for drill containers. Required onsite for local movement of Gens and PDM. | 240 | 96 | 96 | 1 | 1280 | 4255 | 4255 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | No* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *While this shipment is not on the critical path additional ASC crane support will be required to overcome delayed arrival or sleds furnished from the South Pole inventory
1.2 |  | Generator Intake Hood - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 174 | 53 | 96 | 3 | 1537 | 586.6667 | 1760 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Generator Discharge Hoods - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 108 | 53 | 60 | 2 | 397.5 | 1210 | 2420 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 9 Spools - 348 cf / 3532 lbs each - Shipped from Italy | 92 | 92 | 70.5 | 9 | 3107.875 | 3531.5556 | 31784 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-08-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 3 Spools - 348 cf / 5001 lbs each - Shipped from PSL | 92 | 92 | 70.5 | 3 | 1035.9583 | 5001 | 15003 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
|  | Pt. Hueneme totals: |  |  |  | TEU=> | 7.7293 | 7358.3333 |  | 55222
1.2 |  | 8' Refit Container | Priority refit materials including tools, flowmeter assemblies, motor drive installation kits, hardware, fittings, sensors, & consumables | 96 | 86 | 96 | 1 | 458.6667 | 5600 | 5600 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130 | 2022-11-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | 8' container moves with contents by LC130 or is broken down for movement by Basler
1.2 |  | 20' Refit Container A | Refit materials incl. submersible pumps, hardware, filtration components, fall arrest towers, tools, & hose crimper | 240 | 96 | 102 | 1 | 1360 | 17500 | 17500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | 20' Refit Container B | Bulky materials incl. cable trays, vertical turbine pumps, vertical turbine pump motors, ladders, water tank doghouse/railing materials, 287 forks, generator parts, TU20 shaft, & drill weight stack | 240 | 96 | 102 | 1 | 1360 | 15500 | 15500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | ARA Trailer | Enclosed trailer on skis housing 35kw generator | 192 | 96 | 88 | 1 | 938.6667 | 4860 | 4860 | actual | FLAMMABLE liquid power engine | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | *If this shipment is delayed 480 volt power generation support will be required in FW YR 1 by the contractor. Aside from the CRREL generator (far larger than required with high fuel burn rate) the capacity does not currently exist at the Pole.
1.2 |  | Return Water Cable Reel (RWCR) | Smaller reel - can fit in 20' container. Required onsite in FY23 for final integration and pre-drill activites | 112 | 80 | 80 | 1 | 414.8148 | 4000 | 4000 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Weight from Gen 1 shipment information see picture
1.2 |  | Main Cable Reel (MCR) | Required onsite in FY23 for final integration and pre-drill activites. Large cable reel - will require flat rack on vessel | 140 | 96 | 95 | 1 | 738.8889 | 12500 | 12500 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Required onsite in FS Y1 for final integration and pre-drill activities
1.2 |  | Controls infrastructure - Motor drives, PLCs, electrical hardware, and motor drive mounting kits | Components and equipment to support field season 1 controls system tasking - ComSur - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight estimated
1.4 |  | ICL power and timing electronics | 1 crate containing rackmount electronics for power and timing systems - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 600 | 600 | estimated | DNF | U. Wisc. Madison | 2023-08-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12
1.4 |  | ICL patch cables and patch panels | Standard vessel shipping - can overwinter in McM if shipped earlier - Do Not Deep Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNDF [TBD] | U. Wisc. Madison | 2023-06-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12 | (*) storage in McMurdo pending low temperature test
1.2 |  | ARA Drill System Components - Crate 1 | ARA (Antarctic Rodwell Appartus) - downhole pump controller, ePump controller, splash cam kit, and accessories - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | ARA Drill System Components - Crate 2 | ARA (Antarctic Rodwell Appartus) - new downhole pumps, spares, accessories and tools | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Camp Hose - currently staged at PSL | Two spools of hose - 348 cf / 4990 lbs each. Required for SES set-up - no DNDF requirement. | 92 | 92 | 71 | 2 | 695.537 | 4990 | 9980 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY22 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Bull wheel | Bull wheel assembly - used to install main cable on reel in event of main cable damage/failure | 88 | 58 | 97 | 1 | 286.5093 | 2880 | 2880 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2024-02-01 | No | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight and cube used from Gen 1 shipping label still on bull wheel.
1.2 |  | Load member cable reel | Cable Reel used to deploy downhole load member during string installation | 84 | 60 | 48 | 1 | 140 | 3800 | 3800 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-15 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 for integration - recent addition, still in development
1.2 |  | DOM Handling Facility (DHF) | Standard vessel shipping - can overwinter in McM. | 240 | 96 | 96 | 1 | 1280 | 12000 | 12000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Sensor Handling Facility construction scheduled to begin mid-December FY24
1.2 |  | Spare Combo cable | Spare cable for Return Water Cable Reel - on spool | 72 | 72 | 72 | 1 | 216 | 3000 | 3000 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Spare Drill Cable | Standard vessel shipping - can overwinter in McM. Cable on steel spool. | 83 | 83 | 61 | 1 | 243.1881 | 6835 | 6835 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Computing/controls components | Computing and controls equipment (Motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 to support controls system tasking
1.2 |  | Driller resupply/refit components - 8' Container | 8' Mini Milvan; Consumables/drill components | 96 | 86 | 96 | 1 | 458.6667 | 6500 | 6500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season - 8' container moves with contents overland or by air
1.2 |  | Drill refit components | Single crate. Consumables/drill refit components | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated |  | U. Wisc. Madison |  | UWM-PTH | 2023-08-01 | Truck | PTH - CHC |  | Comsur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season
1.2 |  | Drill Heads DNF - X | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-02-12 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | One drill head shipped one year early for ull system wet-test
1.2 |  | Drill Heads DNF - Y | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Heads DNF - R | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Computing/controls components | Computing and controls equipment (Sensor, motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-15 | Yes | FY25 inter | FY25 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Installation Hardware 87-93 | Installation hardware for winterover storage at Pole | 96 | 48 | 48 | 7 | 896 | 1000 | 7000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.2 |  | Installation Weights 87-93 | Installation weights for winterover storage at Pole | 36 | 24 | 24 | 7 | 84 | 785.7143 | 5500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.5 |  | Calibration/Special Devices 87-88 | 3+1 PencilBeams from UW, 2+1 pDOM and 1+1 LOMs - Do Not Deep Freeze | 58 | 38 | 41 | 1 | 52.294 | 836 | 836 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from UW (4+1 Radio Pulsers (all strings) 1+1 Radio Receivers, 3+1 FOM) - Do Not Deep Freeze | 63 | 40 | 42 | 1 | 61.25 | 677 | 677 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 4+1 Radio Pulser, weight 50 kg. 1+1 Radio receiver, assume mDOM weight, 3+1 FOM (assume mDOM weight) + 2ftx2ftx4ft FOM box (50 lbs). Special Devices from UW. FTS, seismometer missing from estimate. 250 lbs crate estimate
1.2 |  | Misc. Science Equipment - FY24 | Scientific and test equipment (SPAT, DCM et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-10-08 | D. Tosi | 2021-10-08
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from UW (4+1 FOM,2+1 Radio Receivers, 11+1 LOM + seismometer*) - Do Not Deep Freeze | 81 | 56 | 51 | 1 | 133.875 | 1797 | 1797 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 21 Special Devices from USA (11+ 1 LOM, 4+1 FOM, 2+1 RR, FTS ? , seismometer), assume mDOM weight. 200 lbs wood crate. FTS not included. (*) Seismometer not yet in CMD
1.5 |  | Calibration/Special Devices 89-93 | 8+1 PencilBeams, 12+1 pDOMs from UW - Do Not Deep Freeze | 75 | 56.5 | 41 | 1 | 100.5425 | 1602 | 1602 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-05 | 8+1 PencilBeams for strings 89-93, 12+1 pDOMs, assume mDOM weight. 244 lbs crate.
1.2 |  | Misc. Science Equipment - FY25 | Scientific and test equipment (Handheld test devices, Paros, et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-12-01 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | D. Tosi | 2021-10-08
1.5 |  | Dust logging device | Blue Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-18 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Green Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-19 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 24 | 24 | 1 | 8.6667 | 120 | 120 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-20 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 23 | 20 | 1 | 6.9213 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-21 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Logging winch | Winch to be used for Dust Logging | 86 | 60 | 68 | 1 | 203.0556 | 3500 | 3500 | IDP deep logging winch for reference |  | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.5 |  | Logging winch control box | Control Box for winch for Dust Logging - sensitive equipment - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 400 | 400 | IDP deep logging winch for reference | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
|  | U. Wisconsin totals: |  |  |  | TEU=> | 12.1277 | 11545.5987 |  | 148947
1.4 |  | Surface Junction Boxes | Surface Junction Boxes can overwinter in McM if shipped earlier. 7 junction boxes | 66 | 30 | 14 | 7 | 112.2917 | 200 | 1400 | preliminary |  | MSU | 2022-11-01 | MSU-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-10 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | Each is 66" x 30" x 14", each is 112 lbs. Assume Folding crate
1.4 |  | Surface Cable Assemblies | Palletized wooden cable drums (Qty: 7). Can overwinter in MCM. | 48 | 65 | 71 | 7 | 897.3611 | 1335.7143 | 9350 | actual |  | MSU | 2021-11-30 | MSU-PTH | 2022-12-01 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-11-20 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Breakout cables for strings 87-88 | Standard vessel shipping. 2 wooden crates containing spooled breakout cable assemblies - 96 cf / 1,000 lbs each - Do Not Deep Freeze | 72 | 48 | 48 | 2 | 192 | 1000 | 2000 | estimated | DNDF[-40C](*) | MSU | 2023-02-28 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | Preliminary estimate of weight and size. Pre-staging string 87-88 equipment in cryo or ICL. - if shipping to Pole not possible before end of 23/24 season could overwinter in McM (at an increased risk and pending low temperature test)
1.4 |  | Breakout cables for strings 89-93 | Stored in McMurdo FY24. 5 wooden crates containing spooled breakout cable assemblies - 96 cf/ 1,000 lbs each (preliminary) - Do Not Deep Freeze | 72 | 48 | 48 | 5 | 480 | 1000 | 5000 | estimated | DNDF[-40C](*) | MSU | 2023-05-22 | MSU-PTH | 2023-06-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-11-25 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-09-20 | Preliminary estimate of weight and size. (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) load members 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 47 | 47 | 39 | 7 | 348.9913 | 766 | 5362 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) cables 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 96 | 96 | 96 | 7 | 3584 | 15000 | 105000 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 25 | 1277.7778 | 573 | 14325 | final weight(**) | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 28 kg/boxed + 35kg pallet, assume 8 mDOMs/pallet (189 to be deployed + 11 spares)(*)Assumed to be shipped in 2x20' HC (5115 lbs, 238inx96inx114in) or a 40 ft HC, purchased by MSU or loaned in PTH (container weight not included)
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) containers (TBD) - Do Not Deep Freeze | 238 | 96 | 114 | 0 | 0 | 5115 | 0 | see notes in item above | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | Assume 2x20HC containers for transport on COMSUR (TBC). Pallets could be loaded to 53 ft truck and loaded into a loaned container in PTH but this would increase touch points (and risk)
|  | MSU Totals: |  |  |  | TEU=> | 7.2399 | 6892.4219 |  | 142437
1.3 |  | DM-Ice | DM-ice (two modules for string 89 and 90) - Do Not Deep Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNDF [-40C] | Yale |  | Yale-PTH |  | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | M. Kauer | 2021-09-20 | D. Tosi | 2021-09-20
|  | Other Institutions Totals: |  |  |  |  | 0.067227 | 64 |  | 1500
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (spares included) - Do Not Deep Freeze | 40 | 48 | 46 | 16 | 817.7778 | 573 | 9168 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - 116 to be deployed + 12 spares - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (SPARES) - Do Not Deep Freeze | 40 | 48 | 46 | 0 | 0 | 573 | 0 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from DESY/Germany/Sweden (8 WOMs, 0 Abalone) + spares - Do Not Deep Freeze | 40 | 21 | 64 | 1 | 31.1111 | 701 | 701 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 8 WOMs (no spares) - AH not included for now. Assume 150 lbs crate.
1.5 |  | Calibration Devices 87-88 | Calibration devices for 2 strings from DESY/Germany/Sweden (4+2 POCAMs, 3+1 Acoustic sensors, 2+1 Swedish Cameras) - Do Not Deep Freeze | 62 | 38 | 41 | 1 | 55.9005 | 836 | 836 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 87-88 = 2+1 Sweden Camera + 3+1 Acoustic Module + 4+1 POCAM, including spares, 200 lbs crate
1.4 |  | FieldHub electronics | Required onsite for FY24 installation. 1 crate containing readout electronics for installation in ICL - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 275 | 275 | preliminary | DNF | DESY | 2023-08-01 | DESY-CHC | 2023-08-15 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | No | FY24 inter | FY24 intra | J. Kelley | 2021-10-13 | D. Tosi | 2021-10-13 | Field Hubs are 442mm x 480mm x 133 mm (17.4" x 18.9" x 5.2") and weight maybe 10 lb each. 100 lbs crate.
1.3 |  | String Sensors 89-93 | Optical sensors for 5 strings from Germany (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 12 | 613.3333 | 573 | 6876 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is (28kg/sensor boxed) + 35kg pallet, assume 8 mDOMs/pallet - 190 to be deployed + 10 spares. (**) shipped in 20 HC container. Container not included in weight as pallets will be taken out.
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from DESY/Germany/Sweden (6 WOMs, 3 Abalone Hubs or WOM Traps) no spares - Do Not Deep Freeze | 32 | 31 | 89 | 1 | 51.0926 | 1035 | 1035 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 6 Special Devices from Germany 6 (WOM + 0 AH) including 0 spare for each. Assume 170 lbs crate.
1.5 |  | Calibration Devices 89-93 | Calibration for 5 strings from DESY/Germany/Sweden (17+2 POCAMs, 7+ 1 Acoustic sensors, 3+ 1 Swedish Cameras) including spares - Do Not Deep Freeze | 62 | 48 | 44 | 1 | 75.7778 | 1694 | 1694 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 89-93 = 3+1 Sweden Camera,7+1 + Acoustic Module,17 +1 POCAM, including spares, 200 lbs crate
|  | DESY/Aachen/TUM/Sweden etc Totals: |  |  |  | TEU=> | 1.7784 | 1692.9931 |  | 20585
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 4 | 335 | 794 | 3176 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter (SPARES - TBD) - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 1 | 83.75 | 794 | 794 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 4 | 469 | 1168.5 | 4674 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter (SPARES - TBD)- Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 1 | 117.25 | 1168.5 | 1168.5 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 8 sensors in McMurdo overwinter - Do Not Deep Freeze | 45 | 48 | 67 | 10 | 837.5 | 794 | 7940 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 12 sensors in McMurdo overwinter - Do Not Deep Freeze | 63 | 48 | 67 | 10 | 1172.5 | 1168.5 | 11685 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
|  | Chiba Totals: |  |  |  | TEU=> | 3.167 | 3015 |  | 29437.5
1.2 |  | Field Season 1 Fuel | Fuel to support FY23 field season - Base fuel |  |  |  | 3191 | 426.5746 | 6.8 | 21698.8 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 1 Fuel Contingency | Fuel to support FY23 field season - Contingency |  |  |  | 452 | 60.4236 | 6.8 | 3073.6 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel | Fuel to support FY24 field season - Base fuel, firn drilling & over winter heating |  |  |  | 18178 | 2430.045 | 6.8 | 123610.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel Contingency | Fuel to suppport FY24 field season - Contingency |  |  |  | 2373 | 317.2239 | 6.8 | 16136.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel | Fuel to support FY25 field season - Base fuel & deep drilling |  |  |  | 62694 | 8380.9682 | 6.8 | 426319.2 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 44483 | I. McEwen | 44483
1.2 |  | Field Season 3 Fuel Contingency | Fuel to suppport FY25 field season - Contingency |  |  |  | 8473 | 1132.6753 | 6.8 | 57616.4 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 44483 | I. McEwen | 44483
|  | Fuel Totals: |  |  |  | TEU=> | 13.3907 | 12747.9106 |  | 648454.8
|  |  | All IC/Upgrade cargo volume: |  |  | TEU=> | 55.9647 | 53278.3808 |  | 1167584.3
|  | total volume [cubic feet] | total weight [lbs]
Total Cargo for selected items |  | 9729.4936 | 111629.4
Total Cargo according to dates |  | 9729.4936 | 111629.4
Start date | End date
2022-11-01 | 2023-02-15

## FY23 intra
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Gen 1 - housed in 20' container | Power generation unit 1 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 2 - housed in 20' container | Power generation unit 2 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 3 - housed in 20' container | Power generation unit 3 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | - | In McMurdo |  | SPoT | 2022-12-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | 287 Loader | Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use | 114 | 77 | 96 | 1 | 487.6667 | 10273 | 10273 | actual |  | U. Wisc. Madison |  | In McMurdo | 2019-11-15 | Truck | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2022-12-01 | No* | In McMurdo | FY23 intra | D. Gibson | 2021-10-07 | I. McEwen | 2021-10-07 | *Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use
1.2 |  | Gen hoods Discharge Hoods - currently staged in McMurdo | Generator air discharge hoods , sheet metal, loose - stored on berm at SPOTSA | 108 | 53 | 60 | 2 | 397.5 | 330 | 660 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo |  |  | In McMurdo |  | - | In McMurdo |  | LC-130/SPoT | 2024-01-01 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Testing/limited operation of Gens can be accomplished without hoods - Hoods required for the drill season
1.2 |  | Firn Drill | Bermed in McM - will require McM fork or crane support. | 264 | 94 | 97 | 1 | 1393.0278 | 12000 | 12000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA
1.2 |  | Firn Drill Components - 1 | Firn drill sheave. Required Field Season 2 for final refit & functional testing | 97 | 44 | 63 | 1 | 155.6042 | 920 | 920 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Firn Drill Components - 2 | Firn drill drillhead. Required Field Season 2 for final refit & functional testing | 125 | 33 | 37 | 1 | 88.3247 | 1048 | 1048 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Weight stack and crates | Bermed in McM - will require McM fork support. Drill head weight stack and remaining bermed crates at SPoTSA | 120 | 48 | 48 | 1 | 160 | 600 | 600 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-15 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack
1.2 |  | Fuel Tower | Bermed in McM - will require McM fork or crane support. | 96 | 72 | 120 | 1 | 480 | 1500 | 1500 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack - overland shipment preferred due to complexities of air transport certification - can be laid on side once drained
1.2 |  | HPU 1 | HPU 1 (University of Nebraska - Lincoln asset) - 40' container housing heating plant on ISO sled | 480 | 96 | 102 | 1 | 2720 | 28000 | 28000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2024-01-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | HPU 1 integration with Rodwell system required before drill season on it's own sled which will require evaluation and repair - Stored at SPOTSA
|  | McMurdo totals: |  |  |  | TEU=> | 10.4644 | 9962.1233 |  | 121001
1.2 |  | Container Ski Stack (comprised of 5 sleds) - currently staged in Pt. Hueneme | Five sets of aluminum skis for 20' containers - stacked. Aluminum skis for drill containers. Required onsite for local movement of Gens and PDM. | 240 | 96 | 96 | 1 | 1280 | 4255 | 4255 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | No* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *While this shipment is not on the critical path additional ASC crane support will be required to overcome delayed arrival or sleds furnished from the South Pole inventory
1.2 |  | Generator Intake Hood - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 174 | 53 | 96 | 3 | 1537 | 586.6667 | 1760 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477
1.2 |  | Generator Discharge Hoods - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 108 | 53 | 60 | 2 | 397.5 | 1210 | 2420 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 9 Spools - 348 cf / 3532 lbs each - Shipped from Italy | 92 | 92 | 70.5 | 9 | 3107.875 | 3531.5556 | 31784 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-08-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 3 Spools - 348 cf / 5001 lbs each - Shipped from PSL | 92 | 92 | 70.5 | 3 | 1035.9583 | 5001 | 15003 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
|  | Pt. Hueneme totals: |  |  |  | TEU=> | 7.7293 | 7358.3333 |  | 55222
1.2 |  | 8' Refit Container | Priority refit materials including tools, flowmeter assemblies, motor drive installation kits, hardware, fittings, sensors, & consumables | 96 | 86 | 96 | 1 | 458.6667 | 5600 | 5600 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130 | 2022-11-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | 8' container moves with contents by LC130 or is broken down for movement by Basler
1.2 |  | 20' Refit Container A | Refit materials incl. submersible pumps, hardware, filtration components, fall arrest towers, tools, & hose crimper | 240 | 96 | 102 | 1 | 1360 | 17500 | 17500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | 20' Refit Container B | Bulky materials incl. cable trays, vertical turbine pumps, vertical turbine pump motors, ladders, water tank doghouse/railing materials, 287 forks, generator parts, TU20 shaft, & drill weight stack | 240 | 96 | 102 | 1 | 1360 | 15500 | 15500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | ARA Trailer | Enclosed trailer on skis housing 35kw generator | 192 | 96 | 88 | 1 | 938.6667 | 4860 | 4860 | actual | FLAMMABLE liquid power engine | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *If this shipment is delayed 480 volt power generation support will be required in FW YR 1 by the contractor. Aside from the CRREL generator (far larger than required with high fuel burn rate) the capacity does not currently exist at the Pole.
1.2 |  | Return Water Cable Reel (RWCR) | Smaller reel - can fit in 20' container. Required onsite in FY23 for final integration and pre-drill activites | 112 | 80 | 80 | 1 | 414.8148 | 4000 | 4000 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight from Gen 1 shipment information see picture
1.2 |  | Main Cable Reel (MCR) | Required onsite in FY23 for final integration and pre-drill activites. Large cable reel - will require flat rack on vessel | 140 | 96 | 95 | 1 | 738.8889 | 12500 | 12500 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FS Y1 for final integration and pre-drill activities
1.2 |  | Controls infrastructure - Motor drives, PLCs, electrical hardware, and motor drive mounting kits | Components and equipment to support field season 1 controls system tasking - ComSur - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight estimated
1.4 |  | ICL power and timing electronics | 1 crate containing rackmount electronics for power and timing systems - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 600 | 600 | estimated | DNF | U. Wisc. Madison | 2023-08-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12
1.4 |  | ICL patch cables and patch panels | Standard vessel shipping - can overwinter in McM if shipped earlier - Do Not Deep Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNDF [TBD] | U. Wisc. Madison | 2023-06-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12 | (*) storage in McMurdo pending low temperature test
1.2 |  | ARA Drill System Components - Crate 1 | ARA (Antarctic Rodwell Appartus) - downhole pump controller, ePump controller, splash cam kit, and accessories - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | ARA Drill System Components - Crate 2 | ARA (Antarctic Rodwell Appartus) - new downhole pumps, spares, accessories and tools | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Camp Hose - currently staged at PSL | Two spools of hose - 348 cf / 4990 lbs each. Required for SES set-up - no DNDF requirement. | 92 | 92 | 71 | 2 | 695.537 | 4990 | 9980 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY22 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Bull wheel | Bull wheel assembly - used to install main cable on reel in event of main cable damage/failure | 88 | 58 | 97 | 1 | 286.5093 | 2880 | 2880 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2024-02-01 | No | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight and cube used from Gen 1 shipping label still on bull wheel.
1.2 |  | Load member cable reel | Cable Reel used to deploy downhole load member during string installation | 84 | 60 | 48 | 1 | 140 | 3800 | 3800 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-15 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 for integration - recent addition, still in development
1.2 |  | DOM Handling Facility (DHF) | Standard vessel shipping - can overwinter in McM. | 240 | 96 | 96 | 1 | 1280 | 12000 | 12000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Sensor Handling Facility construction scheduled to begin mid-December FY24
1.2 |  | Spare Combo cable | Spare cable for Return Water Cable Reel - on spool | 72 | 72 | 72 | 1 | 216 | 3000 | 3000 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Spare Drill Cable | Standard vessel shipping - can overwinter in McM. Cable on steel spool. | 83 | 83 | 61 | 1 | 243.1881 | 6835 | 6835 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Computing/controls components | Computing and controls equipment (Motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 to support controls system tasking
1.2 |  | Driller resupply/refit components - 8' Container | 8' Mini Milvan; Consumables/drill components | 96 | 86 | 96 | 1 | 458.6667 | 6500 | 6500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season - 8' container moves with contents overland or by air
1.2 |  | Drill refit components | Single crate. Consumables/drill refit components | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated |  | U. Wisc. Madison |  | UWM-PTH | 2023-08-01 | Truck | PTH - CHC |  | Comsur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season
1.2 |  | Drill Heads DNF - X | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-02-12 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | One drill head shipped one year early for ull system wet-test
1.2 |  | Drill Heads DNF - Y | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Heads DNF - R | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Computing/controls components | Computing and controls equipment (Sensor, motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-15 | Yes | FY25 inter | FY25 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Installation Hardware 87-93 | Installation hardware for winterover storage at Pole | 96 | 48 | 48 | 7 | 896 | 1000 | 7000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.2 |  | Installation Weights 87-93 | Installation weights for winterover storage at Pole | 36 | 24 | 24 | 7 | 84 | 785.7143 | 5500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.5 |  | Calibration/Special Devices 87-88 | 3+1 PencilBeams from UW, 2+1 pDOM and 1+1 LOMs - Do Not Deep Freeze | 58 | 38 | 41 | 1 | 52.294 | 836 | 836 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from UW (4+1 Radio Pulsers (all strings) 1+1 Radio Receivers, 3+1 FOM) - Do Not Deep Freeze | 63 | 40 | 42 | 1 | 61.25 | 677 | 677 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 4+1 Radio Pulser, weight 50 kg. 1+1 Radio receiver, assume mDOM weight, 3+1 FOM (assume mDOM weight) + 2ftx2ftx4ft FOM box (50 lbs). Special Devices from UW. FTS, seismometer missing from estimate. 250 lbs crate estimate
1.2 |  | Misc. Science Equipment - FY24 | Scientific and test equipment (SPAT, DCM et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-10-08 | D. Tosi | 2021-10-08
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from UW (4+1 FOM,2+1 Radio Receivers, 11+1 LOM + seismometer*) - Do Not Deep Freeze | 81 | 56 | 51 | 1 | 133.875 | 1797 | 1797 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 21 Special Devices from USA (11+ 1 LOM, 4+1 FOM, 2+1 RR, FTS ? , seismometer), assume mDOM weight. 200 lbs wood crate. FTS not included. (*) Seismometer not yet in CMD
1.5 |  | Calibration/Special Devices 89-93 | 8+1 PencilBeams, 12+1 pDOMs from UW - Do Not Deep Freeze | 75 | 56.5 | 41 | 1 | 100.5425 | 1602 | 1602 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-05 | 8+1 PencilBeams for strings 89-93, 12+1 pDOMs, assume mDOM weight. 244 lbs crate.
1.2 |  | Misc. Science Equipment - FY25 | Scientific and test equipment (Handheld test devices, Paros, et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-12-01 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | D. Tosi | 2021-10-08
1.5 |  | Dust logging device | Blue Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-18 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Green Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-19 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 24 | 24 | 1 | 8.6667 | 120 | 120 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-20 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 23 | 20 | 1 | 6.9213 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-21 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Logging winch | Winch to be used for Dust Logging | 86 | 60 | 68 | 1 | 203.0556 | 3500 | 3500 | IDP deep logging winch for reference |  | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.5 |  | Logging winch control box | Control Box for winch for Dust Logging - sensitive equipment - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 400 | 400 | IDP deep logging winch for reference | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
|  | U. Wisconsin totals: |  |  |  | TEU=> | 12.1277 | 11545.5987 |  | 148947
1.4 |  | Surface Junction Boxes | Surface Junction Boxes can overwinter in McM if shipped earlier. 7 junction boxes | 66 | 30 | 14 | 7 | 112.2917 | 200 | 1400 | preliminary |  | MSU | 2022-11-01 | MSU-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-10 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | Each is 66" x 30" x 14", each is 112 lbs. Assume Folding crate
1.4 |  | Surface Cable Assemblies | Palletized wooden cable drums (Qty: 7). Can overwinter in MCM. | 48 | 65 | 71 | 7 | 897.3611 | 1335.7143 | 9350 | actual |  | MSU | 2021-11-30 | MSU-PTH | 2022-12-01 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-11-20 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Breakout cables for strings 87-88 | Standard vessel shipping. 2 wooden crates containing spooled breakout cable assemblies - 96 cf / 1,000 lbs each - Do Not Deep Freeze | 72 | 48 | 48 | 2 | 192 | 1000 | 2000 | estimated | DNDF[-40C](*) | MSU | 2023-02-28 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | Preliminary estimate of weight and size. Pre-staging string 87-88 equipment in cryo or ICL. - if shipping to Pole not possible before end of 23/24 season could overwinter in McM (at an increased risk and pending low temperature test)
1.4 |  | Breakout cables for strings 89-93 | Stored in McMurdo FY24. 5 wooden crates containing spooled breakout cable assemblies - 96 cf/ 1,000 lbs each (preliminary) - Do Not Deep Freeze | 72 | 48 | 48 | 5 | 480 | 1000 | 5000 | estimated | DNDF[-40C](*) | MSU | 2023-05-22 | MSU-PTH | 2023-06-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-11-25 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-09-20 | Preliminary estimate of weight and size. (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) load members 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 47 | 47 | 39 | 7 | 348.9913 | 766 | 5362 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) cables 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 96 | 96 | 96 | 7 | 3584 | 15000 | 105000 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 25 | 1277.7778 | 573 | 14325 | final weight(**) | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 28 kg/boxed + 35kg pallet, assume 8 mDOMs/pallet (189 to be deployed + 11 spares)(*)Assumed to be shipped in 2x20' HC (5115 lbs, 238inx96inx114in) or a 40 ft HC, purchased by MSU or loaned in PTH (container weight not included)
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) containers (TBD) - Do Not Deep Freeze | 238 | 96 | 114 | 0 | 0 | 5115 | 0 | see notes in item above | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | Assume 2x20HC containers for transport on COMSUR (TBC). Pallets could be loaded to 53 ft truck and loaded into a loaned container in PTH but this would increase touch points (and risk)
|  | MSU Totals: |  |  |  | TEU=> | 7.2399 | 6892.4219 |  | 142437
1.3 |  | DM-Ice | DM-ice (two modules for string 89 and 90) - Do Not Deep Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNDF [-40C] | Yale |  | Yale-PTH |  | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | M. Kauer | 2021-09-20 | D. Tosi | 2021-09-20
|  | Other Institutions Totals: |  |  |  |  | 0.067227 | 64 |  | 1500
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (spares included) - Do Not Deep Freeze | 40 | 48 | 46 | 16 | 817.7778 | 573 | 9168 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - 116 to be deployed + 12 spares - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (SPARES) - Do Not Deep Freeze | 40 | 48 | 46 | 0 | 0 | 573 | 0 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from DESY/Germany/Sweden (8 WOMs, 0 Abalone) + spares - Do Not Deep Freeze | 40 | 21 | 64 | 1 | 31.1111 | 701 | 701 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 8 WOMs (no spares) - AH not included for now. Assume 150 lbs crate.
1.5 |  | Calibration Devices 87-88 | Calibration devices for 2 strings from DESY/Germany/Sweden (4+2 POCAMs, 3+1 Acoustic sensors, 2+1 Swedish Cameras) - Do Not Deep Freeze | 62 | 38 | 41 | 1 | 55.9005 | 836 | 836 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 87-88 = 2+1 Sweden Camera + 3+1 Acoustic Module + 4+1 POCAM, including spares, 200 lbs crate
1.4 |  | FieldHub electronics | Required onsite for FY24 installation. 1 crate containing readout electronics for installation in ICL - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 275 | 275 | preliminary | DNF | DESY | 2023-08-01 | DESY-CHC | 2023-08-15 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | No | FY24 inter | FY24 intra | J. Kelley | 2021-10-13 | D. Tosi | 2021-10-13 | Field Hubs are 442mm x 480mm x 133 mm (17.4" x 18.9" x 5.2") and weight maybe 10 lb each. 100 lbs crate.
1.3 |  | String Sensors 89-93 | Optical sensors for 5 strings from Germany (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 12 | 613.3333 | 573 | 6876 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is (28kg/sensor boxed) + 35kg pallet, assume 8 mDOMs/pallet - 190 to be deployed + 10 spares. (**) shipped in 20 HC container. Container not included in weight as pallets will be taken out.
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from DESY/Germany/Sweden (6 WOMs, 3 Abalone Hubs or WOM Traps) no spares - Do Not Deep Freeze | 32 | 31 | 89 | 1 | 51.0926 | 1035 | 1035 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 6 Special Devices from Germany 6 (WOM + 0 AH) including 0 spare for each. Assume 170 lbs crate.
1.5 |  | Calibration Devices 89-93 | Calibration for 5 strings from DESY/Germany/Sweden (17+2 POCAMs, 7+ 1 Acoustic sensors, 3+ 1 Swedish Cameras) including spares - Do Not Deep Freeze | 62 | 48 | 44 | 1 | 75.7778 | 1694 | 1694 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 89-93 = 3+1 Sweden Camera,7+1 + Acoustic Module,17 +1 POCAM, including spares, 200 lbs crate
|  | DESY/Aachen/TUM/Sweden etc Totals: |  |  |  | TEU=> | 1.7784 | 1692.9931 |  | 20585
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 4 | 335 | 794 | 3176 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter (SPARES - TBD) - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 1 | 83.75 | 794 | 794 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 4 | 469 | 1168.5 | 4674 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter (SPARES - TBD)- Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 1 | 117.25 | 1168.5 | 1168.5 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 8 sensors in McMurdo overwinter - Do Not Deep Freeze | 45 | 48 | 67 | 10 | 837.5 | 794 | 7940 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 12 sensors in McMurdo overwinter - Do Not Deep Freeze | 63 | 48 | 67 | 10 | 1172.5 | 1168.5 | 11685 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
|  | Chiba Totals: |  |  |  | TEU=> | 3.167 | 3015 |  | 29437.5
1.2 |  | Field Season 1 Fuel | Fuel to support FY23 field season - Base fuel |  |  |  | 3191 | 426.5746 | 6.8 | 21698.8 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 1 Fuel Contingency | Fuel to support FY23 field season - Contingency |  |  |  | 452 | 60.4236 | 6.8 | 3073.6 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel | Fuel to support FY24 field season - Base fuel, firn drilling & over winter heating |  |  |  | 18178 | 2430.045 | 6.8 | 123610.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel Contingency | Fuel to suppport FY24 field season - Contingency |  |  |  | 2373 | 317.2239 | 6.8 | 16136.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel | Fuel to support FY25 field season - Base fuel & deep drilling |  |  |  | 62694 | 8380.9682 | 6.8 | 426319.2 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 44483 | I. McEwen | 44483
1.2 |  | Field Season 3 Fuel Contingency | Fuel to suppport FY25 field season - Contingency |  |  |  | 8473 | 1132.6753 | 6.8 | 57616.4 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 44483 | I. McEwen | 44483
|  | Fuel Totals: |  |  |  | TEU=> | 13.3907 | 12747.9106 |  | 648454.8
|  |  | All IC/Upgrade cargo volume: |  |  | TEU=> | 55.9647 | 53278.3808 |  | 1167584.3
|  | total volume [cubic feet] | total weight [lbs]
Total Cargo for selected items |  | 11173.7019 | 151220.4
Total Cargo according to dates |  | 11173.7019 | 151220.4
Start date | End date
2022-11-01 | 2023-02-15

## FY24 inter
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Gen 1 - housed in 20' container | Power generation unit 1 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 2 - housed in 20' container | Power generation unit 2 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 3 - housed in 20' container | Power generation unit 3 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | - | In McMurdo |  | SPoT | 2022-12-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | 287 Loader | Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use | 114 | 77 | 96 | 1 | 487.6667 | 10273 | 10273 | actual |  | U. Wisc. Madison |  | In McMurdo | 2019-11-15 | Truck | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2022-12-01 | No* | In McMurdo | FY23 intra | D. Gibson | 2021-10-07 | I. McEwen | 2021-10-07 | *Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use
1.2 |  | Gen hoods Discharge Hoods - currently staged in McMurdo | Generator air discharge hoods , sheet metal, loose - stored on berm at SPOTSA | 108 | 53 | 60 | 2 | 397.5 | 330 | 660 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo |  |  | In McMurdo |  | - | In McMurdo |  | LC-130/SPoT | 2024-01-01 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Testing/limited operation of Gens can be accomplished without hoods - Hoods required for the drill season
1.2 |  | Firn Drill | Bermed in McM - will require McM fork or crane support. | 264 | 94 | 97 | 1 | 1393.0278 | 12000 | 12000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA
1.2 |  | Firn Drill Components - 1 | Firn drill sheave. Required Field Season 2 for final refit & functional testing | 97 | 44 | 63 | 1 | 155.6042 | 920 | 920 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Firn Drill Components - 2 | Firn drill drillhead. Required Field Season 2 for final refit & functional testing | 125 | 33 | 37 | 1 | 88.3247 | 1048 | 1048 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Weight stack and crates | Bermed in McM - will require McM fork support. Drill head weight stack and remaining bermed crates at SPoTSA | 120 | 48 | 48 | 1 | 160 | 600 | 600 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-15 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack
1.2 |  | Fuel Tower | Bermed in McM - will require McM fork or crane support. | 96 | 72 | 120 | 1 | 480 | 1500 | 1500 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack - overland shipment preferred due to complexities of air transport certification - can be laid on side once drained
1.2 |  | HPU 1 | HPU 1 (University of Nebraska - Lincoln asset) - 40' container housing heating plant on ISO sled | 480 | 96 | 102 | 1 | 2720 | 28000 | 28000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2024-01-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | HPU 1 integration with Rodwell system required before drill season on it's own sled which will require evaluation and repair - Stored at SPOTSA
|  | McMurdo totals: |  |  |  | TEU=> | 10.4644 | 9962.1233 |  | 121001
1.2 |  | Container Ski Stack (comprised of 5 sleds) - currently staged in Pt. Hueneme | Five sets of aluminum skis for 20' containers - stacked. Aluminum skis for drill containers. Required onsite for local movement of Gens and PDM. | 240 | 96 | 96 | 1 | 1280 | 4255 | 4255 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | No* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *While this shipment is not on the critical path additional ASC crane support will be required to overcome delayed arrival or sleds furnished from the South Pole inventory
1.2 |  | Generator Intake Hood - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 174 | 53 | 96 | 3 | 1537 | 586.6667 | 1760 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477
1.2 |  | Generator Discharge Hoods - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 108 | 53 | 60 | 2 | 397.5 | 1210 | 2420 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 9 Spools - 348 cf / 3532 lbs each - Shipped from Italy | 92 | 92 | 70.5 | 9 | 3107.875 | 3531.5556 | 31784 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-08-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 3 Spools - 348 cf / 5001 lbs each - Shipped from PSL | 92 | 92 | 70.5 | 3 | 1035.9583 | 5001 | 15003 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 44477 | I. McEwen | 44477 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
|  | Pt. Hueneme totals: |  |  |  | TEU=> | 7.7293 | 7358.3333 |  | 55222
1.2 |  | 8' Refit Container | Priority refit materials including tools, flowmeter assemblies, motor drive installation kits, hardware, fittings, sensors, & consumables | 96 | 86 | 96 | 1 | 458.6667 | 5600 | 5600 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130 | 2022-11-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | 8' container moves with contents by LC130 or is broken down for movement by Basler
1.2 |  | 20' Refit Container A | Refit materials incl. submersible pumps, hardware, filtration components, fall arrest towers, tools, & hose crimper | 240 | 96 | 102 | 1 | 1360 | 17500 | 17500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | 20' Refit Container B | Bulky materials incl. cable trays, vertical turbine pumps, vertical turbine pump motors, ladders, water tank doghouse/railing materials, 287 forks, generator parts, TU20 shaft, & drill weight stack | 240 | 96 | 102 | 1 | 1360 | 15500 | 15500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | ARA Trailer | Enclosed trailer on skis housing 35kw generator | 192 | 96 | 88 | 1 | 938.6667 | 4860 | 4860 | actual | FLAMMABLE liquid power engine | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | *If this shipment is delayed 480 volt power generation support will be required in FW YR 1 by the contractor. Aside from the CRREL generator (far larger than required with high fuel burn rate) the capacity does not currently exist at the Pole.
1.2 |  | Return Water Cable Reel (RWCR) | Smaller reel - can fit in 20' container. Required onsite in FY23 for final integration and pre-drill activites | 112 | 80 | 80 | 1 | 414.8148 | 4000 | 4000 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Weight from Gen 1 shipment information see picture
1.2 |  | Main Cable Reel (MCR) | Required onsite in FY23 for final integration and pre-drill activites. Large cable reel - will require flat rack on vessel | 140 | 96 | 95 | 1 | 738.8889 | 12500 | 12500 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Required onsite in FS Y1 for final integration and pre-drill activities
1.2 |  | Controls infrastructure - Motor drives, PLCs, electrical hardware, and motor drive mounting kits | Components and equipment to support field season 1 controls system tasking - ComSur - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Weight estimated
1.4 |  | ICL power and timing electronics | 1 crate containing rackmount electronics for power and timing systems - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 600 | 600 | estimated | DNF | U. Wisc. Madison | 2023-08-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12
1.4 |  | ICL patch cables and patch panels | Standard vessel shipping - can overwinter in McM if shipped earlier - Do Not Deep Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNDF [TBD] | U. Wisc. Madison | 2023-06-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12 | (*) storage in McMurdo pending low temperature test
1.2 |  | ARA Drill System Components - Crate 1 | ARA (Antarctic Rodwell Appartus) - downhole pump controller, ePump controller, splash cam kit, and accessories - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477
1.2 |  | ARA Drill System Components - Crate 2 | ARA (Antarctic Rodwell Appartus) - new downhole pumps, spares, accessories and tools | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477
1.2 |  | Camp Hose - currently staged at PSL | Two spools of hose - 348 cf / 4990 lbs each. Required for SES set-up - no DNDF requirement. | 92 | 92 | 71 | 2 | 695.537 | 4990 | 9980 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY22 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Bull wheel | Bull wheel assembly - used to install main cable on reel in event of main cable damage/failure | 88 | 58 | 97 | 1 | 286.5093 | 2880 | 2880 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2024-02-01 | No | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight and cube used from Gen 1 shipping label still on bull wheel.
1.2 |  | Load member cable reel | Cable Reel used to deploy downhole load member during string installation | 84 | 60 | 48 | 1 | 140 | 3800 | 3800 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-15 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 for integration - recent addition, still in development
1.2 |  | DOM Handling Facility (DHF) | Standard vessel shipping - can overwinter in McM. | 240 | 96 | 96 | 1 | 1280 | 12000 | 12000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Sensor Handling Facility construction scheduled to begin mid-December FY24
1.2 |  | Spare Combo cable | Spare cable for Return Water Cable Reel - on spool | 72 | 72 | 72 | 1 | 216 | 3000 | 3000 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Spare Drill Cable | Standard vessel shipping - can overwinter in McM. Cable on steel spool. | 83 | 83 | 61 | 1 | 243.1881 | 6835 | 6835 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Computing/controls components | Computing and controls equipment (Motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 to support controls system tasking
1.2 |  | Driller resupply/refit components - 8' Container | 8' Mini Milvan; Consumables/drill components | 96 | 86 | 96 | 1 | 458.6667 | 6500 | 6500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season - 8' container moves with contents overland or by air
1.2 |  | Drill refit components | Single crate. Consumables/drill refit components | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated |  | U. Wisc. Madison |  | UWM-PTH | 2023-08-01 | Truck | PTH - CHC |  | Comsur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season
1.2 |  | Drill Heads DNF - X | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-02-12 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | One drill head shipped one year early for ull system wet-test
1.2 |  | Drill Heads DNF - Y | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Heads DNF - R | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Computing/controls components | Computing and controls equipment (Sensor, motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-15 | Yes | FY25 inter | FY25 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Installation Hardware 87-93 | Installation hardware for winterover storage at Pole | 96 | 48 | 48 | 7 | 896 | 1000 | 7000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.2 |  | Installation Weights 87-93 | Installation weights for winterover storage at Pole | 36 | 24 | 24 | 7 | 84 | 785.7143 | 5500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.5 |  | Calibration/Special Devices 87-88 | 3+1 PencilBeams from UW, 2+1 pDOM and 1+1 LOMs - Do Not Deep Freeze | 58 | 38 | 41 | 1 | 52.294 | 836 | 836 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from UW (4+1 Radio Pulsers (all strings) 1+1 Radio Receivers, 3+1 FOM) - Do Not Deep Freeze | 63 | 40 | 42 | 1 | 61.25 | 677 | 677 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 4+1 Radio Pulser, weight 50 kg. 1+1 Radio receiver, assume mDOM weight, 3+1 FOM (assume mDOM weight) + 2ftx2ftx4ft FOM box (50 lbs). Special Devices from UW. FTS, seismometer missing from estimate. 250 lbs crate estimate
1.2 |  | Misc. Science Equipment - FY24 | Scientific and test equipment (SPAT, DCM et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-10-08 | D. Tosi | 2021-10-08
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from UW (4+1 FOM,2+1 Radio Receivers, 11+1 LOM + seismometer*) - Do Not Deep Freeze | 81 | 56 | 51 | 1 | 133.875 | 1797 | 1797 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 21 Special Devices from USA (11+ 1 LOM, 4+1 FOM, 2+1 RR, FTS ? , seismometer), assume mDOM weight. 200 lbs wood crate. FTS not included. (*) Seismometer not yet in CMD
1.5 |  | Calibration/Special Devices 89-93 | 8+1 PencilBeams, 12+1 pDOMs from UW - Do Not Deep Freeze | 75 | 56.5 | 41 | 1 | 100.5425 | 1602 | 1602 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-05 | 8+1 PencilBeams for strings 89-93, 12+1 pDOMs, assume mDOM weight. 244 lbs crate.
1.2 |  | Misc. Science Equipment - FY25 | Scientific and test equipment (Handheld test devices, Paros, et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-12-01 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | D. Tosi | 2021-10-08
1.5 |  | Dust logging device | Blue Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-18 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Green Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-19 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 24 | 24 | 1 | 8.6667 | 120 | 120 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-20 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 23 | 20 | 1 | 6.9213 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-21 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Logging winch | Winch to be used for Dust Logging | 86 | 60 | 68 | 1 | 203.0556 | 3500 | 3500 | IDP deep logging winch for reference |  | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.5 |  | Logging winch control box | Control Box for winch for Dust Logging - sensitive equipment - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 400 | 400 | IDP deep logging winch for reference | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
|  | U. Wisconsin totals: |  |  |  | TEU=> | 12.1277 | 11545.5987 |  | 148947
1.4 |  | Surface Junction Boxes | Surface Junction Boxes can overwinter in McM if shipped earlier. 7 junction boxes | 66 | 30 | 14 | 7 | 112.2917 | 200 | 1400 | preliminary |  | MSU | 2022-11-01 | MSU-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-10 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | Each is 66" x 30" x 14", each is 112 lbs. Assume Folding crate
1.4 |  | Surface Cable Assemblies | Palletized wooden cable drums (Qty: 7). Can overwinter in MCM. | 48 | 65 | 71 | 7 | 897.3611 | 1335.7143 | 9350 | actual |  | MSU | 2021-11-30 | MSU-PTH | 2022-12-01 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-11-20 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Breakout cables for strings 87-88 | Standard vessel shipping. 2 wooden crates containing spooled breakout cable assemblies - 96 cf / 1,000 lbs each - Do Not Deep Freeze | 72 | 48 | 48 | 2 | 192 | 1000 | 2000 | estimated | DNDF[-40C](*) | MSU | 2023-02-28 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | Preliminary estimate of weight and size. Pre-staging string 87-88 equipment in cryo or ICL. - if shipping to Pole not possible before end of 23/24 season could overwinter in McM (at an increased risk and pending low temperature test)
1.4 |  | Breakout cables for strings 89-93 | Stored in McMurdo FY24. 5 wooden crates containing spooled breakout cable assemblies - 96 cf/ 1,000 lbs each (preliminary) - Do Not Deep Freeze | 72 | 48 | 48 | 5 | 480 | 1000 | 5000 | estimated | DNDF[-40C](*) | MSU | 2023-05-22 | MSU-PTH | 2023-06-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-11-25 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-09-20 | Preliminary estimate of weight and size. (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) load members 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 47 | 47 | 39 | 7 | 348.9913 | 766 | 5362 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) cables 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 96 | 96 | 96 | 7 | 3584 | 15000 | 105000 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 25 | 1277.7778 | 573 | 14325 | final weight(**) | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 28 kg/boxed + 35kg pallet, assume 8 mDOMs/pallet (189 to be deployed + 11 spares)(*)Assumed to be shipped in 2x20' HC (5115 lbs, 238inx96inx114in) or a 40 ft HC, purchased by MSU or loaned in PTH (container weight not included)
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) containers (TBD) - Do Not Deep Freeze | 238 | 96 | 114 | 0 | 0 | 5115 | 0 | see notes in item above | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | Assume 2x20HC containers for transport on COMSUR (TBC). Pallets could be loaded to 53 ft truck and loaded into a loaned container in PTH but this would increase touch points (and risk)
|  | MSU Totals: |  |  |  | TEU=> | 7.2399 | 6892.4219 |  | 142437
1.3 |  | DM-Ice | DM-ice (two modules for string 89 and 90) - Do Not Deep Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNDF [-40C] | Yale |  | Yale-PTH |  | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | M. Kauer | 2021-09-20 | D. Tosi | 2021-09-20
|  | Other Institutions Totals: |  |  |  |  | 0.067227 | 64 |  | 1500
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (spares included) - Do Not Deep Freeze | 40 | 48 | 46 | 16 | 817.7778 | 573 | 9168 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - 116 to be deployed + 12 spares - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (SPARES) - Do Not Deep Freeze | 40 | 48 | 46 | 0 | 0 | 573 | 0 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from DESY/Germany/Sweden (8 WOMs, 0 Abalone) + spares - Do Not Deep Freeze | 40 | 21 | 64 | 1 | 31.1111 | 701 | 701 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 8 WOMs (no spares) - AH not included for now. Assume 150 lbs crate.
1.5 |  | Calibration Devices 87-88 | Calibration devices for 2 strings from DESY/Germany/Sweden (4+2 POCAMs, 3+1 Acoustic sensors, 2+1 Swedish Cameras) - Do Not Deep Freeze | 62 | 38 | 41 | 1 | 55.9005 | 836 | 836 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 87-88 = 2+1 Sweden Camera + 3+1 Acoustic Module + 4+1 POCAM, including spares, 200 lbs crate
1.4 |  | FieldHub electronics | Required onsite for FY24 installation. 1 crate containing readout electronics for installation in ICL - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 275 | 275 | preliminary | DNF | DESY | 2023-08-01 | DESY-CHC | 2023-08-15 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | No | FY24 inter | FY24 intra | J. Kelley | 2021-10-13 | D. Tosi | 2021-10-13 | Field Hubs are 442mm x 480mm x 133 mm (17.4" x 18.9" x 5.2") and weight maybe 10 lb each. 100 lbs crate.
1.3 |  | String Sensors 89-93 | Optical sensors for 5 strings from Germany (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 12 | 613.3333 | 573 | 6876 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is (28kg/sensor boxed) + 35kg pallet, assume 8 mDOMs/pallet - 190 to be deployed + 10 spares. (**) shipped in 20 HC container. Container not included in weight as pallets will be taken out.
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from DESY/Germany/Sweden (6 WOMs, 3 Abalone Hubs or WOM Traps) no spares - Do Not Deep Freeze | 32 | 31 | 89 | 1 | 51.0926 | 1035 | 1035 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 6 Special Devices from Germany 6 (WOM + 0 AH) including 0 spare for each. Assume 170 lbs crate.
1.5 |  | Calibration Devices 89-93 | Calibration for 5 strings from DESY/Germany/Sweden (17+2 POCAMs, 7+ 1 Acoustic sensors, 3+ 1 Swedish Cameras) including spares - Do Not Deep Freeze | 62 | 48 | 44 | 1 | 75.7778 | 1694 | 1694 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 89-93 = 3+1 Sweden Camera,7+1 + Acoustic Module,17 +1 POCAM, including spares, 200 lbs crate
|  | DESY/Aachen/TUM/Sweden etc Totals: |  |  |  | TEU=> | 1.7784 | 1692.9931 |  | 20585
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 4 | 335 | 794 | 3176 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter (SPARES - TBD) - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 1 | 83.75 | 794 | 794 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 4 | 469 | 1168.5 | 4674 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter (SPARES - TBD)- Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 1 | 117.25 | 1168.5 | 1168.5 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 8 sensors in McMurdo overwinter - Do Not Deep Freeze | 45 | 48 | 67 | 10 | 837.5 | 794 | 7940 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 12 sensors in McMurdo overwinter - Do Not Deep Freeze | 63 | 48 | 67 | 10 | 1172.5 | 1168.5 | 11685 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
|  | Chiba Totals: |  |  |  | TEU=> | 3.167 | 3015 |  | 29437.5
1.2 |  | Field Season 1 Fuel | Fuel to support FY23 field season - Base fuel |  |  |  | 3191 | 426.5746 | 6.8 | 21698.8 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 1 Fuel Contingency | Fuel to support FY23 field season - Contingency |  |  |  | 452 | 60.4236 | 6.8 | 3073.6 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel | Fuel to support FY24 field season - Base fuel, firn drilling & over winter heating |  |  |  | 18178 | 2430.045 | 6.8 | 123610.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel Contingency | Fuel to suppport FY24 field season - Contingency |  |  |  | 2373 | 317.2239 | 6.8 | 16136.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel | Fuel to support FY25 field season - Base fuel & deep drilling |  |  |  | 62694 | 8380.9682 | 6.8 | 426319.2 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 44483 | I. McEwen | 44483
1.2 |  | Field Season 3 Fuel Contingency | Fuel to suppport FY25 field season - Contingency |  |  |  | 8473 | 1132.6753 | 6.8 | 57616.4 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 44483 | I. McEwen | 44483
|  | Fuel Totals: |  |  |  | TEU=> | 13.3907 | 12747.9106 |  | 648454.8
|  |  | All IC/Upgrade cargo volume: |  |  | TEU=> | 55.9647 | 53278.3808 |  | 1167584.3
|  | total volume [cubic feet] | total weight [lbs]
Total Cargo for selected items |  | 12025.4483 | 319669.3
Total Cargo according to dates |  | 12025.4483 | 319669.3
Start date | End date
2023-11-01 | 2024-02-15

## FY24 intra
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Gen 1 - housed in 20' container | Power generation unit 1 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 2 - housed in 20' container | Power generation unit 2 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 3 - housed in 20' container | Power generation unit 3 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | - | In McMurdo |  | SPoT | 2022-12-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | 287 Loader | Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use | 114 | 77 | 96 | 1 | 487.6667 | 10273 | 10273 | actual |  | U. Wisc. Madison |  | In McMurdo | 2019-11-15 | Truck | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2022-12-01 | No* | In McMurdo | FY23 intra | D. Gibson | 2021-10-07 | I. McEwen | 2021-10-07 | *Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use
1.2 |  | Gen hoods Discharge Hoods - currently staged in McMurdo | Generator air discharge hoods , sheet metal, loose - stored on berm at SPOTSA | 108 | 53 | 60 | 2 | 397.5 | 330 | 660 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo |  |  | In McMurdo |  | - | In McMurdo |  | LC-130/SPoT | 2024-01-01 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Testing/limited operation of Gens can be accomplished without hoods - Hoods required for the drill season
1.2 |  | Firn Drill | Bermed in McM - will require McM fork or crane support. | 264 | 94 | 97 | 1 | 1393.0278 | 12000 | 12000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA
1.2 |  | Firn Drill Components - 1 | Firn drill sheave. Required Field Season 2 for final refit & functional testing | 97 | 44 | 63 | 1 | 155.6042 | 920 | 920 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Firn Drill Components - 2 | Firn drill drillhead. Required Field Season 2 for final refit & functional testing | 125 | 33 | 37 | 1 | 88.3247 | 1048 | 1048 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Weight stack and crates | Bermed in McM - will require McM fork support. Drill head weight stack and remaining bermed crates at SPoTSA | 120 | 48 | 48 | 1 | 160 | 600 | 600 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-15 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack
1.2 |  | Fuel Tower | Bermed in McM - will require McM fork or crane support. | 96 | 72 | 120 | 1 | 480 | 1500 | 1500 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack - overland shipment preferred due to complexities of air transport certification - can be laid on side once drained
1.2 |  | HPU 1 | HPU 1 (University of Nebraska - Lincoln asset) - 40' container housing heating plant on ISO sled | 480 | 96 | 102 | 1 | 2720 | 28000 | 28000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2024-01-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | HPU 1 integration with Rodwell system required before drill season on it's own sled which will require evaluation and repair - Stored at SPOTSA
|  | McMurdo totals: |  |  |  | TEU=> | 10.4644 | 9962.1233 |  | 121001
1.2 |  | Container Ski Stack (comprised of 5 sleds) - currently staged in Pt. Hueneme | Five sets of aluminum skis for 20' containers - stacked. Aluminum skis for drill containers. Required onsite for local movement of Gens and PDM. | 240 | 96 | 96 | 1 | 1280 | 4255 | 4255 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | No* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *While this shipment is not on the critical path additional ASC crane support will be required to overcome delayed arrival or sleds furnished from the South Pole inventory
1.2 |  | Generator Intake Hood - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 174 | 53 | 96 | 3 | 1537 | 586.6667 | 1760 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Generator Discharge Hoods - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 108 | 53 | 60 | 2 | 397.5 | 1210 | 2420 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 9 Spools - 348 cf / 3532 lbs each - Shipped from Italy | 92 | 92 | 70.5 | 9 | 3107.875 | 3531.5556 | 31784 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-08-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 3 Spools - 348 cf / 5001 lbs each - Shipped from PSL | 92 | 92 | 70.5 | 3 | 1035.9583 | 5001 | 15003 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
|  | Pt. Hueneme totals: |  |  |  | TEU=> | 7.7293 | 7358.3333 |  | 55222
1.2 |  | 8' Refit Container | Priority refit materials including tools, flowmeter assemblies, motor drive installation kits, hardware, fittings, sensors, & consumables | 96 | 86 | 96 | 1 | 458.6667 | 5600 | 5600 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130 | 2022-11-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | 8' container moves with contents by LC130 or is broken down for movement by Basler
1.2 |  | 20' Refit Container A | Refit materials incl. submersible pumps, hardware, filtration components, fall arrest towers, tools, & hose crimper | 240 | 96 | 102 | 1 | 1360 | 17500 | 17500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | 20' Refit Container B | Bulky materials incl. cable trays, vertical turbine pumps, vertical turbine pump motors, ladders, water tank doghouse/railing materials, 287 forks, generator parts, TU20 shaft, & drill weight stack | 240 | 96 | 102 | 1 | 1360 | 15500 | 15500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | ARA Trailer | Enclosed trailer on skis housing 35kw generator | 192 | 96 | 88 | 1 | 938.6667 | 4860 | 4860 | actual | FLAMMABLE liquid power engine | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | *If this shipment is delayed 480 volt power generation support will be required in FW YR 1 by the contractor. Aside from the CRREL generator (far larger than required with high fuel burn rate) the capacity does not currently exist at the Pole.
1.2 |  | Return Water Cable Reel (RWCR) | Smaller reel - can fit in 20' container. Required onsite in FY23 for final integration and pre-drill activites | 112 | 80 | 80 | 1 | 414.8148 | 4000 | 4000 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Weight from Gen 1 shipment information see picture
1.2 |  | Main Cable Reel (MCR) | Required onsite in FY23 for final integration and pre-drill activites. Large cable reel - will require flat rack on vessel | 140 | 96 | 95 | 1 | 738.8889 | 12500 | 12500 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Required onsite in FS Y1 for final integration and pre-drill activities
1.2 |  | Controls infrastructure - Motor drives, PLCs, electrical hardware, and motor drive mounting kits | Components and equipment to support field season 1 controls system tasking - ComSur - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477 | Weight estimated
1.4 |  | ICL power and timing electronics | 1 crate containing rackmount electronics for power and timing systems - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 600 | 600 | estimated | DNF | U. Wisc. Madison | 2023-08-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12
1.4 |  | ICL patch cables and patch panels | Standard vessel shipping - can overwinter in McM if shipped earlier - Do Not Deep Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNDF [TBD] | U. Wisc. Madison | 2023-06-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12 | (*) storage in McMurdo pending low temperature test
1.2 |  | ARA Drill System Components - Crate 1 | ARA (Antarctic Rodwell Appartus) - downhole pump controller, ePump controller, splash cam kit, and accessories - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477
1.2 |  | ARA Drill System Components - Crate 2 | ARA (Antarctic Rodwell Appartus) - new downhole pumps, spares, accessories and tools | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 44477
1.2 |  | Camp Hose - currently staged at PSL | Two spools of hose - 348 cf / 4990 lbs each. Required for SES set-up - no DNDF requirement. | 92 | 92 | 71 | 2 | 695.537 | 4990 | 9980 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY22 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Bull wheel | Bull wheel assembly - used to install main cable on reel in event of main cable damage/failure | 88 | 58 | 97 | 1 | 286.5093 | 2880 | 2880 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2024-02-01 | No | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight and cube used from Gen 1 shipping label still on bull wheel.
1.2 |  | Load member cable reel | Cable Reel used to deploy downhole load member during string installation | 84 | 60 | 48 | 1 | 140 | 3800 | 3800 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-15 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 for integration - recent addition, still in development
1.2 |  | DOM Handling Facility (DHF) | Standard vessel shipping - can overwinter in McM. | 240 | 96 | 96 | 1 | 1280 | 12000 | 12000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Sensor Handling Facility construction scheduled to begin mid-December FY24
1.2 |  | Spare Combo cable | Spare cable for Return Water Cable Reel - on spool | 72 | 72 | 72 | 1 | 216 | 3000 | 3000 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Spare Drill Cable | Standard vessel shipping - can overwinter in McM. Cable on steel spool. | 83 | 83 | 61 | 1 | 243.1881 | 6835 | 6835 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Computing/controls components | Computing and controls equipment (Motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 to support controls system tasking
1.2 |  | Driller resupply/refit components - 8' Container | 8' Mini Milvan; Consumables/drill components | 96 | 86 | 96 | 1 | 458.6667 | 6500 | 6500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season - 8' container moves with contents overland or by air
1.2 |  | Drill refit components | Single crate. Consumables/drill refit components | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated |  | U. Wisc. Madison |  | UWM-PTH | 2023-08-01 | Truck | PTH - CHC |  | Comsur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season
1.2 |  | Drill Heads DNF - X | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-02-12 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | One drill head shipped one year early for ull system wet-test
1.2 |  | Drill Heads DNF - Y | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Heads DNF - R | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Computing/controls components | Computing and controls equipment (Sensor, motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-15 | Yes | FY25 inter | FY25 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Installation Hardware 87-93 | Installation hardware for winterover storage at Pole | 96 | 48 | 48 | 7 | 896 | 1000 | 7000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.2 |  | Installation Weights 87-93 | Installation weights for winterover storage at Pole | 36 | 24 | 24 | 7 | 84 | 785.7143 | 5500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.5 |  | Calibration/Special Devices 87-88 | 3+1 PencilBeams from UW, 2+1 pDOM and 1+1 LOMs - Do Not Deep Freeze | 58 | 38 | 41 | 1 | 52.294 | 836 | 836 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from UW (4+1 Radio Pulsers (all strings) 1+1 Radio Receivers, 3+1 FOM) - Do Not Deep Freeze | 63 | 40 | 42 | 1 | 61.25 | 677 | 677 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 4+1 Radio Pulser, weight 50 kg. 1+1 Radio receiver, assume mDOM weight, 3+1 FOM (assume mDOM weight) + 2ftx2ftx4ft FOM box (50 lbs). Special Devices from UW. FTS, seismometer missing from estimate. 250 lbs crate estimate
1.2 |  | Misc. Science Equipment - FY24 | Scientific and test equipment (SPAT, DCM et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-10-08 | D. Tosi | 2021-10-08
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from UW (4+1 FOM,2+1 Radio Receivers, 11+1 LOM + seismometer*) - Do Not Deep Freeze | 81 | 56 | 51 | 1 | 133.875 | 1797 | 1797 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 21 Special Devices from USA (11+ 1 LOM, 4+1 FOM, 2+1 RR, FTS ? , seismometer), assume mDOM weight. 200 lbs wood crate. FTS not included. (*) Seismometer not yet in CMD
1.5 |  | Calibration/Special Devices 89-93 | 8+1 PencilBeams, 12+1 pDOMs from UW - Do Not Deep Freeze | 75 | 56.5 | 41 | 1 | 100.5425 | 1602 | 1602 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-05 | 8+1 PencilBeams for strings 89-93, 12+1 pDOMs, assume mDOM weight. 244 lbs crate.
1.2 |  | Misc. Science Equipment - FY25 | Scientific and test equipment (Handheld test devices, Paros, et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-12-01 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | D. Tosi | 2021-10-08
1.5 |  | Dust logging device | Blue Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-18 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Green Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-19 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 24 | 24 | 1 | 8.6667 | 120 | 120 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-20 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 23 | 20 | 1 | 6.9213 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-21 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Logging winch | Winch to be used for Dust Logging | 86 | 60 | 68 | 1 | 203.0556 | 3500 | 3500 | IDP deep logging winch for reference |  | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.5 |  | Logging winch control box | Control Box for winch for Dust Logging - sensitive equipment - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 400 | 400 | IDP deep logging winch for reference | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
|  | U. Wisconsin totals: |  |  |  | TEU=> | 12.1277 | 11545.5987 |  | 148947
1.4 |  | Surface Junction Boxes | Surface Junction Boxes can overwinter in McM if shipped earlier. 7 junction boxes | 66 | 30 | 14 | 7 | 112.2917 | 200 | 1400 | preliminary |  | MSU | 2022-11-01 | MSU-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-10 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | Each is 66" x 30" x 14", each is 112 lbs. Assume Folding crate
1.4 |  | Surface Cable Assemblies | Palletized wooden cable drums (Qty: 7). Can overwinter in MCM. | 48 | 65 | 71 | 7 | 897.3611 | 1335.7143 | 9350 | actual |  | MSU | 2021-11-30 | MSU-PTH | 2022-12-01 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-11-20 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Breakout cables for strings 87-88 | Standard vessel shipping. 2 wooden crates containing spooled breakout cable assemblies - 96 cf / 1,000 lbs each - Do Not Deep Freeze | 72 | 48 | 48 | 2 | 192 | 1000 | 2000 | estimated | DNDF[-40C](*) | MSU | 2023-02-28 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | Preliminary estimate of weight and size. Pre-staging string 87-88 equipment in cryo or ICL. - if shipping to Pole not possible before end of 23/24 season could overwinter in McM (at an increased risk and pending low temperature test)
1.4 |  | Breakout cables for strings 89-93 | Stored in McMurdo FY24. 5 wooden crates containing spooled breakout cable assemblies - 96 cf/ 1,000 lbs each (preliminary) - Do Not Deep Freeze | 72 | 48 | 48 | 5 | 480 | 1000 | 5000 | estimated | DNDF[-40C](*) | MSU | 2023-05-22 | MSU-PTH | 2023-06-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-11-25 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-09-20 | Preliminary estimate of weight and size. (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) load members 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 47 | 47 | 39 | 7 | 348.9913 | 766 | 5362 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) cables 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 96 | 96 | 96 | 7 | 3584 | 15000 | 105000 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 25 | 1277.7778 | 573 | 14325 | final weight(**) | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 28 kg/boxed + 35kg pallet, assume 8 mDOMs/pallet (189 to be deployed + 11 spares)(*)Assumed to be shipped in 2x20' HC (5115 lbs, 238inx96inx114in) or a 40 ft HC, purchased by MSU or loaned in PTH (container weight not included)
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) containers (TBD) - Do Not Deep Freeze | 238 | 96 | 114 | 0 | 0 | 5115 | 0 | see notes in item above | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | Assume 2x20HC containers for transport on COMSUR (TBC). Pallets could be loaded to 53 ft truck and loaded into a loaned container in PTH but this would increase touch points (and risk)
|  | MSU Totals: |  |  |  | TEU=> | 7.2399 | 6892.4219 |  | 142437
1.3 |  | DM-Ice | DM-ice (two modules for string 89 and 90) - Do Not Deep Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNDF [-40C] | Yale |  | Yale-PTH |  | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | M. Kauer | 2021-09-20 | D. Tosi | 2021-09-20
|  | Other Institutions Totals: |  |  |  |  | 0.067227 | 64 |  | 1500
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (spares included) - Do Not Deep Freeze | 40 | 48 | 46 | 16 | 817.7778 | 573 | 9168 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - 116 to be deployed + 12 spares - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (SPARES) - Do Not Deep Freeze | 40 | 48 | 46 | 0 | 0 | 573 | 0 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from DESY/Germany/Sweden (8 WOMs, 0 Abalone) + spares - Do Not Deep Freeze | 40 | 21 | 64 | 1 | 31.1111 | 701 | 701 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 8 WOMs (no spares) - AH not included for now. Assume 150 lbs crate.
1.5 |  | Calibration Devices 87-88 | Calibration devices for 2 strings from DESY/Germany/Sweden (4+2 POCAMs, 3+1 Acoustic sensors, 2+1 Swedish Cameras) - Do Not Deep Freeze | 62 | 38 | 41 | 1 | 55.9005 | 836 | 836 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 87-88 = 2+1 Sweden Camera + 3+1 Acoustic Module + 4+1 POCAM, including spares, 200 lbs crate
1.4 |  | FieldHub electronics | Required onsite for FY24 installation. 1 crate containing readout electronics for installation in ICL - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 275 | 275 | preliminary | DNF | DESY | 2023-08-01 | DESY-CHC | 2023-08-15 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | No | FY24 inter | FY24 intra | J. Kelley | 2021-10-13 | D. Tosi | 2021-10-13 | Field Hubs are 442mm x 480mm x 133 mm (17.4" x 18.9" x 5.2") and weight maybe 10 lb each. 100 lbs crate.
1.3 |  | String Sensors 89-93 | Optical sensors for 5 strings from Germany (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 12 | 613.3333 | 573 | 6876 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is (28kg/sensor boxed) + 35kg pallet, assume 8 mDOMs/pallet - 190 to be deployed + 10 spares. (**) shipped in 20 HC container. Container not included in weight as pallets will be taken out.
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from DESY/Germany/Sweden (6 WOMs, 3 Abalone Hubs or WOM Traps) no spares - Do Not Deep Freeze | 32 | 31 | 89 | 1 | 51.0926 | 1035 | 1035 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 6 Special Devices from Germany 6 (WOM + 0 AH) including 0 spare for each. Assume 170 lbs crate.
1.5 |  | Calibration Devices 89-93 | Calibration for 5 strings from DESY/Germany/Sweden (17+2 POCAMs, 7+ 1 Acoustic sensors, 3+ 1 Swedish Cameras) including spares - Do Not Deep Freeze | 62 | 48 | 44 | 1 | 75.7778 | 1694 | 1694 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 89-93 = 3+1 Sweden Camera,7+1 + Acoustic Module,17 +1 POCAM, including spares, 200 lbs crate
|  | DESY/Aachen/TUM/Sweden etc Totals: |  |  |  | TEU=> | 1.7784 | 1692.9931 |  | 20585
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 4 | 335 | 794 | 3176 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter (SPARES - TBD) - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 1 | 83.75 | 794 | 794 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 4 | 469 | 1168.5 | 4674 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter (SPARES - TBD)- Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 1 | 117.25 | 1168.5 | 1168.5 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 8 sensors in McMurdo overwinter - Do Not Deep Freeze | 45 | 48 | 67 | 10 | 837.5 | 794 | 7940 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 12 sensors in McMurdo overwinter - Do Not Deep Freeze | 63 | 48 | 67 | 10 | 1172.5 | 1168.5 | 11685 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
|  | Chiba Totals: |  |  |  | TEU=> | 3.167 | 3015 |  | 29437.5
1.2 |  | Field Season 1 Fuel | Fuel to support FY23 field season - Base fuel |  |  |  | 3191 | 426.5746 | 6.8 | 21698.8 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 1 Fuel Contingency | Fuel to support FY23 field season - Contingency |  |  |  | 452 | 60.4236 | 6.8 | 3073.6 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel | Fuel to support FY24 field season - Base fuel, firn drilling & over winter heating |  |  |  | 18178 | 2430.045 | 6.8 | 123610.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel Contingency | Fuel to suppport FY24 field season - Contingency |  |  |  | 2373 | 317.2239 | 6.8 | 16136.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel | Fuel to support FY25 field season - Base fuel & deep drilling |  |  |  | 62694 | 8380.9682 | 6.8 | 426319.2 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 44483 | I. McEwen | 44483
1.2 |  | Field Season 3 Fuel Contingency | Fuel to suppport FY25 field season - Contingency |  |  |  | 8473 | 1132.6753 | 6.8 | 57616.4 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 44483 | I. McEwen | 44483
|  | Fuel Totals: |  |  |  | TEU=> | 13.3907 | 12747.9106 |  | 648454.8
|  |  | All IC/Upgrade cargo volume: |  |  | TEU=> | 55.9647 | 53278.3808 |  | 1167584.3
|  | total volume [cubic feet] | total weight [lbs]
Total Cargo for selected items |  | 23376.946 | 359912.3
Total Cargo according to dates |  | 23376.946 | 359912.3
Start date | End date
2023-11-01 | 2024-02-15

## FY25 inter
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Gen 1 - housed in 20' container | Power generation unit 1 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 2 - housed in 20' container | Power generation unit 2 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 3 - housed in 20' container | Power generation unit 3 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | - | In McMurdo |  | SPoT | 2022-12-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | 287 Loader | Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use | 114 | 77 | 96 | 1 | 487.6667 | 10273 | 10273 | actual |  | U. Wisc. Madison |  | In McMurdo | 2019-11-15 | Truck | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2022-12-01 | No* | In McMurdo | FY23 intra | D. Gibson | 2021-10-07 | I. McEwen | 2021-10-07 | *Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use
1.2 |  | Gen hoods Discharge Hoods - currently staged in McMurdo | Generator air discharge hoods , sheet metal, loose - stored on berm at SPOTSA | 108 | 53 | 60 | 2 | 397.5 | 330 | 660 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo |  |  | In McMurdo |  | - | In McMurdo |  | LC-130/SPoT | 2024-01-01 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Testing/limited operation of Gens can be accomplished without hoods - Hoods required for the drill season
1.2 |  | Firn Drill | Bermed in McM - will require McM fork or crane support. | 264 | 94 | 97 | 1 | 1393.0278 | 12000 | 12000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA
1.2 |  | Firn Drill Components - 1 | Firn drill sheave. Required Field Season 2 for final refit & functional testing | 97 | 44 | 63 | 1 | 155.6042 | 920 | 920 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Firn Drill Components - 2 | Firn drill drillhead. Required Field Season 2 for final refit & functional testing | 125 | 33 | 37 | 1 | 88.3247 | 1048 | 1048 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Weight stack and crates | Bermed in McM - will require McM fork support. Drill head weight stack and remaining bermed crates at SPoTSA | 120 | 48 | 48 | 1 | 160 | 600 | 600 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-15 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack
1.2 |  | Fuel Tower | Bermed in McM - will require McM fork or crane support. | 96 | 72 | 120 | 1 | 480 | 1500 | 1500 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack - overland shipment preferred due to complexities of air transport certification - can be laid on side once drained
1.2 |  | HPU 1 | HPU 1 (University of Nebraska - Lincoln asset) - 40' container housing heating plant on ISO sled | 480 | 96 | 102 | 1 | 2720 | 28000 | 28000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2024-01-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | HPU 1 integration with Rodwell system required before drill season on it's own sled which will require evaluation and repair - Stored at SPOTSA
|  | McMurdo totals: |  |  |  | TEU=> | 10.4644 | 9962.1233 |  | 121001
1.2 |  | Container Ski Stack (comprised of 5 sleds) - currently staged in Pt. Hueneme | Five sets of aluminum skis for 20' containers - stacked. Aluminum skis for drill containers. Required onsite for local movement of Gens and PDM. | 240 | 96 | 96 | 1 | 1280 | 4255 | 4255 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | No* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *While this shipment is not on the critical path additional ASC crane support will be required to overcome delayed arrival or sleds furnished from the South Pole inventory
1.2 |  | Generator Intake Hood - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 174 | 53 | 96 | 3 | 1537 | 586.6667 | 1760 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Generator Discharge Hoods - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 108 | 53 | 60 | 2 | 397.5 | 1210 | 2420 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 9 Spools - 348 cf / 3532 lbs each - Shipped from Italy | 92 | 92 | 70.5 | 9 | 3107.875 | 3531.5556 | 31784 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-08-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 3 Spools - 348 cf / 5001 lbs each - Shipped from PSL | 92 | 92 | 70.5 | 3 | 1035.9583 | 5001 | 15003 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
|  | Pt. Hueneme totals: |  |  |  | TEU=> | 7.7293 | 7358.3333 |  | 55222
1.2 |  | 8' Refit Container | Priority refit materials including tools, flowmeter assemblies, motor drive installation kits, hardware, fittings, sensors, & consumables | 96 | 86 | 96 | 1 | 458.6667 | 5600 | 5600 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130 | 2022-11-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | 8' container moves with contents by LC130 or is broken down for movement by Basler
1.2 |  | 20' Refit Container A | Refit materials incl. submersible pumps, hardware, filtration components, fall arrest towers, tools, & hose crimper | 240 | 96 | 102 | 1 | 1360 | 17500 | 17500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | 20' Refit Container B | Bulky materials incl. cable trays, vertical turbine pumps, vertical turbine pump motors, ladders, water tank doghouse/railing materials, 287 forks, generator parts, TU20 shaft, & drill weight stack | 240 | 96 | 102 | 1 | 1360 | 15500 | 15500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | ARA Trailer | Enclosed trailer on skis housing 35kw generator | 192 | 96 | 88 | 1 | 938.6667 | 4860 | 4860 | actual | FLAMMABLE liquid power engine | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *If this shipment is delayed 480 volt power generation support will be required in FW YR 1 by the contractor. Aside from the CRREL generator (far larger than required with high fuel burn rate) the capacity does not currently exist at the Pole.
1.2 |  | Return Water Cable Reel (RWCR) | Smaller reel - can fit in 20' container. Required onsite in FY23 for final integration and pre-drill activites | 112 | 80 | 80 | 1 | 414.8148 | 4000 | 4000 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight from Gen 1 shipment information see picture
1.2 |  | Main Cable Reel (MCR) | Required onsite in FY23 for final integration and pre-drill activites. Large cable reel - will require flat rack on vessel | 140 | 96 | 95 | 1 | 738.8889 | 12500 | 12500 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FS Y1 for final integration and pre-drill activities
1.2 |  | Controls infrastructure - Motor drives, PLCs, electrical hardware, and motor drive mounting kits | Components and equipment to support field season 1 controls system tasking - ComSur - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight estimated
1.4 |  | ICL power and timing electronics | 1 crate containing rackmount electronics for power and timing systems - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 600 | 600 | estimated | DNF | U. Wisc. Madison | 2023-08-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12
1.4 |  | ICL patch cables and patch panels | Standard vessel shipping - can overwinter in McM if shipped earlier - Do Not Deep Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNDF [TBD] | U. Wisc. Madison | 2023-06-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12 | (*) storage in McMurdo pending low temperature test
1.2 |  | ARA Drill System Components - Crate 1 | ARA (Antarctic Rodwell Appartus) - downhole pump controller, ePump controller, splash cam kit, and accessories - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | ARA Drill System Components - Crate 2 | ARA (Antarctic Rodwell Appartus) - new downhole pumps, spares, accessories and tools | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Camp Hose - currently staged at PSL | Two spools of hose - 348 cf / 4990 lbs each. Required for SES set-up - no DNDF requirement. | 92 | 92 | 71 | 2 | 695.537 | 4990 | 9980 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY22 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Bull wheel | Bull wheel assembly - used to install main cable on reel in event of main cable damage/failure | 88 | 58 | 97 | 1 | 286.5093 | 2880 | 2880 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2024-02-01 | No | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight and cube used from Gen 1 shipping label still on bull wheel.
1.2 |  | Load member cable reel | Cable Reel used to deploy downhole load member during string installation | 84 | 60 | 48 | 1 | 140 | 3800 | 3800 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-15 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 for integration - recent addition, still in development
1.2 |  | DOM Handling Facility (DHF) | Standard vessel shipping - can overwinter in McM. | 240 | 96 | 96 | 1 | 1280 | 12000 | 12000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Sensor Handling Facility construction scheduled to begin mid-December FY24
1.2 |  | Spare Combo cable | Spare cable for Return Water Cable Reel - on spool | 72 | 72 | 72 | 1 | 216 | 3000 | 3000 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Spare Drill Cable | Standard vessel shipping - can overwinter in McM. Cable on steel spool. | 83 | 83 | 61 | 1 | 243.1881 | 6835 | 6835 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Computing/controls components | Computing and controls equipment (Motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 to support controls system tasking
1.2 |  | Driller resupply/refit components - 8' Container | 8' Mini Milvan; Consumables/drill components | 96 | 86 | 96 | 1 | 458.6667 | 6500 | 6500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season - 8' container moves with contents overland or by air
1.2 |  | Drill refit components | Single crate. Consumables/drill refit components | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated |  | U. Wisc. Madison |  | UWM-PTH | 2023-08-01 | Truck | PTH - CHC |  | Comsur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season
1.2 |  | Drill Heads DNF - X | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-02-12 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | One drill head shipped one year early for ull system wet-test
1.2 |  | Drill Heads DNF - Y | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Heads DNF - R | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Computing/controls components | Computing and controls equipment (Sensor, motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-15 | Yes | FY25 inter | FY25 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Installation Hardware 87-93 | Installation hardware for winterover storage at Pole | 96 | 48 | 48 | 7 | 896 | 1000 | 7000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.2 |  | Installation Weights 87-93 | Installation weights for winterover storage at Pole | 36 | 24 | 24 | 7 | 84 | 785.7143 | 5500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.5 |  | Calibration/Special Devices 87-88 | 3+1 PencilBeams from UW, 2+1 pDOM and 1+1 LOMs - Do Not Deep Freeze | 58 | 38 | 41 | 1 | 52.294 | 836 | 836 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from UW (4+1 Radio Pulsers (all strings) 1+1 Radio Receivers, 3+1 FOM) - Do Not Deep Freeze | 63 | 40 | 42 | 1 | 61.25 | 677 | 677 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 4+1 Radio Pulser, weight 50 kg. 1+1 Radio receiver, assume mDOM weight, 3+1 FOM (assume mDOM weight) + 2ftx2ftx4ft FOM box (50 lbs). Special Devices from UW. FTS, seismometer missing from estimate. 250 lbs crate estimate
1.2 |  | Misc. Science Equipment - FY24 | Scientific and test equipment (SPAT, DCM et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-10-08 | D. Tosi | 2021-10-08
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from UW (4+1 FOM,2+1 Radio Receivers, 11+1 LOM + seismometer*) - Do Not Deep Freeze | 81 | 56 | 51 | 1 | 133.875 | 1797 | 1797 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 21 Special Devices from USA (11+ 1 LOM, 4+1 FOM, 2+1 RR, FTS ? , seismometer), assume mDOM weight. 200 lbs wood crate. FTS not included. (*) Seismometer not yet in CMD
1.5 |  | Calibration/Special Devices 89-93 | 8+1 PencilBeams, 12+1 pDOMs from UW - Do Not Deep Freeze | 75 | 56.5 | 41 | 1 | 100.5425 | 1602 | 1602 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-05 | 8+1 PencilBeams for strings 89-93, 12+1 pDOMs, assume mDOM weight. 244 lbs crate.
1.2 |  | Misc. Science Equipment - FY25 | Scientific and test equipment (Handheld test devices, Paros, et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-12-01 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | D. Tosi | 2021-10-08
1.5 |  | Dust logging device | Blue Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-18 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Green Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-19 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 24 | 24 | 1 | 8.6667 | 120 | 120 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-20 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 23 | 20 | 1 | 6.9213 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-21 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Logging winch | Winch to be used for Dust Logging | 86 | 60 | 68 | 1 | 203.0556 | 3500 | 3500 | IDP deep logging winch for reference |  | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.5 |  | Logging winch control box | Control Box for winch for Dust Logging - sensitive equipment - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 400 | 400 | IDP deep logging winch for reference | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
|  | U. Wisconsin totals: |  |  |  | TEU=> | 12.1277 | 11545.5987 |  | 148947
1.4 |  | Surface Junction Boxes | Surface Junction Boxes can overwinter in McM if shipped earlier. 7 junction boxes | 66 | 30 | 14 | 7 | 112.2917 | 200 | 1400 | preliminary |  | MSU | 2022-11-01 | MSU-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-10 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | Each is 66" x 30" x 14", each is 112 lbs. Assume Folding crate
1.4 |  | Surface Cable Assemblies | Palletized wooden cable drums (Qty: 7). Can overwinter in MCM. | 48 | 65 | 71 | 7 | 897.3611 | 1335.7143 | 9350 | actual |  | MSU | 2021-11-30 | MSU-PTH | 2022-12-01 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-11-20 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Breakout cables for strings 87-88 | Standard vessel shipping. 2 wooden crates containing spooled breakout cable assemblies - 96 cf / 1,000 lbs each - Do Not Deep Freeze | 72 | 48 | 48 | 2 | 192 | 1000 | 2000 | estimated | DNDF[-40C](*) | MSU | 2023-02-28 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | Preliminary estimate of weight and size. Pre-staging string 87-88 equipment in cryo or ICL. - if shipping to Pole not possible before end of 23/24 season could overwinter in McM (at an increased risk and pending low temperature test)
1.4 |  | Breakout cables for strings 89-93 | Stored in McMurdo FY24. 5 wooden crates containing spooled breakout cable assemblies - 96 cf/ 1,000 lbs each (preliminary) - Do Not Deep Freeze | 72 | 48 | 48 | 5 | 480 | 1000 | 5000 | estimated | DNDF[-40C](*) | MSU | 2023-05-22 | MSU-PTH | 2023-06-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-11-25 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-09-20 | Preliminary estimate of weight and size. (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) load members 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 47 | 47 | 39 | 7 | 348.9913 | 766 | 5362 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) cables 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 96 | 96 | 96 | 7 | 3584 | 15000 | 105000 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 25 | 1277.7778 | 573 | 14325 | final weight(**) | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 28 kg/boxed + 35kg pallet, assume 8 mDOMs/pallet (189 to be deployed + 11 spares)(*)Assumed to be shipped in 2x20' HC (5115 lbs, 238inx96inx114in) or a 40 ft HC, purchased by MSU or loaned in PTH (container weight not included)
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) containers (TBD) - Do Not Deep Freeze | 238 | 96 | 114 | 0 | 0 | 5115 | 0 | see notes in item above | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | Assume 2x20HC containers for transport on COMSUR (TBC). Pallets could be loaded to 53 ft truck and loaded into a loaned container in PTH but this would increase touch points (and risk)
|  | MSU Totals: |  |  |  | TEU=> | 7.2399 | 6892.4219 |  | 142437
1.3 |  | DM-Ice | DM-ice (two modules for string 89 and 90) - Do Not Deep Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNDF [-40C] | Yale |  | Yale-PTH |  | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | M. Kauer | 2021-09-20 | D. Tosi | 2021-09-20
|  | Other Institutions Totals: |  |  |  |  | 0.067227 | 64 |  | 1500
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (spares included) - Do Not Deep Freeze | 40 | 48 | 46 | 16 | 817.7778 | 573 | 9168 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - 116 to be deployed + 12 spares - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (SPARES) - Do Not Deep Freeze | 40 | 48 | 46 | 0 | 0 | 573 | 0 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from DESY/Germany/Sweden (8 WOMs, 0 Abalone) + spares - Do Not Deep Freeze | 40 | 21 | 64 | 1 | 31.1111 | 701 | 701 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 8 WOMs (no spares) - AH not included for now. Assume 150 lbs crate.
1.5 |  | Calibration Devices 87-88 | Calibration devices for 2 strings from DESY/Germany/Sweden (4+2 POCAMs, 3+1 Acoustic sensors, 2+1 Swedish Cameras) - Do Not Deep Freeze | 62 | 38 | 41 | 1 | 55.9005 | 836 | 836 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 87-88 = 2+1 Sweden Camera + 3+1 Acoustic Module + 4+1 POCAM, including spares, 200 lbs crate
1.4 |  | FieldHub electronics | Required onsite for FY24 installation. 1 crate containing readout electronics for installation in ICL - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 275 | 275 | preliminary | DNF | DESY | 2023-08-01 | DESY-CHC | 2023-08-15 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | No | FY24 inter | FY24 intra | J. Kelley | 2021-10-13 | D. Tosi | 2021-10-13 | Field Hubs are 442mm x 480mm x 133 mm (17.4" x 18.9" x 5.2") and weight maybe 10 lb each. 100 lbs crate.
1.3 |  | String Sensors 89-93 | Optical sensors for 5 strings from Germany (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 12 | 613.3333 | 573 | 6876 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is (28kg/sensor boxed) + 35kg pallet, assume 8 mDOMs/pallet - 190 to be deployed + 10 spares. (**) shipped in 20 HC container. Container not included in weight as pallets will be taken out.
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from DESY/Germany/Sweden (6 WOMs, 3 Abalone Hubs or WOM Traps) no spares - Do Not Deep Freeze | 32 | 31 | 89 | 1 | 51.0926 | 1035 | 1035 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 6 Special Devices from Germany 6 (WOM + 0 AH) including 0 spare for each. Assume 170 lbs crate.
1.5 |  | Calibration Devices 89-93 | Calibration for 5 strings from DESY/Germany/Sweden (17+2 POCAMs, 7+ 1 Acoustic sensors, 3+ 1 Swedish Cameras) including spares - Do Not Deep Freeze | 62 | 48 | 44 | 1 | 75.7778 | 1694 | 1694 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 89-93 = 3+1 Sweden Camera,7+1 + Acoustic Module,17 +1 POCAM, including spares, 200 lbs crate
|  | DESY/Aachen/TUM/Sweden etc Totals: |  |  |  | TEU=> | 1.7784 | 1692.9931 |  | 20585
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 4 | 335 | 794 | 3176 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter (SPARES - TBD) - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 1 | 83.75 | 794 | 794 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 4 | 469 | 1168.5 | 4674 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter (SPARES - TBD)- Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 1 | 117.25 | 1168.5 | 1168.5 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 8 sensors in McMurdo overwinter - Do Not Deep Freeze | 45 | 48 | 67 | 10 | 837.5 | 794 | 7940 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 12 sensors in McMurdo overwinter - Do Not Deep Freeze | 63 | 48 | 67 | 10 | 1172.5 | 1168.5 | 11685 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
|  | Chiba Totals: |  |  |  | TEU=> | 3.167 | 3015 |  | 29437.5
1.2 |  | Field Season 1 Fuel | Fuel to support FY23 field season - Base fuel |  |  |  | 3191 | 426.5746 | 6.8 | 21698.8 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 1 Fuel Contingency | Fuel to support FY23 field season - Contingency |  |  |  | 452 | 60.4236 | 6.8 | 3073.6 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel | Fuel to support FY24 field season - Base fuel, firn drilling & over winter heating |  |  |  | 18178 | 2430.045 | 6.8 | 123610.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel Contingency | Fuel to suppport FY24 field season - Contingency |  |  |  | 2373 | 317.2239 | 6.8 | 16136.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel | Fuel to support FY25 field season - Base fuel & deep drilling |  |  |  | 62694 | 8380.9682 | 6.8 | 426319.2 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel Contingency | Fuel to suppport FY25 field season - Contingency |  |  |  | 8473 | 1132.6753 | 6.8 | 57616.4 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
|  | Fuel Totals: |  |  |  | TEU=> | 13.3907 | 12747.9106 |  | 648454.8
|  |  | All IC/Upgrade cargo volume: |  |  | TEU=> | 55.9647 | 53278.3808 |  | 1167584.3
|  | total volume [cubic feet] | total weight [lbs]
Total Cargo for selected items |  | 14314.7415 | 541089.6
Total Cargo according to dates |  | 14314.7415 | 541089.6
Start date | End date
2024-11-01 | 2025-02-15

## FY25 intra
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Cubic feet | Unit weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | Date of expected or actual completion | Expected Route: Owner - PTH or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Date of expected or actual shipment | Recommended Transportation Option | Expected Route: CHC - MCM | Date of expected or actual shipment | Recommended Transportation Option | Date Item expected or arrived to MCM | Date of (planned) or actual shipment to SPA | Recommended LC-130 or SPOT | Date/Month for Items needed at South Pole | Critical Path | Intercontinental shipping | Intracontinental shipping | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
1.2 |  | Gen 1 - housed in 20' container | Power generation unit 1 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 2 - housed in 20' container | Power generation unit 2 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | Gen 3 - housed in 20' container | Power generation unit 3 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 22000 | 22000 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | - | In McMurdo |  | SPoT | 2022-12-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 |  | 287 Loader | Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use | 114 | 77 | 96 | 1 | 487.6667 | 10273 | 10273 | actual |  | U. Wisc. Madison |  | In McMurdo | 2019-11-15 | Truck | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2022-12-01 | No* | In McMurdo | FY23 intra | D. Gibson | 2021-10-07 | I. McEwen | 2021-10-07 | *Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use
1.2 |  | Gen hoods Discharge Hoods - currently staged in McMurdo | Generator air discharge hoods , sheet metal, loose - stored on berm at SPOTSA | 108 | 53 | 60 | 2 | 397.5 | 330 | 660 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo |  |  | In McMurdo |  | - | In McMurdo |  | LC-130/SPoT | 2024-01-01 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Testing/limited operation of Gens can be accomplished without hoods - Hoods required for the drill season
1.2 |  | Firn Drill | Bermed in McM - will require McM fork or crane support. | 264 | 94 | 97 | 1 | 1393.0278 | 12000 | 12000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA
1.2 |  | Firn Drill Components - 1 | Firn drill sheave. Required Field Season 2 for final refit & functional testing | 97 | 44 | 63 | 1 | 155.6042 | 920 | 920 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Firn Drill Components - 2 | Firn drill drillhead. Required Field Season 2 for final refit & functional testing | 125 | 33 | 37 | 1 | 88.3247 | 1048 | 1048 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Weight stack and crates | Bermed in McM - will require McM fork support. Drill head weight stack and remaining bermed crates at SPoTSA | 120 | 48 | 48 | 1 | 160 | 600 | 600 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-12-15 | No | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack
1.2 |  | Fuel Tower | Bermed in McM - will require McM fork or crane support. | 96 | 72 | 120 | 1 | 480 | 1500 | 1500 | actual |  | U. Wisc. Madison |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | LC-130/SPoT | 2023-01-01 | Yes | In McMurdo | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack - overland shipment preferred due to complexities of air transport certification - can be laid on side once drained
1.2 |  | HPU 1 | HPU 1 (University of Nebraska - Lincoln asset) - 40' container housing heating plant on ISO sled | 480 | 96 | 102 | 1 | 2720 | 28000 | 28000 | actual |  | U. Wisc. Madison |  | In McMurdo |  |  | In McMurdo | - | - | In McMurdo | - | - | In McMurdo |  | SPoT | 2024-01-01 | Yes | In McMurdo | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | HPU 1 integration with Rodwell system required before drill season on it's own sled which will require evaluation and repair - Stored at SPOTSA
|  | McMurdo totals: |  |  |  | TEU=> | 10.4644 | 9962.1233 |  | 121001
1.2 |  | Container Ski Stack (comprised of 5 sleds) - currently staged in Pt. Hueneme | Five sets of aluminum skis for 20' containers - stacked. Aluminum skis for drill containers. Required onsite for local movement of Gens and PDM. | 240 | 96 | 96 | 1 | 1280 | 4255 | 4255 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | No* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *While this shipment is not on the critical path additional ASC crane support will be required to overcome delayed arrival or sleds furnished from the South Pole inventory
1.2 |  | Generator Intake Hood - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 174 | 53 | 96 | 3 | 1537 | 586.6667 | 1760 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Generator Discharge Hoods - currently staged in Pt. Hueneme | Light weight large volume sheet metal stacks for generator ventilation | 108 | 53 | 60 | 2 | 397.5 | 1210 | 2420 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-11-24 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 9 Spools - 348 cf / 3532 lbs each - Shipped from Italy | 92 | 92 | 70.5 | 9 | 3107.875 | 3531.5556 | 31784 | actual |  | U. Wisc. Madison |  | Already at PTH | 2020-08-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.2 |  | Drill Hose - currently staged in Pt. Hueneme | Drill hose - 3 Spools - 348 cf / 5001 lbs each - Shipped from PSL | 92 | 92 | 70.5 | 3 | 1035.9583 | 5001 | 15003 | actual |  | U. Wisc. Madison |  | Already at PTH | 2021-01-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2024-01-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
|  | Pt. Hueneme totals: |  |  |  | TEU=> | 7.7293 | 7358.3333 |  | 55222
1.2 |  | 8' Refit Container | Priority refit materials including tools, flowmeter assemblies, motor drive installation kits, hardware, fittings, sensors, & consumables | 96 | 86 | 96 | 1 | 458.6667 | 5600 | 5600 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130 | 2022-11-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | 8' container moves with contents by LC130 or is broken down for movement by Basler
1.2 |  | 20' Refit Container A | Refit materials incl. submersible pumps, hardware, filtration components, fall arrest towers, tools, & hose crimper | 240 | 96 | 102 | 1 | 1360 | 17500 | 17500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | 20' Refit Container B | Bulky materials incl. cable trays, vertical turbine pumps, vertical turbine pump motors, ladders, water tank doghouse/railing materials, 287 forks, generator parts, TU20 shaft, & drill weight stack | 240 | 96 | 102 | 1 | 1360 | 15500 | 15500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 |  | ARA Trailer | Enclosed trailer on skis housing 35kw generator | 192 | 96 | 88 | 1 | 938.6667 | 4860 | 4860 | actual | FLAMMABLE liquid power engine | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2022-12-15 | Yes* | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *If this shipment is delayed 480 volt power generation support will be required in FW YR 1 by the contractor. Aside from the CRREL generator (far larger than required with high fuel burn rate) the capacity does not currently exist at the Pole.
1.2 |  | Return Water Cable Reel (RWCR) | Smaller reel - can fit in 20' container. Required onsite in FY23 for final integration and pre-drill activites | 112 | 80 | 80 | 1 | 414.8148 | 4000 | 4000 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight from Gen 1 shipment information see picture
1.2 |  | Main Cable Reel (MCR) | Required onsite in FY23 for final integration and pre-drill activites. Large cable reel - will require flat rack on vessel | 140 | 96 | 95 | 1 | 738.8889 | 12500 | 12500 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2021-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-01-01 | Yes | FY22 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FS Y1 for final integration and pre-drill activities
1.2 |  | Controls infrastructure - Motor drives, PLCs, electrical hardware, and motor drive mounting kits | Components and equipment to support field season 1 controls system tasking - ComSur - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight estimated
1.4 |  | ICL power and timing electronics | 1 crate containing rackmount electronics for power and timing systems - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 600 | 600 | estimated | DNF | U. Wisc. Madison | 2023-08-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12
1.4 |  | ICL patch cables and patch panels | Standard vessel shipping - can overwinter in McM if shipped earlier - Do Not Deep Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNDF [TBD] | U. Wisc. Madison | 2023-06-01 | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | J. Kelley | 2021-10-12 | D. Tosi | 2021-10-12 | (*) storage in McMurdo pending low temperature test
1.2 |  | ARA Drill System Components - Crate 1 | ARA (Antarctic Rodwell Appartus) - downhole pump controller, ePump controller, splash cam kit, and accessories - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130 | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | ARA Drill System Components - Crate 2 | ARA (Antarctic Rodwell Appartus) - new downhole pumps, spares, accessories and tools | 96 | 48 | 48 | 1 | 128 | 1200 | 1200 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-05-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Camp Hose - currently staged at PSL | Two spools of hose - 348 cf / 4990 lbs each. Required for SES set-up - no DNDF requirement. | 92 | 92 | 71 | 2 | 695.537 | 4990 | 9980 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2022-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY22 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Bull wheel | Bull wheel assembly - used to install main cable on reel in event of main cable damage/failure | 88 | 58 | 97 | 1 | 286.5093 | 2880 | 2880 | actual |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2024-02-01 | No | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight and cube used from Gen 1 shipping label still on bull wheel.
1.2 |  | Load member cable reel | Cable Reel used to deploy downhole load member during string installation | 84 | 60 | 48 | 1 | 140 | 3800 | 3800 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-15 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 for integration - recent addition, still in development
1.2 |  | DOM Handling Facility (DHF) | Standard vessel shipping - can overwinter in McM. | 240 | 96 | 96 | 1 | 1280 | 12000 | 12000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel | - | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-01 | Yes | FY23 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Sensor Handling Facility construction scheduled to begin mid-December FY24
1.2 |  | Spare Combo cable | Spare cable for Return Water Cable Reel - on spool | 72 | 72 | 72 | 1 | 216 | 3000 | 3000 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Spare Drill Cable | Standard vessel shipping - can overwinter in McM. Cable on steel spool. | 83 | 83 | 61 | 1 | 243.1881 | 6835 | 6835 | actual |  | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-02-12 | No | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Spare required for drill season
1.2 |  | Computing/controls components | Computing and controls equipment (Motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 to support controls system tasking
1.2 |  | Driller resupply/refit components - 8' Container | 8' Mini Milvan; Consumables/drill components | 96 | 86 | 96 | 1 | 458.6667 | 6500 | 6500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season - 8' container moves with contents overland or by air
1.2 |  | Drill refit components | Single crate. Consumables/drill refit components | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated |  | U. Wisc. Madison |  | UWM-PTH | 2023-08-01 | Truck | PTH - CHC |  | Comsur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-11-15 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season
1.2 |  | Drill Heads DNF - X | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-02-12 | Yes | FY23 inter | FY23 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | One drill head shipped one year early for ull system wet-test
1.2 |  | Drill Heads DNF - Y | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Drill Heads DNF - R | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison |  | UWM-PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-12 | Yes | FY24 inter | FY24 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Computing/controls components | Computing and controls equipment (Sensor, motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-15 | Yes | FY25 inter | FY25 intra | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08
1.2 |  | Installation Hardware 87-93 | Installation hardware for winterover storage at Pole | 96 | 48 | 48 | 7 | 896 | 1000 | 7000 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.2 |  | Installation Weights 87-93 | Installation weights for winterover storage at Pole | 36 | 24 | 24 | 7 | 84 | 785.7143 | 5500 | estimated |  | U. Wisc. Madison |  | UWM - PTH | 2023-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22
1.5 |  | Calibration/Special Devices 87-88 | 3+1 PencilBeams from UW, 2+1 pDOM and 1+1 LOMs - Do Not Deep Freeze | 58 | 38 | 41 | 1 | 52.294 | 836 | 836 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from UW (4+1 Radio Pulsers (all strings) 1+1 Radio Receivers, 3+1 FOM) - Do Not Deep Freeze | 63 | 40 | 42 | 1 | 61.25 | 677 | 677 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 4+1 Radio Pulser, weight 50 kg. 1+1 Radio receiver, assume mDOM weight, 3+1 FOM (assume mDOM weight) + 2ftx2ftx4ft FOM box (50 lbs). Special Devices from UW. FTS, seismometer missing from estimate. 250 lbs crate estimate
1.2 |  | Misc. Science Equipment - FY24 | Scientific and test equipment (SPAT, DCM et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2023-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-10-08 | D. Tosi | 2021-10-08
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from UW (4+1 FOM,2+1 Radio Receivers, 11+1 LOM + seismometer*) - Do Not Deep Freeze | 81 | 56 | 51 | 1 | 133.875 | 1797 | 1797 | preliminary | DNDF [-40C] | UWM/Kansas |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 21 Special Devices from USA (11+ 1 LOM, 4+1 FOM, 2+1 RR, FTS ? , seismometer), assume mDOM weight. 200 lbs wood crate. FTS not included. (*) Seismometer not yet in CMD
1.5 |  | Calibration/Special Devices 89-93 | 8+1 PencilBeams, 12+1 pDOMs from UW - Do Not Deep Freeze | 75 | 56.5 | 41 | 1 | 100.5425 | 1602 | 1602 | use mDOM as estimate | DNDF [-40C] | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-05 | 8+1 PencilBeams for strings 89-93, 12+1 pDOMs, assume mDOM weight. 244 lbs crate.
1.2 |  | Misc. Science Equipment - FY25 | Scientific and test equipment (Handheld test devices, Paros, et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-12-01 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | D. Tosi | 2021-10-08
1.5 |  | Dust logging device | Blue Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-18 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Green Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 8.0278 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-19 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 24 | 24 | 1 | 8.6667 | 120 | 120 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-20 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 23 | 20 | 1 | 6.9213 | 60 | 60 | as in 2019-2020 | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-14 | D. Tosi | 2021-09-21 | Used weights from last deployment season shipment data (could be combined)
1.5 |  | Logging winch | Winch to be used for Dust Logging | 86 | 60 | 68 | 1 | 203.0556 | 3500 | 3500 | IDP deep logging winch for reference |  | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.5 |  | Logging winch control box | Control Box for winch for Dust Logging - sensitive equipment - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 400 | 400 | IDP deep logging winch for reference | DNF | U. Wisc. Madison |  | UWM - PTH | 2024-08-01 | Truck | PTH - CHC |  | ComAir | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
|  | U. Wisconsin totals: |  |  |  | TEU=> | 12.1277 | 11545.5987 |  | 148947
1.4 |  | Surface Junction Boxes | Surface Junction Boxes can overwinter in McM if shipped earlier. 7 junction boxes | 66 | 30 | 14 | 7 | 112.2917 | 200 | 1400 | preliminary |  | MSU | 2022-11-01 | MSU-PTH | 2022-11-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130/SPoT | 2023-12-10 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | Each is 66" x 30" x 14", each is 112 lbs. Assume Folding crate
1.4 |  | Surface Cable Assemblies | Palletized wooden cable drums (Qty: 7). Can overwinter in MCM. | 48 | 65 | 71 | 7 | 897.3611 | 1335.7143 | 9350 | actual |  | MSU | 2021-11-30 | MSU-PTH | 2022-12-01 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2023-02-06 |  | LC-130 | 2023-11-20 | Yes | FY23 inter | FY24 intra | T. DeYoung | 2021-10-13 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Breakout cables for strings 87-88 | Standard vessel shipping. 2 wooden crates containing spooled breakout cable assemblies - 96 cf / 1,000 lbs each - Do Not Deep Freeze | 72 | 48 | 48 | 2 | 192 | 1000 | 2000 | estimated | DNDF[-40C](*) | MSU | 2023-02-28 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130 | 2024-02-15 | Yes | FY24 inter | FY24 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | Preliminary estimate of weight and size. Pre-staging string 87-88 equipment in cryo or ICL. - if shipping to Pole not possible before end of 23/24 season could overwinter in McM (at an increased risk and pending low temperature test)
1.4 |  | Breakout cables for strings 89-93 | Stored in McMurdo FY24. 5 wooden crates containing spooled breakout cable assemblies - 96 cf/ 1,000 lbs each (preliminary) - Do Not Deep Freeze | 72 | 48 | 48 | 5 | 480 | 1000 | 5000 | estimated | DNDF[-40C](*) | MSU | 2023-05-22 | MSU-PTH | 2023-06-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-11-25 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-09-20 | Preliminary estimate of weight and size. (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) load members 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 47 | 47 | 39 | 7 | 348.9913 | 766 | 5362 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.4 |  | Main (downhole) cables 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 96 | 96 | 96 | 7 | 3584 | 15000 | 105000 | preliminary | DNDF[-40C](*) | MSU | 2023-04-01 | MSU-PTH | 2023-04-15 | Truck | PTH - MCM |  | USAP Vessel | USAP Vessel |  | - | 2024-02-06 |  | LC-130/SPoT | 2024-12-01 | Yes | FY24 inter | FY25 intra | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | (*) storage in McMurdo pending low temperature test
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 25 | 1277.7778 | 573 | 14325 | final weight(**) | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 28 kg/boxed + 35kg pallet, assume 8 mDOMs/pallet (189 to be deployed + 11 spares)(*)Assumed to be shipped in 2x20' HC (5115 lbs, 238inx96inx114in) or a 40 ft HC, purchased by MSU or loaned in PTH (container weight not included)
1.3 |  | String Sensors 89-93 | Optical Sensors for 5 strings from MSU (mDOMs) containers (TBD) - Do Not Deep Freeze | 238 | 96 | 114 | 0 | 0 | 5115 | 0 | see notes in item above | DNDF [-40C] | MSU |  | MSU-PTH | 2024-08-01 | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | Assume 2x20HC containers for transport on COMSUR (TBC). Pallets could be loaded to 53 ft truck and loaded into a loaned container in PTH but this would increase touch points (and risk)
|  | MSU Totals: |  |  |  | TEU=> | 7.2399 | 6892.4219 |  | 142437
1.3 |  | DM-Ice | DM-ice (two modules for string 89 and 90) - Do Not Deep Freeze | 48 | 48 | 48 | 1 | 64 | 1500 | 1500 | estimated | DNDF [-40C] | Yale |  | Yale-PTH |  | Truck | PTH - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | M. Kauer | 2021-09-20 | D. Tosi | 2021-09-20
|  | Other Institutions Totals: |  |  |  |  | 0.067227 | 64 |  | 1500
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (spares included) - Do Not Deep Freeze | 40 | 48 | 46 | 16 | 817.7778 | 573 | 9168 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - 116 to be deployed + 12 spares - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87-88 | Optical sensors for 2 strings from Germany (mDOMs) (SPARES) - Do Not Deep Freeze | 40 | 48 | 46 | 0 | 0 | 573 | 0 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - (**) shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | Special Devices 87-88 | Special devices for 2 strings from DESY/Germany/Sweden (8 WOMs, 0 Abalone) + spares - Do Not Deep Freeze | 40 | 21 | 64 | 1 | 31.1111 | 701 | 701 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 8 WOMs (no spares) - AH not included for now. Assume 150 lbs crate.
1.5 |  | Calibration Devices 87-88 | Calibration devices for 2 strings from DESY/Germany/Sweden (4+2 POCAMs, 3+1 Acoustic sensors, 2+1 Swedish Cameras) - Do Not Deep Freeze | 62 | 38 | 41 | 1 | 55.9005 | 836 | 836 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2023-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 87-88 = 2+1 Sweden Camera + 3+1 Acoustic Module + 4+1 POCAM, including spares, 200 lbs crate
1.4 |  | FieldHub electronics | Required onsite for FY24 installation. 1 crate containing readout electronics for installation in ICL - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 275 | 275 | preliminary | DNF | DESY | 2023-08-01 | DESY-CHC | 2023-08-15 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2023-12-01 | No | FY24 inter | FY24 intra | J. Kelley | 2021-10-13 | D. Tosi | 2021-10-13 | Field Hubs are 442mm x 480mm x 133 mm (17.4" x 18.9" x 5.2") and weight maybe 10 lb each. 100 lbs crate.
1.3 |  | String Sensors 89-93 | Optical sensors for 5 strings from Germany (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 12 | 613.3333 | 573 | 6876 | final weight(**) | DNDF [-40C] | DESY |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is (28kg/sensor boxed) + 35kg pallet, assume 8 mDOMs/pallet - 190 to be deployed + 10 spares. (**) shipped in 20 HC container. Container not included in weight as pallets will be taken out.
1.3 |  | Special Devices 89-93 | Special devices for 5 remaining strings from DESY/Germany/Sweden (6 WOMs, 3 Abalone Hubs or WOM Traps) no spares - Do Not Deep Freeze | 32 | 31 | 89 | 1 | 51.0926 | 1035 | 1035 | preliminary | DNDF [-40C] | Mainz |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 6 Special Devices from Germany 6 (WOM + 0 AH) including 0 spare for each. Assume 170 lbs crate.
1.5 |  | Calibration Devices 89-93 | Calibration for 5 strings from DESY/Germany/Sweden (17+2 POCAMs, 7+ 1 Acoustic sensors, 3+ 1 Swedish Cameras) including spares - Do Not Deep Freeze | 62 | 48 | 44 | 1 | 75.7778 | 1694 | 1694 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden |  | DESY-CHC | 2024-08-01 | ComSur | DESY-CHC |  | ComSur | CHC-MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 89-93 = 3+1 Sweden Camera,7+1 + Acoustic Module,17 +1 POCAM, including spares, 200 lbs crate
|  | DESY/Aachen/TUM/Sweden etc Totals: |  |  |  | TEU=> | 1.7784 | 1692.9931 |  | 20585
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 4 | 335 | 794 | 3176 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter (SPARES - TBD) - Cryo location - Do Not Deep Freeze | 45 | 48 | 67 | 1 | 83.75 | 794 | 794 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 4 | 469 | 1168.5 | 4674 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 87 & 88 | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter (SPARES - TBD)- Cryo location - Do Not Deep Freeze | 63 | 48 | 67 | 1 | 117.25 | 1168.5 | 1168.5 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2023-11-01 |  | LC-130 | 2024-01-15 | Yes | FY24 inter | FY24 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. SPARES number to be confirmed. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 8 sensors in McMurdo overwinter - Do Not Deep Freeze | 45 | 48 | 67 | 10 | 837.5 | 794 | 7940 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 |  | String Sensors 89-93 | Sensors (D-Eggs) pallets with 12 sensors in McMurdo overwinter - Do Not Deep Freeze | 63 | 48 | 67 | 10 | 1172.5 | 1168.5 | 11685 | preliminary(*) | DNDF [-40C] | Chiba |  | ChibaU - CHC | 2023-08-01 | Cargo shipment by CHU | ChibaU - CHC |  | ComSur | CHC - MCM |  | USAP Air | 2024-11-01 |  | LC-130 | 2024-11-25 | Yes | FY25 inter | FY25 intra | S. Yoshida | 2021-09-22 | D. Tosi | 2021-09-22 | Pallet sizes are under review. (*) shipped in 20 and 40ft container. Container weight not included in the assumption that pallet will be taken out in CHC.
|  | Chiba Totals: |  |  |  | TEU=> | 3.167 | 3015 |  | 29437.5
1.2 |  | Field Season 1 Fuel | Fuel to support FY23 field season - Base fuel |  |  |  | 3191 | 426.5746 | 6.8 | 21698.8 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 1 Fuel Contingency | Fuel to support FY23 field season - Contingency |  |  |  | 452 | 60.4236 | 6.8 | 3073.6 | preliminary | [12 empty] | 2022-11-01 |  | LC-130/SPoT | 2022-12-01 | Yes | FY23 inter | FY23 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel | Fuel to support FY24 field season - Base fuel, firn drilling & over winter heating |  |  |  | 18178 | 2430.045 | 6.8 | 123610.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 2 Fuel Contingency | Fuel to suppport FY24 field season - Contingency |  |  |  | 2373 | 317.2239 | 6.8 | 16136.4 | preliminary | [12 empty] | 2023-11-01 |  | LC-130/SPoT | 2023-12-01 | Yes | FY24 inter | FY24 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel | Fuel to support FY25 field season - Base fuel & deep drilling |  |  |  | 62694 | 8380.9682 | 6.8 | 426319.2 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
1.2 |  | Field Season 3 Fuel Contingency | Fuel to suppport FY25 field season - Contingency |  |  |  | 8473 | 1132.6753 | 6.8 | 57616.4 | preliminary | [12 empty] | 2024-11-01 |  | LC-130/SPoT | 2024-12-01 | Yes | FY25 inter | FY25 intra | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14
|  | Fuel Totals: |  |  |  | TEU=> | 13.3907 | 12747.9106 |  | 648454.8
|  |  | All IC/Upgrade cargo volume: |  |  | TEU=> | 55.9647 | 53278.3808 |  | 1167584.3
|  | total volume [cubic feet] | total weight [lbs]
Total Cargo for selected items |  | 18727.7328 | 656451.6
Total Cargo according to dates |  | 18727.7328 | 656451.6
Start date | End date
2024-11-01 | 2025-02-15