## MASTER INPUT SHEET
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Unit Volume (cu ft) | Total Volume (cu ft) = quantity x unit volume | Unit Weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | SHIPMENT FLOAT: Time between completion and ship-by-date to USAP site | Date of actuaL or expected [from schedule] completion | Ship by date or actual shipment date | Expected Route: Owner - PTH or CHC | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Recommended Intercontinental Shipping Date (FY) [CALCULATED] | Recommended Transportation Option to CHC/MCM [INPUT] | Expected Route: CHC - MCM [CALCULATED] | Vessel Container Allocation 40F | Vessel Container Allocation 40D | Vessel Container Allocation 20D | Vessel Container Allocation 20F | C-17/LC-130 CHC --> MCM Pallet Allocation | Date Item expected or arrived to MCM [INPUT] | Recommended Intracontinental Date (FY) [CALCULATED] | Recommended Intracontinental Mode MCM--> NPX [CALCULATED] | SPOT Sled Allocation - Swing 1 (11/27) | SPOT Sled Allocation - Swing 2 (12/25) | SPOT Sled Allocation - Swing 3 (2/5) | LC-130 MCM --> NPX Pallet Allocation | Suggested arrival date at South Pole [INPUT] | Latest possible arrival date at South Pole [from schedule] | FLOAT AT NPX (delivery to required) [days] | Total Time Between Ship-By-Date and Latest Arrival Date at NPX [days] | Critical Path | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date2 | Notes
Cargo staged in Port Hueneme
- |  | - | - | [9 empty] | - |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
- |  | - | - | [9 empty] | - |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
- |  | - | - | [9 empty] | - |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
- |  | - | - | [9 empty] | - |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
|  |  | Pt. Hueneme totals: |  |  | TEU=> | 0 |  | 0 |  | 0
Cargo staged in McMurdo
1.2 | Drill | Gen 1 - housed in 20' container | Power generation unit 1 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 1360 | 22000 | 22000 | actual | - | U. Wisc. Madison | In McMurdo | 2020-02-06 | - | In McMurdo | - | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 2 | - | 0.5 | - | - | 2023-01-01 | 2023-12-01 | 334 | - | Yes | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 | Drill | Gen 2 - housed in 20' container | Power generation unit 2 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 1360 | 22000 | 22000 | actual | - | U. Wisc. Madison | In McMurdo | 2020-01-15 | - | In McMurdo | - | In McMurdo | FY23 inter | FY23 Vessel | USAP Vessel | - | - | - | - | - | 2023-02-06 | FY24 intra | FY24 SPOT 1 | 0.5 |  | - | - | 2023-12-01 | 2023-12-01 | 0 | - | Yes | I. McEwen | 2022-02-24 | D.Tosi | 2022-02-24 | Gens 2 Going back to CHC for repairs
1.2 | Drill | Gen 3 - housed in 20' container | Power generation unit 3 housed in 20' shipping container | 240 | 96 | 102 | 1 | 1360 | 1360 | 22000 | 22000 | actual | - | U. Wisc. Madison | In McMurdo | 2020-01-15 | - | In McMurdo | - | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 2 | - | 0.5 | - | - | 2023-01-01 | 2023-12-01 | 334 | - | Yes | D. Gibson | 2021-10-06 | I. McEwen | 2021-10-06 | Gens 2 & 3 need to be tranferred from ISO2 sleds that are limited to use on improved surfaces only. Will require crane for onload/offload - use belly band to support container sidewalls during lift.
1.2 | Drill | Gen Discharge Hoods (bermed) | Generator air discharge hoods , sheet metal, loose - stored on berm at SPOTSA | 108 | 53 | 60 | 2 | 199 | 398 | 330 | 660 | actual | - | U. Wisc. Madison | In McMurdo | 2019-12-15 | - | In McMurdo | - | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 1 | 0.25 | - | - | - | 2022-12-01 | 2023-12-12 | 376 | - | No | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Testing/limited operation of Gens can be accomplished without hoods - Hoods required for the drill season
1.2 | Drill | Firn Drill | Bermed in McM - will require McM fork or crane support. | 264 | 94 | 97 | 1 | 1394 | 1394 | 12000 | 12000 | actual | - | U. Wisc. Madison | In McMurdo | 2020-01-15 | - | In McMurdo | - | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 2 | - | 0.5 | - | - | 2023-01-01 | 2023-12-15 | 348 | - | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA
1.2 | Drill | Weight stack and crates | Bermed in McM - will require McM fork support. Drill head weight stack and remaining bermed crates at SPoTSA | 120 | 48 | 48 | 1 | 160 | 160 | 600 | 600 | actual | - | U. Wisc. Madison | In McMurdo | 2020-01-15 | - | In McMurdo | - | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 1 | 0.25 | - | - | - | 2022-12-01 | 2025-12-01 | 1096 | - | No | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack
1.2 | Drill | Fuel Tower | Bermed in McM - will require McM fork or crane support. | 96 | 72 | 120 | 1 | 480 | 480 | 1500 | 1500 | actual | - | U. Wisc. Madison | In McMurdo | 2020-01-15 | - | In McMurdo | - | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 1 | 0.25 | - | - | - | 2022-12-01 | 2023-12-05 | 369 | - | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Bermed in McMurdo - SPOTSA on UNL flatrack - overland shipment preferred due to complexities of air transport certification - can be laid on side once drained
1.2 | Drill | HPU 2 | HPU 2 (University of Nebraska - Lincoln asset) - 40' container housing heating plant on ISO sled | 480 | 96 | 102 | 1 | 2720 | 2720 | 28000 | 28000 | actual | - | U. Wisc. Madison | In McMurdo | 2020-01-15 | - | In McMurdo | - | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 3 | - | - | 1 | - | 2023-02-01 | 2024-01-17 | 350 | - | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | HPU 1 integration with Rodwell system required before drill season on it's own sled which will require evaluation and repair - Stored at SPOTSA
1.2 | Drill | 8' Refit Container | Priority refit materials including tools, flowmeter assemblies, motor drive installation kits, hardware, fittings, sensors, & consumables | 96 | 86 | 96 | 1 | 459 | 459 | 5000 | 5000 | actual | - | U. Wisc. Madison | In McMurdo | 2021-11-03 | 2021-11-16 | In McMurdo | Truck | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 1 | 0.25 | - | - | - | 2022-12-01 | 2023-11-14 | 348 | 728 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | 8' container moves with contents by LC130 or is broken down for movement by Basler. Packing in progress.
1.2 | Drill | 20' Refit Container A | Refit materials incl. submersible pumps, hardware, filtration components, fall arrest towers, tools, hose crimper and camp hose (2 spools 348 cf/4990 lbs each) | 240 | 96 | 102 | 1 | 1360 | 1360 | 17320 | 17320 | actual | - | U. Wisc. Madison | In McMurdo | 2021-11-13 | 2021-11-16 | In McMurdo | Truck | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 2 | - | 0.5 | - | - | 2023-01-01 | 2023-11-14 | 317 | 728 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized. Container procurement delayed by shortage. Packing in progress.
1.2 | Drill | 20' Refit Container B | Bulky materials incl. cable trays, vertical turbine pumps, vertical turbine pump motors, ladders, water tank doghouse/railing materials, 287 forks, generator parts, TU20 shaft, & drill weight stack | 240 | 96 | 102 | 1 | 1360 | 1360 | 14280 | 14280 | actual | - | U. Wisc. Madison | In McMurdo | 2021-11-02 | 2021-11-02 | In McMurdo | Truck | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 2 | - | 0.5 | - | - | 2023-01-01 | 2023-12-15 | 348 | 773 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | For air shipment container contents will need to be unloaded and palletized
1.2 | Drill | ARA Trailer | Enclosed trailer on skis housing 35kw generator | 192 | 96 | 88 | 1 | 939 | 939 | 5400 | 5400 | actual | FLAMMABLE liquid power engine | U. Wisc. Madison | In McMurdo | 2021-11-02 | 2021-11-02 | In McMurdo | Truck | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 1 | 0.5 | - | - | - | 2022-12-01 | 2023-12-07 | 371 | 765 | Yes* | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *If this shipment is delayed 480 volt power generation support will be required in FW YR 1 by the contractor. Aside from the CRREL generator (far larger than required with high fuel burn rate) the capacity does not currently exist at the Pole.
1.2 | Drill | Return Water Cable Reel (RWCR) | Smaller reel - can fit in 20' container. Required onsite in FY23 for final integration and pre-drill activites | 112 | 80 | 80 | 1 | 415 | 415 | 4000 | 4000 | actual | - | U. Wisc. Madison | In McMurdo | 2021-10-26 | 2021-11-02 | In McMurdo | Truck | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 2 | - | 0.25 | - | - | 2023-01-01 | 2024-01-03 | 367 | 792 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight from Gen 1 shipment information see picture.
1.2 | Drill | Main Cable Reel (MCR) | Required onsite in FY23 for final integration and pre-drill activites. Large cable reel - will require flat rack on vessel | 140 | 96 | 95 | 1 | 739 | 739 | 17800 | 17800 | actual | - | U. Wisc. Madison | In McMurdo | 2021-11-08 | 2021-11-16 | In McMurdo | Truck | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 2 | - | 0.25 | - | - | 2023-01-01 | 2024-01-03 | 367 | 778 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FS Y1 for final integration and pre-drill activities. Shrink wrap contractor rescheduled for later date.
1.2 | Drill | Container Ski Stack (comprised of 5 sleds) | Five sets of aluminum skis for 20' containers - stacked. Aluminum skis for drill containers. Required onsite for local movement of Gens and PDM. | 240 | 96 | 96 | 1 | 1280 | 1280 | 4255 | 4255 | actual | - | U. Wisc. Madison | In McMurdo | 2020-12-28 | 2021-01-15 | In McMurdo | Truck | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 1 | 0.5 | - | - | - | 2022-12-01 | 2023-01-01 | 31 | 716 | No* | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | *While this shipment is not on the critical path additional ASC crane support will be required to overcome delayed arrival or sleds furnished from the South Pole inventory
1.2 | Drill | Generator Intake Hood | Light weight large volume sheet metal stacks for generator ventilation | 174 | 53 | 96 | 3 | 513 | 1539 | 587 | 1761 | actual | - | U. Wisc. Madison | In McMurdo | 2020-10-08 | 2020-11-24 | In McMurdo | Truck | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 1 | 0.5 | - | - | - | 2022-12-01 | 2023-12-12 | 376 | 1113 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | -
1.2 | Drill | Generator Discharge Hoods | Light weight large volume sheet metal stacks for generator ventilation | 108 | 53 | 60 | 2 | 199 | 398 | 1210 | 2420 | actual | - | U. Wisc. Madison | In McMurdo | 2020-10-08 | 2020-11-24 | In McMurdo | Truck | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY23 intra | FY23 SPOT 1 | 0.5 | - | - | - | 2022-12-01 | 2023-12-12 | 376 | 1113 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | -
1.2 | Drill | Drill Hose | Drill hose - 9 Spools - 348 cf / 3532 lbs each - Shipped from Italy - Do Not Deep Freeze | 92 | 92 | 70.5 | 9 | 346 | 3114 | 3532 | 31788 | actual | DNDF [-53C] | U. Wisc. Madison | In McMurdo | 2020-07-29 | 2020-08-15 | In McMurdo | Truck | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY25 intra | FY25 SPOT 1 | 1.8 | - | - | - | 2024-12-01 | 2024-12-15 | 14 | 1583 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2022-03-10 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
1.2 | Drill | Drill Hose | Drill hose - 3 Spools - 348 cf / 5001 lbs each - Shipped from PSL - Do Not Deep Freeze | 92 | 92 | 70.5 | 3 | 346 | 1038 | 5001 | 15003 | actual | DNDF [-53C] | U. Wisc. Madison | In McMurdo | 2020-11-19 | 2021-01-15 | In McMurdo | Truck | In McMurdo | In McMurdo | in McMurdo | in McMurdo | - | - | - | - | - | In McMurdo | FY25 intra | FY25 SPOT 1 | 0.6 | - | - | - | 2024-12-01 | 2024-12-15 | 14 | 1430 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2022-03-10 | Hose to be installed on Main Supply Hose Reel upon arrival at Pole
|  |  | McMurdo totals: |  |  | TEU=> | 22.9758 |  | 21873 |  | 227787
Cargo staged at South Pole
1.2 | Drill | 287 Loader | Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use | 114 | 77 | 96 | 1 | 488 | 488 | 10273 | 10273 | actual | - | U. Wisc. Madison | At South Pole | 2019-10-15 | 2019-11-15 | At South Pole | Truck | At South Pole | at South Pole | at South Pole | at South Pole | - | - | - | - | - | at South Pole | at South Pole | at South Pole | - | - | - | - | at South Pole | 2023-12-01 | at South Pole | 1477 | No* | D. Gibson | 2021-10-07 | I. McEwen | 2021-10-07 | *Required onsite early in FY23 for refit/pre-drill activity support unless ASC can supply dedicated loader for Upgrade use
1.2 | Drill | Firn Drill Components - 1 | Firn drill sheave. Required Field Season 2 for final refit & functional testing | 97 | 44 | 63 | 1 | 156 | 156 | 920 | 920 | actual | - | U. Wisc. Madison | At South Pole | 2020-01-15 | - | At South Pole | - | At South Pole | at South Pole | at South Pole | at South Pole | - | - | - | - | - | at South Pole | at South Pole | at South Pole | - | - | - | - | at South Pole | 2024-12-01 | at South Pole | - | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | -
1.2 | Drill | Firn Drill Components - 2 | Firn drill drillhead. Required Field Season 2 for final refit & functional testing | 125 | 33 | 37 | 1 | 89 | 89 | 1048 | 1048 | actual | - | U. Wisc. Madison | At South Pole | 2020-01-15 | - | At South Pole | - | At South Pole | at South Pole | at South Pole | at South Pole | - | - | - | - | - | at South Pole | at South Pole | at South Pole | - | - | - | - | at South Pole | 2024-12-01 | at South Pole | - | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | -
|  |  | South Pole totals: |  |  | TEU=> | 0.76996 |  | 733 |  | 12241
Cargo departing UW/PSL
1.2 | Drill | ARA Drill System Components - Crate #1 | ARA (Antarctic Rodwell Appartus) - downhole pump controller, ePump controller, splash cam kit, and accessories - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 128 | 1200 | 1200 | estimated | DNF | U. Wisc. Madison | 30 | 2022-09-15 | 2022-10-15 | UWM - PTH | Truck | PTH - MCM | FY23 inter | FY23 Vessel | USAP Vessel | - | - | - | 0.5 | 0.25 | 2023-02-06 | FY24 intra | FY24 LC-130 | - | - | - | 0.25 | 2023-11-15 | 2023-12-01 | 16 | 412 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | -
1.2 | Drill | Computing/controls components Shipment #1 | Components and equipment to support field season 1 controls system tasking). Controls infrastructure - Motor drives, PLCs, electrical hardware, and motor drive mounting kits) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison | 14 | 2022-10-01 | 2022-10-15 | UWM - PTH | Truck | PTH - CHC | FY23 inter | FY23 Vessel | USAP Vessel | - | - | - | - | 0.5 | 2023-02-06 | FY24 intra | FY24 LC-130 | - | - | - | 0.5 | 2023-11-15 | 2023-11-15 | 0 | 396 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Weight estimated
1.2 | Drill | Computing/controls components Shipment #2 | Computing and controls equipment (Motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison | 31 | 2023-07-01 | 2023-08-01 | UWM - PTH | Truck | PTH - CHC | FY24 inter | FY24 ComSur | USAP Air | - | - | - | - | 0.5 | 2023-11-01 | FY24 intra | FY24 LC-130 | - | - | - | 0.5 | 2023-11-15 | 2023-11-15 | 0 | 106 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 to support controls system tasking
1.2 | Drill | Computing/controls components Shipment #3 | Computing and controls equipment (Sensor, motor drives and other sensitive electronics) - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison | 31 | 2024-07-01 | 2024-08-01 | UWM - PTH | Truck | PTH - CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 0.5 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 0.5 | 2024-11-15 | 2024-11-15 | 0 | 106 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | -
1.2 | Drill | 20' Refit Container C: Bull Wheel, Spare Combo & Drill Cables, Hose Heating System Components, ARA Drill System Components Crate #2 | Bull wheel assembly - used to install main cable on reel in event of main cable damage/failure; Spare cable for Return Water Cable Reel - on spool; ARA new downhole pumps, spares, accessories and tools | 240 | 96 | 102 | 1 | 1360 | 1360 | 21500 | 21500 | actual | - | U. Wisc. Madison | 31 | 2022-09-14 | 2022-10-15 | UWM - PTH | Truck | PTH - MCM | FY23 inter | FY23 Vessel | USAP Vessel | - | - | 1 | - | - | 2023-02-06 | FY24 intra | FY24 SPOT 1 | 0.5 | - | - | - | 2023-12-01 | 2025-01-22 | 418 | 830 | Yes | I. McEwen | 2022-02-24 | D. Tosi | 2022-02-24 | Consolidation: 20 ft container with Bull Wheel, Spare Combo & Drill Cables, Hose Heating System Components, ARA Drill System Components Crate #2
1.2 | Drill | Driller resupply/refit components - 8' Container FS2 | 8' Mini Milvan; Consumables/drill components | 96 | 86 | 96 | 1 | 459 | 459 | 6500 | 6500 | estimated | - | U. Wisc. Madison | 31 | 2024-07-01 | 2024-08-01 | UWM - PTH | Truck | PTH - CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 1 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 1 | 2024-11-15 | 2024-11-15 | 0 | 106 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season - 8' container moves with contents overland or by air
1.2 | Drill | Drill refit components FS2 | Single crate. Consumables/drill refit components - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison | 31 | 2024-07-01 | 2024-08-01 | UWM - PTH | Truck | PTH - CHC | FY25 inter | FY25 Comsur | USAP Air | - | - | - | - | 0.5 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 0.5 | 2024-11-15 | 2024-11-15 | 0 | 106 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season
1.2 | Drill | Driller resupply/refit components - 8' Container FS3 | 8' Mini Milvan; Consumables/drill components | 96 | 86 | 96 | 1 | 459 | 459 | 6500 | 6500 | estimated | - | U. Wisc. Madison | 31 | 2025-07-01 | 2025-08-01 | UWM - PTH | Truck | PTH - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 1 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 1 | 2025-11-15 | 2025-11-15 | 0 | 106 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season - 8' container moves with contents overland or by air
1.2 | Drill | Drill refit components FS3 | Single crate. Consumables/drill refit components - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 128 | 3000 | 3000 | estimated | DNF | U. Wisc. Madison | 31 | 2025-07-01 | 2025-08-01 | UWM - PTH | Truck | PTH - CHC | FY26 inter | FY26 Comsur | USAP Air | - | - | - | - | 0.5 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 0.5 | 2025-11-15 | 2025-11-15 | 0 | 106 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Items identifed in prior field season
1.2 | Drill | Drill Heads - X | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison | 409 | 2021-09-01 | 2022-10-15 | UWM - PTH | Truck | PTH - MCM | FY23 inter | FY23 Vessel | USAP Vessel | - | - | 0.25 | - | - | 2023-02-06 | FY24 intra | FY24 LC-130 | - | - | - | 0.3 | 2024-02-06 | 2025-11-15 | 648 | 1127 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | One drill head shipped one year early for ull system wet-test
1.2 | Drill | Drill Heads - Y | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison | 409 | 2021-09-01 | 2022-10-15 | UWM - PTH | Truck | PTH - MCM | FY23 inter | FY23 Vessel | USAP Vessel | - | - | 0.25 | - | - | 2023-02-06 | FY24 intra | FY24 LC-130 | - | - | - | 0.3 | 2024-02-06 | 2025-11-15 | 648 | 1127 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | -
1.2 | Drill | Drill Heads - R | Drill Heads for winterover storage - ICL - Do Not Freeze | 192 | 24 | 24 | 1 | 64 | 64 | 1060 | 1060 | actual | DNF | U. Wisc. Madison | 409 | 2021-09-01 | 2022-10-15 | UWM - PTH | Truck | PTH - MCM | FY23 inter | FY23 Vessel | USAP Vessel | - | - | 0.25 | - | - | 2023-02-06 | FY24 intra | FY24 LC-130 | - | - | - | 0.3 | 2024-02-06 | 2025-11-15 | 648 | 1127 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | -
1.2 | Drill | Load member cable reel [placeholder, may not be required] | Cable Reel used to deploy downhole load member during string installation | 84 | 60 | 48 | 1 | 140 | 140 | 3800 | 3800 | estimated | - | U. Wisc. Madison | 136 | 2023-06-01 | 2023-10-15 | UWM - PTH | Truck | PTH - MCM | FY24 inter | FY24 Vessel | USAP Vessel | - | - | - | 0.25 | - | 2024-02-06 | FY25 intra | FY25 SPOT 2 | - | 0.25 | - | - | 2025-01-01 | 2025-06-01 | 151 | 595 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2021-10-08 | Required onsite in FW YR 2 for integration - recent addition, still in development
1.2 | Logistics | Accelerometer Loggers SPoT 1 | 1x1x1 box | 12 | 12 | 12 | 1 | 1 | 1 | 5 | 5 | estimated | - | U. Wisc. Madison | 62 | 2022-07-01 | 2022-09-01 | UWM - PTH | Truck | PTH - CHC | FY23 inter | FY23 ComSur | USAP Air | - | - | - | - | 0.01 | 2022-10-18 | FY23 intra | FY23 SPOT 1 | - | - | - | 0.01 | 2022-12-01 | 2022-12-01 | 0 | 91 | Yes | I. McEwen | 2022-02-28 | D. Tosi | 2022-02-28 | -
1.2 | Logistics | Accelerometer Loggers SPoT 2 | 1x1x1 box | 12 | 12 | 12 | 1 | 1 | 1 | 5 | 5 | estimated | - | U. Wisc. Madison | 62 | 2022-07-01 | 2022-09-01 | UWM - PTH | Truck | PTH - CHC | FY23 inter | FY23 ComSur | USAP Air | - | - | - | - | 0.01 | 2022-10-18 | FY23 intra | FY23 SPOT 2 | - | - | - | 0.01 | 2023-01-01 | 2023-01-01 | 0 | 122 | Yes | I. McEwen | 2022-02-28 | D. Tosi | 2022-02-28 | -
1.4 | Installation | ICL power and timing electronics | 1 crate containing rackmount electronics for power and timing systems - Do Not Freeze | 96 | 48 | 48 | 1 | 128 | 128 | 600 | 600 | estimated | DNF | U. Wisc. Madison | 462 | 2023-04-27 | 2024-08-01 | UWM - PTH | Truck | PTH - CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 0.25 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 0.25 | 2024-11-30 | 2024-12-01 | 1 | 122 | Yes | J. Kelley | 2021-10-12 | D. Tosi | 2022-04-11 | -
1.4 | Installation | ICL patch cables and patch panels | Standard vessel shipping - can overwinter in McM if shipped earlier - Do Not Deep Freeze | 96 | 48 | 48 | 1 | 128 | 128 | 1200 | 1200 | estimated | DNDF [TBD] | U. Wisc. Madison | 624 | 2022-11-16 | 2024-08-01 | UWM - PTH | Truck | PTH - CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 0.25 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 0.25 | 2024-11-30 | 2024-12-01 | 1 | 122 | Yes | J. Kelley | 2021-10-12 | D. Tosi | 2022-04-11 | (*) storage in McMurdo pending low temperature test
1.2 | Installation | DOM Handling Facility (DHF) | Standard vessel shipping - can overwinter in McM. | 240 | 96 | 96 | 1 | 1280 | 1280 | 12000 | 12000 | estimated | - | U. Wisc. Madison | 50 | 2022-08-26 | 2022-10-15 | UWM - PTH | Truck | PTH - MCM | FY23 inter | FY23 Vessel | USAP Vessel | - | - | 1 | - | - | 2023-02-06 | FY24 intra | FY24 SPOT 1 | 0.5 | - | - | - | 2023-12-01 | 2024-12-03 | 368 | 780 | Yes | D. Gibson | 2021-10-08 | I. McEwen | 2022-04-11 | Sensor Handling Facility construction scheduled to begin mid-December FY24
1.2 | Installation | Installation Hardware 87-93 | Installation hardware | 96 | 48 | 48 | 7 | 128 | 896 | 1000 | 7000 | estimated | - | U. Wisc. Madison | 97 | 2023-07-10 | 2023-10-15 | UWM - PTH | Truck | PTH - MCM | FY24 inter | FY24 Vessel | USAP Vessel | - | - | 2 | - | - | 2024-02-06 | FY25 intra | FY25 SPOT 2 | - | 0.1 | - | - | 2025-01-01 | 2025-11-18 | 321 | 765 | Yes | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22 | -
1.2 | Installation | Installation Weights 87-93 | Installation weights | 36 | 24 | 24 | 7 | 12 | 84 | 786 | 5502 | estimated | - | U. Wisc. Madison | 110 | 2023-06-27 | 2023-10-15 | UWM - PTH | Truck | PTH - MCM | FY24 inter | FY24 Vessel | USAP Vessel | - | - | 1 | - | - | 2024-02-06 | FY25 intra | FY25 SPOT 2 | - | 0.1 | - | - | 2025-01-01 | 2025-11-18 | 321 | 765 | Yes | D. Tosi | 2021-09-22 | I. McEwen | 2021-09-22 | -
1.2 | Installation | Misc. Science Equipment - FS2 (FY25) | Scientific and test equipment (SPAT, DCM, IME, Paros et al.) - Do Not Freeze | 48 | 48 | 48 | 1 | 64 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison | 50 | 2024-06-12 | 2024-08-01 | UWM - PTH | Truck | PTH - CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 0.25 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 0.25 | 2024-11-30 | 2024-12-01 | 1 | 122 | Yes | T. Karg | 2021-10-08 | D. Tosi | 2021-10-08 | -
1.2 | Installation | Misc. Science Equipment - FS3 (FY26) | Scientific and test equipment - Do Not Freeze [science supplies for FS3] | 48 | 48 | 48 | 1 | 64 | 64 | 1500 | 1500 | estimated | DNF | U. Wisc. Madison | 25 | 2025-07-07 | 2025-08-01 | UWM - PTH | Truck | PTH - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 0.25 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 0.25 | 2025-11-15 | 2025-12-01 | 16 | 122 | Yes | D. Tosi | 2021-10-08 | D. Tosi | 2021-10-08 | -
1.5 | Installation | Calibration/Special Devices 87-88 | 3+1 PencilBeams from UW, 2+1 pDOM and 1+1 LOMs - Do Not Deep Freeze | 58 | 38 | 41 | 1 | 53 | 53 | 836 | 836 | estimated | DNDF [-40C] | U. Wisc. Madison | 2 | 2024-07-30 | 2024-08-01 | UWM - PTH | Truck | PTH - CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 0.25 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 0.25 | 2024-12-15 | 2024-12-28 | 13 | 149 | Yes | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | -
1.3 | Installation | Special Devices 87-88 | Special devices for 2 strings from UW (4+1 Radio Pulsers (all strings) 1+1 Radio Receivers, 3+1 FOM) - Do Not Deep Freeze | 63 | 40 | 42 | 1 | 62 | 62 | 677 | 677 | preliminary | DNDF [-40C] | UWM/Kansas | 2 | 2024-07-30 | 2024-08-01 | UWM - PTH | Truck | PTH - CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 0.25 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 0.25 | 2024-12-15 | 2024-12-28 | 13 | 149 | Yes | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 4+1 Radio Pulser, weight 50 kg. 1+1 Radio receiver, assume mDOM weight, 3+1 FOM (assume mDOM weight) + 2ftx2ftx4ft FOM box (50 lbs). Special Devices from UW. FTS, seismometer missing from estimate. 250 lbs crate estimate
1.3 | Installation | Special Devices 89-93 | Special devices for 5 remaining strings from UW (4+1 FOM,2+1 Radio Receivers, 11+1 LOM + seismometer*) - Do Not Deep Freeze | 81 | 56 | 51 | 1 | 134 | 134 | 1797 | 1797 | estimated | DNDF [-40C] | UWM/Kansas | 61 | 2025-06-01 | 2025-08-01 | UWM - PTH | Truck | PTH - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 1.5 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 1.5 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 21 Special Devices from USA (11+ 1 LOM, 4+1 FOM, 2+1 RR, FTS ? , seismometer), assume mDOM weight. 200 lbs wood crate. FTS not included. (*) Seismometer not yet in CMD
1.5 | Installation | Calibration/Special Devices 89-93 | 8+1 PencilBeams, 12+1 pDOMs from UW - Do Not Deep Freeze | 75 | 56.5 | 41 | 1 | 101 | 101 | 1602 | 1602 | preliminary | DNDF [-40C] | U. Wisc. Madison | 61 | 2025-06-01 | 2025-08-01 | UWM - PTH | Truck | PTH - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 0.5 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 0.5 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | D. Williams | 2021-10-13 | D. Tosi | 2021-10-05 | 8+1 PencilBeams for strings 89-93, 12+1 pDOMs, assume mDOM weight. 244 lbs crate.
1.5 | Installation | Dust logging device | Blue Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 9 | 9 | 60 | 60 | actual | DNF | U. Wisc. Madison | 61 | 2025-06-01 | 2025-08-01 | UWM - PTH | Truck | PTH - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 0.0625 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 0.0625 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | D. Williams | 2021-10-14 | D. Tosi | 2021-09-18 | Used weights from last deployment season shipment data (could be combined)
1.5 | Installation | Dust logging device | Green Logging device - sensitive equipment - Do Not Freeze | 48 | 17 | 17 | 1 | 9 | 9 | 60 | 60 | actual | DNF | U. Wisc. Madison | 61 | 2025-06-01 | 2025-08-01 | UWM - PTH | Truck | PTH - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 0.0625 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 0.0625 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | D. Williams | 2021-10-14 | D. Tosi | 2021-09-19 | Used weights from last deployment season shipment data (could be combined)
1.5 | Installation | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 24 | 24 | 1 | 9 | 9 | 120 | 120 | actual | DNF | U. Wisc. Madison | 61 | 2025-06-01 | 2025-08-01 | UWM - PTH | Truck | PTH - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 0.0625 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 0.0625 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | D. Williams | 2021-10-14 | D. Tosi | 2021-09-20 | Used weights from last deployment season shipment data (could be combined)
1.5 | Installation | Dust logging device | Electronics parts - sensitive equipment - Do Not Freeze | 26 | 23 | 20 | 1 | 7 | 7 | 60 | 60 | actual | DNF | U. Wisc. Madison | 61 | 2025-06-01 | 2025-08-01 | UWM - PTH | Truck | PTH - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 0.0625 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 0.0625 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | D. Williams | 2021-10-14 | D. Tosi | 2021-09-21 | Used weights from last deployment season shipment data (could be combined)
1.5 | Installation | Logging winch | Winch to be used for Dust Logging | 86 | 60 | 68 | 1 | 204 | 204 | 3500 | 3500 | preliminary |  | U. Wisc. Madison | 61 | 2025-06-01 | 2025-08-01 | UWM - PTH | Truck | PTH - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 0.5 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 0.5 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
1.5 | Installation | Logging winch control box | Control Box for winch for Dust Logging - sensitive equipment - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 48 | 400 | 400 | preliminary | DNF | U. Wisc. Madison | 61 | 2025-06-01 | 2025-08-01 | UWM - PTH | Truck | PTH - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 0.25 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 0.25 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | D. Tosi | 2021-10-08 | I. McEwen | 2021-10-08 | Used weights and cubes of IDP deep logging winch. Send back end of season
|  |  | U. Wisconsin totals: |  |  | TEU=> | 6.9958 |  | 6660 |  | 96104
Cargo departing MSU
1.4 | Installation | Surface Junction Boxes | Surface Junction Boxes can overwinter in McM if shipped earlier. 7 junction boxes | 66 | 30 | 14 | 7 | 17 | 119 | 200 | 1400 | preliminary | - | MSU | 2 | 2022-10-13 | 2022-10-15 | MSU - PTH | Truck | PTH - MCM | FY23 inter | FY23 Vessel | USAP Vessel | - | - | 1 | - | - | 2023-02-06 | FY24 intra | FY24 SPOT 1 | 0.5 | - | - | - | 2023-12-01 | 2024-12-15 | 380 | 792 | Yes | T. DeYoung | 2021-10-13 | D. Tosi | 2022-04-11 | Each is 66" x 30" x 14", each is 112 lbs. Assume Folding crate. Simple passive objects, work plan can probably be shifted to increase float.
1.4 | Installation | Surface Cable Assemblies | Palletized wooden cable drums (Qty: 7). Can overwinter in MCM. Do Not Deep Freeze | 48 | 65 | 71 | 7 | 129 | 903 | 1336 | 9352 | actual | DNDF [-55C] | MSU | 106 | 2022-07-01 | 2022-10-15 | MSU - PTH | Truck | PTH - MCM | FY23 inter | FY23 Vessel | USAP Vessel | - | - | 2 | - | - | 2023-02-06 | FY25 intra | FY25 SPOT 1 | 0.5 | - | - | - | 2024-12-01 | 2024-12-15 | 14 | 792 | Yes | T. DeYoung | 2021-10-13 | D. Tosi | 2022-04-11 | Shipping date early due to storage limitations at MSU. Additional float at Port Hueneme assuming USAP vessel departure.
1.4 | Installation | Breakout cables for strings 87-88 | Standard vessel shipping. 2 wooden crates containing spooled breakout cable assemblies - 96 cf / 1,000 lbs each - Cryo storage - Do Not Deep Freeze | 72 | 48 | 48 | 2 | 96 | 192 | 1000 | 2000 | estimated | DNDF[-40C](*) | MSU | 477 | 2023-06-26 | 2024-10-15 | MSU - PTH | Truck | PTH - MCM | FY25 inter | FY25 Vessel | USAP Vessel | - | 0.25 | - | - | - | 2025-02-06 | FY25 intra | FY25 LC-130 | - | - | - | 0.5 | 2025-02-15 | 2025-12-10 | 298 | 421 | Yes | T. DeYoung | 2021-09-20 | D. Tosi | 2022-04-11 | Shipping date early due to storage limitations at MSU. Additional float at Port Hueneme assuming USAP vessel departure. Preliminary estimate of weight and size. Pre-staging string 87-88 equipment in cryo or ICL. - if storage at Pole not possible, could overwinter in McM (at an increased risk and pending low temperature test) (*)
1.4 | Installation | Breakout cables for strings 89-93 | Stored in McMurdo FY24. 5 wooden crates containing spooled breakout cable assemblies - 96 cf/ 1,000 lbs each (preliminary) - Do Not Deep Freeze | 72 | 48 | 48 | 5 | 96 | 480 | 1000 | 5000 | estimated | DNDF[-40C](*) | MSU | 379 | 2023-10-02 | 2024-10-15 | MSU - PTH | Truck | PTH - MCM | FY25 inter | FY25 Vessel | USAP Vessel | - | - | 2 | - | - | 2025-02-06 | FY26 intra | FY26 LC-130 | - | - | - | 1 | 2025-11-25 | 2025-12-10 | 15 | 421 | Yes | T. DeYoung | 2021-09-20 | D. Tosi | 2022-04-11 | Float in PTH due to storage limitation in MSU. (*) storage in McMurdo pending low temperature test
1.4 | Installation | Main (downhole) load members 87-93 [placeholder, may not be required] | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 47 | 47 | 39 | 7 | 50 | 350 | 766 | 5362 | preliminary | DNDF[-40C](*) | MSU | 563 | 2023-04-01 | 2024-10-15 | MSU - PTH | Truck | PTH - MCM | FY25 inter | FY25 Vessel | USAP Vessel | - | - | 1 | - | - | 2025-02-06 | FY26 intra | FY26 SPOT 1 | 1 | - | - | - | 2025-12-01 | 2025-12-02 | 1 | 413 | Yes | T. DeYoung | 2021-09-20 | D. Tosi | 2021-10-11 | Shipping date synched with main (downhole) cables due to storage limitation in MSU. Float in PTH.
1.4 | Installation | Main (downhole) cables 87-93 | May be possible to store in McMurdo until drill season - Do Not Deep Freeze | 96 | 96 | 96 | 7 | 512 | 3584 | 15000 | 105000 | preliminary | DNDF[-40C](*) | MSU | 31 | 2023-09-14 | 2023-10-15 | MSU - PTH | Truck | PTH - MCM | FY24 inter | FY24 Vessel | USAP Vessel | - | - | 2 | - | - | 2025-02-06 | FY26 intra | FY26 SPOT 1 | 1.5 | - | - | - | 2025-12-01 | 2025-12-02 | 1 | 779 | Yes | T. DeYoung | 2021-09-20 | D. Tosi | 2022-04-11 | Shipping date chosen to be 2 weeks after scheduled ready to ship date because of storage limitations at MSU. additional 7 months of float at Port Hueneme assuming USAP vessel departure. (*) storage in McMurdo pending low temperature test.
1.3 | Installation | String Sensors 89-93 (mDOMs MSU) | Optical Sensors for 5 strings from MSU (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 25 | 52 | 1300 | 573 | 14325 | actual(**) | DNDF [-40C] | MSU | 686 | 2023-09-15 | 2025-08-01 | MSU - PTH | Truck | PTH - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 3 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 3 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | T. Karg | 2021-09-20 | D. Tosi | 2022-04-11 | mDOM weight is 28 kg/boxed + 35kg pallet, assume 8 mDOMs/pallet (189 to be deployed + 11 spares)(*)Assumed to be shipped in 2x20' HC (5115 lbs, 238inx96inx114in) or a 40 ft HC, purchased by MSU or loaned in PTH (container weight not included)
1.3 | Installation | String Sensors 89-93 (mDOMs MSU) | Optical Sensors for 5 strings from MSU (mDOMs) containers (TBD) - Do Not Deep Freeze | 238 | 96 | 114 | 0 | 1508 | 0 | 5115 | 0 | actual(**) | DNDF [-40C] | MSU | 686 | 2023-09-15 | 2025-08-01 | MSU - PTH | Truck | PTH - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 0.0625 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 0.0625 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | T. Karg | 2021-09-20 | D. Tosi | 2022-04-11 | Assume 2x20HC containers for transport on COMSUR (TBC). Pallets could be loaded to 53 ft truck and loaded into a loaned container in PTH but this would increase touch points (and risk)
|  |  | MSU Totals: |  |  | TEU=> | 7.2773 |  | 6928 |  | 142439
Cargo departing other institutions in US
1.3 | Installation | DM-Ice | DM-ice (two modules for string 89 and 90) - Do Not Deep Freeze | 48 | 48 | 48 | 1 | 64 | 64 | 1500 | 1500 | estimated | DNDF [-40C] | Yale | 426 | 2024-06-01 | 2025-08-01 | Yale - PTH | Truck | PTH - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 0.25 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 0.25 | 2025-11-15 | 2025-12-05 | 20 | 126 | Yes | M. Kauer | 2021-09-20 | D. Tosi | 2021-09-20 | -
|  |  | Other Institutions Totals: |  |  |  | 0.067227 |  | 64 |  | 1500
Cargo departing Germany (Europe)
1.3 | Installation | String Sensors 87-88 (mDOMs DESY) | Optical sensors for 2 strings from Germany (mDOMs) (spares included) - Do Not Deep Freeze | 40 | 48 | 46 | 16 | 52 | 832 | 573 | 9168 | actual | DNDF [-40C] | DESY | 440 | 2023-05-19 | 2024-08-01 | DESY - CHC | ComSur | DESY-CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 2 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 2 | 2024-12-15 | 2024-12-28 | 13 | 149 | Yes | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - 116 to be deployed + 12 spares - shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 | Installation | String Sensors 87-88 (mDOMs DESY) | Optical sensors for 2 strings from Germany (mDOMs) (SPARES) - Do Not Deep Freeze | 40 | 48 | 46 | 0 | 52 | 0 | 573 | 0 | actual | DNDF [-40C] | DESY | 440 | 2023-05-19 | 2024-08-01 | DESY - CHC | ComSur | DESY-CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 0.25 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 0.25 | 2024-12-15 | 2024-12-28 | 13 | 149 | Yes | T. Karg | 2021-09-20 | D. Tosi | 2021-09-22 | mDOM weight is 62 lbs (25kg/sensor + 3 kg/box) + 35kg pallet, assume 8 mDOMs/pallet - shipped in 20 HC container. Container weight not included in the assumption that pallet will be taken out in CHC.
1.3 | Installation | Special Devices 87-88 (Europe) | Special devices for 2 strings from DESY/Germany/Sweden (8 WOMs, 0 Abalone) + spares - Do Not Deep Freeze | 40 | 21 | 64 | 1 | 32 | 32 | 701 | 701 | estimated | DNDF [-40C] | Mainz | 578 | 2023-01-01 | 2024-08-01 | DESY - CHC | ComSur | DESY-CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 0.25 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 0.25 | 2024-12-15 | 2024-12-28 | 13 | 149 | Yes | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 8 WOMs (no spares) - AH not included for now. Assume 150 lbs crate.
1.5 | Installation | Calibration Devices 87-88 (Europe) | Calibration devices for 2 strings from DESY/Germany/Sweden (4+2 POCAMs, 3+1 Acoustic sensors, 2+1 Swedish Cameras) - Do Not Deep Freeze | 62 | 38 | 41 | 1 | 56 | 56 | 836 | 836 | estimated | DNDF [-40C] | TUM/Aachen/Sweden | 792 | 2022-06-01 | 2024-08-01 | DESY - CHC | ComSur | DESY-CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 0.25 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 0.25 | 2024-12-15 | 2024-12-28 | 13 | 149 | Yes | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 87-88 = 2+1 Sweden Camera + 3+1 Acoustic Module + 4+1 POCAM, including spares, 200 lbs crate
1.4 | Installation | FieldHub electronics | Required onsite for FY24 installation. 1 crate containing readout electronics for installation in ICL - Do Not Freeze | 48 | 48 | 36 | 1 | 48 | 48 | 275 | 275 | preliminary | DNF | DESY | 304 | 2023-10-16 | 2024-08-15 | DESY - CHC | ComSur | DESY-CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 0.25 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 0.25 | 2024-11-30 | 2024-12-01 | 1 | 108 | No | J. Kelley | 2021-10-13 | D. Tosi | 2022-04-11 | Field Hubs are 442mm x 480mm x 133 mm (17.4" x 18.9" x 5.2") and weight maybe 10 lb each. 100 lbs crate. Ready to ship date actually chosen to be 2 weeks ahead of ship date to maximize time with the electronics (sort of backloaded)
1.3 | Installation | String Sensors 89-93 (mDOMs DESY) | Optical sensors for 5 strings from Germany (mDOMs) - Do Not Deep Freeze | 40 | 48 | 46 | 12 | 52 | 624 | 573 | 6876 | actual(**) | DNDF [-40C] | DESY | 721 | 2023-08-11 | 2025-08-01 | DESY - CHC | ComSur | DESY-CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 3 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 3 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | T. Karg | 2021-09-20 | D. Tosi | 2022-04-11 | mDOM weight is (28kg/sensor boxed) + 35kg pallet, assume 8 mDOMs/pallet - 190 to be deployed + 10 spares. (**) shipped in 20 HC container. Container not included in weight as pallets will be taken out.
1.3 | Installation | Special Devices 89-93 (Europe) | Special devices for 5 remaining strings from DESY/Germany/Sweden (6 WOMs, 3 Abalone Hubs or WOM Traps) no spares - Do Not Deep Freeze | 32 | 31 | 89 | 1 | 52 | 52 | 1035 | 1035 | preliminary | DNDF [-40C] | Mainz | 578 | 2024-01-01 | 2025-08-01 | DESY - CHC | ComSur | DESY-CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 0.25 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 0.25 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | S. Boeser | 2021-10-13 | D. Tosi | 2021-10-13 | 6 Special Devices from Germany 6 (WOM + 0 AH) including 0 spare for each. Assume 170 lbs crate.
1.5 | Installation | Calibration Devices 89-93 (Europe) | Calibration for 5 strings from DESY/Germany/Sweden (17+2 POCAMs, 7+ 1 Acoustic sensors, 3+ 1 Swedish Cameras) including spares - Do Not Deep Freeze | 62 | 48 | 44 | 1 | 76 | 76 | 1694 | 1694 | preliminary | DNDF [-40C] | TUM/Aachen/Sweden | 1157 | 2022-06-01 | 2025-08-01 | DESY - CHC | ComSur | DESY-CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 0.25 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 0.25 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | D. Williams | 2021-10-13 | D. Tosi | 2021-10-13 | Calibration devices for strings 89-93 = 3+1 Sweden Camera,7+1 + Acoustic Module,17 +1 POCAM, including spares, 200 lbs crate
|  |  | DESY/Aachen/TUM/Sweden etc Totals: |  |  | TEU=> | 1.8067 |  | 1720 |  | 20585
Cargo departing Chiba (Japan)
1.3 | Installation | String Sensors 87 & 88 (D-Eggs-8x) | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 41 | 41 | 69 | 4 | 68 | 272 | 750 | 3000 | actual | DNDF [-40C] | Chiba | 736 | 2022-07-27 | 2024-08-01 | ChibaU - CHC | Cargo shipment by CHU | ChibaU - CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 1 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 1 | 2024-12-15 | 2024-12-28 | 13 | 149 | Yes | S. Yoshida | 2021-09-22 | D. Tosi | 2022-04-11 | Box size is 480x480x770mm (19"x19"x30.5"). 2x12-DEgg pallets combined with 2x8-DEgg pallets to form one 463L pallet
1.3 | Installation | String Sensors 87 & 88 (D-Eggs-8x) | Sensors (D-Eggs) pallets with 8 sensors at Pole overwinter (SPARES - TBD) - Cryo location - Do Not Deep Freeze | 41 | 41 | 69 | 1 | 68 | 68 | 750 | 750 | actual | DNDF [-40C] | Chiba | 736 | 2022-07-27 | 2024-08-01 | ChibaU - CHC | Cargo shipment by CHU | ChibaU - CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 0.25 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 0.25 | 2024-12-15 | 2024-12-28 | 13 | 149 | Yes | S. Yoshida | 2021-09-22 | D. Tosi | 2022-04-11 | SPARES number to be confirmed.
1.3 | Installation | String Sensors 87 & 88 (D-Eggs-12x) | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter - Cryo location - Do Not Deep Freeze | 60 | 41 | 69 | 4 | 99 | 396 | 1102 | 4408 | actual | DNDF [-40C] | Chiba | 736 | 2022-07-27 | 2024-08-01 | ChibaU - CHC | Cargo shipment by CHU | ChibaU - CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 1 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 1 | 2024-12-15 | 2024-12-28 | 13 | 149 | Yes | S. Yoshida | 2021-09-22 | D. Tosi | 2022-04-11 | 2x12-DEgg pallets combined with 2x8-DEgg pallets to form one 463L pallet
1.3 | Installation | String Sensors 87 & 88 (D-Eggs-12x) | Sensors (D-Eggs) pallets with 12 sensors at Pole overwinter (SPARES - TBD)- Cryo location - Do Not Deep Freeze | 60 | 41 | 69 | 1 | 99 | 99 | 1102 | 1102 | actual | DNDF [-40C] | Chiba | 736 | 2022-07-27 | 2024-08-01 | ChibaU - CHC | Cargo shipment by CHU | ChibaU - CHC | FY25 inter | FY25 ComSur | USAP Air | - | - | - | - | 0.25 | 2024-11-01 | FY25 intra | FY25 LC-130 | - | - | - | 0.25 | 2024-12-15 | 2024-12-28 | 13 | 149 | Yes | S. Yoshida | 2021-09-22 | D. Tosi | 2022-04-11 | SPARES number to be confirmed.
1.3 | Installation | String Sensors 89-93 (D-Eggs-8x) | Sensors (D-Eggs) pallets with 8 sensors - Do Not Deep Freeze | 41 | 41 | 69 | 10 | 68 | 680 | 750 | 7500 | actual | DNDF [-40C] | Chiba | 812 | 2023-05-12 | 2025-08-01 | ChibaU - CHC | Cargo shipment by CHU | ChibaU - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 2.5 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 2.5 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | S. Yoshida | 2021-09-22 | D. Tosi | 2022-04-11 | 2x12-DEgg pallets combined with 2x8-DEgg pallets to form one 463L pallet
1.3 | Installation | String Sensors 89-93 (D-Eggs-12x) | Sensors (D-Eggs) pallets with 12 sensors - Do Not Deep Freeze | 60 | 41 | 69 | 10 | 99 | 990 | 1102 | 11020 | actual | DNDF [-40C] | Chiba | 812 | 2023-05-12 | 2025-08-01 | ChibaU - CHC | Cargo shipment by CHU | ChibaU - CHC | FY26 inter | FY26 ComSur | USAP Air | - | - | - | - | 2.5 | 2025-11-01 | FY26 intra | FY26 LC-130 | - | - | - | 2.5 | 2025-11-25 | 2025-12-10 | 15 | 131 | Yes | S. Yoshida | 2021-09-22 | D. Tosi | 2022-04-11 | 2x12-DEgg pallets combined with 2x8-DEgg pallets to form one 463L pallet
|  |  | Chiba Totals: |  |  | TEU=> | 2.6313 |  | 2505 |  | 27780
Fuel
1.2 | Fuel | Field Season 0 Fuel | Fuel to support following field seasons |  |  |  | 0 |  | 0 | 6.8 | 0 | preliminary | - | - | - | - | - | - | - | - | FY23 inter | - | - | - | - | - | - |  | 2022-11-01 | FY23 intra | FY23 LC-Tanker | - | - | - |  | 2022-12-01 | 2023-12-01 | 365 | - | Yes | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14 | -
1.2 | Fuel | Field Season 1 Fuel | Fuel to support FY23 field season - Base fuel |  |  |  | 3191 |  | 426.58 | 6.8 | 21698.8 | preliminary | - | - | - | - | - | - | - | - | FY24 inter | - | - | - | - | - | - |  | 2023-11-01 | FY24 intra | FY24 LC-Tanker | - | - | - |  | 2023-12-01 | 2023-12-01 | 0 | - | Yes | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14 | -
1.2 | Fuel | Field Season 1 Fuel Contingency | Fuel to support FY23 field season - Contingency |  |  |  | 452 |  | 60.43 | 6.8 | 3073.6 | preliminary | - | - | - | - | - | - | - | - | FY24 inter | - | - | - | - | - | - |  | 2023-11-01 | FY24 intra | FY24 LC-Tanker | - | - | - |  | 2023-12-01 | 2023-12-01 | 0 | - | Yes | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14 | -
1.2 | Fuel | Field Season 2 Fuel | Fuel to support FY24 field season - Base fuel, firn drilling & over winter heating |  |  |  | 18178 |  | 2430.05 | 6.8 | 123610.4 | preliminary | - | - | - | - | - | - | - | - | FY25 inter | - | - | - | - | - | - |  | 2024-11-01 | FY25 intra | FY25 LC-Tanker | - | - | - |  | 2024-12-01 | 2024-12-01 | 0 | - | Yes | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14 | -
1.2 | Fuel | Field Season 2 Fuel Contingency | Fuel to support FY24 field season - Contingency |  |  |  | 2373 |  | 317.23 | 6.8 | 16136.4 | preliminary | - | - | - | - | - | - | - | - | FY25 inter | - | - | - | - | - | - |  | 2024-11-01 | FY25 intra | FY25 LC-Tanker | - | - | - |  | 2024-12-01 | 2024-12-01 | 0 | - | Yes | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14 | -
1.2 | Fuel | Field Season 3 Fuel | Fuel to support FY25 field season - Base fuel & deep drilling |  |  |  | 62694 |  | 8380.97 | 6.8 | 426319.2 | preliminary | - | - | - | - | - | - | - | - | FY26 inter | - | - | - | - | - | - |  | 2025-11-01 | FY26 intra | FY26 LC-Tanker | - | - | - |  | 2025-12-01 | 2025-12-01 | 0 | - | Yes | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14 | -
1.2 | Fuel | Field Season 3 Fuel Contingency | Fuel to support FY25 field season - Contingency |  |  |  | 8473 |  | 1132.68 | 6.8 | 57616.4 | preliminary | - | - | - | - | - | - | - | - | FY26 inter | - | - | - | - | - | - |  | 2025-11-01 | FY26 intra | FY26 LC-Tanker | - | - | - |  | 2025-12-01 | 2025-12-01 | 0 | - | Yes | T. Benson | 2021-10-14 | I. McEwen | 2021-10-14 | -
|  |  | Fuel Totals: |  |  | gallons | 95361 |  | 12747.94 |  | 648454.8
|  |  | All IC/Upgrade cargo volume (with fuel): |  |  | TEU | 55.9149 |  | 53230.94 |  | 1176890.8
|  |  | All IC/Upgrade cargo volume (without fuel): |  |  |  | 42.5242 |  | 40483 |  | 528436
Legend:
|  | Cargo Item | Item to be procured or fabricated
|  | Description | Brief description of item | 2022-11-20 | cargo ready before | [5 empty] | 304660 | 323180
|  | Owner/Guardian | UWIsc/ICNO-U Project Team member responsible for completion |  | cargo not ready before | [5 empty] | 247575
|  | Completion Date | Date in PMB for completion (mm/dd/yy) |  | sumcheck | [5 empty] | 552235
|  | Shipment Date | Date in PMB for shipment (mm/dd/yy) | [7 empty] | 528436
|  | Weight | Pounds (lbs)
|  | Dimensions | L x W x H (inches) or cubic feet
|  | General Assumption | All cargo is destined for South Pole
|  | Routing Options | Port Hueneme>>Christchurch>>McMurdo
|  | Transportation Options | USAP Vessel, Commercial ship or air carrier (COMSUR or COMAIR), C-17 (CHC-MCM), LC-130 or SPoT (MCM-SPA)
|  | Month for Items expected at South Pole | Needed on-site date (Nov, Dec, or Jan)
|  | Work Package | Grouping by WPs could be done after the "cargo pipeline" is set by the item's "origin"
|  | Basis of Estimate | Estimate (expert guess), Preliminary (based on design), Actual (as built)
|  | FS1 | Field season to finishing EHWD refurbishment
|  | FS2 | Pre-drilling season: staging Drill Camp, firn holes shallow drilling
|  | FS3 | The season of drilling deep ice holes & deploying DOMs
|  | DNF | Do Not Freeze
|  | DNDF | Do Not Deep Freeze [min Temperature for storage] - for storage temp > -53C
CROSS CHECKS |  | cubic feet | lbs | Cells will be green if all the cargo is taken into account |  | Delta
In McMurdo |  | 20513 | 205787
At South Pole |  | 733 | 12241
inter-continental to go |  | 31984.94 | 958862.8
intra-continental to go |  | 52497.94 | 1164649.8
TOTAL PROJECT CARGO |  | cubic feet | lbs | Cells will be green if all the cargo is taken into account
inter-continental |  | 53230.94 | 1176890.8
intra-continental |  | 53230.94 | 1176890.8
start | end | McMurdo label | Pole label
2021-10-01 | 2022-09-30 | FY22 inter | FY22 intra
2022-10-01 | 2023-09-30 | FY23 inter | FY23 intra
2023-11-01 | 2024-09-30 | FY24 inter | FY24 intra
2024-11-01 | 2025-09-30 | FY25 inter | FY25 intra
2025-11-01 | 2026-09-30 | FY26 inter | FY26 intra
SPOT DATES | USE THESE DATES ONLY FOR SPOT!
FY23 SPOT 1 | 2022-12-01
FY23 SPOT 2 | 2023-01-01
FY23 SPOT 3 | 2023-02-01
FY24 SPOT 1 | 2023-12-01
FY24 SPOT 2 | 2024-01-01
FY24 SPOT 3 | 2024-02-01
FY25 SPOT 1 | 2024-12-01
FY25 SPOT 2 | 2025-01-01
FY25 SPOT 3 | 2025-02-01
FY26 SPOT 1 | 2025-12-01
FY26 SPOT 2 | 2026-01-01
FY26 SPoT 3 | 2026-02-01
Note on G7: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G28: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G33: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G67: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G77: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G90: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G98: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet
Note on G108: TEO - 2--ft Equvalent Unit Exterior Dimensions (in feet): 20' long x 8' wide x 8' 6” high =1,360 cubic feet In this list, a cargo itme' cube takes about 70% of 1,360 cubin feet

## Floats
Item description | Special Handling? | SHIPMENT FLOAT: Time between completion and ship-by-date to USAP site | FLOAT AT NPX (delivery to required) [days] | Total Time Between Ship-By-Date and Latest Arrival Date at NPX [days]
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME?

## Summary tables
| Point of Departure (Point of Origin) | volume [cu ft] | fraction of volume | weight [lbs] | fraction of weight |  |  | volume [cu ft] | fraction of volume | weight [lbs] | fraction of weight
cables (SCAs, MCAs, BCAs, SJBs) | MSU (MSU) | 5628 | 13.9% | 128114 | 24.24% |  | cables (SCAs, MCAs, BCAs, SJBs) | 5628 | 13.9% | 128114 | 24.24%
D-Eggs | CHIBA (CHIBA) | 2505 | 6.188% | 27780 | 5.257% |  | mDOMs + D-Eggs | 5261 | 13% | 58149 | 11%
mDOMs | DESY (DESY) / MSU (MSU) | 2756 | 6.808% | 30369 | 5.747% |  | calibration + special + logging devices | 916 | 2.263% | 14878 | 2.815%
calibration & special devices | UW (various)/ DESY (various) | 566 | 1.398% | 9178 | 1.737% |  | DOM Handling Facility | 1280 | 3.162% | 12000 | 2.271%
dm-ice | YALE (YALE) | 64 | 0.1581% | 1500 | 0.2839% |  | hardware (rigging and weights) | 980 | 2.421% | 12502 | 2.366%
dust logger | UW (UW) | 286 | 0.7065% | 4200 | 0.7948% |  | ICL + science | 432 | 1.067% | 5075 | 0.9604%
DOM Handling Facility | UW (UW) | 1280 | 3.162% | 12000 | 2.271% |  | Installation equipment | 14497 | 35.81% | 230718 | 43.66%
hardware (rigging and weights) | UW (UW) | 980 | 2.421% | 12502 | 2.366% |  | Drill equipment | 25984 | 64.18% | 297708 | 56.34%
misc science | UW (UW) | 128 | 0.3162% | 3000 | 0.5677% |  | Logistics equipment total | 2 | 0.00494% | 10 | 0.001892%
ICL equipment | UW (UW) | 304 | 0.7509% | 2075 | 0.3927% |  | Total | 40483 | 100% | 528436 | 100%
installation equipment total | SEE ABOVE | 14497 | 35.81% | 230718 | 43.66% |  | fuel | 12747.94 |  | 648454.8
Drill equipment total | UW (UW) | 25984 | 64.18% | 297708 | 56.34% |  | total plus fuel | 53230.94 |  | 1176890.8
Logistics equipment total | UW (UW) | 2 | 0.00494% | 10 | 0.001892% | Delta?
total |  | 40483 | 100% | 528436 | 100% | 0
fuel |  | 12747.94 | - | 648454.8 | - | 0
total plus fuel |  | 53230.94 |  | 1176890.8
| Point of Departure (Point of Origin) | volume [cu ft] | fraction of volume | weight [lbs] | fraction of weight
Each String | various | 1785.5714 | 4.411% | 29920.4286 | 5.662%
| volume [cu ft] | fraction of volume | weight [lbs] | fraction of weight |  |  |  | volume [cu ft] | fraction of volume | weight [lbs] | fraction of weight
Firn Drill | 1639 | 4.049% | 13968 | 2.643% |  |  | Firn Drill | 1639 | 4.049% | 13968 | 2.643%
Rodwell Drill and System | 1067 | 2.636% | 6600 | 1.249% |  |  | Rodwell Drill and System | 1067 | 2.636% | 6600 | 1.249%
Generators, HPU, fuel tower | 9615 | 23.75% | 100341 | 18.99% |  |  | Generators, HPU, fuel tower | 9615 | 23.75% | 100341 | 18.99%
Drill Hose | 4152 | 10.26% | 46791 | 8.855% |  |  | Hose, drill heads and weight stack | 4504 | 11.13% | 50571 | 9.57%
Reels | 1294 | 3.196% | 25600 | 4.844% |  |  | Reels | 1294 | 3.196% | 25600 | 4.844%
Drill Heads and weight stack | 352 | 0.8695% | 3780 | 0.7153% |  |  | Refit, spare cable, support equip. | 7865 | 19.43% | 100628 | 19.04%
Refit Components | 7377 | 18.22% | 90355 | 17.1% |  |  | Drill Equipment | 25984 | 64.18% | 297708 | 56.34%
Support Equipment | 488 | 1.205% | 10273 | 1.944% |  |  | Installation Equipment | 14497 | 35.81% | 230718 | 43.66%
Drill equipment | 25984 | 64.18% | 297708 | 56.34% |  |  | Logistics Equipment | 2 | 0.00494% | 10 | 0.001892%
Installation Equipment | 14497 | 35.81% | 230718 | 43.66% |  |  | Total | 40483 | 100% | 528436 | 100%
Logistics Equipment | 2 | 0.00494% | 10 | 0.001892%
Total | 40483 | 100% | 528436 | 100%
| volume [cu ft] | fraction of volume | weight [lbs] | fraction of weight
Sensors | 6177 | 15.26% | 73027 | 13.82%
Cables & hardware | 6608 | 16.32% | 140616 | 26.61%
DHF | 1280 | 3.162% | 12000 | 2.271%
ICL equipment | 432 | 1.067% | 5075 | 0.9604%
Firn Drill & ARA drill | 2706 | 6.684% | 20568 | 3.892%
Generators, HPU, fuel tower | 9615 | 23.75% | 100341 | 18.99%
Hose, drill heads, weight stack, reels | 5798 | 14.32% | 76171 | 14.41%
Refit components, spare cable, support equipment | 7865 | 19.43% | 100628 | 19.04%
Total | 40481 | 100% | 528426 | 100%
By Point Departure | Weight [lbs] |  |  | Volume [cuft] | Weight [lbs]
#NAME? | #NAME? |  | Point of Origin same as Point of Departure | 40205 | 523493
#NAME? | #NAME? |  | Point of Origin different from Point of Departure | 278 | 4943
#NAME? | #NAME? |  |  | 40483 | 528436
#NAME? | #NAME?
#NAME? | #NAME?
#NAME? | #NAME?
#NAME? | #NAME?
#NAME?
Total | 528436
Cargo (total) by BoE | Volume [cuft] | Weight [lbs]
#NAME? | 28432 | 311308
#NAME? | 1924 | 21201
#NAME? | 5483 | 74982
#NAME? | 4644 | 120945
| 40483 | 528436
Cargo (total) by BoE | Volume [cuft] | Weight [lbs]
actual | 30356 | 332509
estimated | 5483 | 74982
preliminary | 4644 | 120945
total | 40483 | 528436
Installation cargo by BoE | Volume [cuft] | Weight [lbs]
#NAME? | 4274 | 46600
#NAME? | 1924 | 21201
#NAME? | 3655 | 41972
#NAME? | 4644 | 120945
| 14497 | 230718
Installation cargo by BoE | Volume [cuft] | Weight [lbs]
actual | 6198 | 67801
estimated | 3655 | 41972
preliminary | 4644 | 120945
total | 14497 | 230718
Drill cargo by BoE | Volume [cuft] | Weight [lbs]
#NAME? | 24158 | 264708
#NAME? | 0 | 0
#NAME? | 1826 | 33000
#NAME? | 0 | 0
| 25984 | 297708
Drill cargo by BoE | Volume [cuft] | Weight [lbs]
actual | 24158 | 264708
estimated | 1826 | 33000
preliminary | 0 | 0
total | 25984 | 297708

## Southbound by Season
Cargo Item respective WBS Level | Work Package | Item Description | Contents & Comments | Length (in) | Width (in) | Height (in) | Quantity | Unit Volume (cu ft) | Total Volume (cu ft) = quantity x unit volume | Unit Weight (lbs) | Total Weight (lbs) = quantity x unit weight | Basis of Estimate | Special Handling? | Owner/Guardian institution | SHIPMENT FLOAT: Time between completion and shipping to USAP site | Date of expected or actual completion | Date of expected or actual shipment | Expected Route: Owner - PTH or CHC | Recommended Transportation Option | Expected Route: PTH - MCM or CHC | Recommended Intercontinental Shipping Date (FY) | Recommended Transportation Option to CHC/MCM [INPUT] | Expected Route: CHC - MCM [CALCULATED] | Vessel Container Allocation 40F | Vessel Container Allocation 40D | Vessel Container Allocation 20D | Vessel Container Allocation 20F | C-17/LC-130 CHC --> MCM Pallet Allocation | Date Item expected or arrived to MCM | Recommended Intracontinental Date (FY) | Recommended Intracontinental Mode MCM--> NPX [CALCULATED] | SPOT Sled Allocation - Swing 1 (11/27) | SPOT Sled Allocation - Swing 2 (12/25) | SPOT Sled Allocation - Swing 3 (2/5) | LC-130 MCM --> NPX Pallet Allocation | Suggested arrival date at South Pole [INPUT] | Latest possible arrival date at South Pole [from schedule] | FLOAT AT NPX (delivery to required) [days] | Total Time Between Shipment and Latest Arrival Date at NPX | Critical Path | Validator 1 (SME) | Validation Date | Validator 2 (Logistics) | Validation Date | Notes
at South Pole
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
[9 empty] | 733 |  | 12241
[9 empty] | Total cu ft |  | Total lbs
in McMurdo
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
[9 empty] | 20513 |  | 205787 | [19 empty] | 9.4 | 5.4 | 3 | 1 | 0
[9 empty] | Total cu ft |  | Total lbs | [19 empty] | Sled count | SPOT 1 | SPOT 2 | SPOT 3 | 463L count
FY23 inter
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
[9 empty] | 5472 |  | 73642 | [11 empty] | 6.25 | 0 | 0 | 5.75 | 0.5 | #NAME?
[9 empty] | Total cu ft |  | Total lbs | [11 empty] | TEU count | 40F | 40D | 20D | 20F | 463L count
FY23 intra
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
[9 empty] | 16363 |  | 159006 | [19 empty] | 7 | 3 | #NAME? | 1 | 0.02
[9 empty] | Total cu ft |  | Total lbs | [19 empty] | Sled count | SPOT 1 | SPOT 2 | SPOT 3 | 463L count
FY24 inter
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
[9 empty] | 5319.01 |  | 149074.4 | [11 empty] | 5.25 | 0 | 0 | 5 | 0.25 | 0.5
[9 empty] | Total cu ft |  | Total lbs | [11 empty] | TEU count | 40F | 40D | 20D | 20F | 463L count
FY24 intra
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
[9 empty] | 5182.01 |  | 92052.4 | [19 empty] | 2 | 2 | #NAME? | #NAME? | #NAME?
[9 empty] | Total cu ft |  | Total lbs | [19 empty] | Sled count | SPOT 1 | SPOT 2 | SPOT 3 | 463L count
FY25 inter
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
[9 empty] | 6722.28 |  | 189661.8 | [11 empty] | 3.5 | 0 | #NAME? | #NAME? | #NAME? | #NAME?
[9 empty] | Total cu ft |  | Total lbs | [11 empty] | TEU count | 40F | 40D | 20D | 20F | 463L count
FY25 intra
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
[9 empty] | 12067.28 |  | 251744.8 | [19 empty] | 3.35 | 2.9 | #NAME? | #NAME? | 9.25
[9 empty] | Total cu ft |  | Total lbs | [19 empty] | Sled count | SPOT 1 | SPOT 2 | SPOT 3 | 463L count
FY26 inter
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
[9 empty] | 14471.65 |  | 546484.6 | [11 empty] | 0 | 0 | #NAME? | #NAME? | #NAME? | 16.5625
[9 empty] | Total cu ft |  | Total lbs | [11 empty] | TEU count | 40F | 40D | 20D | 20F | 463L count
FY26 intra | [7 empty] | 3801 |  | 47713.8
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
[9 empty] | 18885.65 |  | 661846.6 | [19 empty] | 2.5 | 2.5 | #NAME? | #NAME? | #NAME?
[9 empty] | Total cu ft |  | Total lbs | [19 empty] | Sled count | SPOT 1 | SPOT 2 | SPOT 3 | 463L count
|  | At South Pole | [6 empty] | 733 |  | 12241
|  | In McMurdo | [6 empty] | 20513 |  | 205787
|  | INTER TO GO | [6 empty] | 31984.94 |  | 958862.8
|  | INTRA TO GO | [6 empty] | 52497.94 |  | 1164649.8 | total inter cargo equal to total project cargo in master input sheet | TRUE
|  | INTER PROJECT TOTAL (Includes Fuel) | [6 empty] | 53230.94 |  | 1176890.8 | total intra cargo equal to total project cargo in master input sheet | TRUE
|  | INTRA PROJECT TOTAL (Includes Fuel) | [6 empty] | 53230.94 |  | 1176890.8

## Intra Inter Cargo Summary
Intercontinental leg | volume [cu ft] | fraction of volume | weight [lbs] | fraction of weight |  |  |  |  | Intracontinental leg | volume [cu ft] | fraction of volume | weight [lbs] | fraction of weight
FY23 intercontinental | 5472 | 17.11% | 73642 | 7.68% |  |  |  |  | FY23 intracontinental | 16363 | 40.42% | 159006 | 30.09%
FY24 intercontinental | 5319.01 | 16.63% | 149074.4 | 15.55% |  |  |  |  | FY24 intracontinental | 4695 | 11.6% | 67280 | 12.73%
FY25 intercontinental | 6722.28 | 21.02% | 189661.8 | 19.78% |  |  |  |  | FY25 intracontinental | 9320 | 23.02% | 111998 | 21.19%
FY26 intercontinental | 14471.65 | 45.25% | 546484.6 | 56.99% |  |  |  |  | FY25 intracontinental | 9372 | 23.15% | 177911 | 33.67%
Total | 31984.94 | 100% | 958862.8 | 100% |  |  |  |  | At the South Pole | 733 | 1.811% | 12241 | 2.316%
In McMurdo | 20513 |  | 205787 | [5 empty] | Total project cargo | 40483 | 100% | 528436 | 100%
At South Pole | 733 |  | 12241
Total project cargo | 53230.94 |  | 1176890.8 | [5 empty] | cross check | 40483 |  | 528436
[26 empty] | AN-8 lbs/gal | 6.8
Intercontinental leg | volume [cu ft] | weight [lbs] | Vessel Container Allocation 40F | Vessel Container Allocation 40D | Vessel Container Allocation 20D | Vessel Container Allocation 20F | TEU Count | C-17 Pallet Allocation | Intracontinental leg | volume [cu ft] | weight [lbs] | # SPOT Sleds | # 263 Pallets | Fiscal Year | Intracontinental leg | Needed Fuel [Gallons] | # 263 Pallets (ROUND UP) | Cargo Weight including Pallets and TDE [lbs] | Available LC Flights | Available ACLs [lbs] 1 flight = 23800 lbs | LC Cargo | Available Capacity for fuel [lbs] | Fuel delivered by LC -130 for ICU [Gallons] using 6.8 lbs/gallon for AN-8 | Available LC Flight for Tanker Missions | Fuel Delivered by LC -130 for ICU [Gallons]
In McMurdo | 20513 | 205787 | 0 | 0 | 0 | 0 | 0 | 0 | At South Pole | 733 | 12241 | 0 | 0 | [12 empty] | ACL [lbs] | 22600
At South Pole | 733 | 12241 | 0 | 0 | 0 | 0 | 0 | 0 | FY23 LC-130 | 0 | 0 | 0 | 0 | FY23 | FY23 LC-Tanker | 0 | 0 | 0 | 2 | 45200 | 0 | 45200 | 6647.0588 | 2 | 6000 | gallons/LC-130 | 3000
FY23 Vessel | 5470 | 73632 | 0 | 0 | 5.75 | 0.5 | 6.25 | 0.75 | FY23 SPOT 1 | 5654 | 21601 | 3 | [13 empty] | # pallets/LC-130 | 5
FY23 ComSur | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 0.02 | FY23 SPOT 2 | 7989 | 109405 | 3 | [13 empty] | LC-130 flight hours | 5.9
FY24 Vessel | 4704 | 121302 | 0 | 0 | 5 | 0.25 | 5.25 | 0 | FY23 SPOT 3 | 2720 | 28000 | 1
FY24 ComSur | 128 | 3000 | 0 | 0 | 0 | 0 | 0 | 0.5 | FY24 LC-130 | 576 | 10380 | 0 | 2.15 | FY24 | FY24 LC-Tanker | 3643 | 3 | 11445 | 19 | 429400 | 0.6 | 417955 | 61463.9706 | 18.4 | 55200 | Year | FY23 Capacity | FY23 Planned | FY24 Capacity | FY24 Planned | FY25 Capacity | FY25 Planned | FY26 Capacity | FY26 Planned | FY27 Capacity | FY27 Planned
FY25 Vessel | 1022 | 12362 | 0 | 0.25 | 3 | 0 | 3.25 | 0 | FY24 SPOT 1 | 4119 | 56900 | 2 | [13 empty] | Vessel South (TEU) | 18 | 6.25 | as needed | 5.25 | as needed | 3.25 | n/a | n/a | n/a | n/a
FY25 ComSur | 2953 | 37553 | 0 | 0 | 0 | 0 | 0 | 8.75 | FY24 SPOT 2 | 0 | 0 | 0 | [13 empty] | Vessel North (TEU) | n/a | - | 17 | 0.5 (EST) | 50 | 0.5 (EST) | 17 | - | 50 | TBD
FY26 Vessel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | FY24 SPOT 3 | 0 | 0 | 0 | [13 empty] | LC-130: Hours/Flights - Cargo [lbs] | 12/2 | 0/0-0 | 114/19 | 3.54/0.6-11,445 | 60/10 | 11.8/2-43,103 | 42/7 | 21.24/3.6-73,939 | 36/6 | TBD
FY26 ComSur | 4958 | 62549 | 0 | 0 | 0 | 0 | 0 | 16.5625 | FY25 LC-130 | 3145 | 39553 | 0 | 9.25 | FY25 | FY25 LC-Tanker | 20551 | 10 | 43103 | 10 | 226000 | 2 | 182897 | 26896.6176 | 8 | 24000 | LC-130: Hours/Flights - Fuel [gallons] |  | 11.8/2-6,000 |  | 0/18.4-55,200 |  | 47.2/8-24,000 |  | 20.06/3.4-10,200 |  | TBD
Total | 40483 | 528436 | 0 | 0.25 | 13.75 | 0.75 | 14.75 | 26.5825 | FY25 SPOT 1 | 5055 | 56143 | 2.9 | [13 empty] | SPOT-1 (Sleds/Weights, lbs) | 3/180,000 | 3/21,601 | 3/180,000 | 2/56,900 | 3/180,000 | 2.9/56,143 | 3/180,000 | 2.5/110,362 | 3/180,000 | TBD
[9 empty] | FY25 SPOT 2 | 1120 | 16302 | 0.45 | [13 empty] | SPOT-2 (Sleds/Weights, lbs) | 3/180,000 | 3/109,405 | 3/180,000 | 0/0 | 3/180,000 | 0.45/16,302 | 3/180,000 | 0/0 | 3/180,000 | TBD
[9 empty] | FY25 SPOT 3 | 0 | 0 | 0 | [13 empty] | SPOT-3 (Sleds/Weights, lbs) | 3/180,000 | 1/28,000 | 3/180,000 | 0/0 | 3/180,000 | 0/0 | 3/180,000 | 3/46,791 R | 3/180,000 | TBD
Total Vessel | 11196 | 207296 | [6 empty] | FY26 LC-130 | 5438 | 67549 | 0 | 17.5625 | FY26 | FY26 LC-Tanker | 71167 | 18 | 73939 | 7 | 158200 | 3.6 | 84261 | 353.3529 | 3.4 | 10161 | Pole Population (Nov-Jan) | 0 | 0 | 11 | 11 | 21 | 21 | 46 | 46 | 4 | TBD
Total ComSur | 8041 | 103112 | [6 empty] | FY26 SPOT 1 | 3934 | 110362 | 2.5
[9 empty] | FY26 SPOT 2 | 0 | 0 | 0 | [13 empty] | without flight hours
[9 empty] | FY26 SPOT 3 | 0 | 0 | 0 | [13 empty] | Year | FY23 Capacity | FY23 Planned | FY24 Capacity | FY24 Planned | FY25 Capacity | FY25 Planned | FY26 Capacity | FY26 Planned | FY27 Capacity | FY27 Planned
[9 empty] | Total | 40483 | 528436 | 14.85 | 28.9625 | Total | Total | 95361 | 31 | 128487 | 38 |  | 6.2 | 730313 | 95361 | 31.8 | 95361 | Vessel South (TEU) | 18 | 6.25 | as needed | 5.25 | as needed | 3.25 | n/a | n/a | n/a | n/a
[26 empty] | Vessel North (TEU) | n/a | - | 17 | 0.5 (EST) | 50 | 0.5 (EST) | 17 | - | 50 | TBD
[26 empty] | LC-130: Flights / Cargo [lbs] | 2 missions | 0/0 | 19 missions | 0.6/11,445 | 10 missions | 2/43,103 | 7 missions | 3.6/73,939 | 6 missions | TBD
[26 empty] | LC-130: Flights / Fuel [gallons] |  | 2/6,000 |  | 18.4/55,200 |  | 8/24,000 |  | 3.4/10,200 |  | TBD
[26 empty] | SPOT-1 (Sleds/lbs) | 3/180,000 | 3/21,601 | 3/180,000 | 2/56,900 | 3/180,000 | 2.9/56,143 | 3/180,000 | 2.5/110,362 | 3/180,000 | TBD
[26 empty] | SPOT-2 (Sleds/lbs) | 3/180,000 | 3/109,405 | 3/180,000 | 0/0 | 3/180,000 | 0.45/16,302 | 3/180,000 | 0/0 | 3/180,000 | TBD
[26 empty] | SPOT-3 (Sleds/lbs) | 3/180,000 | 1/28,000 | 3/180,000 | 0/0 | 3/180,000 | 0/0 | 3/180,000 | 3/46,791 R | 3/180,000 | TBD
[26 empty] | Pole Population (Nov-Jan) | 0 | 0 | 11 | 11 | 21 | 21 | 46 | 46 | 4 | TBD

## Project Roll Up
FY23 Intercontinental
Vessel Container Allocation 40F | Vessel Container Allocation 40D | Vessel Container Allocation 20D | Vessel Container Allocation 20F | TEU Count | C-17 Pallet Allocation | COMAIR Pounds | COMSUR Pounds |  | TDE + Pallet /463L | 355
0 | 0 | 5.75 | 0.5 | 6.25 | 0.77 |  | 10 |  | gallons/LC-130
FY23 Intracontinental
Vessel Container Allocation 40F | Vessel Container Allocation 40D | Vessel Container Allocation 20D | Vessel Container Allocation 20F | TEU Count | LC-130 Pallet Allocation | LC-130 Missions | LC-130 Flight Hours | SPOT Sled Allocation | LC-130 flight hours | 5.9
n/a | n/a | n/a | n/a | n/a | 0 | 2 | 11.8 | 7
FY24 Intercontinental
Vessel Container Allocation 40F | Vessel Container Allocation 40D | Vessel Container Allocation 20D | Vessel Container Allocation 20F | TEU Count | C-17 Pallet Allocation | COMAIR Pounds | COMSUR Pounds
0 | 0 | 5 | 0.25 | 5.25 | 0.5 |  | 3000
FY24 Intracontinental
Vessel Container Allocation 40F | Vessel Container Allocation 40D | Vessel Container Allocation 20D | Vessel Container Allocation 20F | TEU Count | LC-130 Pallet Allocation | LC-130 Missions | LC-130 Flight Hours | SPOT Sled Allocation
n/a | n/a | n/a | n/a | n/a | 2.15 | 19 | 112.1 | 2
FY25 Intercontinental
Vessel Container Allocation 40F | Vessel Container Allocation 40D | Vessel Container Allocation 20D | Vessel Container Allocation 20F | TEU Count | C-17 Pallet Allocation | COMAIR Pounds | COMSUR Pounds
0 | 0.25 | 3 | 0 | 3.25 | 8.75 |  | 37553
FY25 Intracontinental
Vessel Container Allocation 40F | Vessel Container Allocation 40D | Vessel Container Allocation 20D | Vessel Container Allocation 20F | TEU Count | LC-130 Pallet Allocation | LC-130 Missions | LC-130 Flight Hours | SPOT Sled Allocation
n/a | n/a | n/a | n/a | n/a | 9.25 | 10 | 59 | 3.35
FY26 Intercontinental
Vessel Container Allocation 40F | Vessel Container Allocation 40D | Vessel Container Allocation 20D | Vessel Container Allocation 20F | TEU Count | C-17 Pallet Allocation | COMAIR Pounds | COMSUR Pounds
0 | 0 | 0 | 0 | 0 | 16.5625 |  | 62549
FY26 Intracontinental
Vessel Container Allocation 40F | Vessel Container Allocation 40D | Vessel Container Allocation 20D | Vessel Container Allocation 20F | TEU Count | LC-130 Pallet Allocation | LC-130 Missions | LC-130 Flight Hours | SPOT Sled Allocation
n/a | n/a | n/a | n/a | n/a | 17.5625 | 7 | 41.3 | 2.5
Total Intercontinental Movements for project- vessel/air
Total 40F | Total 40D | Total 20D | Total 20F | Total TEU | Total 463L | COMAIR Pounds | COMSUR Pounds
0 | 0.25 | 13.75 | 0.75 | 14.75 | 26.5825 |  | 103112
Total Intracontinental Movements for project- LC-130
Total 40F | Total 40D | Total 20D | Total 20F | Total TEU | Total 463L | Total LC-130 Missions | Total LC-130 Flight Hours | Total SPOT Sleds
n/a | n/a | n/a | n/a | n/a | 28.9625 | 38 | 224.2 | 14.85

## Retro
WBS | Retrograde | Conveyance | Details | Contents | Outyear Pole Retro | On A2 Critical Path? | Cube [cf] | Weight [lbs]
1.2 | Gen2 | USAP Air to CHC | Gen2 |  | Ship north by station close FY22 | Yes | 1360 | 22000
| TOTAL | [5 empty] | 1360 | 22000
WBS | Retrograde | Conveyance | Details | Contents | Outyear Pole Retro | On A2 Critical Path? | Cube [cf] | Weight [lbs]
1.2 | 8' container | USAP Air + COMSUR | Multiple crates - DNF | Retrograde components and equipment | Ship north by station close FY23 | Yes | 384 | 7500
1.2 | Misc. science equipment | USAP Air + COMSUR | Multiple crates - DNF | Scientific and test equipment | Ship north by station close FY23 | Yes | 256 | 4000
| TOTAL | [5 empty] | 640 | 11500
WBS | Retrograde | Conveyance | Details | Contents | Outyear Pole Retro | On A2 Critical Path? | Cube [cf] | Weight [lbs]
1.2 | 8' container | USAP Air + COMSUR | Multiple crates - DNF | Retrograde components and equipment | Ship north by station close FY24 | Yes | 384 | 7200
1.3-1.6 | Misc. science equipment | USAP Air + COMSUR | Multiple crates - DNF | Scientific and test equipment | Ship north by station close FY24 | Yes | 256 | 4000
| TOTAL | [5 empty] | 640 | 11200
WBS | Retrograde | Conveyance | Details | Contents | Outyear Pole Retro | On A2 Critical Path? | Cube [cf] | Weight [lbs]
1.2 | Drill hose | USAP Air + COMSUR | Must overwinter in McM - DNDF | 13 hose spools: 352 cf / 4800 lbs each | Ship north by station close FY25 | Yes | 4585 | 62400
1.2 | Tools and equipment | USAP Air + COMSUR | Multiple crates - DNF | Retrograde tools and equipment | Ship north by station close FY25 | No | 1360 | 17000
1.5 | Logging winch | USAP Air + COMSUR | Loan for one season only - Expedite return to IDP | IDP supplied logging winch | Ship north by station close FY25 with CONUS arrival by April 1, 2025 | No | 203 | 3500
1.5 | Logging winch control box | USAP Air + COMSUR | Loan for one season only - Expedite return to IDP - DNF | IDP supplied logging winch control box | Ship north by station close FY25 with CONUS arrival by April 1, 2025 | No | 48 | 400
1.2 | Drill heads | USAP Air + COMSUR | DNF | 3 Drill heads | Ship north by station close FY25 | No | 192 | 1800
1.3-1.6 | Misc. science equipment | USAP Air + COMSUR | Multiple crates - DNF | Scientific and test equipment | Ship north by station close FY25 | No | 256 | 4000
1.3 | Spare mDOMs | USAP Air + COMSUR | 3 pallets | 21 mDOMs (3 pallets) |  | No | 153 | 1719
1.3 | Spare D-Eggs pallet 1 | USAP Air + COMSUR | 1 pallet | 8 Spare D-Eggs |  | No | 84 | 794
1.3 | Spare D-Eggs pallet 2 | USAP Air + COMSUR | 1 pallet | 12 Spare D-Eggs |  | No | 117 | 1169
| TOTAL | [5 empty] | 6998 | 92782