## Contingencies
Code | RangeL | RangeH | Midpoint
C1 | 3% | 15% | 9%
C2 | 5% | 20% | 12.5%
C3 | 10% | 30% | 20%
C4 | 20% | 50% | 35%
C5 | 40% | 60% | 50%
C6 | 60% | 80% | 70%

## Combined Rebaseline Cost Workb
L2 | WBS | Institution | Schedule Task Name | Cost Activity | Resource Name | Type | Subtype | Resource ID | Estimating Technique | Actual Rate | Labor Table Rate | Fringe Rate | Indirect | On/Off Ice | ContCode | EstUncertaintyPer | EstUncertaintyAmount | EstUncertaintyIndirect | Notes | 10-2022 | 11-2022 | 12-2022 | 01-2023 | 02-2023 | 03-2023 | 04-2023 | 05-2023 | 06-2023 | 07-2023 | 08-2023 | 09-2023 | LPY5 | PY5 CMo | S_10_22 | S_11_22 | S_12_22 | S_01_23 | S_02_23 | S_03_23 | S_04_23 | S_05_23 | S_06_23 | S_07_23 | S_08_23 | S_09_23 | 12mo Subtotal PY5 | Indirect Subtotal PY5 | Complete Total PY5 | EU Direct PY5 | EU Ind PY5 | 10-2023 | 11-2023 | 12-2023 | 01-2024 | 02-2024 | 03-2024 | 04-2024 | 05-2024 | 06-2024 | 07-2024 | 08-2024 | 09-2024 | LPY6 | PY6 CMo | S_10_23 | S_11_23 | S_12_23 | S_01_24 | S_02_24 | S_03_24 | S_04_24 | S_05_24 | S_06_24 | S_07_24 | S_08_24 | S_09_24 | 12mo Subtotal PY6 | Indirect Subtotal PY6 | Complete Total PY6 | EU Direct PY6 | EU Ind PY6 | 10-2024 | 11-2024 | 12-2024 | 01-2025 | 02-2025 | 03-2025 | 04-2025 | 05-2025 | 06-2025 | 07-2025 | 08-2025 | 09-2025 | LPY7 | PY7 CMo | S_10_24 | S_11_24 | S_12_24 | S_01_25 | S_02_25 | S_03_25 | S_04_25 | S_05_25 | S_06_25 | S_07_25 | S_08_25 | S_09_25 | 12mo Subtotal PY7 | Indirect Subtotal PY7 | Complete Total PY7 | EU Direct PY7 | EU Ind PY7 | 10-2025 | 11-2025 | 12-2025 | 01-2026 | 02-2026 | 03-2026 | 04-2026 | 05-2026 | 06-2026 | 07-2026 | 08-2026 | 09-2026 | LPY8 | PY8 CMo | S_10_25 | S_11_25 | S_12_25 | S_01_26 | S_02_26 | S_03_26 | S_04_26 | S_05_26 | S_06_26 | S_07_26 | S_08_26 | S_09_26 | 12mo Subtotal PY8 | Indirect Subtotal PY8 | Complete Total PY8 | EU Direct PY8 | EU Ind PY8 | Complete Total PY5-PY8 | Escalation PY4 | Escalation PY5 | Escalation PY6 | Escalation PY7 | Escalation PY8 | Salary Cost PY5 | Salary Cost PY6 | Salary Cost PY7 | Salary Cost PY8 | Fringe Cost PY5 | Fringe Cost PY6 | Fringe Cost PY7 | Fringe Cost PY8 | L3
1.1 | 1.1.1.1 | UW | Project Administration (B) | Project admin - principal investigator | Hanson | Labor Hours | Labor - LoE | KE | A - Analogy | 126 | 121 | 35% | 53% | Off Ice | C1 | 9% | 13008.2986 | 6894.3983 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 144 | 0.96 | 2085.0858 | 2085.0858 | 2085.0858 | 2085.0858 | 2085.0858 | 2085.0858 | 2085.0858 | 2085.0858 | 2085.0858 | 2085.0858 | 2085.0858 | 2085.0858 | 25021.0296 | 13261.1457 | 38282.1753 | 2251.8927 | 1193.5031 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 144 | 0.96 | 2129.9151 | 2129.9151 | 2129.9151 | 2129.9151 | 2129.9151 | 2129.9151 | 2129.9151 | 2129.9151 | 2129.9151 | 2129.9151 | 2129.9151 | 2129.9151 | 25558.9817 | 13546.2603 | 39105.2421 | 2300.3084 | 1219.1634 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 144 | 0.96 | 2175.7083 | 2175.7083 | 2175.7083 | 2175.7083 | 2175.7083 | 2175.7083 | 2175.7083 | 2175.7083 | 2175.7083 | 2175.7083 | 2175.7083 | 2175.7083 | 26108.4998 | 13837.5049 | 39946.0048 | 2349.765 | 1245.3754 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  |  |  |  | 96 | 0.64 | 2222.486 | 2222.486 | 2222.486 | 2222.486 | 2222.486 | 2222.486 | 2222.486 | 2222.486 | 0 | 0 | 0 | 0 | 17779.8884 | 9423.3408 | 27203.2292 | 1600.19 | 848.1007 | 144536.6513 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 18534.096 | 18932.5791 | 19339.6295 | 13170.2877 | 6486.9336 | 6626.4027 | 6768.8703 | 4609.6007 | 1.1.1
1.1 | 1.1.1.1 | PSU | Project Administration (B) | Project admin - Doug Cowen | Cowen | Labor Hours | Labor - LoE | KE | A - Analogy | 120 | 116 | 40% | 58.05% | Off Ice | C1 | 9% | 5529.9002 | 3210.1071 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 60 | 0.4 | 858.06 | 858.06 | 858.06 | 858.06 | 858.06 | 858.06 | 858.06 | 858.06 | 858.06 | 858.06 | 858.06 | 858.06 | 10296.72 | 5977.246 | 16273.966 | 926.7048 | 537.9521 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 60 | 0.4 | 876.5083 | 876.5083 | 876.5083 | 876.5083 | 876.5083 | 876.5083 | 876.5083 | 876.5083 | 876.5083 | 876.5083 | 876.5083 | 876.5083 | 10518.0995 | 6105.7567 | 16623.8562 | 946.629 | 549.5181 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 60 | 0.4 | 895.3532 | 895.3532 | 895.3532 | 895.3532 | 895.3532 | 895.3532 | 895.3532 | 895.3532 | 895.3532 | 895.3532 | 895.3532 | 895.3532 | 10744.2386 | 6237.0305 | 16981.2691 | 966.9815 | 561.3327 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 40 | 0.26667 | 914.6033 | 914.6033 | 914.6033 | 914.6033 | 914.6033 | 914.6033 | 914.6033 | 914.6033 | 0 | 0 | 0 | 0 | 7316.8265 | 4247.4178 | 11564.2443 | 658.5144 | 382.2676 | 61443.3356 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 7354.8 | 7512.9282 | 7674.4562 | 5226.3046 | 2941.92 | 3005.1713 | 3069.7825 | 2090.5219 | 1.1.1
1.1 | 1.1.1.1 | UMD | Project Administration (B) | Project admin - Greg Sullivan | Sullivan | Labor Hours | Labor - LoE | KE | A - Analogy | 159 | 116 | 29% | 54.5% | Off Ice | C1 | 9% | 6599.7704 | 3596.8749 | Added by Erik B from UMD | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 60 | 0.4 | 1047.5993 | 1047.5993 | 1047.5993 | 1047.5993 | 1047.5993 | 1047.5993 | 1047.5993 | 1047.5993 | 1047.5993 | 1047.5993 | 1047.5993 | 1047.5993 | 12571.1919 | 6851.2996 | 19422.4915 | 1131.4073 | 616.617 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 60 | 0.4 | 1070.1227 | 1070.1227 | 1070.1227 | 1070.1227 | 1070.1227 | 1070.1227 | 1070.1227 | 1070.1227 | 1070.1227 | 1070.1227 | 1070.1227 | 1070.1227 | 12841.4725 | 6998.6025 | 19840.0751 | 1155.7325 | 629.8742 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 60 | 0.4 | 1093.1303 | 1093.1303 | 1093.1303 | 1093.1303 | 1093.1303 | 1093.1303 | 1093.1303 | 1093.1303 | 1093.1303 | 1093.1303 | 1093.1303 | 1093.1303 | 13117.5642 | 7149.0725 | 20266.6367 | 1180.5808 | 643.4165 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  |  |  | 40 | 0.26667 | 1116.6327 | 1116.6327 | 1116.6327 | 1116.6327 | 1116.6327 | 1116.6327 | 1116.6327 | 1116.6327 | 0 | 0 | 0 | 0 | 8933.0612 | 4868.5184 | 13801.5796 | 803.9755 | 438.1667 | 73330.7828 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9745.11 | 9954.6299 | 10168.6544 | 6924.8537 | 2826.0819 | 2886.8427 | 2948.9098 | 2008.2076 | 1.1.1
1.1 | 1.1.1.1 | UW | Project Administration (B) | Project Director-ODell | ODell | Labor Hours | Labor - LoE | KE | A - Analogy | 112.2 | 121 | 35% | 53% | Off Ice | C1 | 9% | 45631.816 | 24184.8625 |  | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 720 | 4.8 | 9283.5963 | 9283.5963 | 9283.5963 | 9283.5963 | 9283.5963 | 9283.5963 | 9283.5963 | 9283.5963 | 9283.5963 | 9283.5963 | 9283.5963 | 9283.5963 | 111403.1556 | 59043.6725 | 170446.8281 | 10026.284 | 5313.9305 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 600 | 4 | 7902.6614 | 7902.6614 | 7902.6614 | 7902.6614 | 7902.6614 | 7902.6614 | 7902.6614 | 7902.6614 | 7902.6614 | 7902.6614 | 7902.6614 | 7902.6614 | 94831.9362 | 50260.9262 | 145092.8624 | 8534.8743 | 4523.4834 | 50 | 50 | 50 | 50 | 50 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 530 | 3.5333 | 8072.5686 | 8072.5686 | 8072.5686 | 8072.5686 | 8072.5686 | 6458.0549 | 6458.0549 | 6458.0549 | 6458.0549 | 6458.0549 | 6458.0549 | 6458.0549 | 85569.2268 | 45351.6902 | 130920.9171 | 7701.2304 | 4081.6521 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 |  |  |  |  | 240 | 1.6 | 4947.6773 | 4947.6773 | 4947.6773 | 4947.6773 | 4947.6773 | 4947.6773 | 4947.6773 | 4947.6773 | 0 | 0 | 0 | 0 | 39581.4182 | 20978.1517 | 60559.5699 | 3562.3276 | 1888.0336 | 507020.1774 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 82520.856 | 70245.8787 | 63384.6125 | 29319.569 | 28882.2996 | 24586.0575 | 22184.6144 | 10261.8492 | 1.1.1
1.1 | 1.1.1.1 | UW | Project Administration (B) | Project manager-Feyzi | Feyzi | Labor Hours | Labor - LoE | KE | A - Analogy | 98 | 121 | 35% | 53% | Off Ice | C1 | 9% | 74064.2815 | 39254.0692 |  | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1800 | 12 | 20271.6675 | 20271.6675 | 20271.6675 | 20271.6675 | 20271.6675 | 20271.6675 | 20271.6675 | 20271.6675 | 20271.6675 | 20271.6675 | 20271.6675 | 20271.6675 | 243260.01 | 128927.8053 | 372187.8153 | 21893.4009 | 11603.5025 | 100 | 100 | 0 | 0 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 950 | 6.3333 | 13805.0056 | 13805.0056 | 0 | 0 | 6902.5028 | 13805.0056 | 13805.0056 | 13805.0056 | 13805.0056 | 13805.0056 | 13805.0056 | 13805.0056 | 131147.5529 | 69508.203 | 200655.7559 | 11803.2798 | 6255.7383 | 75 | 75 | 0 | 0 | 50 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 725 | 4.8333 | 10576.3599 | 10576.3599 | 0 | 0 | 7050.9066 | 10576.3599 | 10576.3599 | 10576.3599 | 10576.3599 | 10576.3599 | 10576.3599 | 10576.3599 | 102238.1456 | 54186.2172 | 156424.3628 | 9201.4331 | 4876.7595 | 75 | 75 | 0 | 0 | 50 | 75 | 75 | 75 |  |  |  |  | 425 | 2.8333 | 10803.7516 | 10803.7516 | 0 | 0 | 7202.5011 | 10803.7516 | 10803.7516 | 10803.7516 | 0 | 0 | 0 | 0 | 61221.2592 | 32447.2674 | 93668.5266 | 5509.9133 | 2920.2541 | 822936.4606 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 180192.6 | 97146.3355 | 75731.9597 | 45349.0809 | 63067.41 | 34001.2174 | 26506.1859 | 15872.1783 | 1.1.1
1.1 | 1.1.1.1 | UW | Project Administration (B) | Project Office M&S |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 7477.11 | 3962.8683 |  | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1200 | 0 | 0 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1200 | 15500 | 8215 | 23715 | 1395 | 739.35 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1200 | 0 | 0 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1200 | 15500 | 8215 | 23715 | 1395 | 739.35 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1200 | 0 | 0 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 1200 | 15500 | 8215 | 23715 | 1395 | 739.35 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 0 | 0 |  |  |  |  | 0 | 0 | 1300 | 1300 | 1300 | 1300 | 1300 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 7800 | 4134 | 11934 | 702 | 372.06 | 83079 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1
1.1 | 1.1.1.1 | UW | Project Administration (B) | Project Advisory Panel Reviews - Panel Members Compensation | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 5700.78 | 3021.4134 | 6-panel members (domestic travel), 3 require some form of payment ~$1,000 each |  |  |  |  | 13800 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | 7314 | 21114 | 1242 | 658.26 |  |  |  |  | 13800 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | 7314 | 21114 | 1242 | 658.26 | [5 empty] | 13800 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | 0 | 0 | 0 | 0 | 0 | 0 | 13800 | 7314 | 21114 | 1242 | 658.26 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63342 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1
1.1 | 1.1.1.1 | UW | Project Administration (B) | PO-Travel | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 6196.5 | 3284.145 | [8 empty] | 14400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | 0 | 0 | 0 | 14400 | 7632 | 22032 | 1296 | 686.88 | [7 empty] | 14400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | 0 | 0 | 0 | 14400 | 7632 | 22032 | 1296 | 686.88 | [7 empty] | 14400 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400 | 0 | 0 | 0 | 0 | 14400 | 7632 | 22032 | 1296 | 686.88 | 1800 | [11 empty] | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | 68850 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1
1.1 | 1.1.1.1 | UW | Project Administration (B) | PO-Travel | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 3965.76 | 2101.8528 | [8 empty] | 9600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 9600 | 5088 | 14688 | 864 | 457.92 | [7 empty] | 9600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 9600 | 5088 | 14688 | 864 | 457.92 | [7 empty] | 9600 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 9600 | 5088 | 14688 | 864 | 457.92 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44064 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1.1
1.1 | 1.1.2.1 | UW | Project Controls and Finance (B) | Finance - | Finance | Labor Hours | Labor - LoE | MA | A - Analogy | 45 | 46 | 35% | 53% | Off Ice | C1 | 9% | 23229.1047 | 12311.4255 |  | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 720 | 4.8 | 3723.3675 | 3723.3675 | 3723.3675 | 3723.3675 | 3723.3675 | 3723.3675 | 3723.3675 | 3723.3675 | 3723.3675 | 3723.3675 | 3723.3675 | 3723.3675 | 44680.41 | 23680.6173 | 68361.0273 | 4021.2369 | 2131.2556 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 720 | 4.8 | 3803.4199 | 3803.4199 | 3803.4199 | 3803.4199 | 3803.4199 | 3803.4199 | 3803.4199 | 3803.4199 | 3803.4199 | 3803.4199 | 3803.4199 | 3803.4199 | 45641.0388 | 24189.7506 | 69830.7894 | 4107.6935 | 2177.0776 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 720 | 4.8 | 3885.1934 | 3885.1934 | 3885.1934 | 3885.1934 | 3885.1934 | 3885.1934 | 3885.1934 | 3885.1934 | 3885.1934 | 3885.1934 | 3885.1934 | 3885.1934 | 46622.3211 | 24709.8302 | 71332.1514 | 4196.0089 | 2223.8847 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 |  |  |  |  | 480 | 3.2 | 3968.7251 | 3968.7251 | 3968.7251 | 3968.7251 | 3968.7251 | 3968.7251 | 3968.7251 | 3968.7251 | 0 | 0 | 0 | 0 | 31749.8007 | 16827.3944 | 48577.1951 | 2857.4821 | 1514.4655 | 258101.1631 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 33096.6 | 33808.1769 | 34535.0527 | 23518.3709 | 11583.81 | 11832.8619 | 12087.2684 | 8231.4298 | 1.1.2
1.1 | 1.1.2.1 | UW | Project Controls and Finance (B) | Project Controls - | Controls | Labor Hours | Labor - LoE | MA | A - Analogy | 46 | 46 | 35% | 53% | Off Ice | C1 | 9% | 37543.1519 | 19897.8705 | Rogal | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1800 | 12 | 9515.2725 | 9515.2725 | 9515.2725 | 9515.2725 | 9515.2725 | 9515.2725 | 9515.2725 | 9515.2725 | 9515.2725 | 9515.2725 | 9515.2725 | 9515.2725 | 114183.27 | 60517.1331 | 174700.4031 | 10276.4943 | 5446.542 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 6 | 4859.9254 | 4859.9254 | 4859.9254 | 4859.9254 | 4859.9254 | 4859.9254 | 4859.9254 | 4859.9254 | 4859.9254 | 4859.9254 | 4859.9254 | 4859.9254 | 58319.1052 | 30909.1257 | 89228.2309 | 5248.7195 | 2781.8213 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 6 | 4964.4138 | 4964.4138 | 4964.4138 | 4964.4138 | 4964.4138 | 4964.4138 | 4964.4138 | 4964.4138 | 4964.4138 | 4964.4138 | 4964.4138 | 4964.4138 | 59572.9659 | 31573.6719 | 91146.6378 | 5361.5669 | 2841.6305 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 |  |  |  |  | 600 | 4 | 5071.1487 | 5071.1487 | 5071.1487 | 5071.1487 | 5071.1487 | 5071.1487 | 5071.1487 | 5071.1487 | 0 | 0 | 0 | 0 | 40569.1898 | 21501.6706 | 62070.8604 | 3651.2271 | 1935.1504 | 417146.1322 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 84580.2 | 43199.3371 | 44128.1229 | 30051.2517 | 29603.07 | 15119.768 | 15444.843 | 10517.9381 | 1.1.2
1.1 | 1.1.3.1 | UW | Quality, Safety Management, Document Control Systems (B) | Q&A / Safety - Zernick | Zernick | Labor Hours | Labor - LoE | MA | A - Analogy | 61 | 46 | 35% | 53% | Off Ice | C1 | 9% | 44019.308 | 23330.2332 |  | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 1356 | 9.04 | 9505.6193 | 9505.6193 | 9505.6193 | 9505.6193 | 9505.6193 | 9505.6193 | 9505.6193 | 9505.6193 | 9505.6193 | 9505.6193 | 9505.6193 | 9505.6193 | 114067.4319 | 60455.7389 | 174523.1708 | 10266.0689 | 5441.0165 | 113 | 113 | 0 | 0 | 50 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 1067 | 7.1133 | 9709.9901 | 9709.9901 | 0 | 0 | 4296.4558 | 9709.9901 | 9709.9901 | 9709.9901 | 9709.9901 | 9709.9901 | 9709.9901 | 9709.9901 | 91686.3671 | 48593.7746 | 140280.1416 | 8251.773 | 4373.4397 | 113 | 113 | 0 | 0 | 50 | 113 | 113 | 113 | 113 | 113 | 113 | 113 | 1067 | 7.1133 | 9918.7549 | 9918.7549 | 0 | 0 | 4388.8296 | 9918.7549 | 9918.7549 | 9918.7549 | 9918.7549 | 9918.7549 | 9918.7549 | 9918.7549 | 93657.624 | 49638.5407 | 143296.1647 | 8429.1862 | 4467.4687 | 113 | 113 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 226 | 1.5067 | 10132.0082 | 10132.0082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20264.0163 | 10739.9286 | 31003.945 | 1823.7615 | 966.5936 | 489103.4221 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 84494.394 | 67915.8275 | 69376.0178 | 15010.3825 | 29573.0379 | 23770.5396 | 24281.6062 | 5253.6339 | 1.1.3
1.1 | 1.1.4.1 | UW | Logistics (B) | Logistics-Tosi | Tosi | Labor Hours | Labor - LoE | SC | A - Analogy | 47 | 52 | 35% | 53% | Off Ice | C1 | 9% | 6405.3242 | 3394.8218 | Tosi - 25% | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 360 | 2.4 | 1944.4253 | 1944.4253 | 1944.4253 | 1944.4253 | 1944.4253 | 1944.4253 | 1944.4253 | 1944.4253 | 1944.4253 | 1944.4253 | 1944.4253 | 1944.4253 | 23333.103 | 12366.5446 | 35699.6476 | 2099.9793 | 1112.989 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 180 | 1.2 | 993.1152 | 993.1152 | 993.1152 | 993.1152 | 993.1152 | 993.1152 | 993.1152 | 993.1152 | 993.1152 | 993.1152 | 993.1152 | 993.1152 | 11917.3824 | 6316.2126 | 18233.595 | 1072.5644 | 568.4591 | 14 | 14 | 5 | 0 | 8 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 139 | 0.92667 | 946.836 | 946.836 | 338.1557 | 0 | 541.0492 | 946.836 | 946.836 | 946.836 | 946.836 | 946.836 | 946.836 | 946.836 | 9400.7291 | 4982.3864 | 14383.1156 | 846.0656 | 448.4148 | 9 | 9 | 0 | 0 | 0 | 9 | 0 | 0 |  |  |  |  | 27 | 0.18 | 621.7669 | 621.7669 | 0 | 0 | 0 | 621.7669 | 0 | 0 | 0 | 0 | 0 | 0 | 1865.3008 | 988.6094 | 2853.9102 | 167.8771 | 88.9748 | 71170.2684 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 17283.78 | 8827.6906 | 6963.5031 | 1381.7043 | 6049.323 | 3089.6917 | 2437.2261 | 483.5965 | 1.1.4
1.1 | 1.1.5.1 | UW | Systems Engineering (B) | System Engineering-Sandstrom | Sandstrom | Labor Hours | Labor - LoE | SE | A - Analogy | 64 | 55 | 35% | 53% | Off Ice | C1 | 9% | 29719.4535 | 15751.3103 |  | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 6 | 6619.32 | 6619.32 | 6619.32 | 6619.32 | 6619.32 | 6619.32 | 6619.32 | 6619.32 | 6619.32 | 6619.32 | 6619.32 | 6619.32 | 79431.84 | 42098.8752 | 121530.7152 | 7148.8656 | 3788.8988 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 6 | 6761.6354 | 6761.6354 | 6761.6354 | 6761.6354 | 6761.6354 | 6761.6354 | 6761.6354 | 6761.6354 | 6761.6354 | 6761.6354 | 6761.6354 | 6761.6354 | 81139.6246 | 43004.001 | 124143.6256 | 7302.5662 | 3870.3601 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 600 | 4 | 4604.6737 | 4604.6737 | 4604.6737 | 4604.6737 | 4604.6737 | 4604.6737 | 4604.6737 | 4604.6737 | 4604.6737 | 4604.6737 | 4604.6737 | 4604.6737 | 55256.0843 | 29285.7247 | 84541.809 | 4973.0476 | 2635.7152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330216.1498 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 58838.4 | 60103.4256 | 40930.4328 | 0 | 20593.44 | 21036.199 | 14325.6515 | 0 | 1.1.5
1.1 | 1.1.5.1 | UW | Systems Engineering (B) | Technical Coordination-DuVernois | DuVernois | Labor Hours | Labor - LoE | SS | A - Analogy | 74 | 66 | 35% | 53% | Off Ice | C1 | 9% | 41008.6294 | 21734.5736 |  | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 6 | 7653.5887 | 7653.5887 | 7653.5887 | 7653.5887 | 7653.5887 | 7653.5887 | 7653.5887 | 7653.5887 | 7653.5887 | 7653.5887 | 7653.5887 | 7653.5887 | 91843.065 | 48676.8245 | 140519.8894 | 8265.8759 | 4380.9142 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 6 | 7818.1409 | 7818.1409 | 7818.1409 | 7818.1409 | 7818.1409 | 7818.1409 | 7818.1409 | 7818.1409 | 7818.1409 | 7818.1409 | 7818.1409 | 7818.1409 | 93817.6909 | 49723.3762 | 143541.0671 | 8443.5922 | 4475.1039 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 6 | 7986.2309 | 7986.2309 | 7986.2309 | 7986.2309 | 7986.2309 | 7986.2309 | 7986.2309 | 7986.2309 | 7986.2309 | 7986.2309 | 7986.2309 | 7986.2309 | 95834.7713 | 50792.4288 | 146627.2 | 8625.1294 | 4571.3186 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 150 | 1 | 8157.9349 | 8157.9349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16315.8698 | 8647.411 | 24963.2808 | 1468.4283 | 778.267 | 455651.4373 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 68031.9 | 69494.5859 | 70988.7194 | 12085.8295 | 23811.165 | 24323.105 | 24846.0518 | 4230.0403 | 1.1.5
1.2 | 1.2.1.1 | UW | Implementation Management and Controls | EHWD Project Management and Controls (WIPAC_Implementation_Manager) | McEwen | Labor Hours | Labor - LoE | SE | D - Expert Opinion | 61 | 55 | 35% | 53% | Off Ice | C1 | 9% | 76868.8492 | 40740.4901 |  | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1800 | 12 | 12618.0788 | 12618.0788 | 12618.0788 | 12618.0788 | 12618.0788 | 12618.0788 | 12618.0788 | 12618.0788 | 12618.0788 | 12618.0788 | 12618.0788 | 12618.0788 | 151416.945 | 80250.9809 | 231667.9258 | 13627.5251 | 7222.5883 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1800 | 12 | 12889.3674 | 12889.3674 | 12889.3674 | 12889.3674 | 12889.3674 | 12889.3674 | 12889.3674 | 12889.3674 | 12889.3674 | 12889.3674 | 12889.3674 | 12889.3674 | 154672.4093 | 81976.3769 | 236648.7863 | 13920.5168 | 7377.8739 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | 1800 | 12 | 13166.4888 | 13166.4888 | 13166.4888 | 13166.4888 | 13166.4888 | 13166.4888 | 13166.4888 | 13166.4888 | 13166.4888 | 13166.4888 | 13166.4888 | 13166.4888 | 157997.8661 | 83738.869 | 241736.7352 | 14219.808 | 7536.4982 | 150 | 150 | 150 | 150 | 150 | 150 | 150 | [5 empty] | 1050 | 7 | 13449.5684 | 13449.5684 | 13449.5684 | 13449.5684 | 13449.5684 | 13449.5684 | 13449.5684 | 0 | 0 | 0 | 0 | 0 | 94146.9785 | 49897.8986 | 144044.8771 | 8473.2281 | 4490.8109 | 854098.3243 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 112160.7 | 114572.1551 | 117035.4564 | 69738.5026 | 39256.245 | 40100.2543 | 40962.4097 | 24408.4759 | 1.2.1
1.2 | 1.2.1.2.5.1 | PSL | 2022-23 Management & Systems Engineering | 2022-23 Systems Engineering (Terry Benson) | Benson | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 9515.2725 | 0 | Engineering oversight and systems development - coordination and planning, season planning, ASC interface, SIP, logistics coordination, drill procedures, EVMS, seasonal reports | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 6 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 8810.4375 | 105725.25 | 0 | 105725.25 | 9515.2725 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105725.25 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 105725.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.5.1 | PSL | 2022-23 Management & Systems Engineering | 2022-23 Management | Gibson | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 15224.436 | 0 | Drill Manager LOE: 0.8 FTE = 1440 hr/yr | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 1440 | 9.6 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 14096.7 | 169160.4 | 0 | 169160.4 | 15224.436 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169160.4 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 169160.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.5.1 | PSL | 2022-23 Management & Systems Engineering | 2022-23 Systems Engineering Support |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 4859.1325 | 0 | Team meetings - weekly status, reviews, collaboration mtgs, ASC weekly and annual Weekly status mtgs: 35 wks * 1 hr * 12 people = 420 hr ASC coord: 18 wks * 1 hr * 3 people = 78 hr Total = 558 hr | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 38.3 | 459.6 | 3.064 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 4499.1968 | 53990.361 | 0 | 53990.361 | 4859.1325 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53990.361 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 53990.361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.5.2 | PSL | Drill Procedure Review | Drill Procedure Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 4111.5375 | 0 | 1 hr session/wk * 35 wks each year 8 people = 280 hr/yr | [6 empty] | 46 | 47 | 47 | 47 | 47 | 46 | 280 | 1.8667 | 0 | 0 | 0 | 0 | 0 | 0 | 5403.735 | 5521.2075 | 5521.2075 | 5521.2075 | 5521.2075 | 5403.735 | 32892.3 | 0 | 32892.3 | 4111.5375 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32892.3 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 32892.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.5.3 | PSL | Drill Hole Modeling | Drill Hole Modeling |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 1174.725 | 0 | Hole modeling = 120 hr/yr | [8 empty] | 40 | 40 |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 4698.9 | 0 | 0 | 9397.8 | 0 | 9397.8 | 1174.725 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.6.1 | PSL | 2023-24 Management & Systems Engineering | 2023-24 Management & Systems Engineering | Benson | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 6473.4207 | 0 | Engineering oversight and systems development | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6 |  |  |  | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 599.4 | 3.996 | 7991.8774 | 0 | 0 | 0 | 7991.8774 | 7991.8774 | 7991.8774 | 7991.8774 | 7991.8774 | 7991.8774 | 7991.8774 | 7991.8774 | 71926.8964 | 0 | 71926.8964 | 6473.4207 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71926.8964 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 71926.8964 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.6.1 | PSL | 2023-24 Management & Systems Engineering | 2023-24 Management | Gibson | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 10361.361 | 0 | Drill Manager LOE: 0.8 FTE = 1440 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106.6 |  |  |  | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 959.4 | 6.396 | 12791.8037 | 0 | 0 | 0 | 12791.8037 | 12791.8037 | 12791.8037 | 12791.8037 | 12791.8037 | 12791.8037 | 12791.8037 | 12791.8037 | 115126.2335 | 0 | 115126.2335 | 10361.361 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115126.2335 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 115126.2335 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.6.1 | PSL | 2023-24 Management & Systems Engineering | 2023-24 Systems Engineering Support |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 3974.339 | 0 | Team meetings - weekly status, reviews, collaboration mtgs, ASC weekly and annual Weekly status mtgs: 35 wks * 1 hr * 12 people = 420 hr ASC coord: 18 wks * 1 hr * 3 people = 54 hr Total = 1914 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 368 | 2.4533 | 4799.9263 | 0 | 0 | 0 | 4919.9245 | 4919.9245 | 4919.9245 | 4919.9245 | 4919.9245 | 4919.9245 | 4919.9245 | 4919.9245 | 44159.3224 | 0 | 44159.3224 | 3974.339 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44159.3224 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 44159.3224 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.6.2 | PSL | PY6 Season Debrief | PY6 Season Debrief |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 1799.9724 | 0 | Season Debrief - 30 people, hybrid, 4 hr = 120 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 120 | [6 empty] | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 14399.779 | 0 | 0 | 0 | 0 | 0 | 0 | 14399.779 | 0 | 14399.779 | 1799.9724 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14399.779 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 14399.779 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.6.3 | PSL | Drill Procedure Review | Drill Procedure Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 3359.9484 | 0 | 1 hr session/wk * 35 wks each year 8 people = 280 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 37 | 37 | 38 | 38 | 37 | 37 | 224 | 1.4933 | 0 | 0 | 0 | 0 | 0 | 0 | 4439.9319 | 4439.9319 | 4559.93 | 4559.93 | 4439.9319 | 4439.9319 | 26879.5876 | 0 | 26879.5876 | 3359.9484 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26879.5876 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 26879.5876 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.6.5 | PSL | Drill Hole Modeling | Drill Hole Modeling |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 1199.9816 | 0 | Hole modeling = 120 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 40 | 40 |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | 1199.9816 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.7.1 | PSL | 2024-25 Management & Systems Engineering | 2024-25 Management & Systems Engineering | Benson | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 6612.5992 | 0 | System engineering oversight and systems development | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6 |  |  |  | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 66.6 | 599.4 | 3.996 | 8163.7027 | 0 | 0 | 0 | 8163.7027 | 8163.7027 | 8163.7027 | 8163.7027 | 8163.7027 | 8163.7027 | 8163.7027 | 8163.7027 | 73473.3246 | 0 | 73473.3246 | 6612.5992 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73473.3246 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 73473.3246 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.7.1 | PSL | 2024-25 Management & Systems Engineering | 2024-25 Management | Gibson | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 10584.1303 | 0 | Drill Manager LOE: 0.8 FTE = 1440 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 106.6 |  |  |  | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 106.6 | 959.4 | 6.396 | 13066.8275 | 0 | 0 | 0 | 13066.8275 | 13066.8275 | 13066.8275 | 13066.8275 | 13066.8275 | 13066.8275 | 13066.8275 | 13066.8275 | 117601.4475 | 0 | 117601.4475 | 10584.1303 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117601.4475 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 117601.4475 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.7.1 | PSL | 2024-25 Management & Systems Engineering | 2024-25 Systems Engineering Support |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 4059.7873 | 0 | Team meetings - weekly status, reviews, collaboration mtgs, ASC weekly and annual Weekly status mtgs: 35 wks * 1 hr * 12 people = 420 hr ASC coord: 18 wks * 1 hr * 3 people = 54 hr Total = 1914 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 368 | 2.4533 | 4903.1248 | 0 | 0 | 0 | 5025.7029 | 5025.7029 | 5025.7029 | 5025.7029 | 5025.7029 | 5025.7029 | 5025.7029 | 5025.7029 | 45108.7479 | 0 | 45108.7479 | 4059.7873 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45108.7479 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 45108.7479 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.7.2 | PSL | PY7 Season Debrief | PY7 Season Debrief |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 1838.6718 | 0 | Season Debrief - 30 people, hybrid, 4 hr = 120 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 120 | [6 empty] | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 0 | 14709.3743 | 1838.6718 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 14709.3743 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.7.3 | PSL | Drill Procedure Review | Drill Procedure Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 3432.1873 | 0 | 1 hr session/wk * 35 wks each year 8 people = 280 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 37 | 37 | 38 | 38 | 37 | 37 | 224 | 1.4933 | 0 | 0 | 0 | 0 | 0 | 0 | 4535.3904 | 4535.3904 | 4657.9685 | 4657.9685 | 4535.3904 | 4535.3904 | 27457.4987 | 0 | 27457.4987 | 3432.1873 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27457.4987 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 27457.4987 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.7.5 | PSL | Drill Hole Modeling | Drill Hole Modeling |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 1225.7812 | 0 | Hole modeling = 120 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 40 | 40 |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4903.1248 | 4903.1248 | 0 | 0 | 9806.2495 | 0 | 9806.2495 | 1225.7812 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.2495 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 9806.2495 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.7.6 | PSL | Drill Readiness Review (PSL) | Drill Readiness Review (PSL) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 2941.8749 | 0 | 12 Engineers 2 days @ 8 hrs = 192 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 192 |  |  | 192 | 1.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23534.9989 | 0 | 0 | 23534.9989 | 0 | 23534.9989 | 2941.8749 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23534.9989 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 23534.9989 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.8.1 | PSL | 2025-26 Management & Systems Engineering | 2025-26 Systems Engineering | Benson | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 3042.6892 | 0 | System Engineer - Oct (pre-deployment) & March/April for closeout. On-ice hours captured in Field Seasons. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.5 |  |  |  | 67.5 | 67.5 | 67.5 | [5 empty] | 270 | 1.8 | 8451.9145 | 0 | 0 | 0 | 8451.9145 | 8451.9145 | 8451.9145 | 0 | 0 | 0 | 0 | 0 | 33807.6582 | 0 | 33807.6582 | 3042.6892 | 0 | 33807.6582 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 33807.6582 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.8.1 | PSL | 2025-26 Management & Systems Engineering | 2025-26 Management | Gibson | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 4056.919 | 0 | Drill Manager LOE: Oct (pre-deployment) & March/April for closeout. On-ice hours captured in Field Seasons. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 |  |  |  |  | 120 | 120 | [5 empty] | 360 | 2.4 | 15025.6258 | 0 | 0 | 0 | 0 | 15025.6258 | 15025.6258 | 0 | 0 | 0 | 0 | 0 | 45076.8775 | 0 | 45076.8775 | 4056.919 | 0 | 45076.8775 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 45076.8775 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.8.1 | PSL | 2025-26 Management & Systems Engineering | 2025-26 Systems Engineering Support |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 2704.6127 | 0 | Engineering support hours for weekly status meeting & off-ice engineering support | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 |  |  |  |  | 100 | 100 | [5 empty] | 240 | 1.6 | 5008.5419 | 0 | 0 | 0 | 0 | 12521.3549 | 12521.3549 | 0 | 0 | 0 | 0 | 0 | 30051.2517 | 0 | 30051.2517 | 2704.6127 | 0 | 30051.2517 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 30051.2517 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.2.8.2 | PSL | PY8 Season Debrief | PY8 Season Debrief |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 1878.2032 | 0 | Season Debrief - 30 people, hybrid, 4 hr = 120 hr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 120 | [6 empty] | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 15025.6258 | 0 | 0 | 0 | 0 | 0 | 0 | 15025.6258 | 0 | 15025.6258 | 1878.2032 | 0 | 15025.6258 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 15025.6258 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.3.2.1 | UW | String Management and Controls (2022-2023) | String Management and Controls (2022-2023) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 52 | 52 | 35% | 53% | Off Ice | C1 | 9% | 2666.0801 | 1413.0224 | Tosi - 15% | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 22 | 22 | 23 | 23 | 270 | 1.8 | 1577.6046 | 1577.6046 | 1577.6046 | 1577.6046 | 1649.3139 | 1649.3139 | 1649.3139 | 1649.3139 | 1577.6046 | 1577.6046 | 1649.3139 | 1649.3139 | 19361.511 | 10261.6008 | 29623.1118 | 1742.536 | 923.5441 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29623.1118 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 14341.86 | 0 | 0 | 0 | 5019.651 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.3.2.2 | UW | Installation Engineering (2022-2023) | Installation Engineering (2022-2023) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 52 | 52 | 35% | 53% | Off Ice | C1 | 9% | 4443.4668 | 2355.0374 | Tosi - 25% | 38 | 38 | 38 | 38 | 38 | 36 | 36 | 36 | 38 | 38 | 38 | 38 | 450 | 3 | 2724.9534 | 2724.9534 | 2724.9534 | 2724.9534 | 2724.9534 | 2581.5348 | 2581.5348 | 2581.5348 | 2724.9534 | 2724.9534 | 2724.9534 | 2724.9534 | 32269.185 | 17102.6681 | 49371.853 | 2904.2267 | 1539.2401 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49371.853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 23903.1 | 0 | 0 | 0 | 8366.085 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.3.2.3 | PSL | Installation Engineering Support (2022-2023) | Installation Engineering Support (2022-2023) |  | Labor Hours | Labor - LoE | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 704.835 | 0 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 48 | 0.32 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 469.89 | 5638.68 | 0 | 5638.68 | 704.835 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5638.68 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 5638.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.3.3.1 | UW | String Management and Controls (2023-2024) | String Management and Controls (2023-2024) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 52 | 52 | 35% | 53% | Off Ice | C1 | 9% | 1815.6005 | 962.2683 | Tosi - 10% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 180 | 1.2 | 1098.7657 | 1098.7657 | 1098.7657 | 1098.7657 | 1098.7657 | 1098.7657 | 1098.7657 | 1098.7657 | 1098.7657 | 1098.7657 | 1098.7657 | 1098.7657 | 13185.189 | 6988.1502 | 20173.3392 | 1186.667 | 628.9335 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20173.3392 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9766.8067 | 0 | 0 | 0 | 3418.3823 | 0 | 0 | 1.2.1
1.2 | 1.2.1.3.3.2 | UW | Installation Engineering (2023-2024) | Installation Engineering (2023-2024) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 52 | 52 | 35% | 53% | Off Ice | C1 | 9% | 5446.8016 | 2886.8048 | Tosi - 30% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | 3.6 | 3296.2972 | 3296.2972 | 3296.2972 | 3296.2972 | 3296.2972 | 3296.2972 | 3296.2972 | 3296.2972 | 3296.2972 | 3296.2972 | 3296.2972 | 3296.2972 | 39555.567 | 20964.4505 | 60520.0175 | 3560.001 | 1886.8005 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60520.0175 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 29300.42 | 0 | 0 | 0 | 10255.147 | 0 | 0 | 1.2.1
1.2 | 1.2.1.3.3.3 | PSL | Installation Engineering Support (2023-2024) | Installation Engineering Support (2023-2024) |  | Labor Hours | Labor - LoE | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 719.989 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 48 | 0.32 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 479.9926 | 5759.9116 | 0 | 5759.9116 | 719.989 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5759.9116 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 5759.9116 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.3.4.1 | UW | String Management and Controls (2024-2025) | String Management and Controls (2024-2025) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 52 | 52 | 35% | 53% | Off Ice | C1 | 9% | 927.318 | 491.4785 | Tosi - 5% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 90 | 0.6 | 598.6076 | 598.6076 | 0 | 0 | 598.6076 | 673.4335 | 673.4335 | 673.4335 | 673.4335 | 748.2595 | 748.2595 | 748.2595 | 6734.3353 | 3569.1977 | 10303.533 | 606.0902 | 321.2278 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10303.533 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4988.3965 | 0 | 0 | 0 | 1745.9388 | 0 | 1.2.1
1.2 | 1.2.1.3.4.2 | UW | Installation Engineering (2024-2025) | Installation Engineering (2024-2025) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 52 | 52 | 35% | 53% | Off Ice | C1 | 9% | 4636.5898 | 2457.3926 | Tosi - 25% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 450 | 3 | 3367.1676 | 3367.1676 | 0 | 0 | 3367.1676 | 3367.1676 | 3367.1676 | 3367.1676 | 3367.1676 | 3367.1676 | 3367.1676 | 3367.1676 | 33671.6764 | 17845.9885 | 51517.6649 | 3030.4509 | 1606.139 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51517.6649 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 24941.9825 | 0 | 0 | 0 | 8729.6939 | 0 | 1.2.1
1.2 | 1.2.1.3.4.3 | PSL | Installation Engineering Support (2024-2025) | Installation Engineering Support (2024-2025) |  | Labor Hours | Labor - LoE | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 674.1797 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 44 | 0.29333 | 490.3125 | 490.3125 | 490.3125 | 0 | 490.3125 | 490.3125 | 490.3125 | 490.3125 | 490.3125 | 490.3125 | 490.3125 | 490.3125 | 5393.4372 | 0 | 5393.4372 | 674.1797 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5393.4372 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 5393.4372 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.3.5.1 | UW | String Management and Controls (2025-2026) | String Management and Controls (2025-2026) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 52 | 52 | 35% | 53% | Off Ice | C1 | 9% | 189.4511 | 100.4091 | Tosi - 5% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 |  |  |  | 12 | [7 empty] | 18 | 0.12 | 458.6082 | 0 | 0 | 0 | 917.2165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1375.8247 | 729.1871 | 2105.0118 | 123.8242 | 65.6268 | 2105.0118 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 1019.1294 | 0 | 0 | 0 | 356.6953 | 1.2.1
1.2 | 1.2.1.3.5.2 | UW | Installation Engineering (2025-2026) | Installation Engineering (2025-2026) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 52 | 52 | 35% | 53% | Off Ice | C1 | 9% | 810.4295 | 429.5277 | Tosi - 20% | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 |  |  |  | 30 | 16 | 16 | [5 empty] | 77 | 0.51333 | 1146.5206 | 0 | 0 | 0 | 2293.0412 | 1222.9553 | 1222.9553 | 0 | 0 | 0 | 0 | 0 | 5885.4723 | 3119.3003 | 9004.7726 | 529.6925 | 280.737 | 9004.7726 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 4359.6091 | 0 | 0 | 0 | 1525.8632 | 1.2.1
1.2 | 1.2.1.4.5 | PSL | 2022-23 Quality & Safety | 2022-23 Quality & Safety HA Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 2114.505 | 0 | 12 sessions * 2 hr/session each year 6 people = 144 hr/yr | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 144 | 0.96 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 1409.67 | 16916.04 | 0 | 16916.04 | 2114.505 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16916.04 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 16916.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.4.6 | PSL | 2023-24 Quality & Safety | 2023-24 Quality & Safety HA Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 2159.9669 | 0 | 12 sessions * 2 hr/session each year 6 people = 144 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 144 | 0.96 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 1439.9779 | 17279.7349 | 0 | 17279.7349 | 2159.9669 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17279.7349 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 17279.7349 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.4.7 | PSL | 2024-25 Quality & Safety | 2025-25 Quality & Safety HA Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 2206.4061 | 0 | 12 sessions * 2 hr/session each year 6 people = 144 hr/yr | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 144 | 0.96 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 1470.9374 | 17651.2492 | 0 | 17651.2492 | 2206.4061 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17651.2492 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 17651.2492 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.4.8 | PSL | 2025-26 Quality & Safety | 2025-26 Quality & Safety HA Review |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 375.6406 | 0 | 2 sessions * 2 hr/session each year 6 people = 24 hr/yr October & November | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | [10 empty] | 24 | 0.16 | 1502.5626 | 1502.5626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3005.1252 | 0 | 3005.1252 | 375.6406 | 0 | 3005.1252 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 3005.1252 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.5.5 | PSL | 2022-23 Travel (non-deployment) | 2022-23 Travel (non-deployment) | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 1735.02 | 919.5606 | Collab Mtg (international): 1x $3600 ASC/Denver (domestic): 5x $1800 = $9k Total = 3.6k+9k = 12.6k | [5 empty] | 9000 | 3600 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 3600 | 0 | 0 | 0 | 0 | 0 | 12600 | 6678 | 19278 | 1134 | 601.02 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19278 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.5.6 | PSL | 2023-24 Travel (non-deployment) | 2023-24 Travel (non-deployment) | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 1735.02 | 919.5606 | Collab Mtg (international): 1x $3600 ASC/Denver (domestic): 5x $1800 = $9k Total = 3.6k+9k = 12.6k | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 9000 | 3600 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 3600 | 0 | 0 | 0 | 0 | 0 | 12600 | 6678 | 19278 | 1134 | 601.02 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19278 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.5.7 | PSL | 2024-25 Travel (non-deployment) | 2024-25 Travel (non-deployment) | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 1735.02 | 919.5606 | Collab Mtg (international): 1x $3600 ASC/Denver (domestic): 5x $1800 = $9k Total = 3.6k+9k = 12.6k | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 9000 | 3600 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 3600 | 0 | 0 | 0 | 0 | 0 | 12600 | 6678 | 19278 | 1134 | 601.02 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19278 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.11 | PSL | Crate Control Systems Components Shipment 1 - DNF (Vessel) | Crate Control Systems Components Shipment 1 - DNF (Vessel) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 234.945 | 0 |  | 16 | [11 empty] | 16 | 0.10667 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 234.945 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.11 | PSL | Crate Control Systems Components Shipment 1 - DNF (Vessel) | Crate Control Systems Components Shipment 1 - DNF (Vessel) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 160.2675 | 84.9418 | Collapsible Bulk Container, Black, 48 inH x 45 inL x 41 inW, 1EA w/ lid $838 W.W. Grainger Item #36XE25 & #1XGG9 | 838 | [11 empty] | 0 | 0 | 838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838 | 444.14 | 1282.14 | 104.75 | 55.5175 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1282.14 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.20 | PSL | Load Container C (Main/Combo Cables, Bull Wheel, Hose Heating Components, ARA Drill Components - Crate 2) (Vessel) | Load Container C (Main/Combo Cables, Bull Wheel, Hose Heating Components, ARA Drill Components - Crate 2) (Vessel) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 294.9581 | 0 |  | 30 | [11 empty] | 30 | 0.2 | 2359.665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2359.665 | 0 | 2359.665 | 294.9581 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2359.665 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2359.665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.20 | PSL | Load Container C (Main/Combo Cables, Bull Wheel, Hose Heating Components, ARA Drill Components - Crate 2) (Vessel) | Load Container C (Main/Combo Cables, Bull Wheel, Hose Heating Components, ARA Drill Components - Crate 2) (Vessel) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 1147.5 | 608.175 | $6000 estimated for 20' container purchase with delivery. PY3 container procurement was 6k. | 6000 | [11 empty] | 0 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 3180 | 9180 | 750 | 397.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9180 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.21 | PSL | Crate Drill Heads, Spare Parts to PTH (Vessel) Store in ICL - DNF | Crate Drill Heads, Spare Parts to PTH (Vessel) Store in ICL - DNF |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 0 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.22 | PSL | Crate Control Systems Components Shipment 2 - DNF (Comsur) | Crate Control Systems Components Shipment 2 - DNF (Comsur) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 235.9665 | 0 | [9 empty] | 24 |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 0 | 0 | 0 | 1887.732 | 0 | 1887.732 | 235.9665 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1887.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.22 | PSL | Crate Control Systems Components Shipment 2 - DNF (Comsur) | Crate Control Systems Components Shipment 2 - DNF (Comsur) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 320.535 | 169.8836 | Collapsible Bulk Container, Black, 48 inH x 45 inL x 41 inW, 1EA w/ lid $838 W.W. Grainger Item #36XE25 & #1XGG9 | [8 empty] | 1676 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1676 | 0 | 0 | 0 | 1676 | 888.28 | 2564.28 | 209.5 | 111.035 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2564.28 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.23 | PSL | Crate Elect. Distribution System Components (ComSur) | Crate Elect. Distribution System Components (ComSur) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 117.4725 | 0 | [10 empty] | 4 | 4 |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 469.89 | 469.89 | 0 | 939.78 | 0 | 939.78 | 117.4725 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.24 | PSL | Crate MDS Internal Hoses & Spares Resupply (FS2 Resupply Container - Comsur) | Crate MDS Internal Hoses & Spares Resupply (FS2 Resupply Container - Comsur) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 80.3466 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 0 | 0 | 0 | 642.7727 | 0 | 642.7727 | 80.3466 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.25 | PSL | Crate Drill Filtration Resupply (FS2 Resupply Container - Comsur) | Crate Drill Filtration Resupply (FS2 Resupply Container - Comsur) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 80.3466 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 0 | 0 | 0 | 642.7727 | 0 | 642.7727 | 80.3466 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.26 | PSL | Crate FS2 SES Interconnect Resupply (FS2 Resupply Container - Comsur) | Crate FS2 SES Interconnect Resupply (FS2 Resupply Container - Comsur) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 80.3466 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 0 | 0 | 0 | 642.7727 | 0 | 642.7727 | 80.3466 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.28 | PSL | Load FS2 Resupply Container (FS2 Comsur) | Load FS2 Resupply Container (Comsur) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 160.6932 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 16 |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 0 | 0 | 1285.5455 | 0 | 1285.5455 | 160.6932 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285.5455 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1285.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.29 | PSL | Crate Repair/Replacement Components Resupply (FS2 Resupply Container - Comsur) | Crate Repair/Replacement Components Resupply (FS2 Resupply Container - Comsur) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 80.3466 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 8 |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 0 | 0 | 642.7727 | 0 | 642.7727 | 80.3466 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642.7727 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 642.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.2.30 | PSL | Crate Control Systems Components Shipment 3 - DNF (Comsur) | Crate Control Systems Components Shipment 3 - DNF (Vessel) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 164.1481 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 16 |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1313.1847 | 0 | 0 | 1313.1847 | 0 | 1313.1847 | 164.1481 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1313.1847 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1313.1847 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.3.1 | PSL | FS0 - Ship Control Systems Components Shipment 1, ARA System DNF, Drill Heads, & Container C (Vessel) | FS0 - Ship Control Systems Components Shipment 1, ARA System Parts, Drill Heads, & Container C (Vessel) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 765 | 405.45 | Estimated based on November 2021 trucking invoice (SEKO) - October '22 is a full 53' trailer load | 4000 | [11 empty] | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 2120 | 6120 | 500 | 265 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6120 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.3.1 | PSL | FS0 - Ship Control Systems Components Shipment 1, ARA System DNF, Drill Heads, & Container C (Vessel) | FS0 - Ship Control Systems Components Shipment 1, ARA System Parts, Drill Heads, & Container C (Vessel) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 191.25 | 101.3625 | Estimated based on 2021 Reynolds & Reynolds loading support invoice | 1000 | [11 empty] | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 530 | 1530 | 125 | 66.25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.3.2 | PSL | FS1 - Ship Control Systems Components Shipment 2 - DNF (Comsur) | FS1 - Ship Control Systems Components Shipment 2 - DNF (Comsur) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 669.375 | 354.7688 | Estimated based on November 2021 trucking invoice (SEKO) - August '23 is a partial truck load | [10 empty] | 3500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 3500 | 1855 | 5355 | 437.5 | 231.875 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.3.3 | PSL | FS2 - Ship Control Systems Components Shipment 3, Refit Resupply Container (Comsur) | FS2 - Ship Control Systems Components Shipment 3, Resupply Container (Comsur) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 478.125 | 253.4062 | Estimated based on November 2021 trucking invoice (SEKO) - August '24 is a quarter truck load | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 2500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 1325 | 3825 | 312.5 | 165.625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3825 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.3.4 | PSL | FS3 - Ship Resupply Container (Comsur) | FS3 - Ship Resupply Container (Comsur) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 478.125 | 253.4062 | Estimated based on November 2021 trucking invoice (SEKO) - August '25 is a quarter truck load | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 2500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 1325 | 3825 | 312.5 | 165.625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3825 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.4.1 | PSL | Crate Sensor Handling Structure | Crate (Installation): Sensor Handling Structure (Vessel) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 573.75 | 304.0875 |  | 3000 | [11 empty] | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 1590 | 4590 | 375 | 198.75 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4590 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.4.2 | PSL | Crate Installation Kits | Crate (Installation): Installation Kits (Vessel) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 314.622 | 0 | [9 empty] | 16 | 16 |  |  | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 1258.488 | 0 | 0 | 2516.976 | 0 | 2516.976 | 314.622 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2516.976 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2516.976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.4.2 | PSL | Crate Installation Kits | Crate (Installation): Installation Kits (Vessel) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 935.9775 | 496.0681 | 7x 34"H x 48"L x 40"Wx 7crates at $699/each Grainger 1XGG6 | [8 empty] | 2447 | 2447 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2447 | 2447 | 0 | 0 | 4894 | 2593.82 | 7487.82 | 611.75 | 324.2275 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7487.82 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.4.3 | PSL | Crate String Weights | Crate (Installation): String Weights (Vessel) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C2 | 12.5% | 78.6555 | 0 | 2x $517/each Collapsible Bulk Container, Black, 34 inH x 48 inL x 45 inW, 1EA Item # 39H823 |  |  |  | 8 | [8 empty] | 8 | 0.053333 | 0 | 0 | 0 | 629.244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629.244 | 0 | 629.244 | 78.6555 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 629.244 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 629.244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.4.3 | PSL | Crate String Weights | Crate (Installation): String Weights (Vessel) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 197.7525 | 104.8088 | $1317 estimated for three 40" x 48" x 25" bulk containers with lids to package hardware for shipping |  |  |  | 1034 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 1034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1034 | 548.02 | 1582.02 | 129.25 | 68.5025 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1582.02 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.4.4 | PSL | Crate Science Equipment FS2 (SPAT, IME, Pressure Sensors, Laser Rangers) | Crate (Installation): Science Equipment FS2 (SPAT, IME, Laser Rangers, Pressure Sensors)(Comsur) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 141.9075 | 75.211 | $371/each estimated for two 45" x 48" x 44" bulk containers with lids to package hardware for shipping | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 742 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 742 | 0 | 0 | 0 | 742 | 393.26 | 1135.26 | 92.75 | 49.1575 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1135.26 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.4.5 | PSL | Crate Science Equipment FS3 | Crate (Installation): Science Equipment FS3 (Comsur) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 141.9075 | 75.211 | $371/each estimated for two 45" x 48" x 44" bulk containers with lids to package hardware for shipping | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 742 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 742 | 0 | 0 | 742 | 393.26 | 1135.26 | 92.75 | 49.1575 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1135.26 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.5.1 | PSL | Ship Sensor Handling Structure | Ship (Installation): Sensor Handling Structure (Vessel) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 573.75 | 304.0875 | DHF ships on truck with Container C | 3000 | [11 empty] | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 1590 | 4590 | 375 | 198.75 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4590 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.5.2 | PSL | Ship Installation Kits | Ship (Installation): Installation Kits (Vessel) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 392.445 | 207.9958 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052 | [11 empty] | 0 | 0 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2052 | 1087.56 | 3139.56 | 256.5 | 135.945 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3139.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.5.3 | PSL | Ship String Weights | Ship (Installation): String Weights (Vessel) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 99.45 | 52.7085 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | [11 empty] | 0 | 0 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | 275.6 | 795.6 | 65 | 34.45 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 795.6 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.5.4 | PSL | Ship Science Crate FS2 (SPAT, IME, Pressure Sensors, Laser Rangers) | Ship (Installation): Science Equipment FS2 (SPAT, IME, Laser Rangers, Pressure Sensors) (Comsur) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 191.25 | 101.3625 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 530 | 1530 | 125 | 66.25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.1.6.5.5 | PSL | Ship Science Crate FS3 | Ship (Installation): Science Equipment FS3 (Comsur) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 191.25 | 101.3625 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 530 | 1530 | 125 | 66.25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.1
1.2 | 1.2.2.1.6 | PSL | Procure MHP Upgrade, Sub-Components, Spares (PY5) | MHP: Procure MHP Upgrade, Sub-Components, Spares (PY5) | Gibson | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 | [7 empty] | 12 | 12 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 1409.67 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.1.6 | PSL | Procure MHP Upgrade, Sub-Components, Spares (PY5) | MHP: Procure MHP Upgrade, Sub-Components, Spares (PY5) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1000 | 0 | [7 empty] | 2500 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 1000 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.1.7 | PSL | Develop HPU2 Integrate Plan | MHP: Develop HPU2 Integrate Plan |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 2099.9678 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 25 | 25 |  |  |  | 50 | 0.33333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2999.954 | 2999.954 | 0 | 0 | 0 | 5999.9079 | 0 | 5999.9079 | 2099.9678 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5999.9079 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 5999.9079 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.1.8 | PSL | Procure and Assemble HPU2 Integration Components | MHP: Procure and Assemble HPU2 Integration Components |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 20 | 20 |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.1.8 | PSL | Procure and Assemble HPU2 Integration Components | MHP: Procure and Assemble HPU2 Integration Components |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 642.7727 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 20 | 20 |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1606.9319 | 1606.9319 | 0 | 0 | 3213.8637 | 0 | 3213.8637 | 642.7727 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3213.8637 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.1.8 | PSL | Procure and Assemble HPU2 Integration Components | MHP: Procure and Assemble HPU2 Integration Components |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 2000 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 5000 | 5000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 10000 | 0 | 10000 | 2000 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.1.10 | PSL | Procure MHP Upgrade, Sub-Components, Spares (PY6) | MHP: Procure Upgrade, Sub-Components, Spares (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 575.9912 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 12 | 12 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | 575.9912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.1.10 | PSL | Procure MHP Upgrade, Sub-Components, Spares (PY6) | MHP: Procure Upgrade, Sub-Components, Spares (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1000 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2500 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 1000 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.2.4 | PSL | Procure and Upgrade Control Boxes (PY6) | PHS: Procure and Upgrade Control Boxes (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1919.9705 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | 1919.9705 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.2.4 | PSL | Procure and Upgrade Control Boxes (PY6) | PHS: Procure and Upgrade Control Boxes (PY6) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 1285.5455 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 3213.8637 | 0 | 0 | 0 | 0 | 0 | 6427.7275 | 0 | 6427.7275 | 1285.5455 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6427.7275 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 6427.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.2.4 | PSL | Procure and Upgrade Control Boxes (PY6) | PHS: Procure and Upgrade Control Boxes (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 800 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2000 | 2000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 800 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.2.5 | PSL | Procure Upgrade, Sub-Components, Spares (PY6) | PHS: Procure Upgrade, Sub-Components, Spares (PY6) |  | Labor Hours | Labor Hours | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 575.9912 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 12 | 12 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | 575.9912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.2.5 | PSL | Procure Upgrade, Sub-Components, Spares (PY6) | PHS: Procure Upgrade, Sub-Components, Spares (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1000 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 2500 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 1000 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.3.8 | PSL | Procure ARA Fueling Hose & Nozzle (PY5) | Fuel Tower: Procure ARA Fueling Hose & Nozzle (PY5) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [6 empty] | 8 | [6 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.3.8 | PSL | Procure ARA Fueling Hose & Nozzle (PY5) | Fuel Tower: Procure ARA Fueling Hose & Nozzle (PY5) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 888.4 | 0 | [6 empty] | 4442 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4442 | 0 | 0 | 0 | 0 | 0 | 0 | 4442 | 0 | 4442 | 888.4 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4442 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.3.9 | PSL | Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) | Fuel Tower: Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [6 empty] | 16 | [6 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.3.9 | PSL | Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) | Fuel Tower: Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 251.6976 | 0 | [6 empty] | 16 | [6 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 1258.488 | 251.6976 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.3.9 | PSL | Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) | Fuel Tower: Procure Racor Fuel Filter Elements and Gauges Replacements (PY5) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 300 | 0 | [6 empty] | 1500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 300 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.3.10 | PSL | Procure Fuel system Upgrade/Maintenance Subcomponents (PY6) | Fuel Tower: Procure Fuel system Upgrade/Maintenance Subcomponents (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 575.9912 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 12 | 12 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | 575.9912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.3.10 | PSL | Procure Fuel system Upgrade/Maintenance Subcomponents (PY6) | Fuel Tower: Procure Fuel system Upgrade/Maintenance Subcomponents (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 480 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1200 | 1200 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 2400 | 480 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.3.11 | PSL | Procure MHP Fuel Heat Exchangers Replacements (PY6) | Fuel Tower: Procure MHP Fuel Heat Exchangers Replacements (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 383.9941 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 16 | [5 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 1919.9705 | 383.9941 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.2.3.11 | PSL | Procure MHP Fuel Heat Exchangers Replacements (PY6) | Fuel Tower: Procure MHP Fuel Heat Exchangers Replacements (PY6) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 2056.6 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 10283 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10283 | 0 | 0 | 0 | 0 | 0 | 10283 | 0 | 10283 | 2056.6 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10283 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.2
1.2 | 1.2.3.1.5 | PSL | Crescent Emergency Repair Kit Assembly (PY6) | Tower Ops: Crescent Emergency Repair Kit Assembly | Lemery | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | [7 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.5 | PSL | Crescent Emergency Repair Kit Assembly (PY6) | Tower Ops: Crescent Emergency Repair Kit Assembly | Lemry | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 500 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 500 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.6 | PSL | Examine Interface between Dust Logger and Tower & Address as Needed | Tower Ops: Examine Interface between Dust Logger and Tower & Address as Needed |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1644.615 | 0 | [10 empty] | 20 | 20 |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 0 | 4698.9 | 0 | 4698.9 | 1644.615 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.6 | PSL | Examine Interface between Dust Logger and Tower & Address as Needed | Tower Ops: Examine Interface between Dust Logger and Tower & Address as Needed |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 840 | 0 | [10 empty] | 1200 | 1200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 0 | 2400 | 0 | 2400 | 840 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.7.2 | PSL | Calibration Load Cell | Tower Ops: Load Cell Calibration |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 117.4725 | 0 | [5 empty] | 8 | [7 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 117.4725 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.7.2 | PSL | Calibration Load Cell | Tower Ops: Load Cell Calibration |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 223.625 | 0 | [5 empty] | 1789 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1789 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1789 | 0 | 1789 | 223.625 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1789 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.7.3 | PSL | Calibration Load Cell Rigging | Tower Ops: Identify/Procure: Load Cell Rigging Calibration |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 117.4725 | 0 | [6 empty] | 8 | [6 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 117.4725 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.7.3 | PSL | Calibration Load Cell Rigging | Tower Ops: Identify/Procure: Load Cell Rigging Calibration |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 152.5 | 0 | [6 empty] | 1220 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | 0 | 0 | 1220 | 0 | 1220 | 152.5 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.8 | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [9 empty] | 16 |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.8 | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [9 empty] | 8 |  | 8 |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.8 | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY5) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 2046.4 | 0 | Driller tape: 4 cases @ 30 rolls/case = 120 rolls $50/roll -> $6k | [8 empty] | 5232 |  | 5000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5232 | 0 | 5000 | 0 | 10232 | 0 | 10232 | 2046.4 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10232 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.9 | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 383.9941 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 16 |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 0 | 0 | 1919.9705 | 0 | 1919.9705 | 383.9941 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.9 | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) |  | Labor Hours | Labor Hours | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 383.9941 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 16 |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 0 | 1919.9705 | 0 | 1919.9705 | 383.9941 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.9 | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY6) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1846.4 | 0 | Driller tape: 4 cases @ 30 rolls/case = 120 rolls $50/roll -> $6k | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 5232 | 4000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5232 | 4000 | 0 | 0 | 9232 | 0 | 9232 | 1846.4 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9232 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.10 | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 392.25 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 16 |  |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 0 | 0 | 0 | 0 | 1961.2499 | 0 | 1961.2499 | 392.25 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1961.2499 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.10 | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 392.25 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 16 |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 0 | 0 | 0 | 1961.2499 | 0 | 1961.2499 | 392.25 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1961.2499 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.1.10 | PSL | Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) | Tower Ops: Identify/Procure: TOS & Tower Hardware, Repair Parts (PY7) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 4598.4 | 0 | Driller tape: 50 rolls/hole x 7 holes = 350 rolls Plus 3 cases @ 30 rolls/case = 440 rolls $50/roll -> $22k | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 20492 | 2500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20492 | 2500 | 0 | 0 | 0 | 22992 | 0 | 22992 | 4598.4 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22992 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.2.10 | PSL | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  | 24 | [11 empty] | 24 | 0.16 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.2.10 | PSL | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 | Drillheads: Prepare Crates, Spares, Tools, & Docs x3 |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 377.5464 | 0 |  | 24 | [11 empty] | 24 | 0.16 | 1887.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 0 | 1887.732 | 377.5464 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1887.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.3.9 | PSL | Reels & Winches: Drill Reels Sliprings - Final Testing & Prep | Reels & Winches: Drill Reels Sliprings - final testing and prep |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [9 empty] | 16 |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.3.10 | PSL | Reels & Winches: TU20 Sliprings - Spec, Procure, Test | Reels & Winches: TU20 Sliprings - spec, procure, test |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 3759.12 | 0 | [6 empty] | 80 | 80 | [5 empty] | 160 | 1.0667 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 18795.6 | 0 | 18795.6 | 3759.12 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18795.6 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 18795.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.3.10 | PSL | Reels & Winches: TU20 Sliprings - Spec, Procure, Test | Reels & Winches: TU20 Sliprings - spec, procure, test |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1682.6 | 0 | [6 empty] | 8413 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8413 | 0 | 0 | 0 | 0 | 0 | 0 | 8413 | 0 | 8413 | 1682.6 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8413 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.3.11 | PSL | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1919.9705 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 80 | [6 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | 1919.9705 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.3.11 | PSL | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 642.7727 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | [6 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 0 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 0 | 3213.8637 | 642.7727 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3213.8637 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.3.3.11 | PSL | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes | Reels & Winches: Reel Components & Spares (PY6). TU20 brakes) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1754 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 8770 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8770 | 0 | 0 | 0 | 0 | 0 | 0 | 8770 | 0 | 8770 | 1754 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8770 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.3
1.2 | 1.2.4.1.8 | PSL | Coordination with USAP IT (PY5) | Architecture: Coordination with USAP IT (PY5) (station connectivity, internet, phone) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [9 empty] | 20 |  |  |  | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.1.9 | PSL | CS Drawings & Documentation (PY5) | Architecture: CS Drawings & Documentation (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 | [10 empty] | 8 | 16 | 8 | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1879.56 | 939.78 | 3759.12 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.1.10 | PSL | CS Drawings & Documentation (PY6) | Architecture: CS Drawings & Documentation (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 767.9882 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 16 | 16 | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1919.9705 | 3839.9411 | 0 | 3839.9411 | 767.9882 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3839.9411 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3839.9411 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.1.11 | PSL | CS Drawings & Documentation (PY7) | Architecture: CS Drawings & Documentation (PY7) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 784.5 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 16 | 16 | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1961.2499 | 1961.2499 | 3922.4998 | 0 | 3922.4998 | 784.5 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3922.4998 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 3922.4998 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.1.12 | PSL | CS Drawings & Documentation (PY8) | Architecture: CS Drawings & Documentation (PY8) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 801.3667 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 32 | [6 empty] | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 4006.8336 | 0 | 0 | 0 | 0 | 0 | 0 | 4006.8336 | 0 | 4006.8336 | 801.3667 | 0 | 4006.8336 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 4006.8336 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.2.5 | PSL | Procure System Sensors (PY5) | Controls Hardware: Procure System Sensors (PY5) |  | Labor Hours | Labor Hours | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 |  | 32 | [11 empty] | 32 | 0.21333 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.2.5 | PSL | Procure System Sensors (PY5) | Controls Hardware: Procure System Sensors (PY5) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 3472 | 0 |  | 27776 | [11 empty] | 0 | 0 | 27776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27776 | 0 | 27776 | 3472 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27776 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.11.1 | PSL | CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 234.945 | 0 | [5 empty] | 2 | 4 | 4 | [5 empty] | 10 | 0.066667 | 0 | 0 | 0 | 0 | 234.945 | 469.89 | 469.89 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 0 | 1174.725 | 234.945 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1174.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.11.1 | PSL | CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Ignition Servers (3x: DCC, TOS1, TOS2) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 583.875 | 0 | [5 empty] | 4671 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4671 | 0 | 4671 | 583.875 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4671 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.11.2 | PSL | CS HW Production Database Server (1x: DCC) | Network Controllers: CS HW Production Database Server (1x: DCC) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 234.945 | 0 | [5 empty] | 2 | 4 | 4 | [5 empty] | 10 | 0.066667 | 0 | 0 | 0 | 0 | 234.945 | 469.89 | 469.89 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 0 | 1174.725 | 234.945 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1174.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.11.2 | PSL | CS HW Production Database Server (1x: DCC) | Network Controllers: CS HW Production Database Server (1x: DCC) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 363.25 | 0 | [5 empty] | 2906 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2906 | 0 | 2906 | 363.25 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2906 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.11.3 | PSL | CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [6 empty] | 16 | [6 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.11.3 | PSL | CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Peripherals (3x sets: DCC, TOS1, TOS2) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 2190 | 0 | [6 empty] | 17520 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17520 | 0 | 0 | 0 | 0 | 0 | 0 | 17520 | 0 | 17520 | 2190 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17520 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.11.4 | PSL | CS HW DCC Core Switch & Security Appliance | Network Controllers: CS HW DCC Core Switch & Security Appliance |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [6 empty] | 8 | [6 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.11.4 | PSL | CS HW DCC Core Switch & Security Appliance | Network Controllers: CS HW DCC Core Switch & Security Appliance |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 2475.375 | 0 | [6 empty] | 19803 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19803 | 0 | 0 | 0 | 0 | 0 | 0 | 19803 | 0 | 19803 | 2475.375 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19803 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.11.5 | PSL | CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [7 empty] | 16 | 10 | 10 |  |  |  | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1174.725 | 1174.725 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.11.5 | PSL | CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) | Network Controllers: CS HW Production Main PLC - PLC (redundant), I/O, network, UPS, in a box (3x: DCC, TOS1, TOS2) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 3733.375 | 0 | [7 empty] | 29867 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29867 | 0 | 0 | 0 | 0 | 0 | 29867 | 0 | 29867 | 3733.375 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29867 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.13 | PSL | CS HW PY6 Resupply | Network Controllers: CS HW PY6 Resupply |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3359.9484 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | 3359.9484 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.13 | PSL | CS HW PY6 Resupply | Network Controllers: CS HW PY6 Resupply |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1400 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2000 | 2000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 1400 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.14 | PSL | CS HW PY7 Resupply | Network Controllers: CS HW PY7 Resupply |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3432.1873 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 40 | 40 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 4903.1248 | 4903.1248 | 0 | 0 | 0 | 0 | 0 | 9806.2495 | 0 | 9806.2495 | 3432.1873 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.2495 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 9806.2495 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.2.14 | PSL | CS HW PY7 Resupply | Network Controllers: CS HW PY7 Resupply |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1400 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2000 | 2000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 1400 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.4 | PSL | PLC & Software Development (w/sub-tasks) | Controls Software: PLC & Software Development (w/sub-tasks) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2849.6479 | 0 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 60 | 0.4 | 1174.725 | 0 | 1174.725 | 0 | 1174.725 | 0 | 1174.725 | 0 | 1174.725 | 0 | 1174.725 | 0 | 7048.35 | 0 | 7048.35 | 1409.67 | 0 | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  | 60 | 0.4 | 1199.9816 | 0 | 1199.9816 | 0 | 1199.9816 | 0 | 1199.9816 | 0 | 1199.9816 | 0 | 1199.9816 | 0 | 7199.8895 | 0 | 7199.8895 | 1439.9779 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14248.2395 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 7048.35 | 7199.8895 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.5 | PSL | SCADA Monitoring Software and Server Procurement | Controls Software: SCADA Monitoring Software Procurement - Server |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 293.6812 | 0 |  | 20 | [11 empty] | 20 | 0.13333 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | 293.6812 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.5 | PSL | SCADA Monitoring Software and Server Procurement | Controls Software: SCADA Monitoring Software - Server |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 287.125 | 0 |  | 2297 | [11 empty] | 0 | 0 | 2297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2297 | 0 | 2297 | 287.125 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2297 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.1.1 | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen MHP: Local-Panel MDS-specific HMI (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [7 empty] | 20 | [5 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.1.2 | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen MHP: Local-Panel MDS-specific HMI (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 479.9926 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 20 | [5 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 0 | 2399.9632 | 479.9926 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.1.3 | PSL | DCC-based SCADA UI (PY5) | Operator Screen MHP: DCC-based SCADA UI (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 | [7 empty] | 80 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.1.4 | PSL | DCC-based SCADA UI (PY6) | Operator Screen MHP: DCC-based SCADA UI (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1919.9705 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 80 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | 1919.9705 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.2.1 | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen Fuel System: Local-Panel MDS-specific HMI (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [8 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.2.2 | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen Fuel System: Local-Panel MDS-specific HMI (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.2.3 | PSL | DCC-based SCADA (PY5) | Operator Screen Fuel System: DCC-based SCADA (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [8 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.2.4 | PSL | DCC-based SCADA (PY6) | Operator Screen Fuel System: DCC-based SCADA (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.3.1 | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen Gensets: Local-Panel MDS-specific HMI (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [9 empty] | 8 |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.3.2 | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen Gensets: Local-Panel MDS-specific HMI (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.3.3 | PSL | DCC-based SCADA (PY5) | Operator Screen Gensets: DCC-based SCADA (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 281.934 | 0 | [9 empty] | 12 |  |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 0 | 0 | 0 | 1409.67 | 0 | 1409.67 | 281.934 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.3.4 | PSL | DCC-based SCADA (PY6) | Operator Screen Gensets: DCC-based SCADA (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 287.9956 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 12 |  |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 0 | 0 | 0 | 1439.9779 | 0 | 1439.9779 | 287.9956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.4.3 | PSL | DCC-based SCADA (PY5) | Operator Screen Rodwell: DCC-based SCADA (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [10 empty] | 40 |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.4.4 | PSL | DCC-based SCADA (PY6) | Operator Screen Rodwell: DCC-based SCADA (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 40 |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.5.1 | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen HPP: Local-Panel MDS-specific HMI (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 422.901 | 0 | [11 empty] | 18 |  | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2114.505 | 0 | 2114.505 | 0 | 2114.505 | 422.901 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2114.505 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2114.505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.5.2 | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen HPP: Local-Panel MDS-specific HMI (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 431.9934 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 18 |  | 18 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159.9669 | 0 | 2159.9669 | 0 | 2159.9669 | 431.9934 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159.9669 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2159.9669 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.5.3 | PSL | DCC-based SCADA (PY5) | Operator Screen HPP: DCC-based SCADA (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [11 empty] | 40 |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.5.4 | PSL | DCC-based SCADA (PY6) | Operator Screen HPP: DCC-based SCADA (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 40 |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | 0 | 4799.9263 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.6.1 | PSL | Local-Panel MDS-specific HMI (PY5) | Operator Screen PHS: Local-Panel MDS-specific HMI (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [12 empty] | 16 | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.6.2 | PSL | Local-Panel MDS-specific HMI (PY6) | Operator Screen PHS: Local-Panel MDS-specific HMI (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 383.9941 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 16 | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1919.9705 | 0 | 1919.9705 | 383.9941 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.6.3 | PSL | DCC-based SCADA (PY5) | Operator Screen PHS: DCC-based SCADA (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [12 empty] | 40 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.9.6.4 | PSL | DCC-based SCADA (PY6) | Operator Screen PHS: DCC-based SCADA (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 40 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 4799.9263 | 0 | 4799.9263 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.1 | PSL | SCADA - DrillHead (PY5) | TOS Operator Screen: SCADA - DrillHead (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [8 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.2 | PSL | SCADA - DrillHead (PY6) | TOS Operator Screen: SCADA - DrillHead (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.3 | PSL | SCADA - Drill_Settings (PY5) | TOS Operator Screen: SCADA - Drill_Settings (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [8 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.4 | PSL | SCADA - Drill_Settings (PY6) | TOS Operator Screen: SCADA - Drill_Settings (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 |  |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.5 | PSL | SCADA - Drilling_Drill Control (PY5) | TOS Operator Screen: SCADA - SCADA - Drilling_Drill Control (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 281.934 | 0 | [9 empty] | 12 |  |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 0 | 0 | 0 | 1409.67 | 0 | 1409.67 | 281.934 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.6 | PSL | SCADA - Drilling_Drill Control (PY6) | TOS Operator Screen: SCADA - Drilling_Drill Control (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 287.9956 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 12 |  |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 0 | 0 | 0 | 1439.9779 | 0 | 1439.9779 | 287.9956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.7 | PSL | SCADA - Drilling_Cable Level Wind (PY5) | TOS Operator Screen: SCADA - SCADA - Drilling_Cable Level Wind (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 281.934 | 0 | [10 empty] | 12 |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 0 | 0 | 1409.67 | 0 | 1409.67 | 281.934 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.8 | PSL | SCADA - Drilling_Cable Level Wind (PY6) | TOS Operator Screen: SCADA - Drilling_Cable Level Wind (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 287.9956 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 12 |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 0 | 0 | 1439.9779 | 0 | 1439.9779 | 287.9956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.9 | PSL | SCADA - Drilling_Hose Level Wind (PY5) | TOS Operator Screen: SCADA - Drilling_Hose Level Wind (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 281.934 | 0 | [10 empty] | 12 |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 0 | 0 | 1409.67 | 0 | 1409.67 | 281.934 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1409.67 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.10 | PSL | SCADA - Drilling_Hose Level Wind (PY6) | TOS Operator Screen: SCADA - Drilling_Hose Level Wind (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 287.9956 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 12 |  |  | 12 | 0.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 0 | 0 | 1439.9779 | 0 | 1439.9779 | 287.9956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.11 | PSL | SCADA - Return Water Pump (PY5) | TOS Operator Screen: SCADA - Return Water Pump (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [11 empty] | 8 |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.12 | PSL | SCADA - Return Water Pump (PY6) | TOS Operator Screen: SCADA - Return Water Pump (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 8 |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.13 | PSL | SCADA - Deployment - Cable (PY5) | TOS Operator Screen: SCADA - Deployment - Cable (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [12 empty] | 8 | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.14 | PSL | SCADA - Deployment - Cable (PY6) | TOS Operator Screen: SCADA - Deployment - Cable (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 8 | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.15 | PSL | SCADA - Deployment Settings (PY5) | TOS Operator Screen: SCADA - Deployment Settings (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 234.945 | 0 | [12 empty] | 10 | 10 | 0.066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 1174.725 | 0 | 1174.725 | 234.945 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1174.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.10.16 | PSL | SCADA - Deployment Settings (PY6) | TOS Operator Screen: SCADA - Deployment Settings (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 239.9963 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 10 | 10 | 0.066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1199.9816 | 0 | 1199.9816 | 239.9963 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1199.9816 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.11.1 | PSL | Build DCC dB schema (PY5) | TOS Operator Screen: Build DCC dB schema (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 | [7 empty] | 40 | 40 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 4698.9 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.11.2 | PSL | Build DCC dB schema (PY6) | TOS Operator Screen: Build DCC dB schema (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1919.9705 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 80 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | 1919.9705 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.11.3 | PSL | Build Drill dB schema (PY5) | TOS Operator Screen: Build Drill dB schema (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [8 empty] | 40 |  |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.11.4 | PSL | Build Drill dB schema (PY6) | TOS Operator Screen: Build Drill dB schema (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 40 |  |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.11.5 | PSL | Build Deploy dB schema (PY5) | TOS Operator Screen: Build Deploy dB schema (PY5) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 704.835 | 0 | [9 empty] | 30 |  |  |  | 30 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 0 | 0 | 0 | 3524.175 | 0 | 3524.175 | 704.835 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3524.175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.11.6 | PSL | Build Deploy dB schema (PY6) | TOS Operator Screen: Build Deploy dB schema (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 719.989 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 30 |  |  |  | 30 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599.9448 | 0 | 0 | 0 | 3599.9448 | 0 | 3599.9448 | 719.989 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599.9448 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3599.9448 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.12 | PSL | CS SW Standup Production Computing Hardware, Configure, Verify before Shipment (3x systems) (PY6) | Controls Software: CS SW Standup Production Computing Hardware, Configure, Verify before Shipment (3x systems) (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 5879.9098 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20 | 30 | 30 | 30 | 30 |  |  | 140 | 0.93333 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 3599.9448 | 3599.9448 | 3599.9448 | 3599.9448 | 0 | 0 | 16799.7422 | 0 | 16799.7422 | 5879.9098 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16799.7422 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 16799.7422 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.13 | PSL | CS SW MDS-specific HMI Refinement (PY7) | Controls Software: CS SW MDS-specific HMI Refinement (PY7) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3432.1873 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 20 | 20 | 20 | 20 |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 2451.5624 | 2451.5624 | 2451.5624 | 2451.5624 | 0 | 0 | 9806.2495 | 0 | 9806.2495 | 3432.1873 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.2495 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 9806.2495 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.14 | PSL | CS SW DCC-based SCADA Refinement (PY7) | Controls Software: CS SW DCC-based SCADA Refinement (PY7) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 5148.281 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 30 | 30 | 30 | 30 |  |  | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3677.3436 | 3677.3436 | 3677.3436 | 3677.3436 | 0 | 0 | 14709.3743 | 0 | 14709.3743 | 5148.281 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 14709.3743 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.15 | PSL | CS SW TOS-based SCADA Refinement (PY7) | Controls Software: CS SW TOS-based SCADA Refinement (PY7) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 5148.281 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 30 | 30 | 30 | 30 |  |  | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3677.3436 | 3677.3436 | 3677.3436 | 3677.3436 | 0 | 0 | 14709.3743 | 0 | 14709.3743 | 5148.281 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 14709.3743 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.3.16 | PSL | CS SW dB Refinement (PY7) | Controls Software: CS SW dB Refinement (PY7) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 5148.281 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 30 | 30 | 30 | 30 |  |  | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3677.3436 | 3677.3436 | 3677.3436 | 3677.3436 | 0 | 0 | 14709.3743 | 0 | 14709.3743 | 5148.281 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14709.3743 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 14709.3743 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.4.4 | PSL | Programming and Testing at PSL | Motor Drives: Programming and Testing at PSL (PSL_Engineer) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 3171.7575 | 0 | [6 empty] | 35 | 35 |  | 35 |  | 30 |  | 135 | 0.9 | 0 | 0 | 0 | 0 | 0 | 4111.5375 | 4111.5375 | 0 | 4111.5375 | 0 | 3524.175 | 0 | 15858.7875 | 0 | 15858.7875 | 3171.7575 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15858.7875 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 15858.7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.5.6 | PSL | E-Stop Resupply (PY6) | E-stop: Estop PY6 Resupply |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1007.9845 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 24 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | 1007.9845 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.5.6 | PSL | E-Stop Resupply (PY6) | E-stop: Estop PY6 Resupply |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 674.9114 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 24 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 0 | 0 | 0 | 0 | 1928.3182 | 0 | 1928.3182 | 674.9114 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1928.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.5.6 | PSL | E-Stop Resupply (PY6) | E-stop: Estop PY6 Resupply |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1750 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 1750 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.5.7 | PSL | E-Stop Resupply (PY7) | E-stop: Estop PY7 Resupply |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1029.6562 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 24 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 2941.8749 | 1029.6562 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.5.7 | PSL | E-Stop Resupply (PY7) | E-stop: Estop PY7 Resupply |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 689.422 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 24 |  |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1969.7771 | 0 | 0 | 0 | 0 | 1969.7771 | 0 | 1969.7771 | 689.422 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1969.7771 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1969.7771 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.5.7 | PSL | E-Stop Resupply (PY7) | E-stop: Estop PY7 Resupply |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1750 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 1750 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.6.3 | PSL | Update Workspace (desk, chairs), Procure Printer & Accessories | DCC: Update Workspace (desk, chairs), Procure Printer & Accessories |  | Labor Hours | Labor Hours | EN-EE | C - Engineering Buildup | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 | [5 empty] | 8 | 24 | [6 empty] | 32 | 0.21333 | 0 | 0 | 0 | 0 | 939.78 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.6.3 | PSL | Update Workspace (desk, chairs), Procure Printer & Accessories | DCC: Update Workspace (desk, chairs), Procure Printer & Accessories |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 1346.25 | 0 | [5 empty] | 10770 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10770 | 0 | 10770 | 1346.25 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10770 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.7.3 | PSL | Fabricate and Test SES & SES to TOS Cables - Signal | Outdoor Cables: Fabricate and Test SES & SES to TOS Cables - Signal |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [7 empty] | 10 | 10 | 10 | 10 |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 1174.725 | 1174.725 | 1174.725 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.7.4 | PSL | CS Cabling Resupply (PY6) | Outdoor Cables: CS Cabling Resupply (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1007.9845 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 12 | 12 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 1439.9779 | 1439.9779 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | 1007.9845 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.7.4 | PSL | CS Cabling Resupply (PY6) | Outdoor Cables: CS Cabling Resupply (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1750 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2500 | 2500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 1750 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.7.5 | PSL | CS Cabling Resupply (PY7) | Outdoor Cables: CS Cabling Resupply (PY7) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1029.6562 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 12 | 12 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 1470.9374 | 1470.9374 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 2941.8749 | 1029.6562 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.7.5 | PSL | CS Cabling Resupply (PY7) | Outdoor Cables: CS Cabling Resupply (PY7) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1750 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2500 | 2500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 1750 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.2.1 | PSL | Procure sample temperature display and digital thermostat, install in test bed heater, test | CS: Procure sample temperature display and digital thermostat, install in test bed heater, test |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 |  | 8 | [11 empty] | 8 | 0.053333 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.2.1 | PSL | Procure sample temperature display and digital thermostat, install in test bed heater, test | CS: Procure sample temperature display and digital thermostat, install in test bed heater, test |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 37.5 | 0 |  | 300 | [11 empty] | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 300 | 37.5 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.2.2 | PSL | Select and procure temperature display units for heater controls, conversion hardware | CS: Select and procure temperature display units for heater controls, conversion hardware |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 |  |  | 8 | [10 empty] | 8 | 0.053333 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.2.2 | PSL | Select and procure temperature display units for heater controls, conversion hardware | CS: Select and procure temperature display units for heater controls, conversion hardware |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 562.5 | 0 |  |  | 4500 | [10 empty] | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 4500 | 562.5 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.2.3 | PSL | Replace temperature display units, remove RTD DGHs, transfer net connections, test | CS: Replace temperature display units, remove RTD DGHs, transfer net connections, test |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  | 24 | [9 empty] | 24 | 0.16 | 0 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.2.3 | PSL | Replace temperature display units, remove RTD DGHs, transfer net connections, test | CS: Replace temperature display units, remove RTD DGHs, transfer net connections, test |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 1573.11 | 0 |  |  |  | 100 | [9 empty] | 100 | 0.66667 | 0 | 0 | 7865.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7865.55 | 0 | 7865.55 | 1573.11 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7865.55 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 7865.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.2.4 | PSL | Select and procure digital thermostats for heater controls, conversion hardware | CS: Select and procure digital thermostats for heater controls, conversion hardware |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [5 empty] | 8 | [7 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.2.4 | PSL | Select and procure digital thermostats for heater controls, conversion hardware | CS: Select and procure digital thermostats for heater controls, conversion hardware |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 620.25 | 0 | [5 empty] | 4962 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4962 | 0 | 4962 | 620.25 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4962 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.2.5 | PSL | Write thermostat field replacement procedure | CS: Write thermostat field replacement procedure |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 | [7 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.3.1 | PSL | Write rewiring and test instructions for MHP E-stop boxes (fixes switch contact selections made in Gen 1) | CS: Write rewiring and test instructions for MHP E-stop boxes (fixes switch contact selections made in Gen 1) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  | 24 | [10 empty] | 24 | 0.16 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.3.2 | PSL | Write test procedures for dry heater tests | CS: Write test procedures for dry heater tests |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 |  |  | 16 | 16 | [9 empty] | 32 | 0.21333 | 0 | 1879.56 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.3.3 | PSL | Assemble equipment to test flow meters (excitation coil and portable pulse generator) | CS: Assemble equipment to test flow meters (excitation coil and portable pulse generator) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  | 12 | 12 | [8 empty] | 24 | 0.16 | 0 | 0 | 1409.67 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.3.3 | PSL | Assemble equipment to test flow meters (excitation coil and portable pulse generator) | CS: Assemble equipment to test flow meters (excitation coil and portable pulse generator) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 151.8 | 0 |  |  |  | 759 | [9 empty] | 0 | 0 | 0 | 0 | 759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759 | 0 | 759 | 151.8 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.3.4 | PSL | Write flow meter test procedure and assemble test kit | CS: Write flow meter test procedure and assemble test kit |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  |  | 12 | 12 | [7 empty] | 24 | 0.16 | 0 | 0 | 0 | 1409.67 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.5.1 | PSL | Develop heater-based sensor readout; (heater temp/flow manifold pressures | CS: Develop heater-based sensor readout; (heater temp/flow manifold pressures |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 |  |  |  |  | 120 | [8 empty] | 120 | 0.8 | 0 | 0 | 0 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.5.2 | PSL | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | CS: Develop environmental sensor readout; (bldg temps, smoke, e-stop) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 |  |  |  |  | 36 | [8 empty] | 36 | 0.24 | 0 | 0 | 0 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.5.3 | PSL | Develop heater control; (ON/OFF, Thermostat setpoint) | CS: Develop heater control; (ON/OFF, Thermostat setpoint) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [5 empty] | 20 | 20 | [6 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.5.7 | PSL | Implement interlocks | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [6 empty] | 20 | [6 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.1.5.8 | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 211.4505 | 0 | [7 empty] | 20 | [5 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | 211.4505 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.1.3 | PSL | Develop VFD installation strategy & document, procure materials | CS: Develop VFD installation strategy & document, procure materials |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  | 40 | [11 empty] | 40 | 0.26667 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.1.3 | PSL | Develop VFD installation strategy & document, procure materials | CS: Develop VFD installation strategy & document, procure materials |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 251.6976 | 0 |  | 16 | [11 empty] | 16 | 0.10667 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 1258.488 | 251.6976 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.3.2 | PSL | Select and procure new power supplies for the network box, procure one RS-485 gateway | CS: Select and procure new power supplies for the network box, procure one RS-485 gateway |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  | 16 | [11 empty] | 16 | 0.10667 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.3.2 | PSL | Select and procure new power supplies for the network box, procure one RS-485 gateway | CS: Select and procure new power supplies for the network box, procure one RS-485 gateway |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 115.625 | 0 |  | 925 | [11 empty] | 0 | 0 | 925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 925 | 0 | 925 | 115.625 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 925 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.3.3 | PSL | Redesign and rebuild PHS network box with new I/O, document as-built configuration | CS: Redesign and rebuild PHS network box with new I/O, document as-built configuration |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 3383.208 | 0 |  | 44 | 100 | [10 empty] | 144 | 0.96 | 5168.79 | 11747.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16916.04 | 0 | 16916.04 | 3383.208 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16916.04 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 16916.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.3.3 | PSL | Redesign and rebuild PHS network box with new I/O, document as-built configuration | CS: Redesign and rebuild PHS network box with new I/O, document as-built configuration |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 629.244 | 0 |  | 20 | 20 | [10 empty] | 40 | 0.26667 | 1573.11 | 1573.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 3146.22 | 629.244 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.3.3 | PSL | Redesign and rebuild PHS network box with new I/O, document as-built configuration | CS: Redesign and rebuild PHS network box with new I/O, document as-built configuration |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 770 | 0 |  | 3850 | [11 empty] | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 3850 | 770 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.3.4 | PSL | Indicate where approximately 20 sensor and network cables terminate in PHS and document config. plans | CS: Indicate where approximately 20 sensor and network cables terminate in PHS and document config. plans |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2537.406 | 0 |  |  | 50 | 58 | [9 empty] | 108 | 0.72 | 0 | 5873.625 | 6813.405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12687.03 | 0 | 12687.03 | 2537.406 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12687.03 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 12687.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.3.5 | PSL | Configure heater-mounted DGH modules, develop and document DGH installation and test plans | CS: Configure heater-mounted DGH modules, develop and document DGH installation and test plans |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  | 12 | 12 | [8 empty] | 24 | 0.16 | 0 | 0 | 1409.67 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.3.5 | PSL | Configure heater-mounted DGH modules, develop and document DGH installation and test plans | CS: Configure heater-mounted DGH modules, develop and document DGH installation and test plans |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 251.6976 | 0 |  |  |  |  | 16 | [8 empty] | 16 | 0.10667 | 0 | 0 | 0 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 1258.488 | 251.6976 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.4 | PSL | CS PHS HW4: New E-stop Slap Switch & Box for Outdoor Location | CS PHS HW4: New estop slap switch and box for outdoor location |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 |  |  |  |  | 8 | [8 empty] | 8 | 0.053333 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.4 | PSL | CS PHS HW4: New E-stop Slap Switch & Box for Outdoor Location | CS PHS HW4: New estop slap switch and box for outdoor location |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 40 | 0 |  |  |  |  | 200 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 40 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.5 | PSL | CS PHS HW5: Develop heater test procedures, configure test tools, document test plans | CS PHS HW5: Develop heater test procedures, configure test tools, document test plans |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [5 empty] | 18 | 18 | [6 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 2114.505 | 2114.505 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.7.1 | PSL | Develop and document test plans for all PHS system components | CS: Develop and document test plans for all PHS system components |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [7 empty] | 18 | 18 |  |  |  |  | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 2114.505 | 2114.505 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.7.2 | PSL | Review Gen-1 docs, identify where sensor connections terminated, plan for reconnection and test | CS: Develop and document test plans for all PHS system components |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [8 empty] | 18 | 18 |  |  |  | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2114.505 | 2114.505 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.8.1 | PSL | Develop heater-based sensor readout; (heater temp/flow manifold pressures) | CS: Develop heater-based sensor readout; (heater temp/flow manifold pressures) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  |  | 24 | [8 empty] | 24 | 0.16 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.8.2 | PSL | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | CS: Develop environmental sensor readout; (bldg temps, smoke, e-stop) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  |  |  |  | 16 | [8 empty] | 16 | 0.10667 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.8.3 | PSL | Develop water tank sensors readout | CS: Develop water tank sensors readout |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 | [5 empty] | 12 | 12 | [6 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 1409.67 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.8.4 | PSL | Develop heater control; (ON/OFF, Thermostat setpoint) | CS: Develop heater control; (ON/OFF, Thermostat setpoint) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [6 empty] | 16 | [6 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.8.5 | PSL | Develop AB drive/pump control; (variable speed velocity drives) | CS: Develop AB drive/pump control; (variable speed velocity drives) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [6 empty] | 20 | 20 | [5 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.8.10 | PSL | Implement interlocks | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [7 empty] | 20 | [5 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.2.8.11 | PSL | Document Subsystem | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [8 empty] | 40 |  |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.1.3 | PSL | Configure VFDs with accessories, connection pigtails, document | CS: Configure VFDs with accessories, connection pigtails, document |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  | 24 | [11 empty] | 24 | 0.16 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.1.3 | PSL | Configure VFDs with accessories, connection pigtails, document | CS: Configure VFDs with accessories, connection pigtails, document |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 629.244 | 0 |  | 20 | 20 | [10 empty] | 40 | 0.26667 | 1573.11 | 1573.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 3146.22 | 629.244 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.1.3 | PSL | Configure VFDs with accessories, connection pigtails, document | CS: Configure VFDs with accessories, connection pigtails, document |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1000 | 0 |  | 5000 | [11 empty] | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 1000 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.1.4 | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  |  | 40 | [9 empty] | 40 | 0.26667 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.1.4 | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 1258.488 | 0 |  |  |  | 80 | [9 empty] | 80 | 0.53333 | 0 | 0 | 6292.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 0 | 6292.44 | 1258.488 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 6292.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.1.4 | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 400 | 0 |  |  |  | 2000 | [9 empty] | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 400 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.1.5 | PSL | SW configuration and autotuning, make plan - MDCR/LW, DSHR/LW, RWHR, RWCR, Tower Hoist | CS: SW configuration and autotuning, make plan - MDCR/LW, DSHR/LW, RWHR, RWCR, Tower Hoist |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 |  |  |  |  | 80 | [8 empty] | 80 | 0.53333 | 0 | 0 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.2.2 | PSL | Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement | CS: Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 |  | 120 | [11 empty] | 120 | 0.8 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.2.2 | PSL | Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement | CS: Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 629.244 | 0 |  | 40 | [11 empty] | 40 | 0.26667 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 3146.22 | 629.244 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.2.2 | PSL | Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement | CS: Document changes to E-stop and Reel stop interfaces to motor drives, procure materials, implement |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 800 | 0 |  | 4000 | [11 empty] | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 4000 | 800 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.2.3 | PSL | Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives | CS: Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 4698.9 | 0 |  |  | 200 | [10 empty] | 200 | 1.3333 | 0 | 23494.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23494.5 | 0 | 23494.5 | 4698.9 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23494.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 23494.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.2.3 | PSL | Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives | CS: Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 1258.488 | 0 |  |  | 80 | [10 empty] | 80 | 0.53333 | 0 | 6292.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 0 | 6292.44 | 1258.488 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 6292.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.2.3 | PSL | Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives | CS: Test refurbished E-stop panels with reel safety junction boxes, I/O boxes, network boxes, drives |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 50 | 0 |  |  | 250 | [10 empty] | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 250 | 50 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.2.6 | PSL | Design new E-stop controllers for TOS, build and test boxes | CS: Design new E-stop controllers for TOS, build and test boxes |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 | [6 empty] | 30 | 30 | 30 | 30 |  |  |  | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 3524.175 | 3524.175 | 3524.175 | 0 | 0 | 0 | 14096.7 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.2.6 | PSL | Design new E-stop controllers for TOS, build and test boxes | CS: Design new E-stop controllers for TOS, build and test boxes |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 1258.488 | 0 | [6 empty] | 20 | 20 | 20 | 20 |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 1573.11 | 1573.11 | 1573.11 | 1573.11 | 0 | 0 | 0 | 6292.44 | 0 | 6292.44 | 1258.488 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 6292.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.2.6 | PSL | Design new E-stop controllers for TOS, build and test boxes | CS: Design new E-stop controllers for TOS, build and test boxes |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 600 | 0 | [7 empty] | 1500 | 1500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 600 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.3.1 | PSL | Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes | CS: Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  | 24 | [9 empty] | 24 | 0.16 | 0 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.3.1 | PSL | Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes | CS: Spec and procure new power supplies for TOS network boxes, procure DGH gateway, document changes |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 206.25 | 0 |  |  |  | 1650 | [9 empty] | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 1650 | 206.25 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.3.2 | PSL | Document plans for TOS network box upgrades, specify and procure tools and materials | CS: Document plans for TOS network box upgrades, specify and procure tools and materials |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 |  |  |  |  | 12 | 12 | [7 empty] | 24 | 0.16 | 0 | 0 | 0 | 1409.67 | 1409.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.3.2 | PSL | Document plans for TOS network box upgrades, specify and procure tools and materials | CS: Document plans for TOS network box upgrades, specify and procure tools and materials |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 251.6976 | 0 | [5 empty] | 16 | [7 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 1258.488 | 251.6976 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.3.2 | PSL | Document plans for TOS network box upgrades, specify and procure tools and materials | CS: Document plans for TOS network box upgrades, specify and procure tools and materials |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 80 | 0 | [5 empty] | 400 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 400 | 80 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.3.3 | PSL | Spec TOS network switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller | CS: Spec TOS nework switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1409.67 | 0 | [5 empty] | 30 | 30 | [6 empty] | 60 | 0.4 | 0 | 0 | 0 | 0 | 3524.175 | 3524.175 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 0 | 7048.35 | 1409.67 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.3.3 | PSL | Spec TOS network switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller | CS: Spec TOS nework switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 503.3952 | 0 | [5 empty] | 16 | 16 | [6 empty] | 32 | 0.21333 | 0 | 0 | 0 | 0 | 1258.488 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 2516.976 | 0 | 2516.976 | 503.3952 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2516.976 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2516.976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.3.3 | PSL | Spec TOS network switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller | CS: Spec TOS nework switch location, spec cables to drives, I/O boxes, network box, DCC modem, PC, PLC, e-stop controller |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 200 | 0 | [6 empty] | 1000 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 200 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.3.4 | PSL | Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts | CS: Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 | [6 empty] | 20 | 30 | 30 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 3524.175 | 3524.175 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.3.4 | PSL | Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts | CS: Design enclosures for TOS PLCs and attached I/O used for payout encoders, load cells; procure parts |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 400 | 0 | [7 empty] | 2000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 400 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.3.5 | PSL | Construct enclosures for TOS PLCs and attached I/O , test | CS: Construct enclosures for TOS PLCs and attached I/O , test |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1409.67 | 0 | [8 empty] | 20 | 20 | 20 |  |  | 60 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 2349.45 | 0 | 0 | 7048.35 | 0 | 7048.35 | 1409.67 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.3.5 | PSL | Construct enclosures for TOS PLCs and attached I/O , test | CS: Construct enclosures for TOS PLCs and attached I/O , test |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 1132.6392 | 0 | [8 empty] | 20 | 32 | 20 |  |  | 72 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1573.11 | 2516.976 | 1573.11 | 0 | 0 | 5663.196 | 0 | 5663.196 | 1132.6392 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5663.196 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 5663.196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.3.5 | PSL | Construct enclosures for TOS PLCs and attached I/O , test | CS: Construct enclosures for TOS PLCs and attached I/O , test |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 40 | 0 | [8 empty] | 200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 40 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.5.1 | PSL | Develop and document on-ice test plans for E-stop, Reel-Stop, and Fault Detection hardware | CS: Develop and document on-ice test plans for E-stop, Reel-Stop, and Fault Detection hardware |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  |  |  | 40 | [8 empty] | 40 | 0.26667 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.5.2 | PSL | Develop and document on-ice test plans for integrated hardware | CS: Develop and document on-ice test plans for integrated hardware |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 |  |  |  |  | 60 | 60 | [7 empty] | 120 | 0.8 | 0 | 0 | 0 | 7048.35 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.6.2 | PSL | Test load cells and payout encoders with PLC, verify functionality required for payout control, load sharing | CS: Test load cells and payout encoders with PLC, verify functionality required for payout control, load sharing |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 4698.9 | 0 |  |  | 100 | 100 | [9 empty] | 200 | 1.3333 | 0 | 11747.25 | 11747.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23494.5 | 0 | 23494.5 | 4698.9 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23494.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 23494.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.8 | PSL | CS TOS HW9: Tower Hoist Reconnect Materials TOS2, Identify and Procure | CS TOS HW9: Tower hoist reconnect materials TOS2, identify and procure |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [5 empty] | 20 | 20 | [6 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.8 | PSL | CS TOS HW9: Tower Hoist Reconnect Materials TOS2, Identify and Procure | CS TOS HW9: Tower hoist reconnect materials TOS2, identify and procure |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 200 | 0 | [5 empty] | 1000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 200 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.9 | PSL | CS TOS HW10: Review deployment plans and HW, integrate with drill | CS TOS HW10: Review deployment plans and HW, integrate with drill |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 | [6 empty] | 30 | 30 | 30 | 30 |  |  |  | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 3524.175 | 3524.175 | 3524.175 | 0 | 0 | 0 | 14096.7 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.10.1 | PSL | Develop general control/monitoring software | CS: Develop general control/monitoring software |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 |  |  |  |  | 40 | 40 | 40 | [6 empty] | 120 | 0.8 | 0 | 0 | 0 | 4698.9 | 4698.9 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.10.2 | PSL | Develop reel control software(MCR/LW, DSHR/LW, RWHR, RWCR, Tower Winch) | CS: Develop reel control software(MCR/LW, DSHR/LW, RWHR, RWCR, Tower Winch) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 | [6 empty] | 40 | 40 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.10.3 | PSL | Develop tension-sharing algorithm software (MCR/LW, DSHR/LW) | CS: Develop tension-sharing algorithm software (MCR/LW, DSHR/LW) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 2819.34 | 0 | [7 empty] | 30 | 30 | 30 | 30 |  |  | 120 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 3524.175 | 3524.175 | 3524.175 | 0 | 0 | 14096.7 | 0 | 14096.7 | 2819.34 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14096.7 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 14096.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.10.4 | PSL | Develop drillhead data monitoring interface) | CS: Develop drillhead data monitoring interface) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 | [10 empty] | 24 |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.10.8 | PSL | Implement interlocks | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [11 empty] | 20 | 20 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.3.10.9 | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [12 empty] | 40 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.4.1 | PSL | CS HW Drillhead sofware/hardware production version | CS HW Drillhead sofware/hardware production version |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1409.67 | 0 | [8 empty] | 30 | 30 |  |  |  | 60 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 3524.175 | 0 | 0 | 0 | 7048.35 | 0 | 7048.35 | 1409.67 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.4.1 | PSL | CS HW Drillhead sofware/hardware production version | CS HW Drillhead sofware/hardware production version |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 313.75 | 0 | [8 empty] | 2510 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510 | 0 | 0 | 0 | 0 | 2510 | 0 | 2510 | 313.75 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2510 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.4.2.1 | PSL | Port C-Lang ingest process to rPI platform & test | CS: Port C-Lang ingest process to rPI platform & test |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 | [9 empty] | 16 | 16 |  |  | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1879.56 | 0 | 0 | 3759.12 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.4.2.2 | PSL | Integrate rPI platform into PLC infrastructure | CS: Integrate rPI platform into PLC infrastructure |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [11 empty] | 20 | 20 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.4.2.3 | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [12 empty] | 40 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.1 | PSL | Design, construct and test master E-stop controller, produce documentation and user instructions | CS: Design, construct and test master E-stop controller, produce documentation and user instructions |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 3759.12 | 0 |  |  |  |  | 40 | 40 | 40 | 40 | [5 empty] | 160 | 1.0667 | 0 | 0 | 0 | 4698.9 | 4698.9 | 4698.9 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 18795.6 | 0 | 18795.6 | 3759.12 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18795.6 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 18795.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.1 | PSL | Design, construct and test master E-stop controller, produce documentation and user instructions | CS: Design, construct and test master E-stop controller, produce documentation and user instructions |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 629.244 | 0 |  |  |  |  | 10 | 10 | 10 | 10 | [5 empty] | 40 | 0.26667 | 0 | 0 | 0 | 786.555 | 786.555 | 786.555 | 786.555 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 3146.22 | 629.244 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.1 | PSL | Design, construct and test master E-stop controller, produce documentation and user instructions | CS: Design, construct and test master E-stop controller, produce documentation and user instructions |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 600 | 0 | [5 empty] | 1500 | 1500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 600 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.2 | PSL | Design and construct general-purpose I/O box for fuel sled, gather required component stock to install | CS: Design and construct general-purpose I/O box for fuel sled, gather required component stock to install |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 | [7 empty] | 20 | 40 | 20 |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 4698.9 | 2349.45 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.2 | PSL | Design and construct general-purpose I/O box for fuel sled, gather required component stock to install | CS: Design and construct general-purpose I/O box for fuel sled, gather required component stock to install |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 770 | 0 | [8 empty] | 3850 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 3850 | 0 | 3850 | 770 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.3 | PSL | Procure 20 kW three-phase heater for DCC and 208V breakers | CS: Procure 20 kW three-phase heater for DCC and 208V breakers |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 251.6976 | 0 | [9 empty] | 16 |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 0 | 0 | 0 | 1258.488 | 0 | 1258.488 | 251.6976 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258.488 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1258.488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.3 | PSL | Procure 20 kW three-phase heater for DCC and 208V breakers | Procure 20 kW three-phase heater for DCC and 208V breakers |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 394 | 0 | [9 empty] | 3152 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3152 | 0 | 0 | 0 | 3152 | 0 | 3152 | 394 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3152 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.4 | PSL | WT1 VT pump drives: procure, configure, rewire plan | CS: WT1 VT pump drives: procure, configure, rewire plan |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [9 empty] | 16 |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.4 | PSL | WT1 VT pump drives: procure, configure, rewire plan | CS: WT1 VT pump drives: procure, configure, rewire plan |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 635.375 | 0 | [9 empty] | 5083 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5083 | 0 | 0 | 0 | 5083 | 0 | 5083 | 635.375 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5083 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.5 | PSL | WT1 VT pump drives: final configure | CS: WT1 VT pump drives: final configure |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1409.67 | 0 | [11 empty] | 30 | 30 | 60 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3524.175 | 3524.175 | 7048.35 | 0 | 7048.35 | 1409.67 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.6 | PSL | WT1 VT pump drives: install plan and kit | CS: WT1 VT pump drives: install plan and kit |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1409.67 | 0 | [12 empty] | 60 | 60 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 7048.35 | 0 | 7048.35 | 1409.67 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.6 | PSL | WT1 VT pump drives: install plan and kit | CS: WT1 VT pump drives: install plan and kit |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 300 | 0 | [12 empty] | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 1500 | 300 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.7.1 | PSL | Develop fuel system sensor readout ; (multi-level tank status, control relay status ) | CS: Develop fuel system sensor readout ; (multi-level tank status, control relay status ) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [9 empty] | 18 | 18 |  |  | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2114.505 | 2114.505 | 0 | 0 | 4229.01 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.7.2 | PSL | Configure/document Point I/O Block | CS: Configure/document Point I/O Block |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [10 empty] | 8 | 8 |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 939.78 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.7.3 | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [11 empty] | 36 |  | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.5.7.4 | PSL | Implement interlocks | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [11 empty] | 20 |  | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.6.1 | PSL | CS Gensets HW - identify, procure, assemble | CS: CS Gensets HW - identify, procure, assemble |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20 | 20 | [5 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.6.1 | PSL | CS Gensets HW - identify, procure, assemble | CS: CS Gensets HW - identify, procure, assemble |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 642.7727 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20 | 20 | [5 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 1606.9319 | 1606.9319 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 0 | 3213.8637 | 642.7727 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3213.8637 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3213.8637 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.6.1 | PSL | CS Gensets HW - identify, procure, assemble | CS: CS Gensets HW - identify, procure, assemble |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 770 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 3850 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 0 | 3850 | 770 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.6.2.1 | PSL | Develop sensor readout; (bldg temps, fuel temps, supply/return water temps) | CS: Develop sensor readout; (bldg temps, fuel temps, supply/return water temps) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 20 | 20 |  |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.6.2.2 | PSL | Develop sensor readout; (engine jacket temps, exhaust temps, drip pan status) | CS: Develop sensor readout; (engine jacket temps, exhaust temps, drip pan status) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 20 | 20 |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.6.2.3 | PSL | Configure/document network switch | CS: Configure/document network switch |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 191.9971 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 8 |  |  |  | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | 191.9971 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.6.2.4 | PSL | Configure/document RTA gateway to M-DGH interface | CS: Configure/document RTA gateway to M-DGH interface |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 239.9963 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 10 |  |  |  | 10 | 0.066667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 0 | 0 | 0 | 1199.9816 | 0 | 1199.9816 | 239.9963 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1199.9816 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1199.9816 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.6.2.5 | PSL | Configure/document M-DGHs | CS: Configure/document M-DGHs |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 479.9926 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 20 |  |  | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 0 | 0 | 2399.9632 | 0 | 2399.9632 | 479.9926 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.6.2.6 | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 20 | 20 |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 4799.9263 | 0 | 4799.9263 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.1.3 | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1691.604 | 0 |  |  |  | 36 | 36 | [8 empty] | 72 | 0.48 | 0 | 0 | 4229.01 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8458.02 | 0 | 8458.02 | 1691.604 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8458.02 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 8458.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.1.3 | PSL | Develop VFD mechanical and electrical installation strategies & document, procure materials | CS: Develop VFD mechanical and electrical installation strategies & document, procure materials |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 200 | 0 |  |  |  | 1000 | [9 empty] | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 200 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.2.1 | PSL | Define requirements and procedures for reading signals applied to HPP motor drives | CS: Define requirements and procedures for reading signals applied to HPP motor drives |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  | 16 | [11 empty] | 16 | 0.10667 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.2.2 | PSL | Define method of verifying sensor readout accuracy (reading vs stimulus) | CS: Define method of verifying sensor readout accuracy (reading vs stimulus) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  |  | 16 | [10 empty] | 16 | 0.10667 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.2.3 | PSL | Develop and document test procedures for on-ice personnel | CS: Develop and document test procedures for on-ice personnel |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  |  |  | 16 | [9 empty] | 16 | 0.10667 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.3.1 | PSL | Define core HPP PLC functions and requirements, define needed I/O connections | CS: Define core HPP PLC functions and requirements, define needed I/O connections |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  | 20 | 20 | [9 empty] | 40 | 0.26667 | 0 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.3.2 | PSL | Select PLC, Enclosure, Power supplies, I/O expansion cards, power distribution, connectors and cables | CS: Select PLC, Enclosure, Power supplies, I/O expansion cards, power distribution, connectors and cables |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  |  | 20 | 20 | [8 empty] | 40 | 0.26667 | 0 | 0 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.3.3 | PSL | Design and Construct PLC enclosure | CS: Design and Construct PLC enclosure |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 |  |  |  |  | 32 | [8 empty] | 32 | 0.21333 | 0 | 0 | 0 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.3.3 | PSL | Design and Construct PLC enclosure | CS: Design and Construct PLC enclosure |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 629.244 | 0 |  |  |  |  | 20 | 20 | [7 empty] | 40 | 0.26667 | 0 | 0 | 0 | 1573.11 | 1573.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 3146.22 | 629.244 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.3.3 | PSL | Design and Construct PLC enclosure | CS: Design and Construct PLC enclosure |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1410 | 0 | [5 empty] | 7050 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7050 | 0 | 7050 | 1410 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7050 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.3.4 | PSL | Test HPP PLC enclosure with HPP Network box | CS: Test HPP PLC enclosure with HPP Network box |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 | [6 empty] | 24 | [6 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.4.2 | PSL | Procure additional drives for charge pumps (4), AC and network pigtail materials | CS: Procure additional drives for charge pumps (4), AC and network pigtail materials |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  |  |  |  | 16 | [8 empty] | 16 | 0.10667 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.4.2 | PSL | Procure additional drives for charge pumps (4), AC and network pigtail materials | CS: Procure additional drives for charge pumps (4), AC and network pigtail materials |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 1813.125 | 0 |  |  |  |  | 14505 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 14505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14505 | 0 | 14505 | 1813.125 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14505 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.4.3 | PSL | Connectorize four drives with power and network pigtails, test each in test bed | CS: Connectorize four drives with power and network pigtails, test each in test bed |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 563.868 | 0 | [7 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 563.868 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.4.3 | PSL | Connectorize four drives with power and network pigtails, test each in test bed | CS: Connectorize four drives with power and network pigtails, test each in test bed |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 629.244 | 0 | [7 empty] | 20 | 20 |  |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 1573.11 | 1573.11 | 0 | 0 | 0 | 0 | 3146.22 | 0 | 3146.22 | 629.244 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3146.22 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3146.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.4.3 | PSL | Connectorize four drives with power and network pigtails, test each in test bed | CS: Connectorize four drives with power and network pigtails, test each in test bed |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 200 | 0 | [7 empty] | 1000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 200 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.7.1 | PSL | Select and procure E-stop relays for pump VFD Enable signals | CS: Select and procure E-stop relays for pump VFD Enable signals |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [7 empty] | 8 | [5 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.7.1 | PSL | Select and procure E-stop relays for pump VFD Enable signals | CS: Select and procure E-stop relays for pump VFD Enable signals |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 40 | 0 | [7 empty] | 200 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 40 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.7.2 | PSL | Develop and document rewiring instructions for HPP E-stop box | CS: Develop and document rewiring instructions for HPP E-stop box |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [8 empty] | 16 |  |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.9.1 | PSL | Develop and document test plans for all HPP system components | CS: Develop and document test plans for all HPP system components |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 845.802 | 0 | [9 empty] | 36 |  |  |  | 36 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | 845.802 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.9.2 | PSL | Review Gen-1 docs, identify where sensor connections terminated, plan for field integration and test | CS: Review Gen-1 docs, identify where sensor connections terminated, plan for field integration and test |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 751.824 | 0 | [9 empty] | 32 |  |  |  | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 0 | 0 | 0 | 3759.12 | 0 | 3759.12 | 751.824 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.10.1 | PSL | Develop water path sensor readout; (pressure, temp, flow) | CS: Develop water path sensor readout; (pressure, temp, flow) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  |  |  | 40 | [8 empty] | 40 | 0.26667 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.10.2 | PSL | Develop environmental sensor readout; (bldg temps, smoke, e-stop) | CS: Develop environmental sensor readout; (bldg temps, smoke, e-stop) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  |  |  | 40 | [8 empty] | 40 | 0.26667 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.10.9 | PSL | Implement interlocks | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [9 empty] | 20 |  |  |  | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.7.10.10 | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [9 empty] | 40 |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.8.2.1 | PSL | Develop ARA-drill sensor readout; (heater flows, head press, tank level) | CS: Develop ARA-drill sensor readout; (heater flows, head press, tank level) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1879.56 | 0 |  |  | 80 | [10 empty] | 80 | 0.53333 | 0 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | 1879.56 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.8.2.2 | PSL | Develop AB drive/pump control; (variable speed velocity drives) | CS: Develop AB drive/pump control; (variable speed velocity drives) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  |  |  | 20 | 20 | [8 empty] | 40 | 0.26667 | 0 | 0 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.8.2.3 | PSL | Configure/document Point I/O Block | CS: Configure/document Point I/O Block |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  |  |  |  | 16 | [8 empty] | 16 | 0.10667 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.8.2.4 | PSL | Configure/document network switch | CS: Configure/document network switch |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 187.956 | 0 | [5 empty] | 8 | [7 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 187.956 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.8.2.5 | PSL | Configure/document RTA gateway to M-DGH interface | CS: Configure/document RTA gateway to M-DGH interface |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 | [5 empty] | 16 | [7 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.8.2.6 | PSL | Configure/document M-DGHs | CS: Configure/document M-DGHs |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [6 empty] | 20 | [6 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.8.2.7 | PSL | Implement interlocks | CS: Implement interlocks |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 469.89 | 0 | [6 empty] | 20 | [6 empty] | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | 469.89 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.4.8.8.2.8 | PSL | Document Subsystem | CS: Document Subsystem |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 | [7 empty] | 40 | [5 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.4
1.2 | 1.2.5.2.6 | PSL | GEN-1, 2, 3 - Procure Batteries | GEN-2, 3, PDM - Procure Batteries |  | Labor Hours | Labor Hours | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C2 | 12.5% | 117.4725 | 0 |  | 8 | [11 empty] | 8 | 0.053333 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 0 | 939.78 | 117.4725 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.2.6 | PSL | GEN-1, 2, 3 - Procure Batteries | GEN-2, 3, PDM - Procure Batteries |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 250 | 0 |  | 2000 | [11 empty] | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 250 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.2.7 | PSL | Generator 2 Subcontract Repairs in New Zealand | GEN-2, 3, PDM - Generator 2 Subcontract Repairs in New Zealand |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 1850.5 | 0 | Round trip trucking (Bascik Transport) from USAP site to Terra Cat $345 NZD plus GST- $275 USD estimated. Terra Cat quoted repair of injection pump governor shaft and electronic controller - $5229.03 USD. Estimated $6500.00 USD for diagnosis/repair/testing of alternator output issue and $2800 for structural repair of the 20' ISO shipping container that houses the power plant. Terra Cat was not willing to quote without diagnosis of alternator/structural issues. Total $14,804.03 USD |  | 7402 | 7402 | [9 empty] | 0 | 0 | 0 | 7402 | 7402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14804 | 0 | 14804 | 1850.5 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14804 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.2.8 | PSL | PDM - Procure Batteries | PDM - Procure Batteries |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 75 | 0 | [10 empty] | 600 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 600 | 0 | 600 | 75 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.2.9 | PSL | Develop SOW for South Pole Power Generation Technical Support Subcontract & Communicate with Vendor (PY6) | GEN-2, 3, PDM - Develop SOW for South Pole Power Generation Technical Support Subcontract & Communicate with Vendor |  | Labor Hours | Labor Hours | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | South Pole Contractor cost captured in FS2 (2023-24). | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | [10 empty] | 40 | 0.26667 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.2.10 | PSL | Predeployment Coordination with Power Generation Technical Support Subcontract Vendor (PY6) | GEN-2, 3, PDM - Predeployment Coordination with Power Generation Technical Support Subcontract Vendor (PY6) |  | Labor Hours | Labor Hours | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3324.5892 | 0 | [11 empty] | 20 | 20 | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 4698.9 | 0 | 4698.9 | 1644.615 | 0 | 20 | 20 | [10 empty] | 40 | 0.26667 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | 1679.9742 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9498.8263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.4.3 | PSL | System Elec Dist: Design & Procure | Elec Dist. System: Design & Procure |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 822.3075 | 0 |  | 20 | [11 empty] | 20 | 0.13333 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 0 | 2349.45 | 822.3075 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.45 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2349.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.4.3 | PSL | System Elec Dist: Design & Procure | Elec Dist. System: Design & Procure |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1911 | 0 |  | 5460 | [11 empty] | 0 | 0 | 5460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5460 | 0 | 5460 | 1911 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5460 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.4.5 | PSL | System Elec Dist: Build and Test Subcomponents | Elec Dist. System: Build and Test Subcomponents |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1480.1535 | 0 | [5 empty] | 18 |  | 18 | [5 empty] | 36 | 0.24 | 0 | 0 | 0 | 0 | 2114.505 | 0 | 2114.505 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 0 | 4229.01 | 1480.1535 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4229.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4229.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.4.8 | PSL | System Electrical Resupply (PY6) | Elec Dist. System: System Electrical Resupply (PY6) |  | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1007.9845 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | 1007.9845 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.4.8 | PSL | System Electrical Resupply (PY6) | Elec Dist. System: System Electrical Resupply (PY6) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 674.9114 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 0 | 1928.3182 | 674.9114 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928.3182 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1928.3182 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.4.8 | PSL | System Electrical Resupply (PY6) | Elec Dist. System: System Electrical Resupply (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1750 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 1750 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.4.10 | PSL | System Electrical Resupply (PY7) | Elec Dist. System: System Electrical Resupply (PY7) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1029.6562 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 2941.8749 | 1029.6562 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.4.10 | PSL | System Electrical Resupply (PY7) | Elec Dist. System: System Electrical Resupply (PY7) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 689.422 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 1969.7771 | 0 | 0 | 0 | 0 | 0 | 1969.7771 | 0 | 1969.7771 | 689.422 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1969.7771 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 1969.7771 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.5.4.10 | PSL | System Electrical Resupply (PY7) | Elec Dist. System: System Electrical Resupply (PY7) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1750 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 1750 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.5
1.2 | 1.2.6.1.3 | PSL | Procure Repair Parts, Replacements (PY6) | Water Tanks: Procure Repair Parts, Replacements (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1007.9845 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | 1007.9845 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
1.2 | 1.2.6.1.3 | PSL | Procure Repair Parts, Replacements (PY6) | Water Tanks: Procure Repair Parts, Replacements (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1750 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 1750 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
1.2 | 1.2.6.2.5 | PSL | Procure Repair/Replacement Components (PY5) | Pumps: Procure Repair/Replacement Components (PY5) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1644.615 | 0 | [7 empty] | 40 | [5 empty] | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 1644.615 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
1.2 | 1.2.6.2.5 | PSL | Procure Repair/Replacement Components (PY5) | Pumps: Procure Repair/Replacement Components (PY5)) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 2310 | 0 | [7 empty] | 6600 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 6600 | 2310 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
1.2 | 1.2.6.2.6 | PSL | Procure Repair/Replacement Components (PY6) | Pumps: Procure Repair/Replacement Components (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1007.9845 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 24 | [5 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 0 | 2879.9558 | 1007.9845 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2879.9558 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
1.2 | 1.2.6.2.6 | PSL | Procure Repair/Replacement Components (PY6) | Pumps: Procure Repair/Replacement Components (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1750 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 5000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 1750 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
1.2 | 1.2.6.4.9 | PSL | Procure External Interconnect Materials (PY6) | Interconnect: Procure External Interconnect materials (PY6) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1679.9742 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 40 |  |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | 1679.9742 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
1.2 | 1.2.6.4.9 | PSL | Procure External Interconnect Materials (PY6) | Interconnect: Procure External Interconnect materials (PY6) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 3692.85 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 10551 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10551 | 0 | 0 | 0 | 0 | 10551 | 0 | 10551 | 3692.85 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10551 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
1.2 | 1.2.6.5.1 | PSL | Identify Replacement Water Hoses (1-1/2", 3/4", and 1/2" Hose) | MDS: Evaluate Water Hoses (1-1/2", 3/4", and 1/2" Hose) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 335.9948 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 8 | [5 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | 335.9948 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
1.2 | 1.2.6.5.2 | PSL | Identify Replacement Fuel Hoses | MDS: Evaluate Fuel Hoses |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 335.9948 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 8 | [5 empty] | 8 | 0.053333 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 0 | 959.9853 | 335.9948 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
1.2 | 1.2.6.5.3 | PSL | Procure Replacements and Spares | MDS: Procure Replacements Internal Hoses and Spares |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 671.9897 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 8 | 8 |  |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 0 | 0 | 0 | 0 | 1919.9705 | 0 | 1919.9705 | 671.9897 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1919.9705 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1919.9705 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
1.2 | 1.2.6.5.3 | PSL | Procure Replacements and Spares | MDS: Procure Replacements Internal Hoses and Spares |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 3977.75 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 11365 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11365 | 0 | 0 | 0 | 0 | 0 | 11365 | 0 | 11365 | 3977.75 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11365 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.6
1.2 | 1.2.7.1.7 | PSL | IFD Follow-up Tasks (PY5) | Support Equipment: IFD Follow-up Tasks (PY5) |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 939.78 | 0 |  | 40 | [11 empty] | 40 | 0.26667 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 0 | 4698.9 | 939.78 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4698.9 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4698.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.1.7 | PSL | IFD Follow-up Tasks (PY5) | Support Equipment: IFD Follow-up Tasks (PY5) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C3 | 20% | 377.5464 | 0 |  | 24 | [11 empty] | 24 | 0.16 | 1887.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 0 | 1887.732 | 377.5464 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.732 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1887.732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.1.7 | PSL | IFD Follow-up Tasks (PY5) | Support Equipment: IFD Follow-up Tasks (PY5) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 400 | 0 |  | 2000 | [11 empty] | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 400 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.2.1 | PSL | Identify Spares and Replacements | Support Equipment: Identify Spares and Replacements |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 986.769 | 0 |  | 8 |  | 8 | 8 | [8 empty] | 24 | 0.16 | 939.78 | 0 | 939.78 | 939.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 986.769 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.2.2 | PSL | Procure Spares and Replacements | Support Equipment: Procure Spares and Replacements |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1662.2946 | 0 | [9 empty] | 8 | 12 |  |  | 20 | 0.13333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1409.67 | 0 | 0 | 2349.45 | 0 | 2349.45 | 822.3075 | 0 | 8 | [6 empty] | 6 | 6 |  |  |  | 20 | 0.13333 | 959.9853 | 0 | 0 | 0 | 0 | 0 | 0 | 719.989 | 719.989 | 0 | 0 | 0 | 2399.9632 | 0 | 2399.9632 | 839.9871 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4749.4132 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2349.45 | 2399.9632 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.2.2 | PSL | Procure Spares and Replacements | Support Equipment: Procure Spares and Replacements |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 2800 | 0 | [10 empty] | 4000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 4000 | 0 | 4000 | 1400 | 0 | 1000 | [6 empty] | 1000 | 2000 |  |  |  | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 2000 | 0 | 0 | 0 | 4000 | 0 | 4000 | 1400 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.2.4 | PSL | Procure Hose Stock and Fittings (FY5) | Support Equipment: Procure Hose Stock and Fittings |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 986.769 | 0 | [8 empty] | 8 | 16 |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 1879.56 | 0 | 0 | 0 | 2819.34 | 0 | 2819.34 | 986.769 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2819.34 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.2.4 | PSL | Procure Hose Stock and Fittings (FY5) | Support Equipment: Procure Hose Stock and Fittings |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1750 | 0 | [9 empty] | 5000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 5000 | 0 | 5000 | 1750 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.2.5 | PSL | Spare Parts Inventory and Catalog - Electrical/Controls | Support Equipment: Spare Parts Inventory and Catalog - Electrical/Controls |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 657.846 | 0 | [9 empty] | 8 | 8 |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 939.78 | 0 | 0 | 1879.56 | 0 | 1879.56 | 657.846 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.3.1 | PSL | Identify Upgrade-Replacements, Spares | Shops: Identify Upgrade-Replacements, Spares |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 657.846 | 0 | [7 empty] | 8 | 8 |  |  |  |  | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 939.78 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 657.846 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.3.2 | PSL | Procure Upgrade-Replacements, Spares | Shops: Procure Upgrade-Replacements, Spares |  | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1315.692 | 0 | [8 empty] | 16 | 8 | 8 |  |  | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 939.78 | 939.78 | 0 | 0 | 3759.12 | 0 | 3759.12 | 1315.692 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3759.12 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3759.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.3.2 | PSL | Procure Upgrade-Replacements, Spares | Shops: Procure Upgrade-Replacements, Spares |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1225 | 0 | [8 empty] | 1500 | 1000 | 1000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1000 | 1000 | 0 | 0 | 3500 | 0 | 3500 | 1225 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.4.7 | PSL | Commission/Maintenance/Decommission (PY5) | Testbed: Commission/Maintenance/Decommission (PY5) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 2202.354 | 0 | [5 empty] | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 1573.11 | 1573.11 | 1573.11 | 1573.11 | 0 | 0 | 0 | 0 | 6292.44 | 0 | 6292.44 | 2202.354 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6292.44 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 6292.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.4.7 | PSL | Commission/Maintenance/Decommission (PY5) | Testbed: Commission/Maintenance/Decommission (PY5) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3289.23 | 0 | [5 empty] | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 2349.45 | 2349.45 | 2349.45 | 2349.45 | 0 | 0 | 0 | 0 | 9397.8 | 0 | 9397.8 | 3289.23 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9397.8 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9397.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.4.7 | PSL | Commission/Maintenance/Decommission (PY5) | Testbed: Commission/Maintenance/Decommission (PY5) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 3500 | 0 | [5 empty] | 2500 | 2500 | 2500 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 3500 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.4.8 | PSL | Commission/Maintenance/Decommission (PY6) | Testbed: Commission/Maintenance/Decommission (PY6) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 2249.7046 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 1606.9319 | 1606.9319 | 1606.9319 | 1606.9319 | 0 | 0 | 0 | 0 | 6427.7275 | 0 | 6427.7275 | 2249.7046 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6427.7275 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 6427.7275 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.4.8 | PSL | Commission/Maintenance/Decommission (PY6) | Testbed: Commission/Maintenance/Decommission (PY6) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3359.9484 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 0 | 9599.8527 | 0 | 9599.8527 | 3359.9484 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9599.8527 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9599.8527 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.4.8 | PSL | Commission/Maintenance/Decommission (PY6) | Testbed: Commission/Maintenance/Decommission (PY6) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 3500 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2500 | 2500 | 2500 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 3500 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.4.9 | PSL | Commission/Maintenance/Decommission (PY7) | Testbed: Commission/Maintenance/Decommission (PY7) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 2298.0733 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 1641.4809 | 1641.4809 | 1641.4809 | 1641.4809 | 0 | 0 | 0 | 0 | 6565.9236 | 0 | 6565.9236 | 2298.0733 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6565.9236 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 6565.9236 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.4.9 | PSL | Commission/Maintenance/Decommission (PY7) | Testbed: Commission/Maintenance/Decommission (PY7) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3432.1873 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 20 | 20 | 20 | 20 |  |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 2451.5624 | 2451.5624 | 2451.5624 | 2451.5624 | 0 | 0 | 0 | 0 | 9806.2495 | 0 | 9806.2495 | 3432.1873 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9806.2495 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 9806.2495 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.4.9 | PSL | Commission/Maintenance/Decommission (PY7) | Testbed: Commission/Maintenance/Decommission (PY7) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 3500 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2500 | 2500 | 2500 | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 2500 | 2500 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 3500 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.4.10 | PSL | Commission/Maintenance/Decommission (PY8) | Testbed: Commission/Maintenance/Decommission (PY8) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C4 | 35% | 1173.7409 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | [10 empty] | 40 | 0.26667 | 1676.7727 | 1676.7727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3353.5455 | 0 | 3353.5455 | 1173.7409 | 0 | 3353.5455 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 3353.5455 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.4.10 | PSL | Commission/Maintenance/Decommission (PY8) | Testbed: Commission/Maintenance/Decommission (PY8) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 1752.9897 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | [10 empty] | 40 | 0.26667 | 2504.271 | 2504.271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5008.5419 | 0 | 5008.5419 | 1752.9897 | 0 | 5008.5419 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 5008.5419 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.4.10 | PSL | Commission/Maintenance/Decommission (PY8) | Testbed: Commission/Maintenance/Decommission (PY8) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 700 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | [10 empty] | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2000 | 700 | 0 | 2000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.5.5 | PSL | Procure Tools & Equipment, & Consumables | Tools & Equipment: Procure Tools & Consumables |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C4 | 35% | 3024.4097 | 0 | [9 empty] | 8 | 8 | 8 |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.78 | 939.78 | 939.78 | 0 | 2819.34 | 0 | 2819.34 | 986.769 | 0 | [8 empty] | 8 | 8 | 8 |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 959.9853 | 959.9853 | 959.9853 | 0 | 2879.9558 | 0 | 2879.9558 | 1007.9845 | 0 | [7 empty] | 8 | 8 | 8 |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 980.625 | 980.625 | 980.625 | 0 | 0 | 2941.8749 | 0 | 2941.8749 | 1029.6562 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8641.1707 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2819.34 | 2879.9558 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.7.5.5 | PSL | Procure Tools & Equipment, & Consumables | Tools & Equipment: Procure Tools & Consumables |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 8032.5 | 4257.225 | [10 empty] | 2500 | 2500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 5000 | 2650 | 7650 | 1750 | 927.5 | [9 empty] | 2500 | 2500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 5000 | 2650 | 7650 | 1750 | 927.5 | [8 empty] | 2500 | 2500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 5000 | 2650 | 7650 | 1750 | 927.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22950 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.7
1.2 | 1.2.8.1.2 | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - 5 Drillers (w/ 2 alternates) (Driller_PSL_DirectHire) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 1982.1186 | 0 | Contract staff training/travel labor - 3 Direct Hire + 2 alternates - assuming 7 days @ 8 hours per | [10 empty] | 280 |  | 280 | 1.8667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22023.54 | 0 | 22023.54 | 0 | 22023.54 | 1982.1186 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22023.54 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 22023.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.2 | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - 10 PSL (Driller Lead/Engineers) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 3171.7575 | 0 | PSL staff training labor - Assuming 30 hours per PSL team member for training x 10 PSL Engineers | [10 empty] | 300 |  | 300 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35241.75 | 0 | 35241.75 | 0 | 35241.75 | 3171.7575 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35241.75 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 35241.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.2 | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - Safety Training Materials/Vendors |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 688.5 | 364.905 | SafeStart, rigging, and Red Cross training - additional training materials added in coordination with USAP contractor | [10 empty] | 5000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 5000 | 2650 | 7650 | 450 | 238.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7650 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.2 | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - Safety Equipment/Consumables |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 302.94 | 160.5582 | Procurement of replacement smoke detector batteries, smoke detectors, toe warmers, hand warmers, oxygen, CO, H2S, monitors, first aid kit, work gloves, knee pads, goggles, and N95 masks | [7 empty] | 1000 | 1000 | 200 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 200 | 0 | 0 | 2200 | 1166 | 3366 | 198 | 104.94 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3366 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.2 | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - 5 DH Drillers (w/ 2 alternates) - (Direct Hire Travel -1 Domestic, 2 International, 2 Local) | Foreign | Travel | Travel |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 881.28 | 467.0784 | Contract staff training Foreign Travel - 3 Direct Hire w/ 2 alternates - 5 Total (estimating 2 local, 1 domestic, 2 intl). Duration 7 days. $8200 total travel cost 2 Local - No travel costs 1 Domestic - $1800 2 International - $6400 | [10 empty] | 6400 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 0 | 6400 | 3392 | 9792 | 576 | 305.28 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9792 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.2 | PSL | FS1 Off-Ice Safety Training & PPE Procurement - 10 FTE Drillers (10-primary 2-alternates) & 1 Safety Officer | FS1 - Off-Ice EHWD & Safety Training - 5 DH Drillers (w/ 2 alternates) - (Direct Hire Travel -1 Domestic, 2 International, 2 Local) | Domestic | Travel | Travel |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 247.86 | 131.3658 | Contract staff training Domestic Travel - 3 Direct Hire w/ 2 alternates - 5 Total (estimating 2 local, 1 domestic, 2 intl). Duration 7 days. $8200 total travel cost 2 Local - No travel costs 1 Domestic - $1800 2 International - $6400 | [10 empty] | 1800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.3 | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - 8 Drillers (2 alternates) (Driller_PSL_DirectHire) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 3239.5746 | 0 | Contract staff training/travel labor - 8 Direct Hire (w/ 2 alternates) - assuming 7 days @ 8 hours per (448 hours total) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 224 | 224 |  | 448 | 2.9867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17997.6369 | 17997.6369 | 0 | 35995.2738 | 0 | 35995.2738 | 3239.5746 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35995.2738 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 35995.2738 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.3 | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - 10 PSL (Driller_Lead/Engineer) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 3239.9503 | 0 | PSL staff training labor - Assuming 30 hours per PSL team member for training x 10 PSL Engineers | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 150 | 150 |  | 300 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17999.7238 | 17999.7238 | 0 | 35999.4476 | 0 | 35999.4476 | 3239.9503 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35999.4476 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 35999.4476 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.3 | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - Safety Training Materials/Vendors |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 344.25 | 182.4525 | Red Cross and job specific training TBD - additional training materials added in coordination with USAP contractor | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 2500 | 1325 | 3825 | 225 | 119.25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3825 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.3 | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - Safety Equipment/Consumables |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 344.25 | 182.4525 | Procurement of replacement smoke detector batteries, smoke detectors, toe warmers, hand warmers, absorbent pads, N95 masks, smoke and CO monitors | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1000 | 1000 | 500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 500 | 0 | 0 | 2500 | 1325 | 3825 | 225 | 119.25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3825 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.3 | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - 8 DH Drillers w/ 2 alternates - (Direct Hire Travel -1 Domestic 2 International) | Foreign | Travel | Travel |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 1321.92 | 700.6176 | Contract staff training International Travel - 8 Direct Hire w/ 2 alternates Duration 7 days. 2 Local - No travel costs 3 Domestic - $5400 3 International - $9600 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 4800 | 4800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 4800 | 0 | 9600 | 5088 | 14688 | 864 | 457.92 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14688 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.3 | PSL | FS2 Off-Ice Safety Training & PPE Procurement - 16 Drillers (14 - Primary 2 - alternates) & 1 Safety Officer | FS2 - Off-Ice EHWD & Safety Training - 6 DH Drillers w/ 2 alternates - (Direct Hire Travel -1 Domestic 2 International) | Domestic | Travel | Travel |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 743.58 | 394.0974 | Contract staff training Domestic Travel - 8 Direct Hire w/ 2 alternates Duration 7 days. 2 Local - No travel costs 3 Domestic - $5400 3 International - $9600 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 2700 | 2700 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 2700 | 0 | 5400 | 2862 | 8262 | 486 | 257.58 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8262 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.4 | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - 22 Drillers (w/ 4 alternates) (Driller_PSL_DirectHire) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 19855.353 | 0 | Contract staff training/travel labor - 24 Direct Hire - 20 deploy w/ 4 alternates. Duration 14 - 8 hour days with travel. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1344 | 1344 |  | 2688 | 17.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110307.5165 | 110307.5165 | 0 | 220615.033 | 0 | 220615.033 | 19855.353 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220615.033 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 220615.033 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.4 | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - 10 PSL Staff - 2 Rotators (Engineer/Driller PSL_Lead) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 6619.2184 | 0 | PSL staff training labor - Assuming 60 hours per PSL team member for training x 10 PSL Engineers | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 300 | 300 |  | 600 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36773.4357 | 36773.4357 | 0 | 73546.8715 | 0 | 73546.8715 | 6619.2184 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73546.8715 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 73546.8715 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.4 | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - Safety Training Materials/Vendors |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 688.5 | 364.905 | SafeStart, rigging, job specific training (TBD) and Red Cross training - additional training materials added in coordination with USAP contractor | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2000 | 3000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 3000 | 0 | 0 | 0 | 5000 | 2650 | 7650 | 450 | 238.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7650 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.4 | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - Safety Equipment/Consumables |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 619.65 | 328.4145 | Procurement of replacement smoke detector batteries, smoke detectors, toe warmers, hand warmers, absorbent pads, N95 masks, smoke and CO monitors | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 2000 | 2000 | 500 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 500 | 0 | 0 | 4500 | 2385 | 6885 | 405 | 214.65 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6885 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.4 | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - 24 Drillers (Direct Hire Travel) | Foreign | Travel | Travel |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 2643.84 | 1401.2352 | Contract staff - Training Foreign Travel - 24 Direct Hire - 20 deploy w/ 4 alternates Duration 14 days with travel. 6 Local - No travel costs 12 Domestic - $21600 6 International - $19200 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 9600 | 9600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 9600 | 0 | 19200 | 10176 | 29376 | 1728 | 915.84 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29376 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.4 | PSL | FS3 Off-Ice Safety Training & PPE Procurement - 32 Drillers (28 - primary 4 - alternates) & 1 Safety Officer | FS3 - Off-Ice EHWD & Safety Training - 24 Drillers (Direct Hire Travel) | Domestic | Travel | Travel |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 2974.32 | 1576.3896 | Contract staff -Training Domestic Travel - 24 Direct Hire - 20 deploy w/ 4 alternates Duration 14 days with travel. 6 Local - No travel costs 12 Domestic - $21600 6 International - $19200 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 10800 | 10800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10800 | 10800 | 0 | 21600 | 11448 | 33048 | 1944 | 1030.32 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33048 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.1.5 | PSL | FS3 Off-Ice Logging Winch Training with IDP (3 Drillers 1 day) | FS3 - Off-Ice Logging Winch Training - 3 Drillers 1 day |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 264.7687 | 0 | Logging Winch Training - 3 Drillers 1 day training with IDP support (IDP cost in Calibration WBS) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 24 |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 0 | 0 | 2941.8749 | 0 | 2941.8749 | 264.7687 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2941.8749 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.5.2 | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Driller_PSL_Manager) |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 1397.2394 | 0 | 1 Drill Manager, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0.42667 | 0 | 4799.9263 | 0 | 0 | 2879.9558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7679.8822 | 0 | 7679.8822 | 691.1894 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0.42667 | 0 | 4903.1248 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7844.9996 | 0 | 7844.9996 | 706.05 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15524.8818 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 7679.8822 | 7844.9996 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.5.2 | UW | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Safety Engineer) | Zernick | Labor Hours | Labor - Task | EN-S | E - Extrapolation from Actuals | 53 | 46 | 35% | 53% | Off Ice | C1 | 9% | 657.9612 | 348.7194 | 1 Safety Engineer, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0.42667 | 0 | 2986.389 | 0 | 0 | 1791.8334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4778.2223 | 2532.4578 | 7310.6802 | 430.04 | 227.9212 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7310.6802 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3539.424 | 0 | 0 | 0 | 1238.7984 | 0 | 0 | 1.2.8
1.2 | 1.2.8.5.2 | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Driller_PSL_DirectHire) x 3 |  | Labor Hours | Labor - Task | TE | E - Extrapolation from Actuals | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 1388.3891 | 0 | 3 Seasonal drillers, 5 days deployment travel 3 days redeployment (No Contributed drillers) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120 |  |  | 72 | [7 empty] | 192 | 1.28 | 0 | 9641.5912 | 0 | 0 | 5784.9547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15426.5459 | 0 | 15426.5459 | 1388.3891 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15426.5459 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 15426.5459 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.5.2 | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (PSL_Engineer) x 9 |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 6220.7045 | 0 | 9 PSL Engineers (2 Rotators), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 280 | 128 |  | 168 | [7 empty] | 576 | 3.84 | 0 | 33599.4845 | 15359.7643 | 0 | 20159.6907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69118.9394 | 0 | 69118.9394 | 6220.7045 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69118.9394 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 69118.9394 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.5.2 | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Drill Team) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 2093.04 | 1109.3112 | 16 - PQ's 1 Drill Lead, 1 Safety Engineer, 5 Direct Hire (2 alternate) & 9 PSL Engineers @ $950/each (anticipated cost) | [8 empty] | 7600 |  | 7600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7600 | 0 | 7600 | 0 | 15200 | 8056 | 23256 | 1368 | 725.04 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23256 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.5.2 | PSL | PQ, ECW & Deployment Travel Costs (FS1) | Deployment Travel & PQ Costs (FS1) (Drill Team) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 3470.04 | 1839.1212 | 14 - Deployment Travel @ $1800 each | [9 empty] | 12600 | 12600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12600 | 12600 | 0 | 25200 | 13356 | 38556 | 2268 | 1202.04 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38556 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.5.11 | PSL | On-Ice Labor (FS1) | On-Ice Labor (FS1) (PSL Engineers) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 85.1852 | 115 | 0% | 0% | On Ice | C2 | 12.5% | 50999.2175 | 0 | EE/ME Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 0 days northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1044 | 1818 | 1728 | [8 empty] | 4590 | 30.6 | 0 | 92798.5761 | 161597.5205 | 153597.6432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407993.7398 | 0 | 407993.7398 | 50999.2175 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 407993.7398 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 407993.7398 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.5.11 | PSL | On-Ice Labor (FS1) | On-Ice Labor (FS1) (PSL Contract Drillers) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 57.037 | 77 | 0% | 0% | On Ice | C2 | 12.5% | 10980.7011 | 0 | Technician Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 0 days northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 279 | 549 | 648 | [8 empty] | 1476 | 9.84 | 0 | 16604.9626 | 32674.2813 | 38566.3648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87845.6086 | 0 | 87845.6086 | 10980.7011 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87845.6086 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 87845.6086 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.5.11 | UW | On-Ice Labor (FS1) | On-Ice Labor (FS1) (Safety Engineer) | Zernick | Labor Hours | Labor - Task | EN-S | D - Expert Opinion | 34.0741 | 46 | 35% | 53% | On Ice | C1 | 9% | 1963.0211 | 1040.4012 | Safety Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 0 days northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 162 | 135 | [9 empty] | 297 | 1.98 | 0 | 7775.8807 | 6479.9006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14255.7813 | 7555.5641 | 21811.3453 | 1283.0203 | 680.0008 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21811.3453 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 10559.838 | 0 | 0 | 0 | 3695.9433 | 0 | 0 | 1.2.8
1.2 | 1.2.8.6.2 | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (Driller_PSL_Manager) |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 706.05 | 0 | 1 Drill Manager, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0.42667 | 0 | 4903.1248 | 0 | 0 | 2941.8749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7844.9996 | 0 | 7844.9996 | 706.05 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7844.9996 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 7844.9996 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.6.2 | UW | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (Safety_Engineer) | Zernick | Labor Hours | Labor - Task | EN-S | E - Extrapolation from Actuals | 53 | 46 | 35% | 53% | Off Ice | C1 | 9% | 672.1074 | 356.2169 | 1 Safety Engineer, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0.42667 | 0 | 3050.5963 | 0 | 0 | 1830.3578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4880.9541 | 2586.9057 | 7467.8598 | 439.2859 | 232.8215 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7467.8598 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 3615.5216 | 0 | 0 | 0 | 1265.4325 | 0 | 1.2.8
1.2 | 1.2.8.6.2 | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (PSL_Direct_Hire) |  | Labor Hours | Labor - Task | TE | E - Extrapolation from Actuals | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 2836.479 | 0 | 6 PSL Direct Hire, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 240 |  |  | 144 | [7 empty] | 384 | 2.56 | 0 | 19697.7708 | 0 | 0 | 11818.6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31516.4333 | 0 | 31516.4333 | 2836.479 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31516.4333 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 31516.4333 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.6.2 | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (PSL_Engineer) |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 6354.4497 | 0 | 9 PSL Engineers w/ 2 Rotators, 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 280 | 128 |  | 168 | [7 empty] | 576 | 3.84 | 0 | 34321.8734 | 15689.9993 | 0 | 20593.124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70604.9966 | 0 | 70604.9966 | 6354.4497 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70604.9966 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 70604.9966 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.6.2 | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (Drill Team) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 2485.485 | 1317.307 | 19 - PQ's @ $950/each (anticipated cost) - 2 Alternates and 17 Primaries | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 9025 | 9025 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9025 | 9025 | 0 | 18050 | 9566.5 | 27616.5 | 1624.5 | 860.985 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27616.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.6.2 | PSL | PQ, ECW & Deployment Travel Costs (FS2) Team | Deployment Travel & PQ Costs (FS2) (Drill Team) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 4213.62 | 2233.2186 | 17 - Deploy travel costs w/ 2 PSL rotator @ $1800 each | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 15300 | 15300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15300 | 15300 | 30600 | 16218 | 46818 | 2754 | 1459.62 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46818 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.6.6.9 | PSL | Parallel Gens through PDM Bays (Driller & Contract Gen Tech) | Generators/PDM: Parallel Gens through PDM Bays (Contract Gen Tech) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | On Ice | C3 | 20% | 2780 | 0 | Estimated 18 days of contractor cost @ $250 per hour 9 hour days plus travel & PQ allowance of $1200 for a total of $41,700 or $5957 for each of the 7 days of work at the Pole. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13900 | [10 empty] | 0 | 0 | 0 | 13900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13900 | 0 | 13900 | 2780 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13900 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.6.6.10 | PSL | Load Test using Resistance Heaters (Driller & Contract Gen Tech) | Generators/PDM: Load Test using Resistance Heaters (Contract Gen Tech) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | On Ice | C3 | 20% | 2780 | 0 | Estimated 18 days of contractor cost @ $250 per hour 9 hour days plus travel & PQ allowance of $1200 for a total of $41,700 or $5957 for each of the 7 days of work at the Pole. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 13900 | [10 empty] | 0 | 0 | 0 | 13900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13900 | 0 | 13900 | 2780 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13900 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.6.6.11 | PSL | Test Safety Shut-downs (Driller & Contract Gen Tech) | Generators/PDM: Test Safety Shut-downs (Contract Gen Tech) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | On Ice | C3 | 20% | 2780 | 0 | Estimated 18 days of contractor cost @ $250 per hour 9 hour days plus travel & PQ allowance of $1200 for a total of $41,700 or $5957 for each of the 7 days of work at the Pole. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 13900 | [9 empty] | 0 | 0 | 0 | 0 | 13900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13900 | 0 | 13900 | 2780 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13900 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.6.15 | PSL | On-ice Labor FS2 | On-Ice Labor (FS2) (PSL Engineers) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 85.1852 | 115 | 0% | 0% | On Ice | C2 | 12.5% | 50563.4742 | 0 | EE/ME Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 990 | 1818 | 1647 | [8 empty] | 4455 | 29.7 | 0 | 89890.6207 | 165071.8671 | 149545.3054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404507.7932 | 0 | 404507.7932 | 50563.4742 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404507.7932 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 404507.7932 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.6.15 | PSL | On-ice Labor FS2 | On-Ice Labor (FS2) (PSL Drillers) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 57.037 | 77 | 0% | 0% | On Ice | C2 | 12.5% | 25648.1391 | 0 | Technician Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 819 | 1197 | 1359 | [8 empty] | 3375 | 22.5 | 0 | 49791.5873 | 72772.3199 | 82621.2053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205185.1125 | 0 | 205185.1125 | 25648.1391 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 205185.1125 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 205185.1125 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.6.15 | UW | On-ice Labor FS2 | On-Ice Labor (FS2) (Safety Engineer) | Zernick | Labor Hours | Labor - Task | EN-S | D - Expert Opinion | 34.0741 | 46 | 35% | 53% | On Ice | C2 | 12.5% | 3572.7232 | 1893.5433 | Safety Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 48 | 225 | 108 | [8 empty] | 381 | 2.54 | 0 | 2353.4999 | 11032.0307 | 5295.3747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18680.9054 | 9900.8798 | 28581.7852 | 2335.1132 | 1237.61 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28581.7852 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 13837.7077 | 0 | 0 | 0 | 4843.1977 | 0 | 1.2.8
1.2 | 1.2.8.7.2 | PSL | PQ, ECW & Deployment Travel Costs (FS3) | Deployment Travel & PQ Costs (FS3) (Driller_Manager) |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 721.23 | 0 | 1 (Drill Manager), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  |  | 24 | [7 empty] | 64 | 0.42667 | 0 | 5008.5419 | 0 | 0 | 3005.1252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8013.6671 | 0 | 8013.6671 | 721.23 | 0 | 8013.6671 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 8013.6671 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.7.2 | UW | PQ, ECW & Deployment Travel Costs (FS3) | Deployment Travel & PQ Costs (FS3) (Safety_Engineer) | Zernick | Labor Hours | Labor - Task | EN-S | E - Extrapolation from Actuals | 53 | 46 | 35% | 53% | Off Ice | C1 | 9% | 686.5577 | 363.8756 | 1 (Safety Engineer), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 40 |  | 24 | [8 empty] | 64 | 0.42667 | 0 | 3116.1841 | 0 | 1869.7105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4985.8946 | 2642.5242 | 7628.4188 | 448.7305 | 237.8272 | 7628.4188 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 3693.2553 | 0 | 0 | 0 | 1292.6393 | 1.2.8
1.2 | 1.2.8.7.2 | PSL | PQ, ECW & Deployment Travel Costs (FS3) | Deployment Travel & PQ Costs (FS3) (Driller_PSL_Direct_Hire) |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 14424.6008 | 0 | 20 (PSL Direct Hire), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 800 |  | 480 | [8 empty] | 1280 | 8.5333 | 0 | 100170.839 | 0 | 60102.5034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160273.3424 | 0 | 160273.3424 | 14424.6008 | 0 | 160273.3424 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 160273.3424 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.7.2 | PSL | PQ, ECW & Deployment Travel Costs (FS3) | Deployment Travel & PQ Costs (FS3) (Engineer_PSL) |  | Labor Hours | Labor - Task | EN | E - Extrapolation from Actuals | 115 | 115 | 0% | 0% | Off Ice | C1 | 9% | 5769.8403 | 0 | 8 (PSL Engineers), 5 days deployment travel 3 days redeployment | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 320 |  | 192 | [8 empty] | 512 | 3.4133 | 0 | 40068.3356 | 0 | 24041.0014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64109.3369 | 0 | 64109.3369 | 5769.8403 | 0 | 64109.3369 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 64109.3369 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.7.2 | PSL | PQ, ECW & Deployment Travel Costs (FS3) | PQ Costs (FS3) (Drill Team) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 4316.895 | 2287.9543 | 33 - PQ's @ $950/each (anticipated cost) 28 Drillers, Safety Engineer & 4 Alternates | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 15675 | 15675 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15675 | 15675 | 0 | 0 | 31350 | 16615.5 | 47965.5 | 2821.5 | 1495.395 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47965.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.7.2 | PSL | PQ, ECW & Deployment Travel Costs (FS3) | Travel (FS3) (Drill Team) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 7187.94 | 3809.6082 | 29 - Deploy travel costs 29 (28 Drillers & 1 Safety Engineer) @ $1800 each | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 26100 | 26100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26100 | 26100 | 52200 | 27666 | 79866 | 4698 | 2489.94 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79866 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.7.13 | PSL | On-Ice Labor (FS3) | On-Ice Labor (FS3) (PSL Engineers) |  | Labor Hours | Labor - Task | EN | D - Expert Opinion | 85.1852 | 115 | 0% | 0% | On Ice | C2 | 12.5% | 46850.7361 | 0 | EE/ME Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 702 | 1872 | 1467 | [8 empty] | 4041 | 26.94 | 0 | 65111.0453 | 173629.4542 | 136065.3896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374805.8892 | 0 | 374805.8892 | 46850.7361 | 0 | 374805.8892 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 374805.8892 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.7.13 | PSL | On-Ice Labor (FS3) | On-Ice Labor (FS3) (PSL Contract Drillers) |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 57.037 | 77 | 0% | 0% | On Ice | C2 | 12.5% | 80694.6881 | 0 | Technician Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1890 | 4680 | 3825 | [8 empty] | 10395 | 69.3 | 0 | 117374.0918 | 290640.6082 | 237542.8048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 645557.5047 | 0 | 645557.5047 | 80694.6881 | 0 | 645557.5047 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 645557.5047 | 0 | 0 | 0 | 0 | 1.2.8
1.2 | 1.2.8.7.13 | UW | On-Ice Labor (FS3) | On-Ice Labor (FS3) (Safety Engineer) | Zernick | Labor Hours | Labor - Task | EN-S | D - Expert Opinion | 34.0741 | 46 | 35% | 53% | On Ice | C2 | 12.5% | 5862.2479 | 3106.9914 | Safety Engineer Labor Totals from Population file. Assumes 2 days in McMurdo southbound and 1 day northbound. | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 144 | 234 | 234 | [8 empty] | 612 | 4.08 | 0 | 7212.3004 | 11719.9882 | 11719.9882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30652.2767 | 16245.7067 | 46897.9834 | 3831.5346 | 2030.7133 | 46897.9834 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 22705.3902 | 0 | 0 | 0 | 7946.8866 | 1.2.8
1.2 | 1.2.9.1.3.2 | UW | Procure Sensor Handling Equipment | Off-Ice Install: Procure Sensor Handling Equipment |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1690.6 | 0 |  | 8453 | [11 empty] | 0 | 0 | 8453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8453 | 0 | 8453 | 1690.6 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8453 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1.2 | 1.2.9.1.3.3 | UW | Procure ESD Mitigation Equipment | Off-Ice Install: Procure ESD Sensor Handling Equipment |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1942.15 | 0 | Lab coats, ESDgloves, ESD runners | 5549 | [11 empty] | 0 | 0 | 5549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5549 | 0 | 5549 | 1942.15 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5549 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1.2 | 1.2.9.2.8 | UW | Procure Installation Hardware | Off-Ice Install: Procure Installation Hardware |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 21600 | 0 |  |  | 36000 | 36000 | 36000 | [8 empty] | 0 | 0 | 0 | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108000 | 0 | 108000 | 21600 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1.2 | 1.2.9.2.9 | UW | Procure Installation Weights | Off-Ice Install: Procure Installation Weights |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 3465 | 0 |  |  | 3300 | 3300 | 3300 | [8 empty] | 0 | 0 | 0 | 3300 | 3300 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 0 | 9900 | 3465 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1.2 | 1.2.9.3.2.1 | UW | IME ICL Quad Connectivity Tester Design, Prototype, Production (2023-24) | Off-ice Install: IME ICL Quad Connectivity Tester Design, Prototype & Production (2023-24) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1680 | 0 | IME ICL QCT | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 600 | 600 | 600 |  | 2000 | 1000 |  |  |  |  | 0 | 0 | 0 | 0 | 600 | 600 | 600 | 0 | 2000 | 1000 | 0 | 0 | 0 | 0 | 4800 | 0 | 4800 | 1680 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1.2 | 1.2.9.3.2.1 | UW | IME ICL Quad Connectivity Tester Design, Prototype, Production (2023-24) | Off-ice Install: IME ICL Quad Connectivity Tester Design, Prototype & Production (2023-24) | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 247.86 | 131.3658 | IME ICL QCT 1 domestic travel to NTS at MSU | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 900 | 900 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1.2 | 1.2.9.3.3.2 | PSL | IME Depth Readout Development and System Integration (2022-23) | Off-ice Install: IME Depth Readout Development and System Integration (2022-23) | Wisniewski | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 1409.67 | 0 | Duplicate system (1/TOS plus spares) | [7 empty] | 10 | 20 | 20 | 10 |  | 60 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1174.725 | 2349.45 | 2349.45 | 1174.725 | 0 | 7048.35 | 0 | 7048.35 | 1409.67 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048.35 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 7048.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1.2 | 1.2.9.3.3.2 | PSL | IME Depth Readout Development and System Integration (2022-23) | Off-ice Install: IME Depth Readout Development and System Integration (2022-23) | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 247.86 | 131.3658 | 1 domestic trip ($1800/person) to MSU for testing with full length quad | [7 empty] | 450 | 450 | 450 | 450 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 450 | 450 | 450 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1.2 | 1.2.9.3.3.2 | UW | IME Depth Readout Development and System Integration (2022-23) | Off-ice Install: IME Depth Readout Development and System Integration (2022-23) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 1190 | 0 | Purchasing 2x materials for spares | [7 empty] | 1700 |  | 1700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 0 | 1700 | 0 | 0 | 3400 | 0 | 3400 | 1190 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1.2 | 1.2.9.3.3.3 | PSL | IME Depth Readout System Final Integration (2023-24) | Off-Ice Install: IME Depth Readout System Final Integration (2023-24) | Wisniewski | Labor Hours | Labor - Task | EN-EE | D - Expert Opinion | 115 | 115 | 0% | 0% | Off Ice | C3 | 20% | 959.9853 | 0 | Test of all Paro Sensors | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 20 | 20 |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2399.9632 | 2399.9632 | 0 | 0 | 0 | 4799.9263 | 0 | 4799.9263 | 959.9853 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4799.9263 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1.2 | 1.2.9.3.3.7 | UW | Procure Pressure Sensors | Off-Ice Install: Procure Pressure Sensors |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 13099.5 | 0 | May delay pressure sensor procurement if calibration shelf life duration in question. Vendor quote for 2022 is 11800/each, with increment of 3-5% / year | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 34932 | 34932 | 34932 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 34932 | 34932 | 34932 | 0 | 0 | 0 | 0 | 0 | 104796 | 0 | 104796 | 13099.5 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104796 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1.2 | 1.2.9.4.2.3 | UW | Procure Logbook Tablets | Off-Ice Install: Procure Tablets for Logbook |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 2088.45 | 0 | two rugged tablets for logbook keeping | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1989 | 1989 | 1989 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1989 | 1989 | 1989 | 0 | 0 | 0 | 5967 | 0 | 5967 | 2088.45 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5967 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1.2 | 1.2.9.4.2.5 | UW | Procure Laser Rangers, Tape Measures, Shop Lights, Helmets for Installation | Off-Ice Install: Procure Laser Rangers & various Installation Supplies |  | CapEx | CapEx |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1071 | 0 | Laser ranges to measure well depth and distance between DOMs (2) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1339 | 1339 | 1339 | 669 | 669 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1339 | 1339 | 1339 | 669 | 669 | 0 | 0 | 0 | 5355 | 0 | 5355 | 1071 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.9
1.2 | 1.2.10.1.3 | PSL | FS3 Off-Ice Installation Training (Drillers, Installers, Management, including alternates) | Install FS3: FS3 Off-Ice Installation Training: Drillers | PSL Driller | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 2127.3592 | 0 | 3x8 hours installation training (sensor handling, practice at the tower). Need (3+1 spare)x3=12 drillers | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 288 |  | 288 | 1.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23637.325 | 0 | 23637.325 | 0 | 23637.325 | 2127.3592 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23637.325 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 23637.325 | 0 | 0 | 0 | 0 | 0 | 1.2.10
1.2 | 1.2.10.4.2 | UW | PQ, ECW, Deployment Travel Costs Installation Team FS2 (Headcount 1) | Install FS2: Install Team FS2 PQ Costs (Headcount 1) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 96.39 | 51.0867 | 1 - PQ @ $700/each (anticipated cost) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 700 | 371 | 1071 | 63 | 33.39 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.10
1.2 | 1.2.10.4.2 | UW | PQ, ECW, Deployment Travel Costs Installation Team FS2 (Headcount 1) | Install FS2: Install Team FS2 ECW Costs (Headcount 1) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 34.425 | 18.2452 | 1 - ECW allowance @ $250/each | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 250 | 132.5 | 382.5 | 22.5 | 11.925 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.10
1.2 | 1.2.10.4.2 | UW | PQ, ECW, Deployment Travel Costs Installation Team FS2 (Headcount 1) | Install FS2: Install Team FS2 Deployment Travel Costs (Headcount 1) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 247.86 | 131.3658 | 1 - International Travel (3 nights southbound, 2 nights northbound, plus per diem) @ $1800/each | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [7 empty] | 0 | 0 | 0 | 1080 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.10
1.2 | 1.2.10.4.10 | UW | Installation: On-Ice Labor (FS2) | Installation: On-Ice Labor (FS2) (Installation Lead) | Tosi | Labor Hours | Labor - LoE | SC | D - Expert Opinion | 33.3333 | 52 | 35% | 53% | On Ice | C1 | 9% | 2615.5122 | 1386.2215 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 162 | 234 | [8 empty] | 396 | 2.64 | 0 | 0 | 7770.3869 | 11223.8921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18994.279 | 10066.9679 | 29061.2468 | 1709.4851 | 906.0271 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29061.2468 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 14069.8363 | 0 | 0 | 0 | 4924.4427 | 0 | 1.2.10
1.2 | 1.2.10.5.2 | UW | PQ, ECW, Deployment Travel Costs Install FS2 Installation Team | Install FS3: Install Team FS3 PQ Costs (Headcount 1) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 96.39 | 51.0867 | 1 - PQ @ $700/each (anticipated cost) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 700 | 371 | 1071 | 63 | 33.39 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.10
1.2 | 1.2.10.5.2 | UW | PQ, ECW, Deployment Travel Costs Install FS2 Installation Team | Install FS3: Install Team FS3 ECW Costs (Headcount 1) |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 34.425 | 18.2452 | 1 - ECW allowance @ $250/each | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 250 | 132.5 | 382.5 | 22.5 | 11.925 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.10
1.2 | 1.2.10.5.2 | UW | PQ, ECW, Deployment Travel Costs Install FS2 Installation Team | Install FS3: Install Team FS3 Deployment Costs (Headcount 1 + 9 in-kind) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 247.86 | 131.3658 | 1 - International Travel (3 nights southbound, 2 nights northbound, plus per diem) @ $1800/each | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [7 empty] | 0 | 0 | 0 | 1080 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | 2754 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.2.10
1.2 | 1.2.10.5.8 | UW | Installation: On-Ice Labor (FS3) | Installation: On-Ice Labor (FS3) (Installation Lead) | Tosi | Labor Hours | Labor - Task | SC | D - Expert Opinion | 30.1282 | 52 | 35% | 53% | On Ice | C1 | 9% | 3402.7391 | 1803.4517 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 108 | 234 | 216 | [8 empty] | 558 | 3.72 | 0 | 4782.8225 | 10362.7822 | 9565.6451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24711.2498 | 13096.9624 | 37808.2122 | 2224.0125 | 1178.7266 | 37808.2122 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 18304.6295 | 0 | 0 | 0 | 6406.6203 | 1.2.10
1.3 | 1.3.3.1.2.5 | UW | PDOM Rev3 Mainboard production (Qty. 27) | Domestic trip to PCA manufacturer | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 247.86 | 131.3658 |  | 1800 | [11 empty] | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3
1.3 | 1.3.3.1.2.5 | UW | PDOM Rev3 Mainboard production (Qty. 27) | 27 Rev3 PDOM Mainboards |  | CapEx | CapEx |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 5349.375 | 0 |  | 42795 | [11 empty] | 0 | 0 | 42795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42795 | 0 | 42795 | 5349.375 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42795 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3
1.3 | 1.3.3.1.2.5 | UW | PDOM Rev3 Mainboard production (Qty. 27) | 27 PDOM Calibration Boards |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 3510 | 0 |  | 17550 | [11 empty] | 0 | 0 | 17550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17550 | 0 | 17550 | 3510 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17550 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3
1.3 | 1.3.3.2.2.5 | UW | PDOM HV system production (Qty. 27) | 27 PDOM HV subsystems (HV supply PCA) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1890 | 0 |  | 9450 | [11 empty] | 0 | 0 | 9450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9450 | 0 | 9450 | 1890 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9450 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3
1.3 | 1.3.3.4.1 | UW | Refurbish 10 IceCube DOMs | 35 Penetrator Cable Assemblies and attachment hardware |  | CapEx | CapEx |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 1921.5 | 0 |  |  |  | 21350 | [9 empty] | 0 | 0 | 0 | 0 | 21350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21350 | 0 | 21350 | 1921.5 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21350 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3
1.3 | 1.3.3.4.5.1 | PSL | Refurbishment Batch #1 (Qty. 20) | Refurbishment Batch #1 (Qty. 20) | N.N. | Labor Hours | Labor - Task | TE | A - Analogy | 89 | 77 | 0% | 0% | Off Ice | C3 | 20% | 4363.848 | 0 |  | 120 | 120 | [10 empty] | 240 | 1.6 | 10909.62 | 10909.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21819.24 | 0 | 21819.24 | 4363.848 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21819.24 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 21819.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3
1.3 | 1.3.3.4.5.1 | UW | Refurbishment Batch #1 (Qty. 20) | Refurbishment Batch #1 (Qty. 20) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1836 | 973.08 |  | 3000 | 3000 | [10 empty] | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 3180 | 9180 | 1200 | 636 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9180 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3
1.3 | 1.3.3.4.5.2 | UW | FAT Batch #1 | FAT Batch #1 | Scientist | Labor Hours | Labor - Task | SC | A - Analogy | 46 | 52 | 35% | 53% | Off Ice | C3 | 20% | 2523.4503 | 1337.4286 |  |  | 10 | 100 | 20 | [8 empty] | 130 | 0.86667 | 0 | 634.3515 | 6343.515 | 1268.703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8246.5695 | 4370.6818 | 12617.2513 | 1649.3139 | 874.1364 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12617.2513 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 6108.57 | 0 | 0 | 0 | 2137.9995 | 0 | 0 | 0 | 1.3.3
1.3 | 1.3.3.4.5.2 | UW | FAT Batch #1 | FAT Batch #1 |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1530 | 810.9 |  |  | 5000 | [10 empty] | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 2650 | 7650 | 1000 | 530 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7650 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3
1.3 | 1.3.3.4.5.3 | PSL | Packing Batch #1 | Packing Batch #1 | N.N. | Labor Hours | Labor - Task | TE | A - Analogy | 46 | 77 | 0% | 0% | Off Ice | C3 | 20% | 375.912 | 0 |  |  |  |  | 40 | [8 empty] | 40 | 0.26667 | 0 | 0 | 0 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 0 | 1879.56 | 375.912 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1879.56 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1879.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3
1.3 | 1.3.3.4.5.3 | UW | Packing Batch #1 | Packing Batch #1 |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 306 | 162.18 |  |  |  |  | 1000 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 530 | 1530 | 200 | 106 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3
1.3 | 1.3.3.4.6 | UW | Ship 2 + 1 spare PDOMs for Strings 87-88 to Pt. Hueneme | Ship to Pt. Hueneme |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 153 | 81.09 | [11 empty] | 500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500 | 265 | 765 | 100 | 53 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3
1.3 | 1.3.3.4.7 | UW | Ship 12 + 1 spare PDOMs for Strings 89-93 to Pt. Hueneme | Ship to Pt. Hueneme |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 306 | 162.18 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 530 | 1530 | 200 | 106 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3.3
1.3 | 1.3.4.2.3.3 | UW | Firmware support during D-Egg FAT | Firmware support during D-Egg FAT | S. Griffin | Labor Hours | Labor - LoE | EN | D - Expert Opinion | 47 | 49 | 35% | 53% | Off Ice | C1 | 9% | 1570.7845 | 832.5158 |  | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 |  |  |  |  | 176 | 1.1733 | 1425.9118 | 1425.9118 | 1425.9118 | 1425.9118 | 1425.9118 | 1425.9118 | 1425.9118 | 1425.9118 | 0 | 0 | 0 | 0 | 11407.2948 | 6045.8662 | 17453.161 | 1026.6565 | 544.128 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17453.161 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 8449.848 | 0 | 0 | 0 | 2957.4468 | 0 | 0 | 0 | 1.3.4
1.3 | 1.3.4.2.3.5 | UW | Firmware support during mDOM FAT | Firmware support during mDOM FAT | S. Griffin | Labor Hours | Labor - LoE | EN | D - Expert Opinion | 47 | 49 | 35% | 53% | Off Ice | C1 | 9% | 1767.1326 | 936.5803 |  |  |  |  | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 198 | 1.32 | 0 | 0 | 0 | 1425.9118 | 1425.9118 | 1425.9118 | 1425.9118 | 1425.9118 | 1425.9118 | 1425.9118 | 1425.9118 | 1425.9118 | 12833.2067 | 6801.5995 | 19634.8062 | 1154.9886 | 612.144 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19634.8062 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 9506.079 | 0 | 0 | 0 | 3327.1276 | 0 | 0 | 0 | 1.3.4
1.3 | 1.3.4.2.3.6 | UW | Firmware support during development of Calibration Devices, Special Devices, system integration, and commissioning | Firmware support during development of Calibration Devices, Special Devices, system integration, and commissioning | S. Griffin | Labor Hours | Labor - LoE | EN | D - Expert Opinion | 47 | 49 | 35% | 53% | Off Ice | C1 | 9% | 2763.9182 | 1464.8766 |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 84 | 0.56 | 453.6992 | 453.6992 | 453.6992 | 453.6992 | 453.6992 | 453.6992 | 453.6992 | 453.6992 | 453.6992 | 453.6992 | 453.6992 | 453.6992 | 5444.3907 | 2885.5271 | 8329.9178 | 489.9952 | 259.6974 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 84 | 0.56 | 463.4538 | 463.4538 | 463.4538 | 463.4538 | 463.4538 | 463.4538 | 463.4538 | 463.4538 | 463.4538 | 463.4538 | 463.4538 | 463.4538 | 5561.4451 | 2947.5659 | 8509.011 | 500.5301 | 265.2809 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 84 | 0.56 | 473.418 | 473.418 | 473.418 | 473.418 | 473.418 | 473.418 | 473.418 | 473.418 | 473.418 | 473.418 | 473.418 | 473.418 | 5681.0162 | 3010.9386 | 8691.9547 | 511.2915 | 270.9845 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | [5 empty] | 49 | 0.32667 | 483.5965 | 483.5965 | 483.5965 | 483.5965 | 483.5965 | 483.5965 | 483.5965 | 0 | 0 | 0 | 0 | 0 | 3385.1755 | 1794.143 | 5179.3185 | 304.6658 | 161.4729 | 30710.202 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4032.882 | 4119.589 | 4208.1601 | 2507.5374 | 1411.5087 | 1441.8561 | 1472.856 | 877.6381 | 1.3.4
1.4 | 1.4.1.1.1.3.2.1 | MSU | Fabrication | First article cable fabrication | Ng | Labor Hours | Labor - LoE | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C1 | 9% | 424.0778 | 233.2428 |  | 16 | 16 | 16 | [9 empty] | 48 | 0.32 | 1013.328 | 1013.328 | 1013.328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3039.984 | 1671.9912 | 4711.9752 | 273.5986 | 150.4792 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4711.9752 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3039.984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.1.3.2.2 | MSU | Acceptance testing | First article acceptance testing | Ng | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 62 | 62 | 0% | 55% | Off Ice | C4 | 35% | 1099.4609 | 604.7035 |  |  |  |  | 32 | [8 empty] | 32 | 0.21333 | 0 | 0 | 0 | 2026.656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026.656 | 1114.6608 | 3141.3168 | 709.3296 | 390.1313 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141.3168 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2026.656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.1.3.2.2 | MSU | Acceptance testing | First article acceptance testing | Wilkins | Labor Hours | Labor - Task | TE | D - Expert Opinion | 47 | 46.67 | 0% | 55% | Off Ice | C4 | 35% | 833.4623 | 458.4043 |  |  |  |  | 32 | [8 empty] | 32 | 0.21333 | 0 | 0 | 0 | 1536.336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536.336 | 844.9848 | 2381.3208 | 537.7176 | 295.7447 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2381.3208 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1536.336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.1.3.2.4 | MSU | First article shipping to breakout installation facility | First article shipping to breakout installation facility | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 628.2634 | 345.5448 |  |  |  |  | 16 | 16 | [7 empty] | 32 | 0.21333 | 0 | 0 | 0 | 1013.328 | 1013.328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026.656 | 1114.6608 | 3141.3168 | 405.3312 | 222.9322 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141.3168 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2026.656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.1.3.3 | MSU | Production readiness review | Production readiness review | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C2 | 12.5% | 687.163 | 377.9397 | [5 empty] | 56 | [7 empty] | 56 | 0.37333 | 0 | 0 | 0 | 0 | 3546.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3546.648 | 1950.6564 | 5497.3044 | 443.331 | 243.8321 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5497.3044 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3546.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.1.3.3 | MSU | Production readiness review | Production readiness review | Wilkins | Labor Hours | Labor - Task | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C2 | 12.5% | 520.9139 | 286.5027 | [5 empty] | 56 | [7 empty] | 56 | 0.37333 | 0 | 0 | 0 | 0 | 2688.588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2688.588 | 1478.7234 | 4167.3114 | 336.0735 | 184.8404 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4167.3114 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2688.588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.1.3.4 | MSU | Production of final six main cables | Production of final six main cables | Ng | Labor Hours | Labor - LoE | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C1 | 9% | 424.0778 | 233.2428 | [5 empty] | 16 | 16 | 16 | [5 empty] | 48 | 0.32 | 0 | 0 | 0 | 0 | 1013.328 | 1013.328 | 1013.328 | 0 | 0 | 0 | 0 | 0 | 3039.984 | 1671.9912 | 4711.9752 | 273.5986 | 150.4792 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4711.9752 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3039.984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.1.3.6 | MSU | Production main cable shipping to breakout installation facility | Production cable shipping to breakout installation facility | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 628.2634 | 345.5448 | [7 empty] | 8 | 8 | 16 |  |  |  | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 506.664 | 506.664 | 1013.328 | 0 | 0 | 0 | 2026.656 | 1114.6608 | 3141.3168 | 405.3312 | 222.9322 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141.3168 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2026.656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.2.2.1 | MSU | Breakout final design | Breakout final design | Wilkins | Labor Hours | Labor - Task | TE | D - Expert Opinion | 47 | 46.67 | 0% | 55% | Off Ice | C5 | 50% | 297.6651 | 163.7158 |  | 8 | [11 empty] | 8 | 0.053333 | 384.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.084 | 211.2462 | 595.3302 | 192.042 | 105.6231 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595.3302 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 384.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.2.2.1 | MSU | Breakout final design | Breakout final design | Ng | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 62 | 62 | 0% | 55% | Off Ice | C5 | 50% | 1963.323 | 1079.8276 |  | 40 | [11 empty] | 40 | 0.26667 | 2533.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2533.32 | 1393.326 | 3926.646 | 1266.66 | 696.663 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3926.646 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2533.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.2.2.2 | MSU | Breakout prototype production | Breakout prototype production | Ng | Labor Hours | Labor - LoE | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C1 | 9% | 282.7185 | 155.4952 |  | 16 | 16 | [10 empty] | 32 | 0.21333 | 1013.328 | 1013.328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026.656 | 1114.6608 | 3141.3168 | 182.399 | 100.3195 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141.3168 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2026.656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.2.2.3 | MSU | Breakout prototype testing | Breakout prototype testing | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C2 | 12.5% | 490.8308 | 269.9569 |  |  | 40 | [10 empty] | 40 | 0.26667 | 0 | 2533.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2533.32 | 1393.326 | 3926.646 | 316.665 | 174.1658 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3926.646 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2533.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.2.2.3 | MSU | Breakout prototype testing | Breakout prototype testing | Wilkins | Labor Hours | Labor - Task | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C2 | 12.5% | 372.0814 | 204.6448 |  |  | 40 | [10 empty] | 40 | 0.26667 | 0 | 1920.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920.42 | 1056.231 | 2976.651 | 240.0525 | 132.0289 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2976.651 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1920.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.2.2.3 | MSU | Breakout prototype testing | Breakout prototype testing | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 1339.2 | 736.56 |  |  | 9600 | [10 empty] | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 5280 | 14880 | 864 | 475.2 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14880 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.2.2.4 | MSU | Breakout final design review | Breakout final design review | Wilkins | Labor Hours | Labor - Task | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C3 | 20% | 1428.7925 | 785.8359 |  |  |  | 96 | [9 empty] | 96 | 0.64 | 0 | 0 | 4609.008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4609.008 | 2534.9544 | 7143.9624 | 921.8016 | 506.9909 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7143.9624 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4609.008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.2.2.4 | MSU | Breakout final design review | Breakout final design review | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 1884.7901 | 1036.6345 |  |  |  | 96 | [9 empty] | 96 | 0.64 | 0 | 0 | 6079.968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6079.968 | 3343.9824 | 9423.9504 | 1215.9936 | 668.7965 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9423.9504 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 6079.968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.2.2.4 | MSU | Breakout final design review | Breakout final design review | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 753.3 | 414.315 |  |  |  | 5400 | [9 empty] | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 2970 | 8370 | 486 | 267.3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8370 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.3.2 | MSU | MCA production | MCA production | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 892.8 | 491.04 | [9 empty] | 6400 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 0 | 0 | 0 | 6400 | 3520 | 9920 | 576 | 316.8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9920 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.3.2 | MSU | MCA production | MCA production | Ng | Labor Hours | Labor - LoE | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C1 | 9% | 494.7574 | 272.1166 | [9 empty] | 16 | 16 | 16 | 8 | 56 | 0.37333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1013.328 | 1013.328 | 1013.328 | 506.664 | 3546.648 | 1950.6564 | 5497.3044 | 319.1983 | 175.5591 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5497.3044 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3546.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.3.3 | MSU | Pre-ship review | Pre-ship review | Wilkins | Labor Hours | Labor - Task | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C3 | 20% | 833.4623 | 458.4043 | [12 empty] | 56 | 56 | 0.37333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2688.588 | 2688.588 | 1478.7234 | 4167.3114 | 537.7176 | 295.7447 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4167.3114 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2688.588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.3.3 | MSU | Pre-ship review | Pre-ship review | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 1099.4609 | 604.7035 | [12 empty] | 56 | 56 | 0.37333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3546.648 | 3546.648 | 1950.6564 | 5497.3044 | 709.3296 | 390.1313 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5497.3044 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3546.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.1.3.4 | MSU | Main Cable Assembly shipping to PTH (RDD 12/1/23 for FY24 vessel. ROS 12/1/2025) | Main Cable Assembly shipping to PTH | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 635.0172 | 349.2595 | [12 empty] | 16 | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1013.328 | 1013.328 | 557.3304 | 1570.6584 | 202.6656 | 111.4661 | 8 | 8 | [10 empty] | 16 | 0.10667 | 517.5573 | 517.5573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1035.1146 | 569.313 | 1604.4276 | 207.0229 | 113.8626 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3175.086 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1013.328 | 1035.1146 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.1.5 | MSU | BCA prototype testing | BCA prototype evaluation | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C4 | 35% | 1030.7446 | 566.9095 |  | 30 | [11 empty] | 30 | 0.2 | 1899.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899.99 | 1044.9945 | 2944.9845 | 664.9965 | 365.7481 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2944.9845 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1899.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.1.5 | MSU | BCA prototype testing | BCA prototype evaluation | Wilkins | Labor Hours | Labor - Task | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C4 | 35% | 781.3709 | 429.754 |  | 30 | [11 empty] | 30 | 0.2 | 1440.315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440.315 | 792.1733 | 2232.4882 | 504.1103 | 277.2606 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2232.4882 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1440.315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.1.5 | MSU | BCA prototype testing | BCA prototype evaluation | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 1339.2 | 736.56 |  | 9600 | [11 empty] | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 5280 | 14880 | 864 | 475.2 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14880 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.2.1 | MSU | BCA final design | BCA final design | Ng | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 62 | 62 | 0% | 55% | Off Ice | C4 | 35% | 4810.1413 | 2645.5777 |  | 80 | 60 | [10 empty] | 140 | 0.93333 | 5066.64 | 3799.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8866.62 | 4876.641 | 13743.261 | 3103.317 | 1706.8244 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13743.261 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 8866.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.2.1 | MSU | BCA final design | BCA final design | Wilkins | Labor Hours | Labor - Task | TE | D - Expert Opinion | 47 | 46.67 | 0% | 55% | Off Ice | C4 | 35% | 2083.6557 | 1146.0106 |  | 40 | 40 | [10 empty] | 80 | 0.53333 | 1920.42 | 1920.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3840.84 | 2112.462 | 5953.302 | 1344.294 | 739.3617 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5953.302 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3840.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.2.2 | MSU | BCA final design review | BCA final design review | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C2 | 12.5% | 1177.9938 | 647.8966 |  |  | 20 | 76 | [9 empty] | 96 | 0.64 | 0 | 1266.66 | 4813.308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6079.968 | 3343.9824 | 9423.9504 | 759.996 | 417.9978 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9423.9504 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 6079.968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.2.2 | MSU | BCA final design review | BCA final design review | Wilkins | Labor Hours | Labor - Task | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C2 | 12.5% | 892.9953 | 491.1474 |  |  | 20 | 76 | [9 empty] | 96 | 0.64 | 0 | 960.21 | 3648.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4609.008 | 2534.9544 | 7143.9624 | 576.126 | 316.8693 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7143.9624 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 4609.008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.2.2 | MSU | BCA final design review | BCA final design review | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 753.3 | 414.315 |  |  |  | 5400 | [9 empty] | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 2970 | 8370 | 486 | 267.3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8370 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.2.4 | MSU | BCA procurement | BCA procurement | Ng | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 62 | 62 | 0% | 55% | Off Ice | C4 | 35% | 2748.6522 | 1511.7587 |  |  |  | 40 | 32 | 8 | [7 empty] | 80 | 0.53333 | 0 | 0 | 2533.32 | 2026.656 | 506.664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5066.64 | 2786.652 | 7853.292 | 1773.324 | 975.3282 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7853.292 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 5066.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.3.1 | MSU | BCA manufacturing | BCA manufacturing - first two strings | Ng | Labor Hours | Labor - LoE | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C1 | 9% | 706.7963 | 388.738 | [5 empty] | 16 | 16 | 16 | 16 | 16 |  |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 1013.328 | 1013.328 | 1013.328 | 1013.328 | 1013.328 | 0 | 0 | 0 | 5066.64 | 2786.652 | 7853.292 | 455.9976 | 250.7987 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7853.292 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 5066.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.3.1 | MSU | BCA manufacturing | BCA manufacturing - first two strings | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 892.8 | 491.04 | [6 empty] | 6400 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 3520 | 9920 | 576 | 316.8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9920 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.3.1 | MSU | BCA manufacturing | BCA connectors - first two strings, MCA side (62 connectors) |  | CapEx | CapEx |  | A - Analogy |  | 1 | 0% | 55% | Off Ice | C3 | 20% | 4340 | 0 | PCA side connectors already purchased |  |  |  |  | 21700 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 0 | 21700 | 4340 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21700 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.3.1 | MSU | BCA manufacturing | BCA cable - first two strings (2,000 m) |  | CapEx | CapEx |  | A - Analogy |  | 1 | 0% | 55% | Off Ice | C4 | 35% | 10500 | 0 | 2,000 m of cable for first two strings and spares, $15/m based on SB 45027 |  |  |  |  | 30000 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 30000 | 10500 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.3.1 | MSU | BCA manufacturing | BCA fabrication costs - first two strings |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 55% | Off Ice | C4 | 35% | 8750 | 0 | [9 empty] | 25000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 25000 | 0 | 25000 | 8750 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.3.2 | MSU | BCA pre-ship review | BCA pre-ship review | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 1099.4609 | 604.7035 | [9 empty] | 56 |  |  |  | 56 | 0.37333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3546.648 | 0 | 0 | 0 | 3546.648 | 1950.6564 | 5497.3044 | 709.3296 | 390.1313 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5497.3044 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3546.648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.3.3 | MSU | Shipping to PTH (FY24 vessel, RDD 12/1/23 - ROS 2/1/25 to pre-position) | Shipping to PTH | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 628.2634 | 345.5448 | [9 empty] | 16 | 16 |  |  | 32 | 0.21333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1013.328 | 1013.328 | 0 | 0 | 2026.656 | 1114.6608 | 3141.3168 | 405.3312 | 222.9322 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3141.3168 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2026.656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.3.3 | MSU | Shipping to PTH (FY24 vessel, RDD 12/1/23 - ROS 2/1/25 to pre-position) | BCA shipping costs to PTH (1st two strings) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 55% | Off Ice | C4 | 35% | 813.75 | 447.5625 | [9 empty] | 1500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 825 | 2325 | 525 | 288.75 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2325 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.4.1 | MSU | BCA manufacturing - final five strings | BCA manufacturing | Ng | Labor Hours | Labor - LoE | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C1 | 9% | 568.4762 | 312.6619 | [10 empty] | 16 | 16 | 16 | 48 | 0.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1013.328 | 1013.328 | 1013.328 | 3039.984 | 1671.9912 | 4711.9752 | 273.5986 | 150.4792 | 16 | [11 empty] | 16 | 0.10667 | 1035.1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1035.1146 | 569.313 | 1604.4276 | 93.1603 | 51.2382 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6316.4028 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3039.984 | 1035.1146 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.4.1 | MSU | BCA manufacturing - final five strings | BCA manufacturing | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 892.8 | 491.04 | [12 empty] | 6400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6400 | 6400 | 3520 | 9920 | 576 | 316.8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9920 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.4.1 | MSU | BCA manufacturing - final five strings | BCA connectors - last five strings, MCA side (110 connectors) |  | CapEx | CapEx |  | A - Analogy |  | 1 | 0% | 55% | Off Ice | C3 | 20% | 7700 | 0 | [5 empty] | 38500 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 38500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38500 | 0 | 38500 | 7700 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38500 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.4.1 | MSU | BCA manufacturing - final five strings | BCA cable - last five strings (4,556 m) |  | CapEx | CapEx |  | A - Analogy |  | 1 | 0% | 55% | Off Ice | C4 | 35% | 23919 | 0 | 4,556 m of cable for remaining five strings, $15/m based on SB 45027 |  |  |  |  | 68340 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 68340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68340 | 0 | 68340 | 23919 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68340 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.4.1 | MSU | BCA manufacturing - final five strings | BCA fabrication costs - last five strings |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 55% | Off Ice | C4 | 35% | 15750 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | [11 empty] | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 0 | 45000 | 15750 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.4.2 | MSU | Shipping to PTH (FY24 vessel, RDD 12/1/23 - ROS 12/1/25) | Shipping to PTH | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C2 | 12.5% | 401.1069 | 220.6088 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | [11 empty] | 32 | 0.21333 | 2070.2291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2070.2291 | 1138.626 | 3208.8551 | 258.7786 | 142.3283 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3208.8551 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 2070.2291 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.4.2 | MSU | Shipping to PTH (FY24 vessel, RDD 12/1/23 - ROS 12/1/25) | BCA shipping costs to PTH (remaining strings) |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 55% | Off Ice | C4 | 35% | 1085 | 596.75 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | [11 empty] | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 1100 | 3100 | 700 | 385 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.2.5 | MSU | Breakout Cable Assemblies support | Breakout Cable Assembly miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 87.1875 | 47.9531 |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 275 | 775 | 45 | 24.75 | 125 | [11 empty] | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 68.75 | 193.75 | 11.25 | 6.1875 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 968.75 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.3.4.2 | MSU | SPAT cable materials procurement | SPAT cable materials |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | Off Ice | C2 | 12.5% | 186 | 102.3 |  | 960 | [11 empty] | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 528 | 1488 | 120 | 66 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1488 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.3.4.3 | MSU | SPAT cable production | SPAT cable production | Wilkins | Labor Hours | Labor - Task | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C3 | 20% | 595.3302 | 327.4316 |  | 40 | [11 empty] | 40 | 0.26667 | 1920.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920.42 | 1056.231 | 2976.651 | 384.084 | 211.2462 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2976.651 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1920.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.3.4.4 | MSU | SPAT cable shipping to WIPAC | SPAT cable shipping | Wilkins | Labor Hours | Labor - Task | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C2 | 12.5% | 74.4163 | 40.929 |  |  | 8 | [10 empty] | 8 | 0.053333 | 0 | 384.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384.084 | 211.2462 | 595.3302 | 48.0105 | 26.4058 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 595.3302 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 384.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.3.5 | MSU | Penetrator Cable Assemblies support | Penetrator Cable Assembly Miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 17.4375 | 9.5906 |  | 125 | [11 empty] | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 68.75 | 193.75 | 11.25 | 6.1875 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193.75 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.4.1.5 | MSU | String hardware final design review | String hardware final design review | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 502.2 | 276.21 |  | 3600 | [11 empty] | 0 | 0 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 1980 | 5580 | 324 | 178.2 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5580 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.4.1.7 | MSU | String hardware production | String hardware shipping to MCA production facility | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 314.1317 | 172.7724 |  | 8 | 8 | [10 empty] | 16 | 0.10667 | 506.664 | 506.664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1013.328 | 557.3304 | 1570.6584 | 202.6656 | 111.4661 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570.6584 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1013.328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.4.2 | MSU | String hardware support | String hardware miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 34.875 | 19.1812 |  | 125 |  |  | 125 | [8 empty] | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 137.5 | 387.5 | 22.5 | 12.375 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.6.1 | MSU | Off-ice training Cable SMEs (FS3) | Off-Ice Safety Training FS3 Cable SMEs (Headcount 2) | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 502.2 | 276.21 | standard domestic trip $1800 (x2) | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 3600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 3600 | 1980 | 5580 | 324 | 178.2 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5580 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.6.3 | MSU | PQ, ECW & Deployment Travel Costs Cable SMEs (FS3) | Cable SME FS3 PQ costs (Headcount 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 271.25 | 149.1875 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 700 | 700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 0 | 0 | 1400 | 770 | 2170 | 175 | 96.25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.6.3 | MSU | PQ, ECW & Deployment Travel Costs Cable SMEs (FS3) | Cable SME FS3 ECW costs (Headcount 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 96.875 | 53.2812 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 500 | 275 | 775 | 62.5 | 34.375 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.6.3 | MSU | PQ, ECW & Deployment Travel Costs Cable SMEs (FS3) | Cable SME FS3 Deployment travel (Headcount 2) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 502.2 | 276.21 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2160 |  |  | 1440 | [7 empty] | 0 | 0 | 0 | 2160 | 0 | 0 | 1440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 1980 | 5580 | 324 | 178.2 | 5580 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.6.4 | MSU | Cable SME support for FS3 activities (slot 1) | On-Ice Cable SME support for FS3 activities (slot 1) | Ng | Labor Hours | Labor - LoE | EN-ME | C - Engineering Buildup | 62 | 62 | 0% | 55% | On Ice | C1 | 9% | 2825.1443 | 1553.8294 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 75 | 150 | 75 | [8 empty] | 300 | 2 | 0 | 5062.9826 | 10125.9652 | 5062.9826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20251.9305 | 11138.5618 | 31390.4923 | 1822.6737 | 1002.4706 | 31390.4923 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 20251.9305 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.1.6.5 | MSU | Cable SME support for FS3 activities (slot 2) | On-Ice Cable SME support for FS3 activities (slot 2) | TBD | Labor Hours | Labor - LoE | EN-ME | C - Engineering Buildup | 62 | 62 | 0% | 55% | On Ice | C1 | 9% | 1789.2581 | 984.0919 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 40 | 150 | [8 empty] | 190 | 1.2667 | 0 | 0 | 2700.2574 | 10125.9652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12826.2226 | 7054.4225 | 19880.6451 | 1154.36 | 634.898 | 19880.6451 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 12826.2226 | 0 | 0 | 0 | 0 | 1.4.1
1.4 | 1.4.2.2.4 | MSU | Fabrication | Fabrication | Ng | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 62 | 62 | 0% | 55% | Off Ice | C4 | 35% | 274.8652 | 151.1759 |  | 8 | [11 empty] | 8 | 0.053333 | 506.664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506.664 | 278.6652 | 785.3292 | 177.3324 | 97.5328 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 785.3292 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 506.664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.2.4 | MSU | Fabrication | SJBs |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 55% | Off Ice | C4 | 35% | 4900 | 0 |  | 14000 | [11 empty] | 0 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 0 | 14000 | 4900 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.2.6 | MSU | Pre-ship review | Pre-ship review | Wilkins | Labor Hours | Labor - Task | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C2 | 12.5% | 223.2488 | 122.7869 |  | 24 | [11 empty] | 24 | 0.16 | 1152.252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1152.252 | 633.7386 | 1785.9906 | 144.0315 | 79.2173 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1785.9906 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1152.252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.2.6 | MSU | Pre-ship review | Pre-ship review | Ng | Labor Hours | Labor - Task | EN-ME | A - Analogy | 62 | 62 | 0% | 55% | Off Ice | C2 | 12.5% | 294.4984 | 161.9741 |  | 24 | [11 empty] | 24 | 0.16 | 1519.992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519.992 | 835.9956 | 2355.9876 | 189.999 | 104.4994 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2355.9876 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1519.992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.2.6 | UW | Pre-ship review | Pre-ship review | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 55.34 | 66 | 35% | 53% | Off Ice | C2 | 12.5% | 350.287 | 185.6521 |  | 24 | [11 empty] | 24 | 0.16 | 1831.5658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1831.5658 | 970.7299 | 2802.2957 | 228.9457 | 121.3412 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2802.2957 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1356.7154 | 0 | 0 | 0 | 474.8504 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.2.6 | MSU | Pre-ship review | Shipping to PTH | Ng | Labor Hours | Labor - Task | EN-ME | D - Expert Opinion | 62 | 62 | 0% | 55% | Off Ice | C3 | 20% | 471.1975 | 259.1586 |  | 24 | [11 empty] | 24 | 0.16 | 1519.992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1519.992 | 835.9956 | 2355.9876 | 303.9984 | 167.1991 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2355.9876 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1519.992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.2.6 | MSU | Pre-ship review | Shipping costs to PTH |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 55% | Off Ice | C4 | 35% | 813.75 | 447.5625 |  | 1500 | [11 empty] | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 825 | 2325 | 525 | 288.75 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2325 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.2.8 | MSU | Surface Junction Box support | Surface Junction Box miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 17.4375 | 9.5906 |  |  | 125 | [10 empty] | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 68.75 | 193.75 | 11.25 | 6.1875 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 193.75 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.2.3 | UW | Fabrication | Fabrication | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 55.34 | 66 | 35% | 53% | Off Ice | C4 | 35% | 817.3363 | 433.1882 |  | 20 | [11 empty] | 20 | 0.13333 | 1526.3049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1526.3049 | 808.9416 | 2335.2465 | 534.2067 | 283.1296 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2335.2465 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1130.5962 | 0 | 0 | 0 | 395.7087 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.2.4 | UW | Pre-ship review | Pre-ship review | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 55.34 | 66 | 35% | 53% | Off Ice | C2 | 12.5% | 116.7623 | 61.884 |  |  | 8 | [10 empty] | 8 | 0.053333 | 0 | 610.5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610.5219 | 323.5766 | 934.0986 | 76.3152 | 40.4471 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 934.0986 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 452.2385 | 0 | 0 | 0 | 158.2835 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.2.5 | UW | Shipping to PTH (NB: small -- RDD 9/15/23 for ComSur FY25, ROS 12/15/23) | Shipping to PTH (NB: small) | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 55.34 | 66 | 35% | 53% | Off Ice | C3 | 20% | 373.6394 | 198.0289 |  |  | 8 | 8 | [9 empty] | 16 | 0.10667 | 0 | 610.5219 | 610.5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221.0439 | 647.1533 | 1868.1972 | 244.2088 | 129.4307 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1868.1972 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 904.477 | 0 | 0 | 0 | 316.5669 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.2.5 | UW | Shipping to PTH (NB: small -- RDD 9/15/23 for ComSur FY25, ROS 12/15/23) | Shipping costs |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 535.5 | 283.815 |  |  | 1000 | [10 empty] | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 530 | 1530 | 350 | 185.5 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.3.1 | UW | Final design | Final design | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 55.34 | 66 | 35% | 53% | Off Ice | C4 | 35% | 980.8035 | 519.8259 | [5 empty] | 24 | [7 empty] | 24 | 0.16 | 0 | 0 | 0 | 0 | 1831.5658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1831.5658 | 970.7299 | 2802.2957 | 641.048 | 339.7555 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2802.2957 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1356.7154 | 0 | 0 | 0 | 474.8504 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.3.3 | UW | Final design review | Final design review | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 55.34 | 66 | 35% | 53% | Off Ice | C2 | 12.5% | 817.3363 | 433.1882 | [6 empty] | 56 | [6 empty] | 56 | 0.37333 | 0 | 0 | 0 | 0 | 0 | 4273.6536 | 0 | 0 | 0 | 0 | 0 | 0 | 4273.6536 | 2265.0364 | 6538.6901 | 534.2067 | 283.1296 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6538.6901 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3165.6694 | 0 | 0 | 0 | 1107.9843 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.3.4 | UW | Procurement | Procurement | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 55.34 | 66 | 35% | 53% | Off Ice | C3 | 20% | 373.6394 | 198.0289 | [6 empty] | 8 | 8 | [5 empty] | 16 | 0.10667 | 0 | 0 | 0 | 0 | 0 | 610.5219 | 610.5219 | 0 | 0 | 0 | 0 | 0 | 1221.0439 | 647.1533 | 1868.1972 | 244.2088 | 129.4307 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1868.1972 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 904.477 | 0 | 0 | 0 | 316.5669 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.3.4 | MSU | Procurement | Procurement | Wilkins | Labor Hours | Labor - LoE | TE | A - Analogy | 47 | 46.67 | 0% | 55% | Off Ice | C1 | 9% | 267.8986 | 147.3442 | [6 empty] | 8 | 8 | 8 | 8 | 8 |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 384.084 | 384.084 | 384.084 | 384.084 | 384.084 | 0 | 0 | 1920.42 | 1056.231 | 2976.651 | 172.8378 | 95.0608 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2976.651 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1920.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.3.4 | UW | Procurement | Patch cables (169) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 5656.2188 | 2997.7959 | [8 empty] | 29575 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29575 | 0 | 0 | 0 | 0 | 29575 | 15674.75 | 45249.75 | 3696.875 | 1959.3438 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45249.75 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.3.5 | MSU | Production | Production | Wilkins | Labor Hours | Labor - Task | TE | D - Expert Opinion | 47 | 46.67 | 0% | 55% | Off Ice | C3 | 20% | 2688.5856 | 1478.7221 | [10 empty] | 50 | 50 | 50 | 150 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400.525 | 2400.525 | 2400.525 | 7201.575 | 3960.8663 | 11162.4412 | 1440.315 | 792.1733 | 30 | [11 empty] | 30 | 0.2 | 1471.2818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1471.2818 | 809.205 | 2280.4867 | 294.2564 | 161.841 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13442.928 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 7201.575 | 1471.2818 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.3.6 | UW | Pre-ship review | Pre-ship review | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 55.34 | 66 | 35% | 53% | Off Ice | C2 | 12.5% | 357.8181 | 189.6436 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | [11 empty] | 24 | 0.16 | 1870.9445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1870.9445 | 991.6006 | 2862.5451 | 233.8681 | 123.9501 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2862.5451 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1385.8848 | 0 | 0 | 0 | 485.0597 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.3.7 | MSU | Shipping to PTH (RDD 9/15/24 for FY25 ComSur, ROS 12/1/24) | Shipping to PTH | Wilkins | Labor Hours | Labor - Task | TE | D - Expert Opinion | 47 | 46.67 | 0% | 55% | Off Ice | C3 | 20% | 486.5038 | 267.5771 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 8 | [10 empty] | 32 | 0.21333 | 1177.0254 | 392.3418 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1569.3672 | 863.152 | 2432.5192 | 313.8734 | 172.6304 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2432.5192 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1569.3672 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.3.7 | UW | Shipping to PTH (RDD 9/15/24 for FY25 ComSur, ROS 12/1/24) | Patch cable shipping costs |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 642.6 | 340.578 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1200 | [10 empty] | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 636 | 1836 | 420 | 222.6 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1836 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.3.4 | UW | ICL Upgrade support | ICL Upgrade Support miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 240.975 | 127.7168 |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 265 | 765 | 45 | 23.85 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 265 | 765 | 45 | 23.85 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 265 | 765 | 45 | 23.85 | 125 |  |  | 125 | [8 empty] | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 132.5 | 382.5 | 22.5 | 11.925 | 2677.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.4.4 | MSU | PQ, ECW, Deployment Travel Costs Cable SMEs (FS2) | Cable SME FS2 PQ costs (Headcount 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 271.25 | 149.1875 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 700 | 700 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 0 | 0 | 1400 | 770 | 2170 | 175 | 96.25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2170 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.4.4 | MSU | PQ, ECW, Deployment Travel Costs Cable SMEs (FS2) | Cable SME FS2 ECW costs (Headcount 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 96.875 | 53.2812 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 500 | 275 | 775 | 62.5 | 34.375 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.4.4 | MSU | PQ, ECW, Deployment Travel Costs Cable SMEs (FS2) | Cable SME FS2 Deployment travel (Headcount 2) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 502.2 | 276.21 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2160 |  |  | 1440 | [7 empty] | 0 | 0 | 0 | 2160 | 0 | 0 | 1440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 1980 | 5580 | 324 | 178.2 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5580 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.4.5 | MSU | Cable SME support for FS2 activities (slot 1) | Cable SME support for FS2 activities (slot 1) | Ng | Labor Hours | Labor - LoE | EN-ME | C - Engineering Buildup | 62 | 62 | 0% | 55% | On Ice | C1 | 9% | 1060.1782 | 583.098 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 75 | 40 | [8 empty] | 115 | 0.76667 | 0 | 0 | 4956.4196 | 2643.4238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7599.8434 | 4179.9139 | 11779.7573 | 683.9859 | 376.1922 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11779.7573 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 7599.8434 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.2.4.6 | MSU | Cable SME support for FS2 activities (slot 2) | Cable SME support for FS2 activities (slot 2) | Shoolz | Labor Hours | Labor - LoE | EN-EE | C - Engineering Buildup | 72 | 72 | 0% | 55% | On Ice | C1 | 9% | 1605.88 | 883.234 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 75 | 75 | [8 empty] | 150 | 1 | 0 | 0 | 5755.8421 | 5755.8421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11511.6842 | 6331.4263 | 17843.1106 | 1036.0516 | 569.8284 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17843.1106 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 11511.6842 | 0 | 0 | 0 | 0 | 0 | 1.4.2
1.4 | 1.4.4.1.1.1 | UW | Procurement | Procurement | Kelley | Labor Hours | Labor - LoE | SS | A - Analogy | 55.34 | 66 | 35% | 53% | Off Ice | C1 | 9% | 420.3444 | 222.7825 |  | 8 | 8 | 8 | 8 | 8 | [7 empty] | 40 | 0.26667 | 610.5219 | 610.5219 | 610.5219 | 610.5219 | 610.5219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3052.6097 | 1617.8832 | 4670.4929 | 274.7349 | 145.6095 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4670.4929 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2261.1924 | 0 | 0 | 0 | 791.4173 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.1.1 | UW | Procurement | White Rabbit OEM nodes for NTS and SPTS (10 total, 6 to be purchased) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 809.375 | 0 | 4 already purchased by NvE, 6 more planned | 6475 | [11 empty] | 0 | 0 | 6475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6475 | 0 | 6475 | 809.375 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6475 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.1.1 | UW | Procurement | White Rabbit OEM nodes for ICL (10) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 1348.875 | 0 |  | 10791 | [11 empty] | 0 | 0 | 10791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10791 | 0 | 10791 | 1348.875 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10791 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.1.1 | UW | Procurement | Fiber patch cables for ICL (10) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 38.25 | 20.2725 | [5 empty] | 200 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 106 | 306 | 25 | 13.25 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.1.5 | UW | Shipping to PTH (RDD 9/15/24 for FY25 ComSur - ROS 12/1/24) | Shipping to PTH | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 55.34 | 66 | 35% | 53% | Off Ice | C3 | 20% | 560.4591 | 297.0433 | [7 empty] | 8 | 8 | 8 |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 610.5219 | 610.5219 | 610.5219 | 0 | 0 | 0 | 1831.5658 | 970.7299 | 2802.2957 | 366.3132 | 194.146 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2802.2957 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1356.7154 | 0 | 0 | 0 | 474.8504 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.1.5 | UW | Shipping to PTH (RDD 9/15/24 for FY25 ComSur - ROS 12/1/24) | Shipping costs |  | M & S | M & S |  | A - Analogy |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 160.65 | 85.1445 | [7 empty] | 300 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 300 | 159 | 459 | 105 | 55.65 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.2.1 | UW | Final design | Final design | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 55.34 | 66 | 35% | 53% | Off Ice | C4 | 35% | 5844.3629 | 3097.5123 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 40 | 60 | 20 | 20 |  |  |  |  | 140 | 0.93333 | 0 | 0 | 0 | 0 | 3118.2408 | 4677.3613 | 1559.1204 | 1559.1204 | 0 | 0 | 0 | 0 | 10913.843 | 5784.3368 | 16698.1797 | 3819.845 | 2024.5179 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16698.1797 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 8084.3281 | 0 | 0 | 0 | 2829.5148 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.2.2 | UW | Prototype production | Prototype production | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 55.34 | 66 | 35% | 53% | Off Ice | C3 | 20% | 1908.3634 | 1011.4326 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 80 | [5 empty] | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 6236.4817 | 0 | 0 | 0 | 0 | 0 | 6236.4817 | 3305.3353 | 9541.817 | 1247.2963 | 661.0671 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9541.817 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4619.6161 | 0 | 0 | 0 | 1616.8656 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.2.2 | UW | Prototype production | Timing monitoring prototype |  | CapEx | CapEx |  | A - Analogy |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 600 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 3000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3000 | 600 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.2.3 | UW | Installation and testing at NTS/SPTS | Installation and testing at NTS/SPTS | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 55.34 | 66 | 35% | 53% | Off Ice | C3 | 20% | 1431.2725 | 758.5745 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 60 |  |  |  |  | 60 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4677.3613 | 0 | 0 | 0 | 0 | 4677.3613 | 2479.0015 | 7156.3627 | 935.4723 | 495.8003 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7156.3627 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3464.7121 | 0 | 0 | 0 | 1212.6492 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.2.3 | UW | Installation and testing at NTS/SPTS | Installation and testing at NTS/SPTS | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 247.86 | 131.3658 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 1800 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.2.4 | UW | Production of ICL system | Production of ICL system | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 55.34 | 66 | 35% | 53% | Off Ice | C3 | 20% | 1908.3634 | 1011.4326 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 20 | 40 | 20 |  |  | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1559.1204 | 3118.2408 | 1559.1204 | 0 | 0 | 6236.4817 | 3305.3353 | 9541.817 | 1247.2963 | 661.0671 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9541.817 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 4619.6161 | 0 | 0 | 0 | 1616.8656 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.2.4 | UW | Production of ICL system | Timing monitoring system for ICL |  | CapEx | CapEx |  | A - Analogy |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 1200 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 6000 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 0 | 0 | 6000 | 0 | 6000 | 1200 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.2.6 | UW | Shipping to PTH (RDD 9/15/24 for FY25 ComSur, ROS 12/1/24) | Shipping to PTH | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 55.34 | 66 | 35% | 53% | Off Ice | C3 | 20% | 572.509 | 303.4298 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 24 |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1870.9445 | 0 | 0 | 1870.9445 | 991.6006 | 2862.5451 | 374.1889 | 198.3201 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2862.5451 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 1385.8848 | 0 | 0 | 0 | 485.0597 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.2.6 | UW | Shipping to PTH (RDD 9/15/24 for FY25 ComSur, ROS 12/1/24) | Shipping costs |  | M & S | M & S |  | A - Analogy |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 160.65 | 85.1445 | assumes joint shipment with 1.4.4.1.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 300 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 300 | 159 | 459 | 105 | 55.65 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.1.3 | UW | Timing systems support | Timing systems miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 154.9125 | 82.1036 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  | 0 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 500 | 265 | 765 | 45 | 23.85 |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  | 0 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 500 | 265 | 765 | 45 | 23.85 |  | 125 | [10 empty] | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 66.25 | 191.25 | 11.25 | 5.9625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1721.25 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.1.5 | UW | Procurement | Procurement | Kelley | Labor Hours | Labor - LoE | SS | A - Analogy | 55.34 | 66 | 35% | 53% | Off Ice | C1 | 9% | 588.4821 | 311.8955 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  |  |  | 56 | 0.37333 | 0 | 610.5219 | 610.5219 | 610.5219 | 610.5219 | 610.5219 | 610.5219 | 610.5219 | 0 | 0 | 0 | 0 | 4273.6536 | 2265.0364 | 6538.6901 | 384.6288 | 203.8533 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6538.6901 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3165.6694 | 0 | 0 | 0 | 1107.9843 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.1.5 | UW | Procurement | DC power supply chassis for ICL (3) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 249.375 | 0 | [8 empty] | 1995 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | 0 | 0 | 0 | 0 | 1995 | 0 | 1995 | 249.375 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.1.5 | UW | Procurement | 48V DC power supply modules for ICL (15) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 903.75 | 0 | [8 empty] | 7230 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 0 | 0 | 0 | 0 | 7230 | 0 | 7230 | 903.75 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.2.1 | UW | Final design | Final design | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 55.34 | 66 | 35% | 53% | Off Ice | C4 | 35% | 653.869 | 346.5506 |  | 16 | [11 empty] | 16 | 0.10667 | 1221.0439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1221.0439 | 647.1533 | 1868.1972 | 427.3654 | 226.5036 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1868.1972 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 904.477 | 0 | 0 | 0 | 316.5669 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.2.4 | UW | Production | Production | Kelley | Labor Hours | Labor - LoE | SS | A - Analogy | 55.34 | 66 | 35% | 53% | Off Ice | C1 | 9% | 630.5165 | 334.1738 |  |  | 10 | 10 | 10 | 10 | 10 | 10 | [5 empty] | 60 | 0.4 | 0 | 763.1524 | 763.1524 | 763.1524 | 763.1524 | 763.1524 | 763.1524 | 0 | 0 | 0 | 0 | 0 | 4578.9146 | 2426.8247 | 7005.7394 | 412.1023 | 218.4142 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7005.7394 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 3391.7886 | 0 | 0 | 0 | 1187.126 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.2.4 | UW | Production | Custom power fanout unit for NTS |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 255 | 0 | [5 empty] | 1275 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275 | 0 | 1275 | 255 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.2.4 | UW | Production | Power fanout cables for NTS (5) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 100 | 0 | [5 empty] | 800 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 800 | 100 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.2.4 | UW | Production | Custom power fanout units for ICL (2) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 510 | 0 | [7 empty] | 2550 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550 | 0 | 0 | 0 | 0 | 0 | 2550 | 0 | 2550 | 510 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.2.4 | UW | Production | Power fanout cables for ICL (10) |  | CapEx | CapEx |  | C - Engineering Buildup |  | 1 | 0% | 53% | Off Ice | C2 | 12.5% | 200 | 0 | [7 empty] | 1600 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 1600 | 200 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.3.4 | UW | Production | Production | Kelley | Labor Hours | Labor - LoE | SS | A - Analogy | 55.34 | 66 | 35% | 53% | Off Ice | C1 | 9% | 1261.0331 | 668.3475 |  |  | 24 | 24 | 24 | 24 | 24 | [6 empty] | 120 | 0.8 | 0 | 1831.5658 | 1831.5658 | 1831.5658 | 1831.5658 | 1831.5658 | 0 | 0 | 0 | 0 | 0 | 0 | 9157.8292 | 4853.6495 | 14011.4787 | 824.2046 | 436.8285 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14011.4787 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 6783.5772 | 0 | 0 | 0 | 2374.252 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.3.4 | UW | Production | Power control unit for NTS |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 150 | 0 |  |  |  |  | 750 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 750 | 150 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.3.4 | UW | Production | Power control units for ICL (2) |  | CapEx | CapEx |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 300 | 0 | [6 empty] | 1500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1500 | 300 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.4.1 | UW | Power system installation and testing at NTS | Installation and testing at NTS | Kelley | Labor Hours | Labor - Task | SS | D - Expert Opinion | 55.34 | 66 | 35% | 53% | Off Ice | C3 | 20% | 934.0986 | 495.0722 |  | 40 | [11 empty] | 40 | 0.26667 | 3052.6097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3052.6097 | 1617.8832 | 4670.4929 | 610.5219 | 323.5766 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4670.4929 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2261.1924 | 0 | 0 | 0 | 791.4173 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.4.1 | UW | Power system installation and testing at NTS | Installation and testing at NTS | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 247.86 | 131.3658 |  | 1800 | [11 empty] | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.4.2 | UW | Power system final design review | Power system final design review | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 55.34 | 66 | 35% | 53% | Off Ice | C3 | 20% | 2241.8366 | 1188.1734 |  | 40 | 56 | [10 empty] | 96 | 0.64 | 3052.6097 | 4273.6536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7326.2634 | 3882.9196 | 11209.183 | 1465.2527 | 776.5839 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11209.183 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 5426.8618 | 0 | 0 | 0 | 1899.4016 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.4.3 | UW | Pre-ship review | Pre-ship review | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 55.34 | 66 | 35% | 53% | Off Ice | C3 | 20% | 934.0986 | 495.0722 | [8 empty] | 40 |  |  |  |  | 40 | 0.26667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3052.6097 | 0 | 0 | 0 | 0 | 3052.6097 | 1617.8832 | 4670.4929 | 610.5219 | 323.5766 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4670.4929 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 2261.1924 | 0 | 0 | 0 | 791.4173 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.4.4 | UW | Shipping to PTH (ComSur RDD 9/15/24, ROS 12/1/24) | Shipping to PTH | Kelley | Labor Hours | Labor - Task | SS | A - Analogy | 55.34 | 66 | 35% | 53% | Off Ice | C2 | 12.5% | 350.287 | 185.6521 | [8 empty] | 8 | 16 |  |  |  | 24 | 0.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610.5219 | 1221.0439 | 0 | 0 | 0 | 1831.5658 | 970.7299 | 2802.2957 | 228.9457 | 121.3412 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2802.2957 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 1356.7154 | 0 | 0 | 0 | 474.8504 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.4.4 | UW | Shipping to PTH (ComSur RDD 9/15/24, ROS 12/1/24) | Shipping costs |  | M & S | M & S |  | A - Analogy |  | 1 | 0% | 53% | Off Ice | C4 | 35% | 267.75 | 141.9075 | [9 empty] | 500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 500 | 265 | 765 | 175 | 92.75 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.2.5 | UW | Power systems support | Power systems miscellaneous supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 240.975 | 127.7168 |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 265 | 765 | 45 | 23.85 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 265 | 765 | 45 | 23.85 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 265 | 765 | 45 | 23.85 | 125 |  |  | 125 | [8 empty] | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 132.5 | 382.5 | 22.5 | 11.925 | 2677.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.3.2 | MSU | PQ, ECW, Deployment Travel Costs FS2 Electronics SMEs (Headcount 2) | Electronics SME FS2 PQ costs (slot 1) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 135.625 | 74.5938 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 700 | 385 | 1085 | 87.5 | 48.125 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.3.2 | MSU | PQ, ECW, Deployment Travel Costs FS2 Electronics SMEs (Headcount 2) | Electronics SME FS2 ECW costs (slot 1) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 48.4375 | 26.6406 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 250 | 137.5 | 387.5 | 31.25 | 17.1875 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.3.2 | MSU | PQ, ECW, Deployment Travel Costs FS2 Electronics SMEs (Headcount 2) | Electronics SME FS2 Deployment travel (slot 1) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 251.1 | 138.105 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [7 empty] | 0 | 0 | 0 | 1080 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 990 | 2790 | 162 | 89.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2790 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.3.2 | MSU | PQ, ECW, Deployment Travel Costs FS2 Electronics SMEs (Headcount 2) | Electronics SME FS2 PQ costs (slot 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 135.625 | 74.5938 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 700 | 385 | 1085 | 87.5 | 48.125 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.3.2 | MSU | PQ, ECW, Deployment Travel Costs FS2 Electronics SMEs (Headcount 2) | Electronics SME FS2 ECW costs (slot 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 48.4375 | 26.6406 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 250 | 137.5 | 387.5 | 31.25 | 17.1875 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.3.2 | MSU | PQ, ECW, Deployment Travel Costs FS2 Electronics SMEs (Headcount 2) | Electronics SME FS2 Deployment travel (slot 2) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 251.1 | 138.105 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [7 empty] | 0 | 0 | 0 | 1080 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 990 | 2790 | 162 | 89.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2790 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.3.3 | MSU | Electronics SME support for FS2 activities (slot 1) | Electronics SME support for FS2 activities | Halliday | Labor Hours | Labor - LoE | PO | D - Expert Opinion | 31 | 31 | 31% | 55% | On Ice | C1 | 9% | 905.7609 | 498.1685 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 150 | [8 empty] | 150 | 1 | 0 | 0 | 0 | 6492.9097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6492.9097 | 3571.1003 | 10064.01 | 584.3619 | 321.399 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10064.01 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4956.4196 | 0 | 0 | 0 | 1536.4901 | 0 | 1.4.4
1.4 | 1.4.4.3.8 | UW | Electronics SME support for FS3 activities (slot 1) | Electronics SME support for FS3 activities (slot 1) | Kelley | Labor Hours | Labor - LoE | SS | D - Expert Opinion | 55.34 | 66 | 35% | 53% | On Ice | C1 | 9% | 1680.1637 | 890.4868 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 75 | 75 | [9 empty] | 150 | 1 | 0 | 6100.8124 | 6100.8124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12201.6248 | 6466.8611 | 18668.4859 | 1098.1462 | 582.0175 | 18668.4859 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 9038.2406 | 0 | 0 | 0 | 3163.3842 | 1.4.4
1.4 | 1.4.4.3.5 | MSU | Off-ice training Electronics SMEs (FS3) | Off-ice safety training FS3 Electronics SMEs | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 251.1 | 138.105 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1800 | 990 | 2790 | 162 | 89.1 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2790 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.3.7 | UW | PQ, ECW, Deployment Travel Costs FS3 Electronics SMEs (Headcount 2) | Electronics SME FS3 PQ costs (slot 1) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 53% | On Ice | C2 | 12.5% | 133.875 | 70.9537 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 700 | 371 | 1071 | 87.5 | 46.375 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1071 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.3.7 | UW | PQ, ECW, Deployment Travel Costs FS3 Electronics SMEs (Headcount 2) | Electronics SME FS3 ECW costs (slot 1) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 53% | On Ice | C2 | 12.5% | 47.8125 | 25.3406 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 250 | 132.5 | 382.5 | 31.25 | 16.5625 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 382.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.3.7 | UW | PQ, ECW, Deployment Travel Costs FS3 Electronics SMEs (Headcount 2) | Electronics SME FS3 Deployment travel (slot 1) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 247.86 | 131.3658 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [7 empty] | 0 | 0 | 0 | 1080 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | 2754 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.3.7 | MSU | PQ, ECW, Deployment Travel Costs FS3 Electronics SMEs (Headcount 2) | Electronics SME FS3 PQ costs (slot 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 135.625 | 74.5938 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 350 | 350 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 700 | 385 | 1085 | 87.5 | 48.125 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1085 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.3.7 | MSU | PQ, ECW, Deployment Travel Costs FS3 Electronics SMEs (Headcount 2) | Electronics SME FS3 ECW costs (slot 2) |  | M & S | M & S |  | C - Engineering Buildup |  | 1 | 0% | 55% | On Ice | C2 | 12.5% | 48.4375 | 26.6406 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 250 | 137.5 | 387.5 | 31.25 | 17.1875 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.4.3.7 | MSU | PQ, ECW, Deployment Travel Costs FS3 Electronics SMEs (Headcount 2) | Electronics SME FS3 Deployment travel (slot 2) | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | On Ice | C1 | 9% | 251.1 | 138.105 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1080 |  |  | 720 | [7 empty] | 0 | 0 | 0 | 1080 | 0 | 0 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 990 | 2790 | 162 | 89.1 | 2790 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.4
1.4 | 1.4.6 | MSU | CPT Management (PY4 onward) | CPT Management - Ty DeYoung | DeYoung | Labor Hours | Labor - LoE | KE | E - Extrapolation from Actuals | 97 | 97 | 8% | 55% | Off Ice | C1 | 9% | 10294.7479 | 5662.1113 | [8 empty] | 37 | 75 | 75 | 38 |  | 225 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3959.4566 | 8025.9255 | 8025.9255 | 4066.4689 | 0 | 24077.7765 | 13242.7771 | 37320.5536 | 2166.9999 | 1191.8499 | [7 empty] | 37 | 75 | 75 | 38 |  | 225 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4044.5849 | 8198.4829 | 8198.4829 | 4153.898 | 0 | 24595.4487 | 13527.4968 | 38122.9455 | 2213.5904 | 1217.4747 | [7 empty] | 37 | 75 | 75 | 38 |  | 225 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4131.5435 | 8374.7503 | 8374.7503 | 4243.2068 | 0 | 25124.2508 | 13818.338 | 38942.5888 | 2261.1826 | 1243.6504 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114386.0879 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 22294.2375 | 22773.5636 | 23263.1952 | 0 | 1783.539 | 1821.8851 | 1861.0556 | 0 | 1.4.6
1.4 | 1.4.6 | MSU | CPT Management (PY4 onward) | CPT Management miscellaneous Supplies |  | M & S | M & S |  | F - Parametric |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 244.125 | 134.2688 |  | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 275 | 775 | 45 | 24.75 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 275 | 775 | 45 | 24.75 | 125 |  |  | 125 |  |  | 125 |  |  | 125 |  |  | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 500 | 275 | 775 | 45 | 24.75 | 125 |  |  | 125 | [8 empty] | 0 | 0 | 125 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 137.5 | 387.5 | 22.5 | 12.375 | 2712.5 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.6
1.4 | 1.4.6 | MSU | CPT Management (PY4 onward) | Reviews and Project Planning Meetings | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 55% | Off Ice | C1 | 9% | 1757.7 | 966.735 |  | 1800 | [5 empty] | 1800 | [5 empty] | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 3600 | 1980 | 5580 | 324 | 178.2 | 1800 | [5 empty] | 1800 | [5 empty] | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 3600 | 1980 | 5580 | 324 | 178.2 | 1800 | [5 empty] | 1800 | [5 empty] | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 3600 | 1980 | 5580 | 324 | 178.2 | 1800 | [11 empty] | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 990 | 2790 | 162 | 89.1 | 19530 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4.6
1.5 | 1.5.2.2.2.0 | UW | Pencil Beam Engineering | Overall coordination for Pencil Beam | Wendt | Labor Hours | Labor - LoE | SS | D - Expert Opinion | 65 | 66 | 35% | 53% |  | C1 | 9% | 10755.2725 | 5700.2944 |  | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 450 | 3 | 3361.3734 | 3361.3734 | 3361.3734 | 3361.3734 | 3361.3734 | 3361.3734 | 3361.3734 | 3361.3734 | 3361.3734 | 3361.3734 | 3361.3734 | 3361.3734 | 40336.4812 | 21378.3351 | 61714.8163 | 3630.2833 | 1924.0502 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 | 37.5 |  | 412.5 | 2.75 | 3433.643 | 3433.643 | 3433.643 | 3433.643 | 3433.643 | 3433.643 | 3433.643 | 3433.643 | 3433.643 | 3433.643 | 3433.643 | 0 | 37770.0726 | 20018.1385 | 57788.2111 | 3399.3065 | 1801.6325 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 119503.0274 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 29878.875 | 27977.8316 | 0 | 0 | 10457.6063 | 9792.2411 | 0 | 0 | 1.5.2
1.5 | 1.5.3.1.1 | UA | Simulation Studies | Simulation Studies |  | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 6297.5572 | 3085.803 | zeroed postdoc, needed later years when we have schedule approved | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 75 | 75 | 450 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2572.1136 | 2572.1136 | 2572.1136 | 2572.1136 | 2572.1136 | 2572.1136 | 15432.6815 | 7562.0139 | 22994.6954 | 1388.9413 | 680.5813 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 6 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 31528.9682 | 15449.1944 | 46978.1627 | 2837.6071 | 1390.4275 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69972.858 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 13147.6244 | 26860.5965 | 0 | 0 | 2285.0571 | 4668.3717 | 0 | 1.5.3
1.5 | 1.5.3.2.4 | UA | Create Database Structure for Timing Calibration Data | Create Database Structure for Timing Calibration Data |  | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 7377.2916 | 3614.8729 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 75 | 75 | 75 | 75 | 75 | 75 | 450 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2572.1136 | 2572.1136 | 2572.1136 | 2572.1136 | 2572.1136 | 2572.1136 | 15432.6815 | 7562.0139 | 22994.6954 | 1388.9413 | 680.5813 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 6 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 31528.9682 | 15449.1944 | 46978.1627 | 2837.6071 | 1390.4275 | 75 | 75 | 75 | [9 empty] | 225 | 1.5 | 2683.9034 | 2683.9034 | 2683.9034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8051.7103 | 3945.338 | 11997.0483 | 724.6539 | 355.0804 | 81969.9063 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 13147.6244 | 26860.5965 | 6859.5248 | 0 | 2285.0571 | 4668.3717 | 1192.1854 | 1.5.3
1.5 | 1.5.3.2.5 | UA | Analyze Timing Calibration Data from Deployed Modules | Analyze Timing Calibration Data from Deployed Modules |  | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 1079.7343 | 529.0698 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 75 | 75 | 75 | [6 empty] | 225 | 1.5 | 0 | 0 | 0 | 2683.9034 | 2683.9034 | 2683.9034 | 0 | 0 | 0 | 0 | 0 | 0 | 8051.7103 | 3945.338 | 11997.0483 | 724.6539 | 355.0804 | 11997.0483 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 6859.5248 | 0 | 0 | 0 | 1192.1854 | 1.5.3
1.5 | 1.5.3.3.2 | UA | Create Database Structure for Geometry Calibration Data | Create Database Structure for Geometry Calibration Data |  | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 7377.2916 | 3614.8729 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 75 | 75 | 75 | 75 | 75 | 75 | 450 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2572.1136 | 2572.1136 | 2572.1136 | 2572.1136 | 2572.1136 | 2572.1136 | 15432.6815 | 7562.0139 | 22994.6954 | 1388.9413 | 680.5813 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 6 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 31528.9682 | 15449.1944 | 46978.1627 | 2837.6071 | 1390.4275 | 75 | 75 | 75 | [9 empty] | 225 | 1.5 | 2683.9034 | 2683.9034 | 2683.9034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8051.7103 | 3945.338 | 11997.0483 | 724.6539 | 355.0804 | 81969.9063 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 13147.6244 | 26860.5965 | 6859.5248 | 0 | 2285.0571 | 4668.3717 | 1192.1854 | 1.5.3
1.5 | 1.5.3.3.3 | UA | Analyze Geometry Calibration Data from Deployed Modules | Analyze Geometry Calibration Data from Deployed Modules |  | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 1079.7343 | 529.0698 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 75 | 75 | 75 | [6 empty] | 225 | 1.5 | 0 | 0 | 0 | 2683.9034 | 2683.9034 | 2683.9034 | 0 | 0 | 0 | 0 | 0 | 0 | 8051.7103 | 3945.338 | 11997.0483 | 724.6539 | 355.0804 | 11997.0483 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 6859.5248 | 0 | 0 | 0 | 1192.1854 | 1.5.3
1.5 | 1.5.3.4.2 | UA | Software Development | Software Development |  | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 8457.0259 | 4143.9427 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 75 | 75 | 75 | 75 | 75 | 75 | 450 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2572.1136 | 2572.1136 | 2572.1136 | 2572.1136 | 2572.1136 | 2572.1136 | 15432.6815 | 7562.0139 | 22994.6954 | 1388.9413 | 680.5813 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 75 | 900 | 6 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 2627.414 | 31528.9682 | 15449.1944 | 46978.1627 | 2837.6071 | 1390.4275 | 150 | 150 | 150 | [9 empty] | 450 | 3 | 5367.8068 | 5367.8068 | 5367.8068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16103.4205 | 7890.6761 | 23994.0966 | 1449.3078 | 710.1608 | 93966.9546 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 13147.6244 | 26860.5965 | 13719.0497 | 0 | 2285.0571 | 4668.3717 | 2384.3708 | 1.5.3
1.5 | 1.5.3.4.3 | UA | Execution of Array Calibration | Execution |  | Labor Hours | Labor - Task | PO | D - Expert Opinion | 28 | 35 | 17.38% | 49% | Off Ice | C1 | 9% | 2159.4687 | 1058.1397 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 150 | 150 | 150 | [6 empty] | 450 | 3 | 0 | 0 | 0 | 5367.8068 | 5367.8068 | 5367.8068 | 0 | 0 | 0 | 0 | 0 | 0 | 16103.4205 | 7890.6761 | 23994.0966 | 1449.3078 | 710.1608 | 23994.0966 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 13719.0497 | 0 | 0 | 0 | 2384.3708 | 1.5.3
1.5 | 1.5.3.5.1 | UW | Testing of dust logger and IDP winch | Dust logger shipping UCB to UW/PSL |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 137.7 | 72.981 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1000 | 530 | 1530 | 90 | 47.7 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3
1.5 | 1.5.3.5.1 | PSL | Testing of dust logger and IDP winch | PSL Engineering support for summer 2024 testing |  | Labor Hours | Labor - Task | TE | D - Expert Opinion | 77 | 77 | 0% | 0% | Off Ice | C1 | 9% | 347.0973 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 48 |  | 48 | 0.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3856.6365 | 0 | 3856.6365 | 0 | 3856.6365 | 347.0973 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3856.6365 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 3856.6365 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3
1.5 | 1.5.3.5.1 | UW | Testing of dust logger and IDP winch | Research Scientist to test dust logger | Senior Scientist | Labor Hours | Labor - Task | SS | D - Expert Opinion | 66 | 66 | 35% | 53% | Off Ice | C1 | 9% | 2048.3698 | 1085.636 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 160 |  | 160 | 1.0667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14875.5978 | 0 | 14875.5978 | 7884.0669 | 22759.6647 | 1338.8038 | 709.566 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22759.6647 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 11018.9614 | 0 | 0 | 0 | 3856.6365 | 0 | 0 | 1.5.3
1.5 | 1.5.3.5.1 | UW | Testing of dust logger and IDP winch | Travel to test dust logger | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 247.86 | 131.3658 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 1800 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3
1.5 | 1.5.3.5.3 | UW | Delivery of logger and winch to PTH | Shipping of logger and winch to PTH |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 550.8 | 291.924 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 2120 | 6120 | 360 | 190.8 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6120 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.3
1.5 | 1.5.4.1 | UA | Calibration management | Calibration Management | Williams | Labor Hours | Labor - LoE | KE | D - Expert Opinion | 73 | 116 | 32% | 49% | Off Ice | C1 | 9% | 3236.5257 | 1585.8976 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7874.5392 | 0 | 0 | 7874.5392 | 3858.5242 | 11733.0634 | 708.7085 | 347.2672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8043.8418 | 0 | 0 | 8043.8418 | 3941.4825 | 11985.3243 | 723.9458 | 354.7334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 80 | 0.53333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8216.7844 | 0 | 0 | 8216.7844 | 4026.2244 | 12243.0087 | 739.5106 | 362.3602 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35961.3964 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 5965.56 | 6093.8195 | 6224.8367 | 0 | 1908.9792 | 1950.0223 | 1991.9477 | 0 | 1.5.4
1.5 | 1.5.4.1 | UA | Calibration management | Miscellaneous supplies for calibration and outreach activities |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 49% | Off Ice | C1 | 9% | 402.3 | 197.127 |  | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 0 | 0 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 3000 | 1470 | 4470 | 270 | 132.3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4470 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.4
1.5 | 1.5.4.2 | UA | Travel | Travel to reviews and working meetings - Domestic | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 49% | Off Ice | C1 | 9% | 1689.66 | 827.9334 | [5 empty] | 1800 |  |  |  |  | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 3600 | 1764 | 5364 | 324 | 158.76 |  |  |  |  | 1800 |  |  |  |  | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 3600 | 1764 | 5364 | 324 | 158.76 |  |  |  |  | 1800 |  |  |  |  | 1800 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 3600 | 1764 | 5364 | 324 | 158.76 |  |  |  |  | 1800 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 882 | 2682 | 162 | 79.38 | 18774 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.4
1.5 | 1.5.4.2 | UA | Travel | Travel to reviews and working meetings - International | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 49% | Off Ice | C1 | 9% | 2574.72 | 1261.6128 | [8 empty] | 3200 |  |  | 3200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 3200 | 0 | 6400 | 3136 | 9536 | 576 | 282.24 | [7 empty] | 3200 |  |  | 3200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 3200 | 0 | 6400 | 3136 | 9536 | 576 | 282.24 | [7 empty] | 3200 |  |  | 3200 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 3200 | 0 | 6400 | 3136 | 9536 | 576 | 282.24 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28608 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5.4
1.6 | 1.6.0 | UMD | L2 Task Management | L2 Task management - Erik Blaufuss | Blaufuss | Labor Hours | Labor - LoE | SS | E - Extrapolation from Actuals | 79 | 66 | 29% | 54.5% | Off Ice | C1 | 9% | 13749.2959 | 7493.3663 | 20% effort for management - EKB | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 264 | 1.76 | 2290.2234 | 2290.2234 | 2290.2234 | 2290.2234 | 2290.2234 | 2290.2234 | 2290.2234 | 2290.2234 | 2290.2234 | 2290.2234 | 2290.2234 | 2290.2234 | 27482.6812 | 14978.0612 | 42460.7424 | 2473.4413 | 1348.0255 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 264 | 1.76 | 2339.4632 | 2339.4632 | 2339.4632 | 2339.4632 | 2339.4632 | 2339.4632 | 2339.4632 | 2339.4632 | 2339.4632 | 2339.4632 | 2339.4632 | 2339.4632 | 28073.5588 | 15300.0895 | 43373.6484 | 2526.6203 | 1377.0081 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 264 | 1.76 | 2389.7617 | 2389.7617 | 2389.7617 | 2389.7617 | 2389.7617 | 2389.7617 | 2389.7617 | 2389.7617 | 2389.7617 | 2389.7617 | 2389.7617 | 2389.7617 | 28677.1403 | 15629.0415 | 44306.1818 | 2580.9426 | 1406.6137 | 22 | 22 | 22 | 22 | 22 | 22 | [6 empty] | 132 | 0.88 | 2441.1416 | 2441.1416 | 2441.1416 | 2441.1416 | 2441.1416 | 2441.1416 | 0 | 0 | 0 | 0 | 0 | 0 | 14646.8494 | 7982.5329 | 22629.3824 | 1318.2164 | 718.428 | 152769.9549 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 21304.404 | 21762.4487 | 22230.3413 | 11354.1468 | 6178.2772 | 6311.1101 | 6446.799 | 3292.7026 | 1.6.0
1.6 | 1.6.0 | UMD | L2 Task Management | Travel to annual project reviews | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 54.5% | Off Ice | C1 | 9% | 1251.45 | 682.0403 | [7 empty] | 1800 |  |  |  |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 3600 | 1962 | 5562 | 324 | 176.58 | [6 empty] | 1800 |  |  |  |  | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 3600 | 1962 | 5562 | 324 | 176.58 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 981 | 2781 | 162 | 88.29 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13905 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.0
1.6 | 1.6.0 | UMD | L2 Task Management | Travel to project planning workshops and meetings | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 54.5% | Off Ice | C1 | 9% | 250.29 | 136.4081 | [7 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 981 | 2781 | 162 | 88.29 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.0
1.6 | 1.6.0 | UW | L2 Task Management | PQ process - all L3 areas |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 261.63 | 138.6639 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 950 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 503.5 | 1453.5 | 85.5 | 45.315 | [5 empty] | 950 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 503.5 | 1453.5 | 85.5 | 45.315 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2907 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.0
1.6 | 1.6.0 | UW | L2 Task Management | Deployment to Pole - all L3 areas | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | On Ice | C1 | 9% | 495.72 | 262.7316 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 954 | 2754 | 162 | 85.86 | [11 empty] | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5508 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.0
1.6 | 1.6.0 | UMD | L2 Task Management | PQ process - all L3 areas |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 54.5% | On Ice | C1 | 9% | 132.0975 | 71.9931 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 950 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 517.75 | 1467.75 | 85.5 | 46.5975 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1467.75 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.0
1.6 | 1.6.0 | UMD | L2 Task Management | Deployment to Pole - all L3 areas | Foreign | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 54.5% | On Ice | C1 | 9% | 250.29 | 136.4081 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 981 | 2781 | 162 | 88.29 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2781 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.0
1.6 | 1.6.1.0 | UW | L3 Task Management | L3 Task Management - Jim Braun | Braun | Labor Hours | Labor Hours | SC | E - Extrapolation from Actuals | 54 | 52 | 35% | 53% | Off Ice | C1 | 9% | 3541.7788 | 1877.1428 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96 | 0.64 | 595.7388 | 595.7388 | 595.7388 | 595.7388 | 595.7388 | 595.7388 | 595.7388 | 595.7388 | 595.7388 | 595.7388 | 595.7388 | 595.7388 | 7148.8656 | 3788.8988 | 10937.7644 | 643.3979 | 341.0009 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96 | 0.64 | 608.5472 | 608.5472 | 608.5472 | 608.5472 | 608.5472 | 608.5472 | 608.5472 | 608.5472 | 608.5472 | 608.5472 | 608.5472 | 608.5472 | 7302.5662 | 3870.3601 | 11172.9263 | 657.231 | 348.3324 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96 | 0.64 | 621.6309 | 621.6309 | 621.6309 | 621.6309 | 621.6309 | 621.6309 | 621.6309 | 621.6309 | 621.6309 | 621.6309 | 621.6309 | 621.6309 | 7459.5714 | 3953.5728 | 11413.1442 | 671.3614 | 355.8216 | 8 | 8 | 8 | 8 | 8 | 8 | [6 empty] | 48 | 0.32 | 634.996 | 634.996 | 634.996 | 634.996 | 634.996 | 634.996 | 0 | 0 | 0 | 0 | 0 | 0 | 3809.9761 | 2019.2873 | 5829.2634 | 342.8978 | 181.7359 | 39353.0983 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 5295.456 | 5409.3083 | 5525.6084 | 2822.2045 | 1853.4096 | 1893.2579 | 1933.963 | 987.7716 | 1.6.1
1.6 | 1.6.1.0 | UW | L3 Task Management | Travel to project planning workshops and meetings | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 743.58 | 394.0974 | [7 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8262 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1
1.6 | 1.6.1.0 | UW | L3 Task Management | Travel to NTS for new OM integration work | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 247.86 | 131.3658 | [7 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1
1.6 | 1.6.1.0 | UW | L3 Task Management | Travel to NTS for new calibration device integration work | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 495.72 | 262.7316 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5508 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1
1.6 | 1.6.1.0 | UW | L3 Task Management | Travel to NTS for OM integration work | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 495.72 | 262.7316 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5508 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1
1.6 | 1.6.1.4.3.8 | UW | Support OM testing app thru FAT testing cycles | Support OM testing app thru FAT testing cycles | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 64.75 | 55 | 35% | 53% | Off Ice | C1 | 9% | 6639.5648 | 3518.9693 |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | 3.6 | 4018.1341 | 4018.1341 | 4018.1341 | 4018.1341 | 4018.1341 | 4018.1341 | 4018.1341 | 4018.1341 | 4018.1341 | 4018.1341 | 4018.1341 | 4018.1341 | 48217.6091 | 25555.3328 | 73772.942 | 4339.5848 | 2299.98 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73772.942 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 35716.7475 | 0 | 0 | 0 | 12500.8616 | 0 | 0 | 0 | 1.6.1
1.6 | 1.6.1.4.3.9.1 | UW | Extend OM testing app to include support for MMB based special devices | Extend OM testing app to include support for MMB based special devices | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 64.75 | 55 | 35% | 53% | Off Ice | C4 | 35% | 21038.9501 | 11150.6436 |  | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 20 |  |  |  |  | 440 | 2.9333 | 5357.5121 | 5357.5121 | 5357.5121 | 5357.5121 | 5357.5121 | 5357.5121 | 5357.5121 | 1785.8374 | 0 | 0 | 0 | 0 | 39288.4223 | 20822.8638 | 60111.286 | 13750.9478 | 7288.0023 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60111.286 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 29102.535 | 0 | 0 | 0 | 10185.8872 | 0 | 0 | 0 | 1.6.1
1.6 | 1.6.1.4.3.9.2 | UW | Support OM testing app thru calibration device DVT and FAT testing | Support OM testing app thru calibration device DVT and FAT testing | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 64.75 | 55 | 35% | 53% | Off Ice | C2 | 12.5% | 12631.4817 | 6694.6853 | [8 empty] | 40 | 60 | 60 | 60 | 60 | 280 | 1.8667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3571.6748 | 5357.5121 | 5357.5121 | 5357.5121 | 5357.5121 | 25001.7232 | 13250.9133 | 38252.6366 | 3125.2154 | 1656.3642 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 30 |  |  |  |  | 450 | 3 | 5472.6986 | 5472.6986 | 5472.6986 | 5472.6986 | 5472.6986 | 5472.6986 | 5472.6986 | 2736.3493 | 0 | 0 | 0 | 0 | 41045.2398 | 21753.9771 | 62799.2168 | 5130.655 | 2719.2471 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101051.8534 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 18519.795 | 30403.8813 | 0 | 0 | 6481.9282 | 10641.3585 | 0 | 0 | 1.6.1
1.6 | 1.6.1.4.3.10 | UW | Prototype and test SPAT testing software at NTS | Prototype and test SPAT testing software at NTS | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 64.75 | 55 | 35% | 53% | Off Ice | C3 | 20% | 6698.5831 | 3550.2491 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 60 | 60 | 60 | 60 | [5 empty] | 240 | 1.6 | 0 | 0 | 0 | 5472.6986 | 5472.6986 | 5472.6986 | 5472.6986 | 0 | 0 | 0 | 0 | 0 | 21890.7945 | 11602.1211 | 33492.9157 | 4378.1589 | 2320.4242 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33492.9157 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 16215.4034 | 0 | 0 | 0 | 5675.3912 | 0 | 0 | 1.6.1
1.6 | 1.6.1.4.3.11 | UW | Prepare and ship SPAT toolset to Pole | Prepare and ship SPAT toolset to Pole | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 64.75 | 55 | 35% | 53% | Off Ice | C2 | 12.5% | 2354.9706 | 1248.1344 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 45 | 45 | 45 |  |  | 135 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4104.524 | 4104.524 | 4104.524 | 0 | 0 | 12313.5719 | 6526.1931 | 18839.7651 | 1539.1965 | 815.7741 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18839.7651 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 9121.1644 | 0 | 0 | 0 | 3192.4075 | 0 | 0 | 1.6.1
1.6 | 1.6.1.4.3.11 | UW | Prepare and ship SPAT toolset to Pole | Prepare and ship SPAT toolset to Pole |  | M & S | M & S |  | D - Expert Opinion |  | 1 | 0% | 53% |  | C2 | 12.5% | 1434.375 | 760.2188 | tools and computers for SPAT | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 7500 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 7500 | 3975 | 11475 | 937.5 | 496.875 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11475 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.1
1.6 | 1.6.1.4.3.13 | UW | SPAT testing preparation and execution at Pole FS2 | SPAT testing preparation and execution at Pole FS2 | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 64.75 | 55 | 35% | 53% | On Ice | C2 | 12.5% | 8018.675 | 4249.8978 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 150 | 150 | 150 | [7 empty] | 450 | 3 | 0 | 0 | 13975.9041 | 13975.9041 | 13975.9041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41927.7124 | 22221.6876 | 64149.4 | 5240.9641 | 2777.7109 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64149.4 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 31057.5648 | 0 | 0 | 0 | 10870.1477 | 0 | 1.6.1
1.6 | 1.6.1.4.3.15 | UW | SPAT testing preparation and execution at Pole FS3 | SPAT testing preparation and execution at Pole FS3 | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 64.75 | 55 | 35% | 53% | On Ice | C2 | 12.5% | 8191.0765 | 4341.2706 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 150 | 150 | 150 | [8 empty] | 450 | 3 | 0 | 14276.3861 | 14276.3861 | 14276.3861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42829.1582 | 22699.4539 | 65528.6121 | 5353.6448 | 2837.4317 | 65528.6121 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 31725.3024 | 0 | 0 | 0 | 11103.8558 | 1.6.1
1.6 | 1.6.1.4.5.4.3 | UW | Extend xDOMapp to include support for calibration devices in operations | Extend xDOMapp to include support for calibration devices in operations | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 64.75 | 55 | 35% | 53% | Off Ice | C4 | 35% | 20666.1064 | 10953.0364 | [11 empty] | 45 | 45 | 90 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4018.1341 | 4018.1341 | 8036.2682 | 4259.2221 | 12295.4903 | 2812.6939 | 1490.7277 | 45 | 45 | 45 | 30 | 30 | 30 | 30 | 30 | 30 | 20 |  |  | 335 | 2.2333 | 4104.524 | 4104.524 | 4104.524 | 2736.3493 | 2736.3493 | 2736.3493 | 2736.3493 | 2736.3493 | 2736.3493 | 1824.2329 | 0 | 0 | 30555.9007 | 16194.6274 | 46750.5281 | 10694.5653 | 5668.1196 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59046.0184 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 5952.7913 | 22634.0005 | 0 | 0 | 2083.4769 | 7921.9002 | 0 | 0 | 1.6.1
1.6 | 1.6.1.4.5.6 | UW | Support full DAQ testing with xDOMapp at NTS/SPTS with Calibration devices | Support full DAQ testing with xDOMapp at NTS/SPTS with Calibration devices | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 64.75 | 55 | 35% | 53% | Off Ice | C2 | 12.5% | 3143.2761 | 1665.9363 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 20 | 45 | 45 | 110 | 0.73333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1863.4539 | 4192.7712 | 4192.7712 | 10248.9964 | 5431.9681 | 15680.9644 | 1281.1245 | 678.996 | 45 |  |  |  | 20 | [7 empty] | 65 | 0.43333 | 4282.9158 | 0 | 0 | 0 | 1903.5181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6186.434 | 3278.81 | 9465.244 | 773.3042 | 409.8513 | 25146.2084 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 7591.8492 | 4582.5437 | 0 | 0 | 2657.1472 | 1603.8903 | 1.6.1
1.6 | 1.6.1.4.5.8 | UW | Support xDOMapp through SPAT testing and deployment | Support xDOMapp through SPAT testing and deployment | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 64.75 | 55 | 35% | 53% | Off Ice | C2 | 12.5% | 6437.9269 | 3412.1012 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 300 | 2 | 0 | 0 | 2795.1808 | 2795.1808 | 2795.1808 | 2795.1808 | 2795.1808 | 2795.1808 | 2795.1808 | 2795.1808 | 2795.1808 | 2795.1808 | 27951.8083 | 14814.4584 | 42766.2667 | 3493.976 | 1851.8073 | 30 |  |  |  | 30 | [7 empty] | 60 | 0.4 | 2855.2772 | 0 | 0 | 0 | 2855.2772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5710.5544 | 3026.5938 | 8737.1483 | 713.8193 | 378.3242 | 51503.415 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 20705.0432 | 4230.0403 | 0 | 0 | 7246.7651 | 1480.5141 | 1.6.1
1.6 | 1.6.1.4.6.5 | UW | Support MMB software for calibration device interface development | Support MMB-xDOMapp software for calibration devices | Weber | Labor Hours | Labor - Task | SE | D - Expert Opinion | 64.75 | 55 | 35% | 53% | Off Ice | C2 | 12.5% | 14097.4901 | 7471.6698 | [7 empty] | 45 | 45 | 45 | 45 |  |  | 180 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 4018.1341 | 4018.1341 | 4018.1341 | 4018.1341 | 0 | 0 | 16072.5364 | 8518.4443 | 24590.9807 | 2009.067 | 1064.8055 | 45 | 45 | 45 |  |  |  |  | 45 | 90 | 90 | 90 | 90 | 540 | 3.6 | 4104.524 | 4104.524 | 4104.524 | 0 | 0 | 0 | 0 | 4104.524 | 8209.048 | 8209.048 | 8209.048 | 8209.048 | 49254.2877 | 26104.7725 | 75359.0602 | 6156.786 | 3263.0966 | 45 | 45 | [10 empty] | 90 | 0.6 | 4192.7712 | 4192.7712 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8385.5425 | 4444.3375 | 12829.88 | 1048.1928 | 555.5422 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112779.9209 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 11905.5825 | 36484.6576 | 6211.513 | 0 | 4166.9539 | 12769.6301 | 2174.0295 | 0 | 1.6.1
1.6 | 1.6.1.6.6 | PSU | Firmware device maintenance and support for all OM devices during DAQ Development | Firmware device maintenance and support for all OM devices during DAQ Development | Anderson | Labor Hours | Labor - Task | SE | D - Expert Opinion | 64 | 64 | 40% | 58.05% | Off Ice | C3 | 20% | 12423.1671 | 7211.6485 |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 180 | 1.2 | 1372.896 | 1372.896 | 1372.896 | 1372.896 | 1372.896 | 1372.896 | 1372.896 | 1372.896 | 1372.896 | 1372.896 | 1372.896 | 1372.896 | 16474.752 | 9563.5935 | 26038.3455 | 3294.9504 | 1912.7187 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96 | 0.64 | 747.9537 | 747.9537 | 747.9537 | 747.9537 | 747.9537 | 747.9537 | 747.9537 | 747.9537 | 747.9537 | 747.9537 | 747.9537 | 747.9537 | 8975.4449 | 5210.2458 | 14185.6906 | 1795.089 | 1042.0492 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 96 | 0.64 | 764.0347 | 764.0347 | 764.0347 | 764.0347 | 764.0347 | 764.0347 | 764.0347 | 764.0347 | 764.0347 | 764.0347 | 764.0347 | 764.0347 | 9168.417 | 5322.266 | 14490.683 | 1833.6834 | 1064.4532 | 8 | 8 | 8 | 8 | 8 | 8 | [6 empty] | 48 | 0.32 | 780.4615 | 780.4615 | 780.4615 | 780.4615 | 780.4615 | 780.4615 | 0 | 0 | 0 | 0 | 0 | 0 | 4682.769 | 2718.3474 | 7401.1163 | 936.5538 | 543.6695 | 62115.8355 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 11767.68 | 6411.0321 | 6548.8693 | 3344.835 | 4707.072 | 2564.4128 | 2619.5477 | 1337.934 | 1.6.1
1.6 | 1.6.4.0 | UW | L3 Task Management | L3 Task management - Ralf Auer | Auer | Labor Hours | Labor - LoE | EN | E - Extrapolation from Actuals | 60 | 49 | 35% | 53% | Off Ice | C1 | 9% | 1438.9122 | 762.6234 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 72 | 0.48 | 0 | 0 | 0 | 690.7011 | 690.7011 | 690.7011 | 690.7011 | 690.7011 | 690.7011 | 690.7011 | 690.7011 | 690.7011 | 6216.3095 | 3294.644 | 9510.9535 | 559.4679 | 296.518 | 8 | 8 | 8 | 8 | 8 | 8 | [6 empty] | 48 | 0.32 | 705.5511 | 705.5511 | 705.5511 | 705.5511 | 705.5511 | 705.5511 | 0 | 0 | 0 | 0 | 0 | 0 | 4233.3068 | 2243.6526 | 6476.9593 | 380.9976 | 201.9287 | 15987.9129 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 4604.6737 | 3135.7828 | 0 | 0 | 1611.6358 | 1097.524 | 1.6.4
1.6 | 1.6.4.0 | UW | L3 Task Management | Miscellaneous supplies |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 137.7 | 72.981 | [7 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 265 | 765 | 45 | 23.85 | [6 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 265 | 765 | 45 | 23.85 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4
1.6 | 1.6.4.0 | UW | L3 Task Management | Trip to MSU to install NTS equipment | Domestic | Travel | Travel |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 247.86 | 131.3658 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 1800 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 954 | 2754 | 162 | 85.86 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4
1.6 | 1.6.4.0 | UW | L3 Task Management | NTS computing system purchase |  | CapEx | CapEx |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 500 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2500 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2500 | 500 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4
1.6 | 1.6.4.0 | UW | L3 Task Management | Miscellaneous supplies |  | M & S | M & S |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C1 | 9% | 68.85 | 36.4905 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 500 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 500 | 265 | 765 | 45 | 23.85 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4
1.6 | 1.6.4.0 | UW | L3 Task Management | SPS computing system additions |  | CapEx | CapEx |  | E - Extrapolation from Actuals |  | 1 | 0% | 53% | Off Ice | C3 | 20% | 2400 | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 12000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 12000 | 0 | 12000 | 2400 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.6.4
1.6 | 1.6.5.0 | UMD | L3 Task Management | L3 Task Management |  | Labor Hours | Labor - Task | SC | E - Extrapolation from Actuals | 52 | 52 | 29% | 54.5% | Off Ice | C1 | 9% | 1203.3151 | 655.8067 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 72 | 0.48 | 0 | 0 | 0 | 572.0028 | 572.0028 | 572.0028 | 572.0028 | 572.0028 | 572.0028 | 572.0028 | 572.0028 | 572.0028 | 5148.0252 | 2805.6737 | 7953.6989 | 463.3223 | 252.5106 | 8 | 8 | 8 | 8 | 8 | 8 | [6 empty] | 48 | 0.32 | 584.3009 | 584.3009 | 584.3009 | 584.3009 | 584.3009 | 584.3009 | 0 | 0 | 0 | 0 | 0 | 0 | 3505.8052 | 1910.6638 | 5416.469 | 315.5225 | 171.9597 | 13370.1679 | 1 | 1.0215 | 1.0435 | 1.0659 | 1.0888 | 0 | 0 | 3990.7172 | 2717.6784 | 0 | 0 | 1157.308 | 788.1267 | 1.6.5
[17 empty] | 1835084.4802 | 451425.5103 | [29 empty] | 4806290.6382 | 572007.8507 | 108575.7925 | [29 empty] | 397022.2406 | 82643.0607 | [29 empty] | 346221.0301 | 71743.8032 | [29 empty] | 225059.5103 | 31811.1921 | 14731624.3968

## PY5 Pivots
Institution | UW
Type | Labor Hours
Sum of Salary Cost PY5 | L3
Resource Name | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.10 | 1.2.8 | 1.3.3 | 1.3.4 | 1.4.2 | 1.4.4 | 1.5.2 | 1.5.3 | 1.6.1 | 1.6.4 | Total Result
Auer | [15 empty] | 0 | 0
Braun | [14 empty] | 5295.456 |  | 5295.456
Controls |  | 84580.2 | [14 empty] | 84580.2
DuVernois |  |  |  |  | 68031.9 | [11 empty] | 68031.9
Feyzi | 180192.6 | [15 empty] | 180192.6
Finance |  | 33096.6 | [14 empty] | 33096.6
Hanson | 18534.096 | [15 empty] | 18534.096
Kelley | [10 empty] | 9270.8888 | 29169.382 |  |  |  |  | 38440.2708
McEwen | [5 empty] | 112160.7 | [10 empty] | 112160.7
ODell | 82520.856 | [15 empty] | 82520.856
S. Griffin | [9 empty] | 21988.809 | [6 empty] | 21988.809
Sandstrom |  |  |  |  | 58838.4 | [11 empty] | 58838.4
Scientist | [8 empty] | 6108.57 | [7 empty] | 6108.57
Senior Scientist | [13 empty] | 0 |  |  | 0
Tosi |  |  |  | 17283.78 |  | 38244.96 | 0 | [9 empty] | 55528.74
Weber | [14 empty] | 101197.4512 |  | 101197.4512
Wendt | [12 empty] | 29878.875 |  |  |  | 29878.875
Zernick |  |  | 84494.394 |  |  |  |  | 0 | [8 empty] | 84494.394
Total Result | 281247.552 | 117676.8 | 84494.394 | 17283.78 | 126870.3 | 150405.66 | 0 | 0 | 6108.57 | 21988.809 | 9270.8888 | 29169.382 | 29878.875 | 0 | 106492.9073 | 0 | 980887.9181
Institution | UW
Type | Labor Hours
Sum of Fringe Cost PY5 | L3
Resource Name | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.10 | 1.2.8 | 1.3.3 | 1.3.4 | 1.4.2 | 1.4.4 | 1.5.2 | 1.5.3 | 1.6.1 | 1.6.4 | Total Result
Auer | [15 empty] | 0 | 0
Braun | [14 empty] | 1853.4096 |  | 1853.4096
Controls |  | 29603.07 | [14 empty] | 29603.07
DuVernois |  |  |  |  | 23811.165 | [11 empty] | 23811.165
Feyzi | 63067.41 | [15 empty] | 63067.41
Finance |  | 11583.81 | [14 empty] | 11583.81
Hanson | 6486.9336 | [15 empty] | 6486.9336
Kelley | [10 empty] | 3244.8111 | 10209.2837 |  |  |  |  | 13454.0948
McEwen | [5 empty] | 39256.245 | [10 empty] | 39256.245
ODell | 28882.2996 | [15 empty] | 28882.2996
S. Griffin | [9 empty] | 7696.0832 | [6 empty] | 7696.0832
Sandstrom |  |  |  |  | 20593.44 | [11 empty] | 20593.44
Scientist | [8 empty] | 2137.9995 | [7 empty] | 2137.9995
Senior Scientist | [13 empty] | 0 |  |  | 0
Tosi |  |  |  | 6049.323 |  | 13385.736 | 0 | [9 empty] | 19435.059
Weber | [14 empty] | 35419.1079 |  | 35419.1079
Wendt | [12 empty] | 10457.6063 |  |  |  | 10457.6063
Zernick |  |  | 29573.0379 |  |  |  |  | 0 | [8 empty] | 29573.0379
Total Result | 98436.6432 | 41186.88 | 29573.0379 | 6049.323 | 44404.605 | 52641.981 | 0 | 0 | 2137.9995 | 7696.0832 | 3244.8111 | 10209.2837 | 10457.6063 | 0 | 37272.5175 | 0 | 343310.7713
Institution | - multiple -
Type | CapEx
L3
1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.3.3 | 1.4.4 | 1.6.4 | Total Result
10942 | 24054 | 194456 | 22864 | 6600 | 24500 | 0 | 135302 | 91145 | 34966 | 0 | 544829
Institution | PSL
Type | Labor Hours
L3
1.2.1 | 1.2.10 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.3.3 | 1.5.3 | Total Result
403933.788 | 0 | 6897.168 | 35719.812 | 670748.5665 | 12217.14 | 4698.9 | 40602.582 | 57265.29 | 7048.35 | 23698.8 | 0 | 1262830.3965
Institution | - multiple -
Type | Travel
Sum of 12mo Subtotal PY5 | L3
Resource Name | 1.1.1 | 1.2.1 | 1.2.10 | 1.2.8 | 1.2.9 | 1.3.3 | 1.4.4 | 1.5.3 | 1.6.0 | 1.6.1 | 1.6.4 | Total Result
Domestic | 28200 | 12600 |  | 1800 | 1800 | 1800 | 1800 | 0 |  | 3600 | 0 | 51600
Foreign | 9600 |  | 0 | 31600 |  |  | 0 |  | 0 |  |  | 41200
Total Result | 37800 | 12600 | 0 | 33400 | 1800 | 1800 | 1800 | 0 | 0 | 3600 | 0 | 92800
Institution | - multiple -
Type | M & S
L3
1.1.1 | 1.2.1 | 1.2.10 | 1.2.7 | 1.2.8 | 1.3.3 | 1.4.2 | 1.4.4 | 1.5.3 | 1.6.0 | 1.6.1 | 1.6.4 | Total Result
15500 | 28942 | 0 | 5000 | 22400 | 12500 | 31075 | 2000 | 0 | 0 | 0 | 500 | 117917
Type | - all -
Sum of Complete Total PY5 | L3
Institution | 1.1.1 | 1.4.1 | 1.4.2 | 1.4.4 | 1.4.6 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.5 | Total Result
MSU |  | 424951.9374 | 37941.1372 | 0 | 43675.5536 | [5 empty] | 506568.6282
PSU | 16273.966 | [7 empty] | 26038.3455 |  | 42312.3115
UA | [5 empty] | 0 | 31103.0634 |  |  |  | 31103.0634
UMD | 19422.4915 | [6 empty] | 50803.7424 |  | 0 | 70226.2339
Total Result | 35696.4574 | 424951.9374 | 37941.1372 | 0 | 43675.5536 | 0 | 31103.0634 | 50803.7424 | 26038.3455 | 0 | 650210.237
Type | - all -
Institution | - multiple -
L3
1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.10 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.3.3 | 1.3.4 | 1.4.2 | 1.4.4 | 1.5.2 | 1.5.3 | 1.6.0 | 1.6.1 | 1.6.4 | Total Result
229481.6235 | 84197.7504 | 60455.7389 | 12366.5446 | 90775.6996 | 129632.5097 | 0 | 0 | 0 | 0 | 0 | 0 | 2650 | 29574 | 954 | 11949.6818 | 15732.9928 | 23103.071 | 22884.6928 | 21378.3351 | 0 | 0 | 78103.6751 | 265 | 813505.3154
Type | Labor Hours
Institution | UW
Resource Name | Sum of PY5 CMo
Auer | 0
Braun | 0.64
Controls | 12
DuVernois | 6
Feyzi | 12
Finance | 4.8
Hanson | 0.96
Kelley | 4.5333
McEwen | 12
ODell | 4.8
S. Griffin | 3.0533
Sandstrom | 6
Scientist | 0.86667
Senior Scientist | 0
Tosi | 7.2
Weber | 10.2
Wendt | 3
Zernick | 9.04
Total Result | 97.0933
Data |  | Discrete Risks Direct | Discrete Risks Ind | Discrete Risks Total | Total Contingency | Total Direct | Total Indirect
Sum of EU Direct PY5 | Sum of EU Ind PY5 | 521437.2726 | 98976.7274 | 620414 | 1300997.6432 | 1093445.1233 | 207552.5199
572007.8507 | 108575.7925 | 84.05% | 15.95%

## PY5 1030
Year 5 Budget
|  |  |  | 1.1 Project Office |  |  |  |  | 1.2 Drilling and Installation | [9 empty] | 1.3 Deep Ice Sensor Modules |  |  |  |  | 1.4 Comm/Power/Timing | [5 empty] | 1.5 Characterization and Calibration System |  |  |  | 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 5
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Hanson | 0.96 | 18534.096 | 18534.096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | Feyzi | 12 | 180192.6 | 180192.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Director | ODell | 4.8 | 82520.856 | 82520.856
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Controls Manager | Finance | 4.8 | 33096.6 | 0 | 33096.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Controls Analyst | Controls | 12 | 84580.2 | 0 | 84580.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality and Safety | Zernick | 9.04 | 84494.394 | 0 | 0 | 84494.394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical Coordinator | DuVernois | 6 | 68031.9 | 0 | 0 | 0 | 0 | 68031.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Engineer | Sandstrom | 6 | 58838.4 | 0 | 0 | 0 | 0 | 58838.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Logistics Manager | Tosi | 7.2 | 55528.74 | 0 | 0 | 0 | 17283.78 | 0 | 38244.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation Manager | McEwen | 12 | 112160.7 | 0 | 0 | 0 | 0 | 0 | 112160.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer / Technician | Wendt | 3 | 29878.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29878.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer / Technician | Weber | 10.2 | 101197.4512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101197.4512 | 0 | 0 | 0 | 0
Engineer | Kelley | 4.5333 | 38440.2708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9270.8888 | 0 | 29169.382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | Braun | 0.64 | 5295.456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5295.456 | 0 | 0 | 0 | 0
Engineer | Auer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior Scientist | Senior Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | Scientist | 0.86667 | 6108.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6108.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | S. Griffin | 3.0533 | 21988.809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21988.809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 980887.918 | 281247.552 | 117676.8 | 84494.394 | 17283.78 | 126870.3 | 150405.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6108.57 | 21988.809 | 0 | 0 | 9270.8888 | 0 | 29169.382 | 0 | 0 | 0 | 29878.875 | 0 | 0 | 0 | 106492.9073 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 343310.7713 | 98436.6432 | 41186.88 | 29573.0379 | 6049.323 | 44404.605 | 52641.981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2137.9995 | 7696.0832 | 0 | 0 | 3244.8111 | 0 | 10209.2837 | 0 | 0 | 0 | 10457.6063 | 0 | 0 | 0 | 37272.5175 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Eqipment | 1 | 1 | 544829 | 0 | 0 | 0 | 0 | 0 | 0 | 10942 | 24054 | 194456 | 22864 | 6600 | 24500 | 0 | 135302 | 0 | 0 | 0 | 91145 | 0 | 0 | 0 | 0 | 0 | 34966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 1262830.3965 | 0 | 0 | 0 | 0 | 0 | 403933.788 | 6897.168 | 35719.812 | 670748.5665 | 12217.14 | 4698.9 | 40602.582 | 57265.29 | 7048.35 | 0 | 0 | 0 | 23698.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 1807659.3965 | 0 | 0 | 0 | 0 | 0 | 403933.788 | 17839.168 | 59773.812 | 865204.5665 | 35081.14 | 11298.9 | 65102.582 | 57265.29 | 142350.35 | 0 | 0 | 0 | 114843.8 | 0 | 0 | 0 | 0 | 0 | 34966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 51600 | 28200 | 0 | 0 | 0 | 0 | 12600 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0
Foreign |  |  | 41200 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 92800 | 37800 | 0 | 0 | 0 | 0 | 12600 | 0 | 0 | 0 | 0 | 0 | 0 | 33400 | 1800 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 117917 | 15500 | 0 | 0 | 0 | 0 | 28942 | 0 | 0 | 0 | 0 | 0 | 5000 | 22400 | 0 | 0 | 0 | 0 | 12500 | 0 | 0 | 0 | 31075 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 117917 | 15500 | 0 | 0 | 0 | 0 | 28942 | 0 | 0 | 0 | 0 | 0 | 5000 | 22400 | 0 | 0 | 0 | 0 | 12500 | 0 | 0 | 0 | 31075 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Another professional service |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
MSU |  |  | 506568.6282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424951.9374 | 37941.1372 | 0 | 0 | 0 | 43675.5536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSU |  |  | 42312.3115 | 16273.966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26038.3455 | 0 | 0 | 0 | 0
UA |  |  | 31103.0634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31103.0634 | 0 | 0 | 0 | 0 | 0 | 0
UMD |  |  | 70226.2339 | 19422.4915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50803.7424 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 650210.237 | 35696.4574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424951.9374 | 37941.1372 | 0 | 0 | 0 | 43675.5536 | 0 | 0 | 0 | 31103.0634 | 50803.7424 | 26038.3455 | 0 | 0 | 0 | 0
Other - Contingency |  |  | 1093445.1233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 5086230.4461 | 468680.6526 | 158863.68 | 114067.4319 | 23333.103 | 171274.905 | 648523.429 | 17839.168 | 59773.812 | 865204.5665 | 35081.14 | 11298.9 | 70102.582 | 113065.29 | 144150.35 | 0 | 0 | 0 | 137390.3695 | 29684.8921 | 0 | 424951.9374 | 81531.8372 | 0 | 78144.6656 | 0 | 43675.5536 | 0 | 40336.4812 | 0 | 31103.0634 | 50803.7424 | 173403.7703 | 0 | 0 | 500 | 0
Indirect Costs
Office OH |  |  | 813505.3154 | 229481.6235 | 84197.7504 | 60455.7389 | 12366.5446 | 90775.6996 | 129632.5097 | 0 | 0 | 0 | 0 | 0 | 2650 | 29574 | 954 | 0 | 0 | 0 | 11949.6818 | 15732.9928 | 0 | 0 | 23103.071 | 0 | 22884.6928 | 0 | 0 | 0 | 21378.3351 | 0 | 0 | 0 | 78103.6751 | 0 | 0 | 265 | 0
Other OH Contingency |  |  | 207552.5199 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 1021057.8353 | 229481.6235 | 84197.7504 | 60455.7389 | 12366.5446 | 90775.6996 | 129632.5097 | 0 | 0 | 0 | 0 | 0 | 2650 | 29574 | 954 | 0 | 0 | 0 | 11949.6818 | 15732.9928 | 0 | 0 | 23103.071 | 0 | 22884.6928 | 0 | 0 | 0 | 21378.3351 | 0 | 0 | 0 | 78103.6751 | 0 | 0 | 265 | 0
0
Total - Direct and Indirect
|  |  | 6107288.2814 | 698162.2761 | 243061.4304 | 174523.1708 | 35699.6476 | 262050.6046 | 778155.9387 | 17839.168 | 59773.812 | 865204.5665 | 35081.14 | 11298.9 | 72752.582 | 142639.29 | 145104.35 | 0 | 0 | 0 | 149340.0513 | 45417.885 | 0 | 424951.9374 | 104634.9081 | 0 | 101029.3584 | 0 | 43675.5536 | 0 | 61714.8163 | 0 | 31103.0634 | 50803.7424 | 251507.4455 | 0 | 0 | 765 | 0

## PY6 Pivots
Institution | UW
Type | Labor Hours
Sum of Salary Cost PY6 | L3
Resource Name | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.10 | 1.2.8 | 1.3.3 | 1.3.4 | 1.4.2 | 1.4.4 | 1.5.2 | 1.5.3 | 1.6.1 | 1.6.4 | Total Result
Auer | [15 empty] | 0 | 0
Braun | [14 empty] | 5409.3083 |  | 5409.3083
Controls |  | 43199.3371 | [14 empty] | 43199.3371
DuVernois |  |  |  |  | 69494.5859 | [11 empty] | 69494.5859
Feyzi | 97146.3355 | [15 empty] | 97146.3355
Finance |  | 33808.1769 | [14 empty] | 33808.1769
Hanson | 18932.5791 | [15 empty] | 18932.5791
Kelley | [10 empty] | 1385.8848 | 22174.1572 |  |  |  |  | 23560.042
McEwen | [5 empty] | 114572.1551 | [10 empty] | 114572.1551
ODell | 70245.8787 | [15 empty] | 70245.8787
S. Griffin | [9 empty] | 4119.589 | [6 empty] | 4119.589
Sandstrom |  |  |  |  | 60103.4256 | [11 empty] | 60103.4256
Scientist | [8 empty] | 0 | [7 empty] | 0
Senior Scientist | [13 empty] | 11018.9614 |  |  | 11018.9614
Tosi |  |  |  | 8827.6906 |  | 39067.2266 | 0 | [9 empty] | 47894.9173
Weber | [14 empty] | 114859.1072 |  | 114859.1072
Wendt | [12 empty] | 27977.8316 |  |  |  | 27977.8316
Zernick |  |  | 67915.8275 |  |  |  |  | 14099.2619 | [8 empty] | 82015.0894
Total Result | 186324.7932 | 77007.514 | 67915.8275 | 8827.6906 | 129598.0115 | 153639.3817 | 0 | 14099.2619 | 0 | 4119.589 | 1385.8848 | 22174.1572 | 27977.8316 | 11018.9614 | 120268.4155 | 0 | 824357.3198
Institution | UW
Type | Labor Hours
Sum of Fringe Cost PY6 | L3
Resource Name | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.10 | 1.2.8 | 1.3.3 | 1.3.4 | 1.4.2 | 1.4.4 | 1.5.2 | 1.5.3 | 1.6.1 | 1.6.4 | Total Result
Auer | [15 empty] | 0 | 0
Braun | [14 empty] | 1893.2579 |  | 1893.2579
Controls |  | 15119.768 | [14 empty] | 15119.768
DuVernois |  |  |  |  | 24323.105 | [11 empty] | 24323.105
Feyzi | 34001.2174 | [15 empty] | 34001.2174
Finance |  | 11832.8619 | [14 empty] | 11832.8619
Hanson | 6626.4027 | [15 empty] | 6626.4027
Kelley | [10 empty] | 485.0597 | 7760.955 |  |  |  |  | 8246.0147
McEwen | [5 empty] | 40100.2543 | [10 empty] | 40100.2543
ODell | 24586.0575 | [15 empty] | 24586.0575
S. Griffin | [9 empty] | 1441.8561 | [6 empty] | 1441.8561
Sandstrom |  |  |  |  | 21036.199 | [11 empty] | 21036.199
Scientist | [8 empty] | 0 | [7 empty] | 0
Senior Scientist | [13 empty] | 3856.6365 |  |  | 3856.6365
Tosi |  |  |  | 3089.6917 |  | 13673.5293 | 0 | [9 empty] | 16763.221
Weber | [14 empty] | 40200.6875 |  | 40200.6875
Wendt | [12 empty] | 9792.2411 |  |  |  | 9792.2411
Zernick |  |  | 23770.5396 |  |  |  |  | 4934.7417 | [8 empty] | 28705.2813
Total Result | 65213.6776 | 26952.6299 | 23770.5396 | 3089.6917 | 45359.304 | 53773.7836 | 0 | 4934.7417 | 0 | 1441.8561 | 485.0597 | 7760.955 | 9792.2411 | 3856.6365 | 42093.9454 | 0 | 288525.0619
Institution | - multiple -
Type | CapEx
L3
1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.3.3 | 1.4.4 | 1.6.4 | Total Result
36683 | 20502 | 17850 | 5000 | 31916 | 14000 | 0 | 120918 | 0 | 9000 | 0 | 255869
Institution | PSL
Type | Labor Hours
L3
1.2.1 | 1.2.10 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.3.3 | 1.5.3 | Total Result
308987.9545 | 0 | 40601.1161 | 21453.5839 | 134260.2008 | 14408.1267 | 14399.779 | 21307.4991 | 660059.4373 | 4799.9263 | 0 | 3856.6365 | 1224134.2604
Institution | - multiple -
Type | Travel
Sum of 12mo Subtotal PY6 | L3
Resource Name | 1.1.1 | 1.2.1 | 1.2.10 | 1.2.8 | 1.2.9 | 1.3.3 | 1.4.4 | 1.5.3 | 1.6.0 | 1.6.1 | 1.6.4 | Total Result
Domestic | 28200 | 12600 |  | 5400 | 1800 | 0 | 1800 | 1800 |  | 5400 | 0 | 57000
Foreign | 9600 |  | 0 | 40200 |  |  | 0 |  | 1800 |  |  | 51600
Total Result | 37800 | 12600 | 0 | 45600 | 1800 | 0 | 1800 | 1800 | 1800 | 5400 | 0 | 108600
Institution | - multiple -
Type | M & S
L3
1.1.1 | 1.2.1 | 1.2.10 | 1.2.7 | 1.2.8 | 1.3.3 | 1.4.2 | 1.4.4 | 1.5.3 | 1.6.0 | 1.6.1 | 1.6.4 | Total Result
15500 | 6814 | 950 | 5000 | 23050 | 1000 | 1700 | 1300 | 1000 | 950 | 7500 | 500 | 65264
Type | - all -
Sum of Complete Total PY6 | L3
Institution | 1.1.1 | 1.4.1 | 1.4.2 | 1.4.4 | 1.4.6 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.5 | Total Result
MSU |  | 54711.4602 | 7658.0059 | 2945 | 44477.9455 | [5 empty] | 109792.4116
PSU | 16623.8562 | [7 empty] | 14185.6906 |  | 30809.5469
UA | [5 empty] | 91978.7815 | 26885.3243 |  |  |  | 118864.1058
UMD | 19840.0751 | [6 empty] | 48935.6484 |  | 0 | 68775.7234
Total Result | 36463.9313 | 54711.4602 | 7658.0059 | 2945 | 44477.9455 | 91978.7815 | 26885.3243 | 48935.6484 | 14185.6906 | 0 | 328241.7877
Type | - all -
Institution | - multiple -
L3
1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.10 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.3.3 | 1.3.4 | 1.4.2 | 1.4.4 | 1.5.2 | 1.5.3 | 1.6.0 | 1.6.1 | 1.6.4 | Total Result
161564.3895 | 55098.8763 | 48593.7746 | 6316.2126 | 92727.3772 | 120218.3976 | 503.5 | 0 | 0 | 0 | 0 | 0 | 2650 | 46472.5219 | 954 | 530 | 2947.5659 | 1892.6006 | 17508.6094 | 20018.1385 | 9368.0669 | 1457.5 | 92889.0513 | 265 | 681975.5823
Type | Labor Hours
Institution | UW
Resource Name | Sum of PY6 CMo
Auer | 0
Braun | 0.64
Controls | 6
DuVernois | 6
Feyzi | 6.3333
Finance | 4.8
Hanson | 0.96
Kelley | 2.72
McEwen | 12
ODell | 4
S. Griffin | 0.56
Sandstrom | 6
Scientist | 0
Senior Scientist | 1.0667
Tosi | 6
Weber | 11.3333
Wendt | 2.75
Zernick | 9.52
Total Result | 80.6833
Data |  | Discrete Risks Direct | Discrete Risks Ind | Discrete Risks Total | Total Contingency | Total Direct | Total Indirect
Sum of EU Direct PY6 | Sum of EU Ind PY6 | 513520.8982 | 106893.1018 | 620414 | 1100079.3013 | 910543.1388 | 189536.1625
397022.2406 | 82643.0607 | 82.77% | 17.23%

## PY6 1030
Year 6 Budget
|  |  |  | 1.1 Project Office |  |  |  |  | 1.2 Drilling and Installation | [9 empty] | 1.3 Deep Ice Sensor Modules |  |  |  |  | 1.4 Comm/Power/Timing | [5 empty] | 1.5 Characterization and Calibration System |  |  |  | 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 6
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Hanson | 0.96 | 18932.5791 | 18932.5791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | Feyzi | 6.3333 | 97146.3355 | 97146.3355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Director | ODell | 4 | 70245.8787 | 70245.8787
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Controls Manager | Finance | 4.8 | 33808.1769 | 0 | 33808.1769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Controls Analyst | Controls | 6 | 43199.3371 | 0 | 43199.3371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality and Safety | Zernick | 9.52 | 82015.0894 | 0 | 0 | 67915.8275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14099.2619 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical Coordinator | DuVernois | 6 | 69494.5859 | 0 | 0 | 0 | 0 | 69494.5859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Engineer | Sandstrom | 6 | 60103.4256 | 0 | 0 | 0 | 0 | 60103.4256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Logistics Manager | Tosi | 6 | 47894.9173 | 0 | 0 | 0 | 8827.6906 | 0 | 39067.2266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation Manager | McEwen | 12 | 114572.1551 | 0 | 0 | 0 | 0 | 0 | 114572.1551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer / Technician | Wendt | 2.75 | 27977.8316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27977.8316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer / Technician | Weber | 11.3333 | 114859.1072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114859.1072 | 0 | 0 | 0 | 0
Engineer | Kelley | 2.72 | 23560.042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1385.8848 | 0 | 22174.1572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | Braun | 0.64 | 5409.3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5409.3083 | 0 | 0 | 0 | 0
Engineer | Auer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior Scientist | Senior Scientist | 1.0667 | 11018.9614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11018.9614 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | S. Griffin | 0.56 | 4119.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4119.589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 824357.3198 | 186324.7932 | 77007.514 | 67915.8275 | 8827.6906 | 129598.0115 | 153639.3817 | 0 | 0 | 0 | 0 | 0 | 0 | 14099.2619 | 0 | 0 | 0 | 0 | 0 | 4119.589 | 0 | 0 | 1385.8848 | 0 | 22174.1572 | 0 | 0 | 0 | 27977.8316 | 11018.9614 | 0 | 0 | 120268.4155 | 0 | 0 | 0 | 0
Fringe Benefits
|  |  | 288525.0619 | 65213.6776 | 26952.6299 | 23770.5396 | 3089.6917 | 45359.304 | 53773.7836 | 0 | 0 | 0 | 0 | 0 | 0 | 4934.7417 | 0 | 0 | 0 | 0 | 0 | 1441.8561 | 0 | 0 | 485.0597 | 0 | 7760.955 | 0 | 0 | 0 | 9792.2411 | 3856.6365 | 0 | 0 | 42093.9454 | 0 | 0 | 0 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Eqipment | 1 | 1 | 255869 | 0 | 0 | 0 | 0 | 0 | 0 | 36683 | 20502 | 17850 | 5000 | 31916 | 14000 | 0 | 120918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 1224134.2604 | 0 | 0 | 0 | 0 | 0 | 308987.9545 | 40601.1161 | 21453.5839 | 134260.2008 | 14408.1267 | 14399.779 | 21307.4991 | 660059.4373 | 4799.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3856.6365 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 1480003.2604 | 0 | 0 | 0 | 0 | 0 | 308987.9545 | 77284.1161 | 41955.5839 | 152110.2008 | 19408.1267 | 46315.779 | 35307.4991 | 660059.4373 | 125717.9263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 3856.6365 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 57000 | 28200 | 0 | 0 | 0 | 0 | 12600 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 5400 | 0 | 0 | 0 | 0
Foreign |  |  | 51600 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 108600 | 37800 | 0 | 0 | 0 | 0 | 12600 | 0 | 0 | 0 | 0 | 0 | 0 | 45600 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 1800 | 0 | 1800 | 5400 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 65264 | 15500 | 0 | 0 | 0 | 0 | 6814 | 0 | 0 | 0 | 0 | 0 | 5000 | 23050 | 0 | 950 | 0 | 0 | 1000 | 0 | 0 | 0 | 1700 | 0 | 1300 | 0 | 0 | 0 | 0 | 1000 | 0 | 950 | 7500 | 0 | 0 | 500 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 65264 | 15500 | 0 | 0 | 0 | 0 | 6814 | 0 | 0 | 0 | 0 | 0 | 5000 | 23050 | 0 | 950 | 0 | 0 | 1000 | 0 | 0 | 0 | 1700 | 0 | 1300 | 0 | 0 | 0 | 0 | 1000 | 0 | 950 | 7500 | 0 | 0 | 500 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Another professional service |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
MSU |  |  | 109792.4116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54711.4602 | 7658.0059 | 0 | 2945 | 0 | 44477.9455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSU |  |  | 30809.5469 | 16623.8562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14185.6906 | 0 | 0 | 0 | 0
UA |  |  | 118864.1058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91978.7815 | 26885.3243 | 0 | 0 | 0 | 0 | 0 | 0
UMD |  |  | 68775.7234 | 19840.0751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48935.6484 | 0 | 0 | 0 | 0 | 0
Subtotal - Subawards
|  |  | 328241.7877 | 36463.9313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54711.4602 | 7658.0059 | 0 | 2945 | 0 | 44477.9455 | 0 | 0 | 91978.7815 | 26885.3243 | 48935.6484 | 14185.6906 | 0 | 0 | 0 | 0
Other - Contingency |  |  | 910543.1388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 4005534.5686 | 341302.4021 | 103960.144 | 91686.3671 | 11917.3824 | 174957.3155 | 535815.1198 | 77284.1161 | 41955.5839 | 152110.2008 | 19408.1267 | 46315.779 | 40307.4991 | 747743.4409 | 127517.9263 | 950 | 0 | 0 | 1000 | 5561.4451 | 0 | 54711.4602 | 11228.9505 | 0 | 44980.1122 | 0 | 44477.9455 | 0 | 37770.0726 | 113511.0158 | 26885.3243 | 51685.6484 | 189448.0515 | 0 | 0 | 500 | 0
Indirect Costs
Office OH |  |  | 681975.5823 | 161564.3895 | 55098.8763 | 48593.7746 | 6316.2126 | 92727.3772 | 120218.3976 | 0 | 0 | 0 | 0 | 0 | 2650 | 46472.5219 | 954 | 503.5 | 0 | 0 | 530 | 2947.5659 | 0 | 0 | 1892.6006 | 0 | 17508.6094 | 0 | 0 | 0 | 20018.1385 | 9368.0669 | 0 | 1457.5 | 92889.0513 | 0 | 0 | 265 | 0
Other OH - Contingency |  |  | 189536.1625 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 871511.7448 | 161564.3895 | 55098.8763 | 48593.7746 | 6316.2126 | 92727.3772 | 120218.3976 | 0 | 0 | 0 | 0 | 0 | 2650 | 46472.5219 | 954 | 503.5 | 0 | 0 | 530 | 2947.5659 | 0 | 0 | 1892.6006 | 0 | 17508.6094 | 0 | 0 | 0 | 20018.1385 | 9368.0669 | 0 | 1457.5 | 92889.0513 | 0 | 0 | 265 | 0
0
Total - Direct and Indirect
|  |  | 4877046.3134 | 502866.7917 | 159059.0203 | 140280.1416 | 18233.595 | 267684.6926 | 656033.5174 | 77284.1161 | 41955.5839 | 152110.2008 | 19408.1267 | 46315.779 | 42957.4991 | 794215.9628 | 128471.9263 | 1453.5 | 0 | 0 | 1530 | 8509.011 | 0 | 54711.4602 | 13121.551 | 0 | 62488.7216 | 0 | 44477.9455 | 0 | 57788.2111 | 122879.0827 | 26885.3243 | 53143.1484 | 282337.1028 | 0 | 0 | 765 | 0

## PY7 Pivots
Institution | UW
Type | Labor Hours
Sum of Salary Cost PY7 | L3
Resource Name | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.10 | 1.2.8 | 1.3.3 | 1.3.4 | 1.4.2 | 1.4.4 | 1.5.2 | 1.5.3 | 1.6.1 | 1.6.4 | Total Result
Auer | [15 empty] | 4604.6737 | 4604.6737
Braun | [14 empty] | 5525.6084 |  | 5525.6084
Controls |  | 44128.1229 | [14 empty] | 44128.1229
DuVernois |  |  |  |  | 70988.7194 | [11 empty] | 70988.7194
Feyzi | 75731.9597 | [15 empty] | 75731.9597
Finance |  | 34535.0527 | [14 empty] | 34535.0527
Hanson | 19339.6295 | [15 empty] | 19339.6295
Kelley | [10 empty] | 0 | 0 |  |  |  |  | 0
McEwen | [5 empty] | 117035.4564 | [10 empty] | 117035.4564
ODell | 63384.6125 | [15 empty] | 63384.6125
S. Griffin | [9 empty] | 4208.1601 | [6 empty] | 4208.1601
Sandstrom |  |  |  |  | 40930.4328 | [11 empty] | 40930.4328
Scientist | [8 empty] | 0 | [7 empty] | 0
Senior Scientist | [13 empty] | 0 |  |  | 0
Tosi |  |  |  | 6963.5031 |  | 29930.379 | 14069.8363 | [9 empty] | 50963.7184
Weber | [14 empty] | 65565.97 |  | 65565.97
Wendt | [12 empty] | 0 |  |  |  | 0
Zernick |  |  | 69376.0178 |  |  |  |  | 17453.2292 | [8 empty] | 86829.247
Total Result | 158456.2017 | 78663.1756 | 69376.0178 | 6963.5031 | 111919.1523 | 146965.8354 | 14069.8363 | 17453.2292 | 0 | 4208.1601 | 0 | 0 | 0 | 0 | 71091.5785 | 4604.6737 | 683771.3636
Institution | UW
Type | Labor Hours
Sum of Fringe Cost PY7 | L3
Resource Name | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.10 | 1.2.8 | 1.3.3 | 1.3.4 | 1.4.2 | 1.4.4 | 1.5.2 | 1.5.3 | 1.6.1 | 1.6.4 | Total Result
Auer | [15 empty] | 1611.6358 | 1611.6358
Braun | [14 empty] | 1933.963 |  | 1933.963
Controls |  | 15444.843 | [14 empty] | 15444.843
DuVernois |  |  |  |  | 24846.0518 | [11 empty] | 24846.0518
Feyzi | 26506.1859 | [15 empty] | 26506.1859
Finance |  | 12087.2684 | [14 empty] | 12087.2684
Hanson | 6768.8703 | [15 empty] | 6768.8703
Kelley | [10 empty] | 0 | 0 |  |  |  |  | 0
McEwen | [5 empty] | 40962.4097 | [10 empty] | 40962.4097
ODell | 22184.6144 | [15 empty] | 22184.6144
S. Griffin | [9 empty] | 1472.856 | [6 empty] | 1472.856
Sandstrom |  |  |  |  | 14325.6515 | [11 empty] | 14325.6515
Scientist | [8 empty] | 0 | [7 empty] | 0
Senior Scientist | [13 empty] | 0 |  |  | 0
Tosi |  |  |  | 2437.2261 |  | 10475.6327 | 4924.4427 | [9 empty] | 17837.3014
Weber | [14 empty] | 22948.0895 |  | 22948.0895
Wendt | [12 empty] | 0 |  |  |  | 0
Zernick |  |  | 24281.6062 |  |  |  |  | 6108.6302 | [8 empty] | 30390.2364
Total Result | 55459.6706 | 27532.1115 | 24281.6062 | 2437.2261 | 39171.7033 | 51438.0424 | 4924.4427 | 6108.6302 | 0 | 1472.856 | 0 | 0 | 0 | 0 | 24882.0525 | 1611.6358 | 239319.9773
Institution | - multiple -
Type | CapEx
L3
1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.3.3 | 1.4.4 | 1.6.4 | Total Result
0 | 22992 | 14000 | 5000 | 0 | 10000 | 41700 | 0 | 0 | 0 | 14500 | 108192
Institution | PSL
Type | Labor Hours
L3
1.2.1 | 1.2.10 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.3.3 | 1.5.3 | Total Result
336049.5125 | 23637.325 | 0 | 3922.4998 | 75516.6486 | 4911.6519 | 0 | 19314.048 | 1024608.1143 | 0 | 0 | 0 | 1487959.8001
Institution | - multiple -
Type | Travel
Sum of 12mo Subtotal PY7 | L3
Resource Name | 1.1.1 | 1.2.1 | 1.2.10 | 1.2.8 | 1.2.9 | 1.3.3 | 1.4.4 | 1.5.3 | 1.6.0 | 1.6.1 | 1.6.4 | Total Result
Domestic | 28200 | 12600 |  | 21600 | 0 | 0 | 0 | 0 |  | 5400 | 1800 | 69600
Foreign | 9600 |  | 1800 | 71400 |  |  | 0 |  | 1800 |  |  | 84600
Total Result | 37800 | 12600 | 1800 | 93000 | 0 | 0 | 0 | 0 | 1800 | 5400 | 1800 | 154200
Institution | - multiple -
Type | M & S
L3
1.1.1 | 1.2.1 | 1.2.10 | 1.2.7 | 1.2.8 | 1.3.3 | 1.4.2 | 1.4.4 | 1.5.3 | 1.6.0 | 1.6.1 | 1.6.4 | Total Result
15500 | 4242 | 950 | 5000 | 40850 | 0 | 500 | 1575 | 4000 | 950 | 0 | 500 | 74067
Type | - all -
Sum of Complete Total PY7 | L3
Institution | 1.1.1 | 1.4.1 | 1.4.2 | 1.4.4 | 1.4.6 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.5 | Total Result
MSU |  | 8525 | 35202.8678 | 19906.51 | 45297.5888 | [5 empty] | 108931.9666
PSU | 16981.2691 | [7 empty] | 14490.683 |  | 31471.9521
UA | [5 empty] | 187912.6506 | 27143.0087 |  |  |  | 215055.6594
UMD | 20266.6367 | [6 empty] | 51335.9318 |  | 7953.6989 | 79556.2674
Total Result | 37247.9058 | 8525 | 35202.8678 | 19906.51 | 45297.5888 | 187912.6506 | 27143.0087 | 51335.9318 | 14490.683 | 7953.6989 | 435015.8455
Type | - all -
Institution | - multiple -
L3
1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.10 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.3.3 | 1.3.4 | 1.4.2 | 1.4.4 | 1.5.2 | 1.5.3 | 1.6.0 | 1.6.1 | 1.6.4 | Total Result
141624.4123 | 56283.5021 | 49638.5407 | 4982.3864 | 80078.1535 | 114080.3152 | 11524.4679 | 0 | 0 | 0 | 0 | 0 | 2650 | 83428.2855 | 0 | 0 | 3010.9386 | 265 | 834.75 | 0 | 2120 | 1457.5 | 53728.0244 | 4513.644 | 610219.9207
Type | Labor Hours
Institution | UW
Resource Name | Sum of PY7 CMo
Auer | 0.48
Braun | 0.64
Controls | 6
DuVernois | 6
Feyzi | 4.8333
Finance | 4.8
Hanson | 0.96
Kelley | 0
McEwen | 12
ODell | 3.5333
S. Griffin | 0.56
Sandstrom | 4
Scientist | 0
Senior Scientist | 0
Tosi | 7.1667
Weber | 6.3333
Wendt | 0
Zernick | 10.08
Total Result | 67.3867
Data |  | Discrete Risks Direct | Discrete Risks Ind | Discrete Risks Total | Total Contingency | Total Direct | Total Indirect
Sum of EU Direct PY7 | Sum of EU Ind PY7 | 513919.7298 | 106494.2702 | 620414 | 1038378.8333 | 860140.7599 | 178238.0734
346221.0301 | 71743.8032 | 82.83% | 17.17%

## PY7 1030
Year 7 Budget
|  |  |  | 1.1 Project Office |  |  |  |  | 1.2 Drilling and Installation | [9 empty] | 1.3 Deep Ice Sensor Modules |  |  |  |  | 1.4 Comm/Power/Timing | [5 empty] | 1.5 Characterization and Calibration System |  |  |  | 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 7
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Hanson | 0.96 | 19339.6295 | 19339.6295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | Feyzi | 4.8333 | 75731.9597 | 75731.9597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Director | ODell | 3.5333 | 63384.6125 | 63384.6125
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Controls Manager | Finance | 4.8 | 34535.0527 | 0 | 34535.0527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Controls Analyst | Controls | 6 | 44128.1229 | 0 | 44128.1229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality and Safety | Zernick | 10.08 | 86829.247 | 0 | 0 | 69376.0178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17453.2292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical Coordinator | DuVernois | 6 | 70988.7194 | 0 | 0 | 0 | 0 | 70988.7194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Engineer | Sandstrom | 4 | 40930.4328 | 0 | 0 | 0 | 0 | 40930.4328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Logistics Manager | Tosi | 7.1667 | 50963.7184 | 0 | 0 | 0 | 6963.5031 | 0 | 29930.379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14069.8363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation Manager | McEwen | 12 | 117035.4564 | 0 | 0 | 0 | 0 | 0 | 117035.4564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer / Technician | Wendt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer / Technician | Weber | 6.3333 | 65565.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65565.97 | 0 | 0 | 0 | 0
Engineer | Kelley | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | Braun | 0.64 | 5525.6084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5525.6084 | 0 | 0 | 0 | 0
Engineer | Auer | 0.48 | 4604.6737 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4604.6737 | 0
Senior Scientist | Senior Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | S. Griffin | 0.56 | 4208.1601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4208.1601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 683771.3636 | 158456.2017 | 78663.1756 | 69376.0178 | 6963.5031 | 111919.1523 | 146965.8354 | 0 | 0 | 0 | 0 | 0 | 0 | 17453.2292 | 0 | 14069.8363 | 0 | 0 | 0 | 4208.1601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71091.5785 | 0 | 0 | 4604.6737 | 0
Fringe Benefits
|  |  | 239319.9773 | 55459.6706 | 27532.1115 | 24281.6062 | 2437.2261 | 39171.7033 | 51438.0424 | 0 | 0 | 0 | 0 | 0 | 0 | 6108.6302 | 0 | 4924.4427 | 0 | 0 | 0 | 1472.856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24882.0525 | 0 | 0 | 1611.6358 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Eqipment | 1 | 1 | 108192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22992 | 14000 | 5000 | 0 | 10000 | 41700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14500 | 0
Capitalized Labor | 1 | 1 | 1487959.8001 | 0 | 0 | 0 | 0 | 0 | 336049.5125 | 0 | 3922.4998 | 75516.6486 | 4911.6519 | 0 | 19314.048 | 1024608.1143 | 0 | 23637.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 1596151.8001 | 0 | 0 | 0 | 0 | 0 | 336049.5125 | 0 | 3922.4998 | 98508.6486 | 18911.6519 | 5000 | 19314.048 | 1034608.1143 | 41700 | 23637.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14500 | 0
Travel
Domestic |  |  | 69600 | 28200 | 0 | 0 | 0 | 0 | 12600 | 0 | 0 | 0 | 0 | 0 | 0 | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5400 | 0 | 0 | 1800 | 0
Foreign |  |  | 84600 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71400 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 154200 | 37800 | 0 | 0 | 0 | 0 | 12600 | 0 | 0 | 0 | 0 | 0 | 0 | 93000 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 5400 | 0 | 0 | 1800 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 74067 | 15500 | 0 | 0 | 0 | 0 | 4242 | 0 | 0 | 0 | 0 | 0 | 5000 | 40850 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 1575 | 0 | 0 | 0 | 0 | 4000 | 0 | 950 | 0 | 0 | 0 | 500 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 74067 | 15500 | 0 | 0 | 0 | 0 | 4242 | 0 | 0 | 0 | 0 | 0 | 5000 | 40850 | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 1575 | 0 | 0 | 0 | 0 | 4000 | 0 | 950 | 0 | 0 | 0 | 500 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Another professional service |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
MSU |  |  | 108931.9666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8525 | 35202.8678 | 0 | 19906.51 | 0 | 45297.5888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSU |  |  | 31471.9521 | 16981.2691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14490.683 | 0 | 0 | 0 | 0
UA |  |  | 215055.6594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187912.6506 | 27143.0087 | 0 | 0 | 0 | 0 | 0 | 0
UMD |  |  | 79556.2674 | 20266.6367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51335.9318 | 0 | 0 | 0 | 0 | 7953.6989
Subtotal - Subawards
|  |  | 435015.8455 | 37247.9058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8525 | 35202.8678 | 0 | 19906.51 | 0 | 45297.5888 | 0 | 0 | 187912.6506 | 27143.0087 | 51335.9318 | 14490.683 | 0 | 0 | 0 | 7953.6989
Other - Contingency |  |  | 860140.7599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 4042666.7464 | 304463.7781 | 106195.2871 | 93657.624 | 9400.7291 | 151090.8556 | 551295.3903 | 0 | 3922.4998 | 98508.6486 | 18911.6519 | 5000 | 24314.048 | 1192019.9737 | 41700 | 45381.6039 | 0 | 0 | 0 | 5681.0162 | 0 | 8525 | 35702.8678 | 0 | 21481.51 | 0 | 45297.5888 | 0 | 0 | 191912.6506 | 27143.0087 | 54085.9318 | 115864.3139 | 0 | 0 | 23016.3095 | 7953.6989
Indirect Costs
Office OH |  |  | 610219.9207 | 141624.4123 | 56283.5021 | 49638.5407 | 4982.3864 | 80078.1535 | 114080.3152 | 0 | 0 | 0 | 0 | 0 | 2650 | 83428.2855 | 0 | 11524.4679 | 0 | 0 | 0 | 3010.9386 | 0 | 0 | 265 | 0 | 834.75 | 0 | 0 | 0 | 0 | 2120 | 0 | 1457.5 | 53728.0244 | 0 | 0 | 4513.644 | 0
Other OH Contingency |  |  | 178238.0734 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 788457.994 | 141624.4123 | 56283.5021 | 49638.5407 | 4982.3864 | 80078.1535 | 114080.3152 | 0 | 0 | 0 | 0 | 0 | 2650 | 83428.2855 | 0 | 11524.4679 | 0 | 0 | 0 | 3010.9386 | 0 | 0 | 265 | 0 | 834.75 | 0 | 0 | 0 | 0 | 2120 | 0 | 1457.5 | 53728.0244 | 0 | 0 | 4513.644 | 0
0
Total - Direct and Indirect
|  |  | 4831124.7404 | 446088.1904 | 162478.7892 | 143296.1647 | 14383.1156 | 231169.009 | 665375.7055 | 0 | 3922.4998 | 98508.6486 | 18911.6519 | 5000 | 26964.048 | 1275448.2593 | 41700 | 56906.0718 | 0 | 0 | 0 | 8691.9547 | 0 | 8525 | 35967.8678 | 0 | 22316.26 | 0 | 45297.5888 | 0 | 0 | 194032.6506 | 27143.0087 | 55543.4318 | 169592.3383 | 0 | 0 | 27529.9535 | 7953.6989

## PY8 Pivots
Institution | UW
Type | Labor Hours
Sum of Salary Cost PY8 | L3
Resource Name | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.10 | 1.2.8 | 1.3.3 | 1.3.4 | 1.4.2 | 1.4.4 | 1.5.2 | 1.5.3 | 1.6.1 | 1.6.4 | Total Result
Auer | [15 empty] | 3135.7828 | 3135.7828
Braun | [14 empty] | 2822.2045 |  | 2822.2045
Controls |  | 30051.2517 | [14 empty] | 30051.2517
DuVernois |  |  |  |  | 12085.8295 | [11 empty] | 12085.8295
Feyzi | 45349.0809 | [15 empty] | 45349.0809
Finance |  | 23518.3709 | [14 empty] | 23518.3709
Hanson | 13170.2877 | [15 empty] | 13170.2877
Kelley | [10 empty] | 0 | 9038.2406 |  |  |  |  | 9038.2406
McEwen | [5 empty] | 69738.5026 | [10 empty] | 69738.5026
ODell | 29319.569 | [15 empty] | 29319.569
S. Griffin | [9 empty] | 2507.5374 | [6 empty] | 2507.5374
Sandstrom |  |  |  |  | 0 | [11 empty] | 0
Scientist | [8 empty] | 0 | [7 empty] | 0
Senior Scientist | [13 empty] | 0 |  |  | 0
Tosi |  |  |  | 1381.7043 |  | 5378.7385 | 18304.6295 | [9 empty] | 25065.0723
Weber | [14 empty] | 40537.8864 |  | 40537.8864
Wendt | [12 empty] | 0 |  |  |  | 0
Zernick |  |  | 15010.3825 |  |  |  |  | 26398.6454 | [8 empty] | 41409.0279
Total Result | 87838.9377 | 53569.6226 | 15010.3825 | 1381.7043 | 12085.8295 | 75117.2411 | 18304.6295 | 26398.6454 | 0 | 2507.5374 | 0 | 9038.2406 | 0 | 0 | 43360.0909 | 3135.7828 | 347748.6442
Institution | UW
Type | Labor Hours
Sum of Fringe Cost PY8 | L3
Resource Name | 1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.10 | 1.2.8 | 1.3.3 | 1.3.4 | 1.4.2 | 1.4.4 | 1.5.2 | 1.5.3 | 1.6.1 | 1.6.4 | Total Result
Auer | [15 empty] | 1097.524 | 1097.524
Braun | [14 empty] | 987.7716 |  | 987.7716
Controls |  | 10517.9381 | [14 empty] | 10517.9381
DuVernois |  |  |  |  | 4230.0403 | [11 empty] | 4230.0403
Feyzi | 15872.1783 | [15 empty] | 15872.1783
Finance |  | 8231.4298 | [14 empty] | 8231.4298
Hanson | 4609.6007 | [15 empty] | 4609.6007
Kelley | [10 empty] | 0 | 3163.3842 |  |  |  |  | 3163.3842
McEwen | [5 empty] | 24408.4759 | [10 empty] | 24408.4759
ODell | 10261.8492 | [15 empty] | 10261.8492
S. Griffin | [9 empty] | 877.6381 | [6 empty] | 877.6381
Sandstrom |  |  |  |  | 0 | [11 empty] | 0
Scientist | [8 empty] | 0 | [7 empty] | 0
Senior Scientist | [13 empty] | 0 |  |  | 0
Tosi |  |  |  | 483.5965 |  | 1882.5585 | 6406.6203 | [9 empty] | 8772.7753
Weber | [14 empty] | 14188.2602 |  | 14188.2602
Wendt | [12 empty] | 0 |  |  |  | 0
Zernick |  |  | 5253.6339 |  |  |  |  | 9239.5259 | [8 empty] | 14493.1598
Total Result | 30743.6282 | 18749.3679 | 5253.6339 | 483.5965 | 4230.0403 | 26291.0344 | 6406.6203 | 9239.5259 | 0 | 877.6381 | 0 | 3163.3842 | 0 | 0 | 15176.0318 | 1097.524 | 121712.0255
Institution | - multiple -
Type | CapEx
L3
1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.3.3 | 1.4.4 | 1.6.4 | Total Result
0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 2000
Institution | PSL
Type | Labor Hours
L3
1.2.1 | 1.2.10 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.3.3 | 1.5.3 | Total Result
126966.5384 | 0 | 0 | 0 | 4006.8336 | 0 | 0 | 8362.0874 | 1252759.7403 | 0 | 0 | 0 | 1392095.1997
Institution | - multiple -
Type | Travel
Sum of 12mo Subtotal PY8 | L3
Resource Name | 1.1.1 | 1.2.1 | 1.2.10 | 1.2.8 | 1.2.9 | 1.3.3 | 1.4.4 | 1.5.3 | 1.6.0 | 1.6.1 | 1.6.4 | Total Result
Domestic | 1800 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1800
Foreign | 0 |  | 1800 | 0 |  |  | 1800 |  | 0 |  |  | 3600
Total Result | 1800 | 0 | 1800 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 5400
Institution | - multiple -
Type | M & S
L3
1.1.1 | 1.2.1 | 1.2.10 | 1.2.7 | 1.2.8 | 1.3.3 | 1.4.2 | 1.4.4 | 1.5.3 | 1.6.0 | 1.6.1 | 1.6.4 | Total Result
7800 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0 | 0 | 0 | 0 | 8300
Type | - all -
Sum of Complete Total PY8 | L3
Institution | 1.1.1 | 1.4.1 | 1.4.2 | 1.4.4 | 1.4.6 | 1.5.3 | 1.5.4 | 1.6.0 | 1.6.1 | 1.6.5 | Total Result
MSU |  | 56851.1374 | 0 | 2790 | 3177.5 | [5 empty] | 62818.6374
PSU | 11564.2443 | [7 empty] | 7401.1163 |  | 18965.3606
UA | [5 empty] | 95976.3863 | 2682 |  |  |  | 98658.3863
UMD | 13801.5796 | [6 empty] | 22629.3824 |  | 5416.469 | 41847.4309
Total Result | 25365.8239 | 56851.1374 | 0 | 2790 | 3177.5 | 95976.3863 | 2682 | 22629.3824 | 7401.1163 | 5416.469 | 222289.8152
Type | - all -
Institution | - multiple -
L3
1.1.1 | 1.1.2 | 1.1.3 | 1.1.4 | 1.1.5 | 1.2.1 | 1.2.10 | 1.2.2 | 1.2.3 | 1.2.4 | 1.2.5 | 1.2.6 | 1.2.7 | 1.2.8 | 1.2.9 | 1.3.3 | 1.3.4 | 1.4.2 | 1.4.4 | 1.5.2 | 1.5.3 | 1.6.0 | 1.6.1 | 1.6.4 | Total Result
67936.7599 | 38329.065 | 10739.9286 | 988.6094 | 8647.411 | 53746.386 | 14050.9624 | 0 | 0 | 0 | 0 | 0 | 0 | 18888.2308 | 0 | 0 | 1794.143 | 132.5 | 7553.3611 | 0 | 0 | 0 | 31024.145 | 2243.6526 | 256075.1549
Type | Labor Hours
Institution | UW
Resource Name | Sum of PY8 CMo
Auer | 0.32
Braun | 0.32
Controls | 4
DuVernois | 1
Feyzi | 2.8333
Finance | 3.2
Hanson | 0.64
Kelley | 1
McEwen | 7
ODell | 1.6
S. Griffin | 0.32667
Sandstrom | 0
Scientist | 0
Senior Scientist | 0
Tosi | 4.5333
Weber | 3.8333
Wendt | 0
Zernick | 6.0133
Total Result | 36.62
Data |  | Discrete Risks Direct | Discrete Risks Ind | Discrete Risks Total | Total Contingency | Total Direct | Total Indirect
Sum of EU Direct PY8 | Sum of EU Ind PY8 | 0 | 0 | 0 | 256870.7024 | 225059.5103 | 31811.1921
225059.5103 | 31811.1921 | 87.62% | 12.38%

## PY8 1030
Year 8 Budget
|  |  |  | 1.1 Project Office |  |  |  |  | 1.2 Drilling and Installation | [9 empty] | 1.3 Deep Ice Sensor Modules |  |  |  |  | 1.4 Comm/Power/Timing | [5 empty] | 1.5 Characterization and Calibration System |  |  |  | 1.6 IceCube Data Systems Integration
|  |  |  | 1.1.1 Project Management | 1.1.2 Project Controls | 1.1.3 Quality and Safety | 1.1.4 Polar Operations | 1.1.5 Project Engineering | 1.2.1 Implementation Management & Systems Engineering | 1.2.2 Thermal Plant - Off-ice | 1.2.3 Tower Operations Site (TOS) - Off-ice | 1.2.4 Computing and Control System - Off-ice | 1.2.5 Power Generation & Distribution | 1.2.6 Water Handling Systems - Off-ice | 1.2.7 Support Equipment - Off-ice | 1.2.8 Drill Field Seasons - Antarctica | 1.2.9 Installation - Off-ice | 1.2.10 Installation Field Seasons - Antarctica | 1.3.1 mDOM | 1.3.2 D-Egg | 1.3.3 PDOM | 1.3.4 Ice Comms Module | 1.3.5 Special Devices | 1.4.1 Downhole Cables | 1.4.2 Surface Cables | 1.4.3 FieldHub | 1.4.4 CPT Central Infrastructure | 1.4.5 Northern Test System | 1.4.6 CPT Management (PY4 onward) | 1.5.1 Module Calibration | 1.5.2 Calibration Assemblies | 1.5.3 Array Calibration | 1.5.4 Calibration Management and Organization | 1.6.0 L2 Task Management | 1.6.1 Online Systems Software | 1.6.2 Offline Systems | 1.6.3 Simulation Software | 1.6.4 Computing Infrastructure | 1.6.5 Upgrade String Commissioning
Expense Description |  |  | Total Yr 8
Senior Personnel
Title | Last Name | Cal. Mo.
Principal Investigator | Hanson | 0.64 | 13170.2877 | 13170.2877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Manager | Feyzi | 2.8333 | 45349.0809 | 45349.0809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Director | ODell | 1.6 | 29319.569 | 29319.569
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Personnel |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Controls Manager | Finance | 3.2 | 23518.3709 | 0 | 23518.3709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Controls Analyst | Controls | 4 | 30051.2517 | 0 | 30051.2517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality and Safety | Zernick | 6.0133 | 41409.0279 | 0 | 0 | 15010.3825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26398.6454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical Coordinator | DuVernois | 1 | 12085.8295 | 0 | 0 | 0 | 0 | 12085.8295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Engineer | Sandstrom | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Logistics Manager | Tosi | 4.5333 | 25065.0723 | 0 | 0 | 0 | 1381.7043 | 0 | 5378.7385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18304.6295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation Manager | McEwen | 7 | 69738.5026 | 0 | 0 | 0 | 0 | 0 | 69738.5026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer / Technician | Wendt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer / Technician | Weber | 3.8333 | 40537.8864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40537.8864 | 0 | 0 | 0 | 0
Engineer | Kelley | 1 | 9038.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9038.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | Braun | 0.32 | 2822.2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2822.2045 | 0 | 0 | 0 | 0
Engineer | Auer | 0.32 | 3135.7828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3135.7828 | 0
Senior Scientist | Senior Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scientist | Scientist | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineer | S. Griffin | 0.32667 | 2507.5374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2507.5374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Salaries and Wages
|  |  | 347748.6442 | 87838.9377 | 53569.6226 | 15010.3825 | 1381.7043 | 12085.8295 | 75117.2411 | 0 | 0 | 0 | 0 | 0 | 0 | 26398.6454 | 0 | 18304.6295 | 0 | 0 | 0 | 2507.5374 | 0 | 0 | 0 | 0 | 9038.2406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43360.0909 | 0 | 0 | 3135.7828 | 0
Fringe Benefits
|  |  | 121712.0255 | 30743.6282 | 18749.3679 | 5253.6339 | 483.5965 | 4230.0403 | 26291.0344 | 0 | 0 | 0 | 0 | 0 | 0 | 9239.5259 | 0 | 6406.6203 | 0 | 0 | 0 | 877.6381 | 0 | 0 | 0 | 0 | 3163.3842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15176.0318 | 0 | 0 | 1097.524 | 0
Equipment
Descrip. | Qty | Unit Cost
Capital Eqipment | 1 | 1 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capitalized Labor | 1 | 1 | 1392095.1997 | 0 | 0 | 0 | 0 | 0 | 126966.5384 | 0 | 0 | 4006.8336 | 0 | 0 | 8362.0874 | 1252759.7403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Eqpt
|  |  | 1394095.1997 | 0 | 0 | 0 | 0 | 0 | 126966.5384 | 0 | 0 | 4006.8336 | 0 | 0 | 8362.0874 | 1254759.7403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Travel
Domestic |  |  | 1800 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Foreign |  |  | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Travel
|  |  | 5400 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Participant Support Costs
Descr | # participants |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Part. Supp.
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Costs
Materials and Supplies |  |  | 8300 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computers/Office |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/licenses |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other categories |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
And other cats… |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Materials and Supplies
|  |  | 8300 | 7800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Publication Costs/Documentation/Dissemination
Consultant Services Description |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Software/Programming |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Database consultant |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Another professional service |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Etc. |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Consultant/Prof Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Computer Services |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subotal Computer Services
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subawards
MSU |  |  | 62818.6374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56851.1374 | 0 | 0 | 2790 | 0 | 3177.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSU |  |  | 18965.3606 | 11564.2443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7401.1163 | 0 | 0 | 0 | 0
UA |  |  | 98658.3863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95976.3863 | 2682 | 0 | 0 | 0 | 0 | 0 | 0
UMD |  |  | 41847.4309 | 13801.5796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22629.3824 | 0 | 0 | 0 | 0 | 5416.469
Subtotal - Subawards
|  |  | 222289.8152 | 25365.8239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56851.1374 | 0 | 0 | 2790 | 0 | 3177.5 | 0 | 0 | 95976.3863 | 2682 | 22629.3824 | 7401.1163 | 0 | 0 | 0 | 5416.469
Other - Contingency |  |  | 225059.5103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Leases |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Repair |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shipping/Postage |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Other
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total - Direct Costs
|  |  | 2324605.1949 | 153548.3897 | 72318.9905 | 20264.0163 | 1865.3008 | 16315.8698 | 228374.8139 | 0 | 0 | 4006.8336 | 0 | 0 | 8362.0874 | 1290397.9117 | 0 | 26511.2498 | 0 | 0 | 0 | 3385.1755 | 0 | 56851.1374 | 250 | 0 | 17041.6248 | 0 | 3177.5 | 0 | 0 | 95976.3863 | 2682 | 22629.3824 | 65937.2391 | 0 | 0 | 4233.3068 | 5416.469
Indirect Costs
Office OH |  |  | 256075.1549 | 67936.7599 | 38329.065 | 10739.9286 | 988.6094 | 8647.411 | 53746.386 | 0 | 0 | 0 | 0 | 0 | 0 | 18888.2308 | 0 | 14050.9624 | 0 | 0 | 0 | 1794.143 | 0 | 0 | 132.5 | 0 | 7553.3611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31024.145 | 0 | 0 | 2243.6526 | 0
Other OH Contingency |  |  | 31811.1921 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal - Indirect Costs |  |  | 287886.347 | 67936.7599 | 38329.065 | 10739.9286 | 988.6094 | 8647.411 | 53746.386 | 0 | 0 | 0 | 0 | 0 | 0 | 18888.2308 | 0 | 14050.9624 | 0 | 0 | 0 | 1794.143 | 0 | 0 | 132.5 | 0 | 7553.3611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31024.145 | 0 | 0 | 2243.6526 | 0
0
Total - Direct and Indirect
|  |  | 2612491.5419 | 221485.1496 | 110648.0554 | 31003.945 | 2853.9102 | 24963.2808 | 282121.1999 | 0 | 0 | 4006.8336 | 0 | 0 | 8362.0874 | 1309286.1425 | 0 | 40562.2122 | 0 | 0 | 0 | 5179.3185 | 0 | 56851.1374 | 382.5 | 0 | 24594.9859 | 0 | 3177.5 | 0 | 0 | 95976.3863 | 2682 | 22629.3824 | 96961.3841 | 0 | 0 | 6476.9593 | 5416.469