## 1.2.6 Water Handling
Upgrade Cost Estimate
Name: | 1.2.6 Water Handling
Parent WBS: | 1.2 Implementation |  | MATERIALS ESTIMATE | [14 empty] | LABOR ESTIMATE | [6 empty] | TOTAL | SCHEDULE INPUT
Description of Scope:
Initials/Date: |  |  | Quantities | [6 empty] | Basis of Estimate (Select One, See Table Below) | [7 empty] | HOURS | [8 empty] | SCHEDULE LOGIC
WBS (if known) | Project Year (0-10) | Description | QTY | Spare | Total | Fabricate or Procure? | Procurement Details Manufacturer, Model, P/N, Vendor | Unit Price | Total Expected Price | C1 LOE Tasks | C2 Advanced | C3 Preliminary | C4 Conceptual | C5 Pre- Conceptual | C6 Rough Estimate | Cost Estimating Technique (See Table Below) | Materials Comments/Notes (procurement lead time, shipping restrictions, etc) | ENGR ($115/hr) | CAD ($81/hr) | SHOP ($77/hr) | STUDENT ($15/hr) | Total Hours | Total Hours Cost | Labor Comments/Schedule Inputs (eg. "March" or "After Microturbine running", etc) |  | Duration (Weeks) | Predecessors | Successors | Milestone | % of total | orig mat'l | orig labor | orig tot | delta | 9766.44
1.2.6.1 |  | Water Tanks |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.6.1.3 | 6 | Procure Repair Parts, Replacements (PY6) |  |  | 0 |  |  |  | 5000 |  |  |  | X |  |  | D | expert opinion. after FS1 assessment. WT1 return manifold reconfigure and reassemble, submersible pump riser hose refit materials | 24 |  |  |  | 24 | 2760 | expert opinion, procure and some assembly | 7760 |  |  |  |  | 13.634
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.6.2 |  | Pumps |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.6.2.5 | 5 | Procure Repair/Replacement Components (PY5) |  |  | 0 |  |  |  | 6600 |  |  |  | X |  |  | D | VT pump feeders, cold rated cable $4k, 6x HubbleSW connectors $100/ea = $600, HPP cylinder linings and tooling $2k Total = $6600 | 40 |  |  |  | 40 | 4600 |  | 11200 |  |  |  |  | 19.678 | 6250 | 4600 | 10850 | 350
1.2.6.2.6 | 6 | Procure Repair/Replacement Components (PY6) |  |  | 0 |  |  |  | 5000 |  |  |  | X |  |  | D | expert opinion. after FS1 assessment. HPP, VT, and submersible pump parts, return water pump configuration plumbing and rigging | 24 |  |  |  | 24 | 2760 |  | 7760 |  |  |  |  | 13.634
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.6.4 |  | Interconnects - External |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.6.4.9 | 6 | Procure External Interconnect Materials (PY6) |  |  | 0 |  |  |  | 10551.44 |  |  |  | X |  |  | C | See catalog items named "1.2.6 xxx" at this link (breakdown is provided below) - ignore 1.2.6 AeroquipHoseResupply | 40 |  |  |  | 40 | 4600 | expert opinion, procure and organize, pre-terminate heat trace | 15151.44 |  |  |  |  | 26.6205 | 10000 | 4600 | 14600 | 551.44
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.6.5 |  | MDS Internal Hoses |  |  | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
1.2.6.5.1 | 6 | Identify Replacement Water Hoses (1-1/2", 3/4", and 1/2" Hose) |  |  | 0 | [7 empty] | X |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 1.6164
1.2.6.5.2 | 6 | Identify Replacement Fuel Hoses |  |  | 0 | [7 empty] | X |  |  | D |  | 8 |  |  |  | 8 | 920 | expert opinion | 920 |  |  |  |  | 1.6164
1.2.6.5.3 | 6 | Procure Replacements and Spares |  |  | 0 |  |  |  | 11365 |  |  |  | X |  |  | D | see breakdown with est. costs here | 16 |  |  |  | 16 | 1840 | expert opinion | 13205 |  |  |  |  | 23.2007 | 2500 | 1840 | 4340 | 8865
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
[5 empty] | 0 | [16 empty] | 0 | 0 |  | 0 |  |  |  |  | 0
[9 empty] | 38516.44 | Total Expected Materials Cost | [7 empty] | 160 | 0 | 0 | 0 | 160 | 18400 | Total Hours Cost | 56916.44
Schedule Logic Terms that can be used:
FS = Finish-to-Start
[8 empty] | 1.2.6.4 | [18 empty] | SS = Start-Start
[8 empty] | Qty | Item | $/ea | subtotal | [15 empty] | FF = Finish-Finsh
[8 empty] | 300 | heat trace | 9.67 | 2901 | [15 empty] | SF = Start-to-Finish
[8 empty] | 6 | LED termination | 266.17 | 1597.02
[8 empty] | 6 | Power termination | 182.96 | 1097.76
[8 empty] | 4 | bubble insulation, 125' | 81.74 | 326.96
[8 empty] | 20 | tape | 43.11 | 862.2
[8 empty] | 150 | Camp hose insulation, 6' | 25.11 | 3766.5
10551.44